## Unilever WAN Migration MASTER T
Unilever Circuit Reference | New Circuit Reference | Wave | Device Validated with Deepak (device type,BW,net) | Priority | Cluster | Country | Site Name | RFP_Reference | Router Hostname | New Router Hostname | Cisco Project Manager | Project Workstream | Scope | Supplier | Supplier (short) | Intermediate supplier | Supplier Unique Identifier for Circuit | Baseline Circuit Order Date | Forecast/ Actual Circuit Order Date | Circuit Order RAG | Baseline Circuit order Accepted Date | Forecast/ Actual Circuit order Accepted Date | Circuit Order Accepted RAG | Baseline Circuit Delivery Date | Forecast/ Actual Circuit Delivery Date | Circuit Delivery RAG | Baseline Migration Go Live Date | Forecast/ Actual Migration Go Live Date | Computed Delivery RAG | Status Tracking Comments/Updates | PM Forecast RAG | Circuit Status | Next Action Item Owner | Dates check | Site WorkDay Code | Legacy Site Name | Cease date | Cease status | Cease Request # | Cease Approval Date | Site Address | City | ZIP/Postcode | Site Type (Office, Warehouse, Factory) | Site Contact Name | Site Contact Email | Telephone | Geo IT Contact Name | Geo IT Contact Email | Existing BW ( as seen on the device) | Ordered Bandwidth (Mbps) | Old Latitude | Old Longitude | Planned Year | Planned Month | Legacy Circuit Type | Legacy Circuit Contract End Date | Business Driver | Service Priority | Service Feedback | Service Criticality | Planning considerations | Suggested Migration window time | Site access requirements | Insurance Requirement (Y/N) | Impact analysis | IP Address Ordered | Justification (If IP Address reqrmnt is not/30) | Demarcation Details (CPE/NTP Details, additional | IP from Circuit Provider | PE IP | CE IP | LAN segment(if any) | Availability SLA | Time to Restore | Last Mile Provider | PoP | AS Number (not mandatory) | Site Survey (Cisco) | Remediation Status | Remediation Details | Cisco Engineer Assigned for prep of circuit | Cisco Engineer for Migration | Cisco Engineer for Day 1 support | Day 1 support day | Circuit Presentation type | Technical Pre-Assessment for the Site | Technical Assessment Status | Assessment Follow up - HW required | Assessment follow up - OS upgrade/license | Assessment follow up - IP address/mask change | Assessment follow up- BW change | Assessment follow up -New device onboarding to CMS | Migration Deliverables prep status | Migration date agreed & end user comms sent | Order details | Migration window time (UTC) | Migration Window time (Local) | CMSP Ticket Number | Remedy RFC Number | RFC Approval Status | AlgoSec Request Number | AlgoSec RFC Number | AlgoSec Status | Zscaler status | Circuit Testing Status | Circuit Testing comments | UAT Testers (Name/Email) | Circuit Migration Status | Failed Root Cause | Post Go Live Incident Reference | Incident Root Cause | Monthly Baseline Circuit Delivery Date | Monthly Baseline Circuit Migration Date
Unilever Input | Unilever Input | Unilever Input | From BW, netmask and device type check sheet | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Cisco Input | Cisco Input | Cisco Input | Cisco Input | Cisco Input | Unilever Input | Control column | Unilever Input - Different from last mile provider | Supplier Input | Unilever Input | Unilever Input | Calculation Fill "Complete" status manually | Supplier input | Supplier input / PM Input to be made in supplier sheet | Calculation Fill "Complete" status manually | Supplier input | Supplier input / PM Input | Calculation Fill "Complete" status manually | Cisco Input | Cisco Input | Calculation Fill "Complete" status manually | Cisco Input | Cisco Input | Calculation | Cisco Input | Calculation | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | From tech prep sheet | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Unilever Input | Supplier input | Supplier input | From tech prep sheet | From tech prep sheet | From tech prep sheet | Supplier input | Supplier input | Supplier input | Supplier input | Supplier input | Cisco Input | Cisco Input | Cisco Input | Fill in here, will be replicated in other sheets | Fill in here, will be replicated in other sheets | Fill in here, will be replicated in other sheets | Fill in here, will be replicated in other sheets | Supplier input | From tech prep sheet | From tech prep sheet | From tech prep sheet | From tech prep sheet | From tech prep sheet | From tech prep sheet | From tech prep sheet | From tech prep sheet | Cisco Input | Cisco Input | PM Input Format 24 hours ex., 1300 - 1700 | PM Input Format 24 hours ex., 1300 - 1700 | Cisco Input | Cisco Input | Cisco Input | Cisco Input | Cisco Input | Cisco Input | Cisco Input | Cisco Input | Cisco Input | PM Input | Cisco Input | Cisco Input | Cisco Input - input incident number | Cisco Input | Vishal Input | Vishal Input
CKT-I-01-CI-ABJ01-0002-VOD-1 | I014767VOD1 | 1 | Yes. Devices swapped | Top | Africa | COTE DIVOIRE | CDI | 2018_57 | un-amt-civabi-vpn001 |  | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | S19090338558 | 2019-08-19 | 2019-08-16 | Complete | 2019-08-26 | 2019-08-21 | Complete | 2019-11-04 | 2020-08-13 | Complete | 2019-11-18 | 2020-08-22 | Complete | Action Item : Vodacom to proceed with delivery of circuit. 8-May: Internal escalation within Vodacom to get feedback from last mile provider. 22 April - Project ON HOLD - due to COVID-19 lockdown. Feedback regarding lockdown regulations to be provided by Vodacom LCON on the 2904. Attempts to contact Vodacom LL partner and Unilever onsite contact was unsuccessful. 13 Dec: No new update 06 Dec : Same as below 29 Nov : Same status 22 Nov -Pending documents submitted - Sign-off expected by 2211. Physical site survey then to be scheduled. IDD to be provided by 0412. 18 Nov : Target delivery date as Feb 20 provided by VF. No site survey's done yet. 11-Nov : Site survey not yet done, no date provided by VF. 5-Nov: Do Not schedule migration at month end or beginning of the month. Asked feedback from GEO IT on possible suggested dates. Possible options are Saturday or mid of the month. Date changed to 14 Dec tentatively. | Complete | Circuit Migrated | Circuit Provider |  | CI-ABJ01-0002 | COTE_DIVOIRE_ABIDJAN_BLOHORN |  |  |  |  | Unilever Cote D'Ivoire Boulevard de Vridi 01 BP 1751 Abidjan 01 |  |  |  | Aichath Nzi-Akande | <frederic.maika@unilever.com> |  | Dees Rampartab | Dees.Rampartab@unilever.com | 51MB50MB | 50 |  |  | 2019 | Oct | Internet | 2019-05-23 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Saturday or mid of month. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Joelle.Kouassi@unilever.com +225 0993 2277 | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | 169.239.66.136 /30 169.239.66.120 /29 | 169.239.66.137/30 | 169.239.66.138/30 | 169.239.66.120/29 |  |  | Vodacom CI | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No |  | Yes |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 9 am to 6 pm UTC | 9 am to 6 pm local time | 108396 | CRQ000000697932 | Approved |  | CRQ000000696051 | Completed | Completed |  |  |  | Circuit Migrated |  |  |  | 2020-04-01
CKT-I-02-CI-ABJ01-0002-VOD-1 | I024767VOD1 | 1 | Yes. Devices swapped | Top | Africa | COTE DIVOIRE | CDI | 2018_58 | un-amt-civabi-vpn002 |  | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | S19090338984 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-08-13 | Complete | 2019-11-18 | 2020-08-22 | Complete | Action Item : Vodacom to proceed with delivery of circuit. 8-May: Internal escalation within Vodacom to get feedback from last mile provider. 22 April - Project ON HOLD - due to COVID-19 lockdown. Feedback regarding lockdown regulations to be provided by Vodacom LCON on the 2904. Attempts to contact Vodacom LL partner and Unilever onsite contact was unsuccessful. 13 Dec: No new update 06 Dec : Same as below 29 Nov : Same status 22 Nov : Pending documents submitted - Sign-off expected by 2211. Physical site survey then to be scheduled. IDD to be provided by 0412. 18 Nov : Target delivery date as Feb 20 provided by VF. No site survey's done yet. 11-Nov : Site survey not yet done, no date provided by VF. 5-Nov: Do Not schedule migration at month end of beginning of the month. Asked feedback from GEO IT on possible suggested dates. Possible options are Saturday or mid of the month | Complete | Circuit Migrated | Circuit Provider |  | CI-ABJ01-0002 | COTE_DIVOIRE_ABIDJAN_BLOHORN |  |  |  |  | Unilever Cote D'Ivoire Boulevard de Vridi 01 BP 1751 Abidjan 01 |  |  |  | Aichath Nzi-Akande | <frederic.maika@unilever.com> |  | Dees Rampartab | Dees.Rampartab@unilever.com | 80MB80MB | 80 |  |  | 2019 | Oct | Internet | 2019-05-15 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Saturday or mid of month. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Joelle.Kouassi@unilever.com +225 0993 2277 | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | 169.239.64.136 /30 169.239.64.120 /29 | 169.239.64.137/30 | 169.239.64.138/30 | 169.239.64.120/29 |  |  | Vodacom CI | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No |  | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 9 am to 6 pm UTC | 9 am to 6 pm local time | 108396 | CRQ000000697932 | Approved |  | CRQ000000696052 | Completed | Completed |  |  |  | Circuit Migrated |  |  |  | 2020-04-01
CKT-I-01-ET-DKM02-0001-VOD-1 | I017687VOD1 | 1 | Yes | Medium | Africa | ETHIOPIA | Ethiopia Addis Ababa | 2018_70 | un-amt-ethadd-vpn001 | un-amt-ethadd-vpn001-new | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | 2-18805196083 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-07-27 | Complete | 2019-11-18 | 2020-08-31 | Complete | Action Item: Vodacom to schedule installation with last mile provider. 20-Aug: MIgration did not proceed ahead as the IP were incorrect from ISP. Migration to be re-planned after ISP provides new IP. 1305:SNT team to facilitate site access to vodacom engineers. 0605-Site Access denied. Request intervention from global team. (mail sent to Welington and Mohan) 2904-LCON engagement has commenced to facilitate access requirement for a physical site survey. 2204- Project ON HOLD - due to COVID-19 lockdown. Feedback regarding lockdown regulations to be provided by Vodacom LCON on the 2904. Attempts to contact Vodacom LL partner and Unilever onsite contact was unsuccessful. Project is managed by our Kenya team, and the lockdown uplifting for Kenya is scheduled for the 13 Dec: No new update 06 Dec : Same as below 29 Nov : Same as below 22 Nov : Pending documents submitted - Sign-off expected by 2211. Physical site survey then to be scheduled. IDD to be provided by 0412. 18 Nov : Target delivery date as Feb 20 provided by VF. No site survey's done yet. 11-Nov : Site survey not yet done, no date provided by VF. | Complete | Circuit Migrated | Circuit Provider |  | ET-DKM02-0001 | ETHIOPIA_UNILEVER |  |  |  |  | Unilever Manufacturing plc woreda 8 Kirkos sub city,house P.O. Box 2396 Addis Abeba | [6 empty] | Dees Rampartab | Dees.Rampartab@unilever.com | 20MB | 20 |  |  | 2019 | Nov | Internet | 2019-11-06 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing |  | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | WAN - 196.189.116.50/30 LAN - 196.188.95.6/29 | 196.189.116.49 | 196.189.116.50 | 196.188.95.6/29 |  |  | Vodacom Kenya\PCCW\G2G | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created | Window Date agreed - End user Comms sent |  | 8 am to 2 pm UTC | 11 am to 5 pm local time | 113337 SSR 113712 Second Ticket:119796 | CRQ000000700458 | Approved |  | CRQ000000701141/CRQ000000704014 | Completed | Completed |  |  |  | Circuit Migrated |  |  |  | 2020-04-01
CKT-I-01-ET-DKM01-0002-VOD-1 | I0112012VOD1 | 1 | Congested but ordered same BW as existing. On further discussion with Deepak, closed. | High | Africa | ETHIOPIA | Ethiopia EIZ | 2018_68 | un-amt-etheiz-vpn001 | un-amt-etheiz-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | 2-18744800944 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-08-31 | Red | 2019-11-18 | 2020-10-30 | Red | Action Item: Vodacom to schedule installation with last mile provider. 2-Sep: This is moved out of scope as ISP is unable to deliver new circuit. UL will continue with existing ISP circuit. 1305:SNT team to facilitate site access to vodacom engineers. 0605-Site Access denied. Request intervention from global team. (mail sent to Welington and Mohan) 2904-LCON engagement has commenced to facilitate access requirement for a physical site survey. 2204- Project ON HOLD - due to COVID-19 lockdown. Feedback regarding lockdown regulations to be provided by Vodacom LCON on the 2904. Attempts to contact Vodacom LL partner and Unilever onsite contact was unsuccessful. Project is managed by our Kenya team, and the lockdown uplifting for Kenya is scheduled for the 13 Dec: No new update 06 Dec : Same as below 29 Nov : Same as below 22 Nov : Pending documents submitted - Sign-off expected by 2211. Physical site survey then to be scheduled. IDD to be provided by 0412. 18 Nov : Target delivery date as Feb 20 provided by VF. No site survey's done yet. 11-Nov : Site survey not yet done, no date provided by VF. | Out of Scope | Circuit Order Accepted | Circuit Provider |  | ET-DKM01-0002 | ETHIOPIA_MANUFACTURING_PLC |  |  |  |  | ETHIOPIA INDUSTRIAL ZONE WAREHOUSE 2 EASTERN INDUSTRY ZONE PLC DUKEM - ADDIS ABABA DUKEM CITY ADDIS ABABA ETHIOPIA | [6 empty] | Dees Rampartab | Dees.Rampartab@unilever.com | 10000Kbps | 10 |  |  | 2019 | Nov | Internet | 2019-11-14 | Commercial Benefit | 1 | Congested Link | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing |  | N | Warehouse 8x 5 - low impact after 5pm | /30 | [8 empty] | Vodacom Kenya\PCCW\G2G | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi |  | Copper - RJ45 | Standard site type - Dual DMVPN |  |  | No | No | No | [20 empty] | 2020-04-01
CKT-I-01-GH-TEM01-0001-VOD-1 | I015VOD1 | 1 | Yes | High | Africa | GHANA | TEMA Head Office | 2018_88 | un-amt-ghatem-vpn001 |  | Prasenjit Pal | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQM-00003 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2019-11-21 | Complete | 2019-11-18 | 2020-01-25 | Complete | 25 Jan: Zscalar Issue resolved. Migration is successful. 19 Jan: Migration schedule confirmed 25th Jan. Risk: May get delayed as Zscalar issue still not resolved. 10-Jan : Testing scheduled on 16th Jan . Migration on 25th Jan 6-Jan: RESCHEDULED: VF changed the IP address as part of redelivery. Hence migration need to be rescheduled. 13 Dec: No new update 06 Dec : Same as below 02 Dec : Geo IT requested for this to be scheduled on 20th Dec. 22 Nov : Migration to be scheduled, 17 Dec. Business approval pending. 21 Nov : Circuit delivered. 18 Nov : Order is well in progress and looks to be delivered by early December. 11-Nov : Order in progress with local partner. Will be able to handover to Vodafone on 19th December if no issues are encountered on-site. Order placed with local partner and pending acceptance. 5-Nov: Plan for a saturday and suggested start time is 8 am. | Complete | Circuit Migrated |  |  | GH-TEM01-0001 | GHANA_ACCRA_PUBLISHING_ROAD_HO_TEMA |  |  |  |  | Tema HO and Factory PLOT No.Industrial Area 2/3A-4 | Tema | 233 |  | Sophia Adjei/Naana Fobil | Sophia.Adjei@unilever.com OR Naana.Fobil@unilever.com | +233 0501323688 or +233202041685 | Dees Rampartab | Dees.Rampartab@unilever.com | 50MB | 60 | 5.6457 | 0.00811 | 2019 | Oct | Internet | 2019-06-11 | Commercial Benefit | 1 | Congested Link | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Jeffrey.Acheampong@unilever.com +233501617364 | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  | Installed Location: Light Industrial Area, Publishing Road Network Rack 3P. Cisco router on-site: Model: Cisco 3560 Serial No.: FOC2035Y4FV | Your vEdge WAN IP: 41.191.244.19 Subnet Mask: 255.255.255.248 Default Gateway:41.191.244.17 Additional Routed subnet for LAN: 41.191.244.8/29 (routed to 41.191.244.19) | 41.191.244.17 | 41.191.244.19 | 41.191.244.16/29 |  |  | Busy Internet | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | 2020-01-27 |  | Standard site type - Dual DMVPN | Complete | NO | No | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 10:00Hrs to 16:00Hrs | 10:00Hrs to 16:00Hrs | 19818 | CRQ000000627654 | Approved | 40795 | CRQ000000632117 | Completed | Completed | Tested -Pass-First Time | Testing of new circuit was successful, ISP cable link was short to be extended to the production router, an ethernet cable and patch panel bridge existing in the server room will be used during migration. Testing done considering the additional expereo device will be bypassed as ISP link should not be terminated on the expereo device. 16th jan: Partial Success testing done considering the expereo monitoring device. Zscaler issue. action item for geoit to test on another laptop on the site 21st Jan: circuit testing completely successful zscaler seeing the right proxy IP |  | Circuit Migrated - First Time right |  |  |  |  | 2019-12-01
CKT-I-02-GH-TEM01-0001-VOD-1 | I025VOD1 | 1 | Yes | Top | Africa | GHANA | TEMA Head Office | 2018_89 | un-amt-ghatem-vpn002 |  | Vishal Joshi | WAN Circuit Migration | Soft Upgrade | Vodafone Local | Vod |  | 2-18805196085 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-08-04 | Complete | 2019-11-18 | 2020-08-04 | Complete | 18-May: Novation to be effective 4th Aug. 29-Apr: These are move out of WAN migration scope to SNT. These circuits will only have change in ownership and no circuit migration required. 13 Dec: No new update 06 Dec : Same as below 29 Nov : Same as below 22 Nov : Pending documents submitted - Sign-off expected by 2211. Physical site survey then to be scheduled. IDD to be provided by 0412. 18 Nov : Target delivery date as Mar 20 provided by VF. No site survey's done yet. 11-Nov : Site survey done, no date provided by VF yet. 5-Nov: Plan for a saturday and suggested start time is 8 am. | Complete | Circuit Migrated | Circuit Provider | Check dates | GH-TEM01-0001 | GHANA_ACCRA_PUBLISHING_ROAD_HO_TEMA |  |  |  |  | Tema HO and Factory PLOT No.Industrial Area 2/3A-4 | Tema | 233 |  | Sophia Adjei/Naana Fobil | Sophia.Adjei@unilever.com OR Naana.Fobil@unilever.com | +233 0501323688 or +233202041685 | Dees Rampartab | Dees.Rampartab@unilever.com | 80MB | 80 | 5.6457 | 0.00811 | 2019 | Oct | Internet | 2019-07-02 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Jeffrey.Acheampong@unilever.com +233501617364 | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 | [8 empty] | Vodafone Ghana | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  | Copper - RJ45 |  | Complete | [5 empty] | Assessment Complete |  |  |  |  | 107850 |  | Approved | [7 empty] | Circuit Migrated
CKT-I-01-GH-TWI01-0001-VOD-1 | I011229VOD1 | 1 | Existing 20 MB, ordered 10 MB. Deepak has already requested for revisions in BW and pricing to make a soft upgrade, Vishal to follow up | Medium | Africa | GHANA | TWIFO Oil Plantation | 2018_90 | un-amt-ghatop-vpn002 |  | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQM-00009 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-07-05 | Complete | 2019-11-18 | 2020-07-25 | Complete | Action Item: Vodafone progressing with circuit delivery. > 7/5/2020: Order has been accepted by the last mile provider. > 2/4/2020: Vodafone has provided confirmation to proceed with 20M/20M service. Expereo shared the PO and pending approval from Vodafone side. 06-April'20 : Hi Prasenjit – I have confirmed our agreement to proceed.Thanks Deepak. Wed 01-04-2020 02:08 07-Jan'20: Unilever has asked VF to increase the bandwidth. Keeping the circuit on hold to avoid delay in migration timeline 13 Dec: Local contact person said the connectivity was rather needed at a another site (1.3km away from the location earlier indicated. Implication: • To deliver the service over fiber to the new site their will be additional higher approx. (12K $) options: • At no additional cost, fibre will be terminated at site 1 and extend to point 2 on point to point (microwave backhaul) on dedicated 10mbps (1:1). 06 Dec : Order is in progress. Our local partner has started the link deployment process. Site to be delivered between the last week of Dec and the second week of Jan. 29 Nov : Four weeks lead time to deliver the circuit 22 Nov : Same update as below. 18 Nov : More than 1km of fiber build is required to reach customer's premises. Estimated provisioning leadtime will be 7 - 9 weeks. 11-Nov : Order in progress with local partner. Will be able to handover to Vodafone on 19th December if no issues are encountered on-site. Order placed with local partner and pending acceptance. 5-Nov: Plan for a saturday and suggested start time is 8 am. | Complete | Circuit Migrated | Circuit Provider |  | GH-TWI01-0001 | GHANA_CAPE_COAST_TOPP |  |  |  |  | Twifo Oil Palm Plantation | TOPP | 233 |  | Samuel Abbey | Samuel.Abbey@unilever.com | +233 0501436035 | Dees Rampartab | Dees.Rampartab@unilever.com | 20MB | 20 | 5.1092 | -1.2454 | 2019 | Nov | Internet | 2019-10-10 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | 1 hr Safety induction from 8 am to 9 am , Nose Mask, ID Card | N | Plantation 8x 5 - low impact after 5pm | /30 |  | 1) Please connect your device to any LAN port (Fa0-Fa3) of Cisco 881-K9(S/N:FCZ2231105Q) | IP Address Subnet Mask Note Static 41.191.241.128 255.255.255.252 Network Address Static 41.191.241.129 255.255.255.252 LAN IP / Default gateway Static 41.191.241.130 255.255.255.252 IP free to use Static 41.191.241.131 255.255.255.252 Broadcast Address Static 41.191.245.96 255.255.255.248 Additional /29 subnet routed to 41.191.241.130 | 41.191.241.129/30 | 41.191.241.130 | 41.191.245.96/29 |  |  | Busy Internet | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 9:30 am – 3:30pm | 9:30 am – 3:30pm | 101556 | CRQ000000692064 | Approved |  | CRQ000000688947 | Completed | Completed |  |  | Samuel. Abbey – +233 0501436035 | Circuit Migrated - First Time right
CKT-I-02-GH-TWI01-0001-VOD-1 | I021229VOD1 | 1 | Yes | Medium | Africa | GHANA | TWIFO Oil Plantation | 2018_91 | un-amt-ghatop-vpn001 |  | Vishal Joshi | WAN Circuit Migration | Soft Upgrade | Vodafone Local | Vod |  | 2-18805762076 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-08-17 | Complete | 2019-11-18 | 2020-09-16 | Red | Action Item: ISP to deliver circuit 1-Sep: This circuit was novated by Vodacom on 25th Aug. Cisco needs to do backend updates. Also address LAN IP pool issue for first link. 2904-Commercial clarification to be resolved by the 0805. Will then proceed with delivery. 2204- COVID-19 lockdown was uplifted on the 2004. Project delays expected due to back logs. 13 Dec : No new update 06 Dec : Same as below 29 Nov : Same as below 22 Nov : Pending documents submitted - Sign-off expected by 2211. Physical site survey then to be scheduled. IDD to be provided by 0412. 18 Nov : No change in status. 11-Nov : Site survey not done, no date provided by VF yet. 5-Nov: Plan for a saturday and suggested start time is 8 am. | Pink | Circuit Delivered | Circuit Provider |  | GH-TWI01-0001 | GHANA_CAPE_COAST_TOPP |  |  |  |  | Twifo Oil Palm Plantation | TOPP | 233 |  | Samuel Abbey | Samuel.Abbey@unilever.com | +233 0501436035 | Dees Rampartab | Dees.Rampartab@unilever.com | 15MB | 15 | 5.1092 | -1.2454 | 2019 | Nov | Internet | 2019-10-10 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | 1 hr Safety induction from 8 am to 9 am , Nose Mask, ID Card | N | Plantation 8x 5 - low impact after 5pm | /30 | [8 empty] | Vodacom Ghana | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN |  |  |  | Yes | No |  | CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression |  |  | 6:00 am – 8:00 am | 6:00 am – 8:00 am | CHG000000000042111 | CRQ000000709331 | Approved | [6 empty] | Samuel. Abbey – +233 0501436035 |  |  |  |  | 2020-03-01
CKT-I-01-KE-NBO06-0001-VOD-1 | I0112002VOD1 | 1 | Yes | Top | Africa | KENYA | Karen | 2018_132 | un-amt-kenkar-vpn001 |  | Prasenjit Pal | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | 2-18805196089 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2019-10-25 | Complete | 2019-11-18 | 2019-12-06 | Complete | 06 Dec : Migration Successful. 02 Dec : Migration planned for 6th Dec. 22 Nov : ISP link testing successful. Migration planned for 6th Dec 18 Nov : Same as below. 11 Nov : Migration planned for 22nd Nov. Agreed by business. Request sent to Geo IT for details. 28-Oct: Received handover certificate from VF on delivery of circuit 27/10 /29 required. existing BW is 50 MBPS and the new BW is 30MPBS | Complete | Circuit Migrated |  |  | KE-NBO06-0001 | KENYA_NAIROBI_LANGATA_COVE_COURT |  |  |  |  | COVE COURT, WATERMARK, NDEGE RD OFF LANGATA RD, NAIROBI, KENYA | Nairobi |  |  | Kumpumula, Muai | Muai.kumpumula@unilever.com | +254 (704) 625008 | Dees Rampartab | Dees.Rampartab@unilever.com | 30MB | 30 |  |  | 2019 | Nov | Internet | 2019-09-28 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing |  | N | Head Office - low impact after 5pm | /29 | 25/10/19: Original order was /30, existing is /29, requested vodacom for /29 IP |  | WAN Block : 41.79.253.20/31 CE IP (WAN) : 41.79.253.21/31 PE IP (WAN) : 41.79.253.20/31 LAN Block : 41.79.253.120/29 | 41.79.253.20/31 | 41.79.253.21/31 | 41.79.253.121/29-41.79.253.126/29 |  |  | Vodacom\Access Kenya | [5 empty] | Pawan Nandigama | Pawan Nandigama | Pawan Nandigama |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | No | No |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression | Window Date agreed - End user Comms sent |  |  |  | 18818 | CRQ000000615545 | Approved | 39861 | CRQ000000616587 | Completed | Completed | Tested -Pass-First Time | Testing of new circuit was successful. During testing, it was identified that LAN IP was not advertised in the ISP end, packet drops observed on ISP link and speed issue was raised to stakeholders - issue was fixed the next day |  | Circuit Migrated - First Time right |  |  |  | 2019-10-01 | 2019-11-01
CKT-I-02-KE-NBO06-0001-VOD-1 | I0212002VOD1 | 1 | Yes | Medium | Africa | KENYA | Karen | 2018_131 | un-amt-kenkar-vpn002 |  | Prasenjit Pal | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | 2-18805196090 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2019-10-25 | Complete | 2019-11-18 | 2020-02-10 | Complete | 11 Feb: Migration done on 10-Feb'20 31 Jan: Unilever requested reschedule. Revised planned date is 10-Feb'20 19 Jan: Troubleshooting call has been scheduled on 21 Jan. 14 Jan: Standby router IOS is lower version. Will check the option of testing on production router. 10 Jan: Test 2 and troubleshooting planned on 14th Jan. UL to confirm time. VC to confirm engineer during testing. 6-Jan: Second attempt. DMVPN tunnel was not coming up. No response for UDP500 packets from hub router. Received confirmation from BT that FW changes are done correctly. Escalated to Vodacom for investigation at their end. Need further troubleshooting. 13 Dec : No new update 06 Dec : Same as below 02 Dec : Migration scheduled for 17th Dec. 22 Nov : Migration planned for 06th Dec. 18 Nov : Same as below. 11 Nov : Migration planned for 06th Dec. Agreed by business. 28-Oct: Received handover certificate from VF on delivery of circuit 27/10 /29 required. existing BW is 50 MBPS and the new BW is 30MPBS | Complete | Circuit Migrated |  |  | KE-NBO06-0001 | KENYA_NAIROBI_LANGATA_COVE_COURT |  |  |  |  | COVE COURT, WATERMARK, NDEGE RD OFF LANGATA RD, NAIROBI, KENYA | Nairobi |  |  | Kumpumula, Muai | Muai.kumpumula@unilever.com | +254 (704) 625008 | Christopher Gatumbi | Christopher.Gatumbi@unilever.com | 50MB50MB | 50 |  |  | 2019 | Oct | Internet | 2019-05-17 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing |  | N | Head Office - low impact after 5pm | /29 | 25/10/19: Original order was /30, existing is /29, requested vodacom for /29 IP |  | WAN Block : 41.79.252.52/31 CE IP (WAN) : 41.79.252.53/31 PE IP (WAN) : 41.79.252.52/31 LAN Block : 41.79.252.64/29 | 41.79.252.52/31 | 41.79.252.53/31 | 41.79.252.65/29-41.79.252.70/29 |  |  | Vodacom\Liquid Telecom | [5 empty] | Pawan Nandigama | Pawan Nandigama | Pawan Nandigama | 2020-02-11 | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | No | No | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created | Window Date agreed - End user Comms sent |  | 15:00 Hrs – 21:00 Hrs UTC | 18:00 Hrs – 00:00 Hrs | 15007 | CRQ000000636896 CRQ000000625265 CMSP : 18818 | Approved | 39861 | CRQ000000616587 | Completed | Completed | Tested -Pass-First Time | Testing of new circuit was successful. During testing, it was identified that LAN IP was not advertised in the ISP end, packet drops observed on ISP link and speed issue was raised to stakeholders - issue was fixed the next day |  | Circuit Migrated | DMVPN Tunnel is not coming up post migration. |  |  | 2019-10-01 | 2019-11-01
CKT-I-01-KE-KEY05-0001-VOD-1 | I012776VOD1 | 1 | Yes | High | Africa | KENYA | Kericho | 2018_126 | un-amt-kenker-vpn001 | un-amt-kenker-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQM-00020 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-08-26 | Complete | 2019-11-18 | 2020-09-10 | Red | Action Item: ISP to deliver circuit 4-Aug: Agile resiliency need to be configured on both links. Allocate 20MB for agile 9/4/2020: Order is not progressing due to Covid-19 lockdown in-country. 13 Dec: Our local partner has completed the external fiber pulling to customer's premises. We are now pending the scheduleing of modem installation, circuit activation and CPE installation. 06 Dec : Revised EDD of 27th December updated for this site. 29 Nov : Same as below 22 Nov : EDD around mid-Dec. 18 Nov : No change in status. 11-Nov : Order in progress with local partner. EDD is around mid-December. Order placed with local partner and pending acceptance. | Green | Circuit Delivered | Circuit Provider |  | KE-KEY05-0001 | KENYA_KERICHO_HO_NAKURU_KERICHO_HIGHWAY_2 |  |  |  |  | Unilever Tea Kenya Limited Registered Office: Unilever Tea Kenya Limited, Off Nakuru-Kericho Highway |  |  |  | Kumpumula, Muai | Muai.Kumpumula@unilever.com | +254 (709) 050257 | Christopher Gatumbi | Christopher.Gatumbi@unilever.com | 40MB | 70 |  |  | 2019 | Nov | Internet | 2019-10-24 | Commercial Benefit | 1 | Congested Link | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | Jane.Muchunu@unilever.com +254 721436753 George.Wanjohi@unilever.com + 254 722307394 | N | Plantation 8x 5 - low impact after 5pm | /30 |  |  | Static 41.209.12.184 255.255.255.252 Network Address Static 41.209.12.185 255.255.255.252 LAN IP / Default gateway Static 41.209.12.186 255.255.255.252 IP free to use Static 41.209.12.187 255.255.255.252 Broadcast Address Static 41.209.12.208 255.255.255.248 Additional /29 subnet routed to 41.209.12.186 | 41.209.12.185 | 41.209.12.186 | 41.209.12.208/29 |  |  | MTN | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi |  |  | Standard site type - Dual DMVPN | In Progress |  | No |  | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 7 am to 1 pm UTC | 10 am to 4 pm Local time | CHG000000000041889 | CRQ000000707595 | Approved |  | CRQ000000705724 | Completed | Completed | [7 empty] | 2020-02-01
CKT-I-02-KE-KEY05-0001-VOD-1 | I022776VOD1 | 1 | Yes | High | Africa | KENYA | Kericho | 2018_125 | un-amt-kenker-vpn002 | un-amt-kenker-vpn002 | Prasenjit Pal | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQM-00011 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-02-07 | Complete | 2019-11-18 | 2020-03-06 | Complete | 06- Feb: RFS Shared. Circuit delivered 03 Feb: Design document updating is in progress, considering merger of Agile Wifi with this circuit. 13 Dec: No new update 06 Dec : No update 29 Nov: Expereo have notified us that full diversity cannot be reached if this link is delivered via fiber. This is due to there being only one single POP in the area for fiber. An alternative we can deliver is to provision this service via wireless, which will allow for full diversity. Also, there will not be any commercial changes if this option is accepted. Pending Unilever to take a decission. 22 Nov : Same as below. 18 Nov : Local contacts provided. Order placed with local partner and currently in design stage. 11-Nov : VF has sent the POs to Expereo. Delay in progress. | Complete | Circuit Migrated |  |  | KE-KEY05-0001 | KENYA_KERICHO_HO_NAKURU_KERICHO_HIGHWAY_2 |  |  |  |  | KENYA_KERICHO_HO, KENYA_KERICHO_HO_NAKURU_KERICHO_HIGHWAY_2 | Kericho | 20200 |  | Joseph Nganga | joseph.nganga2@unilever.com | +254704976421 | Christopher Gatumbi | Christopher.Gatumbi@unilever.com | 40 | 70 |  |  | 2019 | Oct | Internet | 2019-10-24 | Commercial Benefit | 1 | Congested Link | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | Jane.Muchunu@unilever.com +254 721436753 George.Wanjohi@unilever.com + 254 722307394 | N | Plantation 8x 5 - low impact after 5pm | /30 |  |  | IP Address Subnet Mask Note Static 196.216.69.96 255.255.255.252 Network Address Static 196.216.69.97 255.255.255.252 LAN IP / Default gateway Static 196.216.69.98 255.255.255.252 IP free to use Static 196.216.69.99 255.255.255.252 Broadcast Address Static 196.216.67.80 255.255.255.248 Additional /29 Subnet Routed to 196.216.69.98 Brand CPE Type Wan IP Address Lan IP Address Lan Interface MikroTik RB2011UiAS Router 196.216.67.66 196.216.69.97 FastEthernet 100BaseT MikroTik RB260GS NID 0.0.0.0 0.0.0.0 FastEthernet | 196.216.69.97/30 | 196.216.69.98/30 | 196.216.67.80/29 | [8 empty] | Kastriot Dragusha | Kastriot Dragusha | Kastriot Dragusha | 2020-03-09 |  | Standard site type - Dual DMVPN | Complete | NO | No | No | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 14:00 Hrs. – 20:00 Hrs | 17:00 Hrs – 23:00 Hrs | 44657 | CRQ000000648357 | Approved | 41333 | CRQ000000642814 | Completed | Completed | Tested -Pass-First Time | The test was successful, including the Zscaler as confirmed by Dragusha Kastriot | Kastriot Dragusha | Circuit Migrated - First Time right |  |  |  | 2019-12-01 | 2020-03-01
CKT-I-01-KE-NBO02-0001-VOD-1 | I016VOD1 | 1 | Yes | High | Africa | KENYA | Nairobi Commercial Street | 2018_130 | un-amt-kennai-vpn001 | un-amt-kennai-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQM-00004 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-02-10 | Complete | 2019-11-18 | 2020-07-24 | Complete | Next Action: ISP to investigate and advise root cause. 24-Jul: Completed in 3rd attempt. No changes done by ISP or Cisco and tunnels came up in this attempt. 20-Jul: Timing changed to 6 am local time. 22-Jun: Migration rolled back, DMVPN tunnel did not come up. 11-Jun: GEO IT asked for revised schedule of 20 Jun. 3-Jun: GEO IT asked to replan the migration on 19 Jun from 15 Jun. Schedule will be confirmed after lockdown is lifted on 6th Jun. 27-May: GEO IT advised to plan migration after 6th Jun when lock down will end. Sent a proposal to migrate the link on 15th Jun and need GEO IT confirmation 29 April: Action Item for Geo IT (Christopher Gatumbi) to confirm the date to schedule migration. (Currently migration on Hold as requested by Geo IT due to Covid situation) 18 Apr: ON HOLD - Not received site approval 23 Mar: Migration not successful. DMVPN not coming up. Need to troubleshoot at service provider end 02 Mar: Reinitiated migration process. 25 Feb: All migration process suspended. 24 Feb: As advised by Deepak by email on 24 Feb'20 12 Feb: Circuit delivered on 12 Feb'20 13 Dec: External fiber build is in progress for this site and is targeted to be completed by end of next week. 06 Nov : External fiber build is in progress for this site. 29 Nov : Currently the fiber deployment to site is in progress. 18 Nov : Change request to deliver /29 accepted by Expereo. 11-Nov : order in progress with local partner. EDD is around mid-December. Order placed with local partner and pending acceptance 24/10 (AP) Tech team requested change from /30 to /29. Email sent to Deepak and Welington. Vishal to pick up with the provider. | Complete | Circuit Migrated | Circuit Provider |  | KE-NBO02-0001 | KENYA_NAIROBI_HO_COMMERCIAL_STREET |  |  |  |  | Unilever, Commercial Street, Industrial Area ,Nairobi | Nairobi |  |  | Khan, Clyde | Clyde clyde.khan@unilever.com | +254 (721) 847965 | Christopher Gatumbi | Christopher.Gatumbi@unilever.com | 40MB | 40 |  |  | 2019 | Nov | Internet | 2019-09-21 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing |  | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /29 | 25/10/19: Original order was /30, existing is /29, requested vodacom for /29 IP |  | 08-April'20 NEW IP : PE IP: 197.155.76.73/30 CE IP: 197.155.76.74/30 OLD-------- IP Address Subnet Mask Note Static 196.216.69.36 255.255.255.252 Network Address Static 196.216.69.37 255.255.255.252 LAN IP / Default gateway Static 196.216.69.38 255.255.255.252 IP free to use Static 196.216.69.39 255.255.255.252 Broadcast Address Static 196.216.69.16 255.255.255.248 Additional /29 subnet routed to 196.216.69.38 Brand CPE Type Wan IP Address Lan IP Address Lan Interface MikroTIk 2011UiAS-2HnD Router 196.216.69.2 196.216.69.38 FastEthernet 100BaseT MikroTik RB260 NID 0 0 FastEthernet 100BaseT AN Block CE IP (WAN) PE IP (WAN) LAN Block | 196.216.69.37/30 | 196.216.69.38/30 | 196.216.69.16/29 |  |  | ZTE | [5 empty] | Kastriot Dragusha | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | 2020-06-22 |  | Standard site type - Dual DMVPN | Complete | NO | No | No |  | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression | Window Date agreed - End user Comms not sent |  | 06:00 Hrs. – 09:00 Hrs | 06:00 Hrs – 12:00 Hrs. | 75158(20th June) 101814(24th July) | CRQ000000653327(Old March) CRQ000000682830 (20 JUn) CRQ000000693239 (24 Jul) | Approved | 41363 | CRQ000000643840 | Completed | Completed | Tested -Pass-First Time | Everything worked fine- Internet, Ping test and Speed except Zscaler, will check with BT and go back to unilever team. Till then this will not be considered as complete. BT came back stating it's fine, if it is reflecting lagos II. Based on that it is considered as successful. |  | Circuit Migrated | DMVPN not coming up in both iterations of migration. Completed successfully in third attempt | INCV00291067 |  | 2019-12-01 | 2020-03-01
CKT-I-02-KE-NBO02-0001-VOD-1 | I026VOD1 | 1 | Yes | Medium | Africa | KENYA | Nairobi Commercial Street | 2018_129 | un-amt-kennai-vpn002 |  | Prasenjit Pal | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | 2-18805196088 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2019-10-28 | Complete | 2019-11-18 | 2019-12-11 | Complete | 13 Dec: Migration successful. 06 Nov : Same as below. 02 Dec : Migration re-planned for 11th Dec. 22 Nov : Migration planned for 28th Nov. 18 Nov : Migration planned for today. Issues faced. LAN configurations were not checked by the provider. Also they could only get 20 Mbps download speeds during their test. Need to ensure for other sites all these tests to be done at the time of providing the circuit. 11 Nov : Migration planned for 18th Nov. Agreed by business. Request sent to Geo IT for details. 29-Oct: Received handover certificate from VF on delivery of circuit | Complete | Circuit Migrated |  |  | KE-NBO02-0001 | KENYA_NAIROBI_HO_COMMERCIAL_STREET |  |  |  |  | Unilever, Commercial Street, Industrial Area ,Nairobi | Nairobi |  |  | Khan, Clyde | Clyde clyde.khan@unilever.com | +254 (721) 847965 | Christopher Gatumbi | Christopher.Gatumbi@unilever.com | 70MB30MB | 70 |  |  | 2019 | Nov | Internet | 2019-05-22 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Training required must be provided by SHE officer. Reach site before 2 pm. Training will be from 2 pm for 1 hour | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /29 | 25/10/19: Original order was /30, existing is /29, requested vodacom for /29 IP | Server Room, 1 Floor | WAN Block : 41.79.253.94/31 CE IP (WAN) : 41.79.253.95/31 PE IP (WAN) : 41.79.253.94/31 LAN Block : 41.79.253.112/29 | 41.79.253.94/31 | 41.79.253.95/31 | 41.79.253.113/29-41.79.253.118/29 |  |  | Vodacom\Jamii Telcom | [5 empty] | Karthik Ravi | Karthik Ravi | Karthik Ravi |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | [5 empty] | Assessment Complete MOP created & config created | Window Date agreed - End user Comms sent |  |  |  | 16552 | CRQ000000620623 CMSP : 16552 | Approved | 39855 | CRQ000000623252 | Completed | Completed | Tested-Pass | 13th Nov: Testing of new circuit was failed. During testing, it was identified that LAN IP was not advertised in the ISP end, issue resolved the next day 14th Nov: Testing was successful, however there was a speed issue and was raised to stakeholders | Muai.Kumpumula@unilever.com +254 (704) 625008 | Circuit Migrated - First Time right | Existing link failed before start of migration and window had to be cancelled. |  |  | 2019-10-01 | 2019-11-01
CKT-I-01-MW-LLW01-0001-VOD-1 | I0111200VOD1 | 1 | Yes | High | Africa | MALAWI | Malawi Office | 2018_135 | un-amt-mwilil-vpn002 | un-amt-mwilil-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | 2-18805196087 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-03-12 | Complete | 2019-11-18 | 2020-05-20 | Complete | Action Item: Migrated. 11-Jun: Additional maintenance window scheduled on 11 Jun to configure NAT on LAN IP pool. Had issues with the routing of LAN IP Pool. Mwayi joined the bridge after multiple escalation and fixed the routing issues. Change was successful. 20-May: Links were successfully tested on 19 may by Vodacom. Circuit migrated. Had issue with LAN IP pol delivered by Vodacom. There was no internet connectivity when configured on router. Applied a work around to overload interface with NAT IP. Escalated to Vodacom to investigate further. 5-May: Testing of the circuit failed. Escalated to Vodacom to fix the issue. Based on discussion with Tawanda, need to plan migration of both links on the same day. 29 April: Action Item: Cisco to test the circuit on 05 May and plan the migration 18 Apr: ON HOLD due to lockdown 22 Mar: Circuit has been delivered 13 Dec: No new update 06 Nov : Same as below, PO expected by 0612 29 Nov : On track for PO 22 Nov : Vendor PO creation in progress. Expecting PO's by 0612 18 Nov : Target delivery date as Mar 20 provided by VF. No site survey's done yet. 11 Nov : VF is expecting the PO from vendor by mid-Nov. Site survey not yet done | Complete | Circuit Migrated | Circuit Provider |  | MW-LLW01-0001 | MALAWI_LILONGWE_OLD_TOWN | 01-August-2020 | Open |  |  | Unilever Lilongwe office – Office No 33, Gateway Mall, Area 47, Lilongwe. | Lilongwe |  | Office | Kamanga, George | GeorgePhillip.Kamanga@intoutsource.com | Mobile: +26599188 6452 | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com | 10000Kbps | 10 |  |  | 2019 | Nov | Internet | 2019-07-02 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | Need to carry Masks | N | Sales office - low impact after 5pm | /30 |  |  | LAN 41.75.127.56/29 WAN 41.75.127.144/30 | 41.75.127.145/30 | 41.75.127.146/30 | 41.75.127.56/29 |  |  | Vodacom\Skyband | [5 empty] | Kastriot Dragusha | Kastriot Dragusha | Kastriot Dragusha | 2020-05-21 | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | [5 empty] | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 08:00 Hrs. To 14:00 Hrs. | 10:00 Hrs. To 16:00 Hrs 7:00 Hrs. To 23:00 Hrs | 73943 62740, SSR 67829 | CRQ000000669503 | Approved | 41889 | CRQ000000655334 | Completed | Completed | Tested-Pass | Test failed as we were unable to connect to the internet and also all the ping test returned 100% loss. We were able to connect to the internet, when we did the testing for the 2nd time on 19th May the Speed was very good and also there were no loss of packets with the Ping. We can consider this testing as successful. | Email: Kamanga, George GeorgePhillip.Kamanga@intoutsource.com Mobile: +26599188 6452 | Circuit Migrated - First Time right |  |  |  | 2020-03-01 | 2020-04-01
CKT-I-02-MW-LLW01-0001-VOD-1 | I0211200VOD1 | 1 | Yes | Medium | Africa | MALAWI | Malawi Office | 2018_136 | un-amt-mwilil-vpn001 | un-amt-mwilil-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | 2-18805196087 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-03-12 | Complete | 2019-11-18 | 2020-05-20 | Complete | Action Item: Migrated. 11-Jun: Additional maintenance window scheduled on 11 Jun to configure NAT on LAN IP pool. Had issues with the routing of LAN IP Pool. Mwayi joined the bridge after multiple escalation and fixed the routing issues. Change was successful. 20-May: Links were successfully tested on 19 may by Vodacom. Circuit migrated. Had issue with LAN IP pol delivered by Vodacom. There was no internet connectivity when configured on router. Applied a work around to overload interface with NAT IP. Escalated to Vodacom to investigate further. 5-May: Testing of the circuit failed. Escalated to Vodacom to fix the issue. Based on discussion with Tawanda, need to plan migration of both links on the same day. 29 April: Action Item: Cisco to test the circuit on 05 May and plan the migration 18 Apr: ON HOLD due to lockdown 22 Mar: Circuit has been delivered 13 Dec: No new update 06 Nov : Same as below, PO expected by 0612 29 Nov : On track for PO 22 Nov : Vendor PO creation in progress. Expecting PO's by 0612 18 Nov : Target delivery date as Mar 20 provided by VF. No site survey's done yet. 11 Nov : VF is expecting the PO from vendor by mid-Nov. Site survey not yet done | Complete | Circuit Migrated | Circuit Provider |  | MW-LLW01-0001 | MALAWI_LILONGWE_OLD_TOWN | 01-August-2020 | Open |  |  | Unilever Lilongwe office – Office No 33, Gateway Mall, Area 47, Lilongwe. | Lilongwe |  | Office | Kamanga, George | GeorgePhillip.Kamanga@intoutsource.com | Mobile: +26599188 6452 | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com | 10000Kbps | 10 |  |  | 2019 | Nov | Internet | 2019-06-20 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | Need to carry Masks | N | Sales office - low impact after 5pm | /30 |  |  | LAN 41.75.127.64/29 WAN 41.75.127.244/30 | 41.75.127.245/30 | 41.75.127.246/30 | 41.75.127.64/29 |  |  | Vodacom\Skyband | [5 empty] | Kastriot Dragusha | Kastriot Dragusha | Kastriot Dragusha | 2020-05-21 | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | [5 empty] | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 08:00 Hrs. To 14:00 Hrs. | 10:00 Hrs. To 16:00 Hrs 7:00 Hrs. To 23:00 Hrs | 73943 62740, SSR 67829 | CRQ000000669503 | Approved | 42828 | CRQ000000670683 | Completed | Completed | Tested-Pass | Test failed as we were unable to connect to the internet and also all the ping test returned 100% loss. We were able to connect to the internet, when we did the testing for the 2nd time on 19th May the Speed was very good and also there were no loss of packets with the Ping. We can consider this testing as successful. | Email: Kamanga, George GeorgePhillip.Kamanga@intoutsource.com Mobile: +26599188 6452 | Circuit Migrated - First Time right |  |  |  | 2020-03-01 | 2020-04-01
CKT-I-01-NG-AGB02-0001-VOD-1 | I0110VOD1 | 1 | Congested but ordered same BW as existing. On further discussion with Deepak, closed. | High | Africa | NIGERIA | AGBARA FACTORY | 2018_172 | un-amt-ngaabg-vpn002 | un-amt-ngaabg-vpn002 | Vishal Joshi | WAN Circuit Migration | Soft Upgrade | Vodafone Local | Vod |  | 2-18805196103 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-07-17 | Complete | 2019-11-18 | 2020-07-17 | Complete | Action Item: ISP to proceed with delivery 15-JUl: As discussed in call with Vodacom and GEO IT, no mirgation is required. This is a soft upgrade and Cisco will do the back end chnages. 2904-Commercial clarification to be resolved by the 0805. Will then proceed with delivery. 2204-COVID-19 lockdown is scheduled to uplifted by 3004. Delivery to commence thereafter. 13 Dec: No new update 06 Nov : Same as below 29 Nov : Pending LOI and SO sign-off - escalated to Wellignton\Babara\Naren. 22 Nov : Pending documents submitted - Sign-off expected by 2211. Physical site survey to then be scheduled. IDD to be provided by 0412. 18 Nov : Target delivery date as Feb 20 provided by VF. No site survey's done yet. 11 Nov : VF is expecting the PO from vendor by mid-Nov. Site survey not yet done | Complete | Circuit Migrated | Circuit Provider | Check dates | NG-AGB02-0001 | NIGERIA_OREGUN_STATE_AGBARA |  |  |  |  | KM 32 Lagos Badagry Expressway, Agbara, Ogun State, Nigeria | Agbara | 112102 |  | Paul Anoruem | Paul.Anoruem@unilever.com | 2348034035153 | Dees Rampartab | Dees.Rampartab@unilever.com | 70MB | 70 | 6.4531 | 3.3958 | 2019 | Oct | Internet | 2019-07-16 | Commercial Benefit | 1 | Congested Link | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Rachael Ezembakwe Rachael.Ezembakwe@unilever.com +2349070001799 or +2348023020249 | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | 155.93.107.22/30 subnet255.255.255.252 gw 155.93.107.21 | [5 empty] | Vodacom Nigeria | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN |  | NO | No | No | No | [6 empty] | 102214 |  | Approved | [7 empty] | Circuit Migrated |  |  |  | 2020-04-01
CKT-I-01-NG-AGB01-0001-VOD-1 | I0110098VOD1 | 1 | Yes | High | Africa | NIGERIA | MEGA DC AGBARA | 2018_168 | un-amt-ngamdc-vpn002 | un-amt-ngamdc-vpn002 | Vishal Joshi | WAN Circuit Migration | Soft Upgrade | Vodafone Local | Vod |  | 2-18805196099 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-07-17 | Complete | 2019-11-18 | 2020-07-17 | Complete | Action Item : ISP to proceed with delivery 15-JUl: As discussed in call with Vodacom and GEO IT, no mirgation is required. This is a soft upgrade and Cisco will do the back end chnages. 2904-Commercial clarification to be resolved by the 0805. Will then proceed with delivery. 2204-COVID-19 lockdown is scheduled to uplifted by 3004. Delivery to commence thereafter. 13 Dec: No new update 06 Nov : Same as below 29 Nov : Pending LOI and SO sign-off - escalated to Wellignton\Babara\Naren. 22 Nov : Pending documents submitted - Sign-off expected by 2211. Physical site survey to then be scheduled. IDD to be provided by 0412. 18 Nov : Target delivery date as Feb 20 provided by VF. No site survey's done yet. 11 Nov : VF is expecting the PO from vendor by mid-Nov. Site survey not yet done | Complete | Circuit Migrated | Circuit Provider | Check dates | NG-AGB01-0001 | NIGERIA_MEGA DISTRIBUTION CENTER |  |  |  |  | Mega Distribution Center, Plot No. C20/3 Industrial Layout, Agbara Village via Igbesa, Ado-Odo/Otta South L.G.A. Ogun State. | Agbara | 112102 |  | Olufemi AKINGBEHIN | Olufemi.AKINGBEHIN@unilever.com | 2348165624539 | Dees Rampartab | Dees.Rampartab@unilever.com | 25MB | 25 | 6.4531 | 3.3958 | 2019 | Nov | Internet | 2019-07-16 | Commercial Benefit | 1 | Congested Link | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Rachael Ezembakwe Rachael.Ezembakwe@unilever.com +2349070001799 or +2348023020249 | N | Warehouse 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | 155.93.107.50/30 subnet 255.255.255.252 gw155.93.107.49 | [5 empty] | Vodacom Nigeria | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN |  | NO | No |  | No | [6 empty] | 102214 |  | Approved | [7 empty] | Circuit Migrated |  |  |  | 2020-04-01
CKT-I-01-NG-LOS02-0001-VOD-1 | I0112VOD1 | 1 | Yes. Routers swapped | Top | Africa | NIGERIA | OREGUN HO | 2018_170 | un-amt-ngalag-vpn001 |  | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | 2-18805196101 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-07-27 | Complete | 2019-11-18 | 2020-08-21 | Complete | Action Item: ISP to proceed with delivery 17-Aug: Migration cancelled on 14 Aug as the circuit testing results were not satisfactory for GEO IT. 2904-Commercial clarification to be resolved by the 0805. Will then proceed with delivery. 18/3/2020: Site is closed until further notice due to COVID-19 pandemic. 13 Dec: No new update 06 Nov : Same as below 29 Nov : Pending LOI and SO sign-off - escalated to Wellignton\Babara\Naren. 22 Nov : Pending documents submitted - Sign-off expected by 2211.Physical site survey to then be scheduled. IDD to be provided by 0412. 18 Nov : Target delivery date as Feb 20 provided by VF. No site survey's done yet. 11-Nov : Site survey not done, no date provided by VF yet. | Complete | Circuit Migrated | Circuit Provider |  | NG-LOS02-0001 | NIGERIA_OREGUN_HO_BILLINGSWAY |  |  |  |  | 1 Billings Way, Oregun, Ikeja | Lagos | 100212 |  | Chidobem Mgbachi | Chidobem.Mgbachi@unilever.com | 2347064002008 | Dees Rampartab | Dees.Rampartab@unilever.com | 60MB | 60 | 6.7052 | 3.2611 | 2019 | Oct | Internet | 2019-08-14 | Commercial Benefit |  |  | SC2 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Rachael Ezembakwe Rachael.Ezembakwe@unilever.com +2349070001799 or +2348023020249 | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | IP 155.93.107.42 255.255.255.252 GW 155.93.107.41 | 155.93.107.41/30 | 155.93.107.42/30 |  |  |  | Vodacom Nigeria | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No |  | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 6 am to 8 am UTC | 7 am to 9 am local time | 112029 | CRQ000000699548 | Approved |  | CRQ000000697636 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-04-01
CKT-I-02-NG-LOS02-0001-VOD-1 | I0212VOD1 | 1 | Yes. Routers swapped | High | Africa | NIGERIA | OREGUN HO | 2018_169 | un-amt-ngalag-vpn002 |  | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | 2-18805196100 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-07-27 | Complete | 2019-11-18 | 2020-09-14 | Red | Action Item: ISP to proceed with delivery 2904-Commercial clarification to be resolved by the 0805. Will then proceed with delivery. 2204-COVID-19 lockdown is scheduled to uplifted by 3004. Delivery to commence thereafter. 13 Dec: No new update 06 Nov : Same as below 29 Nov : Pending LOI and SO sign-off - escalated to Wellignton\Babara\Naren. 22 Nov : Pending documents submitted - Sign-off expected by 2211. Physical site survey to then be scheduled. IDD to be provided by 0412. 18 Nov : Target delivery date as Feb 20 provided by VF. No site survey's done yet. 11-Nov : Site survey not done, no date provided by VF yet. 05/11 Welington requested to move one of the migrations in Oregun HO to January to ensure there is enough lead time between migrations | Pink | Circuit Delivered | Circuit Provider |  | NG-LOS02-0001 | NIGERIA_OREGUN_HO_BILLINGSWAY |  |  |  |  | 1 Billings Way, Oregun, Ikeja | Lagos | 100212 |  | Chidobem Mgbachi | Chidobem.Mgbachi@unilever.com | 2347064002008 | Dees Rampartab | Dees.Rampartab@unilever.com | 100M | 100 | 6.7052 | 3.2611 | 2019 | Oct | Internet | 2019-07-17 | Commercial Benefit | 1 | Congested Link | SC2 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Rachael Ezembakwe Rachael.Ezembakwe@unilever.com +2349070001799 or +2348023020249 | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | IP 155.93.117.238 255.255.255.252 GW155.93.117.237 | 155.93.117.237/30 | 155.93.117.238/30 |  |  |  | Vodacom Nigeria | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No |  | No |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression |  |  | 6 am to 8 am UTC | 7 am to 9 am local time | 112309 | CRQ000000700156(Cancelled) |  |  | CRQ000000697752 | Completed | Completed | [7 empty] | 2020-04-01
CKT-I-01-ZA-SDT01-0001-VOD-1 | I0120117VOD1 | 1 | Yes | High | Africa | SOUTH AFRICA | Athol Towers (Sandton) | 2018_227 | un-amt-zafwmd-vpn001 |  | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  |  | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-11-30 | Red | 2019-11-18 | 2020-12-31 | Red | Next Action: ISP to deliver circuit 28-Jul: Moving out of scope as the site is relocating and will be handled under a BAU project. 15-May: This is added back to scope per discussion with Mark. 18 Mar: Athol Tower moving to Sandton and will be taken care by BAU project team as part of office move GDM00003524 - Relocation of Atholl office to new location Mon 09-03-2020 18:34 Hi Mark, Update – We will work on it as a BAU project. I will have another round of internal discussions and share the proposal for the WAN IP configuration. Regards Mayur 13 Dec: No new update 06 Dec : Unilever has requested for a hardcopy of the H&S file on the 0212. H&S file will be submitted by 0612. 29 Nov : IDD: end Jan 20 22 Nov : Approvals received. IDD to be provided 2711 18 Nov : Target delivery date as Mar 20 provided by VF. No site survey's done yet. 11-Nov : Site survey not done, no date provided by VF yet. | Out of Scope | Circuit Order Accepted | Circuit Provider |  | ZA-SDT01-0001 | SOUTH_AFRICA_SANDTON |  |  |  |  | 129 Patricia Rd, Sandown, Atholl Towers, 2nd floor | Sandton | 2031 |  | Angela Ramothata | Angela.Ramothata@unilever.com | +27 11 540 0400 | Dees Rampartab | Dees.Rampartab@unilever.com | 50MB50MB | 50 | -26.1056 | 28.0686 | 2019 | Nov | Internet | 2019-07-19 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | Kelello.Mota@unilever.com | N | Head Office - low impact after 5pm | /30 |  |  |  | 105.247.209.185/30 | 105.247.209.186/30 | 105.242.195.72/29 |  |  | Vodacom\Mobax | [9 empty] | Copper - RJ45 | Standard site type - Dual DMVPN | In Progress |  | No | Yes | No |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression | Window Date agreed - End user Comms not sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 96115 | CRQ000000690619 |  |  | CRQ000000687779 | Completed | Completed | [7 empty] | 2020-02-01
CKT-I-02-ZA-SDT01-0001-VOD-1 | I0220117VOD1 | 1 | Yes | High | Africa | SOUTH AFRICA | Athol Towers (Sandton) | 2018_228 | un-amt-zafwmd-vpn002 |  | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  |  | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-11-30 | Complete | 2019-11-18 | 2020-12-31 | Red | Next Action: IISP to deliver circuit 28-Jul: Moving out of scope as the site is relocating and will be handled under a BAU project. 15-May: This is added back to scope per discussion with Mark. 18 Mar: Athol Tower moving to Sandton and will be taken care by BAU project team as part of office move GDM00003524 - Relocation of Atholl office to new location Mon 09-03-2020 18:34 Hi Mark, Update – We will work on it as a BAU project. I will have another round of internal discussions and share the proposal for the WAN IP configuration. Regards Mayur 13 Dec: No new update 06 Dec : Unilever has requested for a hardcopy of the H&S file on the 0212. H&S file will be submitted by 0612. 29 Nov : IDD: end Jan 20 22 Nov : Approvals received. IDD to be provided 2711 18 Nov : Target delivery date as Mar 20 provided by VF. No site survey's done yet. 11-Nov : Site survey not done, no date provided by VF yet. | Out of Scope | Circuit Delivered | Circuit Provider |  | ZA-SDT01-0001 | SOUTH_AFRICA_SANDTON |  |  |  |  | 129 Patricia Rd, Sandown, Atholl Towers, 2nd floor | Sandton | 2031 |  | Angela Ramothata | Angela.Ramothata@unilever.com | +27 11 540 0400 | Dees Rampartab | Dees.Rampartab@unilever.com | 70MB70MB | 70 | -26.1056 | 28.0686 | 2019 | Nov | Internet | 2019-12-12 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | Kelello.Mota@unilever.com | N | Head Office - low impact after 5pm | /30 |  |  |  | 105.242.122.113/30 | 105.242.122.114/30 | 105.242.122.112/29 |  |  | Vodacom\Mobax | [9 empty] | Copper - RJ45 | Standard site type - Dual DMVPN | In Progress |  | No | Yes | No |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression | Window Date agreed - End user Comms not sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 96115 | CRQ000000690619 |  |  | CRQ000000688002 | Completed | Completed | [7 empty] | 2020-02-01
CKT-I-01-ZA-BOK01-0004-VOD-1 | I0115VOD1 | 1 | Existing 60 MB, ordered 40 MB. Revised capacity ordered by Deepak. Need to validate during circuit testing. | High | Africa | SOUTH AFRICA | Boksburg Factory | 2018_221 | un-amt-zafbbg-vpn001 | un-amt-zafbbg-vpn001 | Prasenjit Pal | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | L19090570082 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-03-18 | Complete | 2019-11-18 | 2020-03-12 | Complete | 8 Jan: New BW of 60 MB ordered by Deepak for this circuit on feedback from Ashritha 13 Dec: No new update 06 Dec : Unilever has requested for a hardcopy of the H&S file on the 0212. H&S file will be submitted by 0612. 29 Nov : IDD: end Jan 20 22 Nov : Approvals received. IDD to be provided 2711 18 Nov : Target delivery date as Feb 20 provided by VF. No site survey's done yet. 11-Nov : Site survey not done, no date provided by VF yet. | Complete | Circuit Migrated |  | Check dates | ZA-BOK01-0004 | SOUTH_AFRICA_BOKSBURG_COMMISSIONER_STREET_UNIFOODS |  |  |  |  | 511 Commissioner Street | Boksburg | 1460 |  | Louisa Maphuthaees | louisa.maphutha@unilever.com | +27794385224 | Louisa Maphuthaees | louisa.maphutha@unilever.com | 60MB60MB | 60 | -26.2197 | 28.2732 | 2019 | Oct | Internet | 2019-07-19 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Mathubamahle.Ntshangase@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | WAN RANGE: 105.247.222.104/30 WAN PE IP: 105.247.222.105/30 WAN CE IP: 105.247.222.106/30 LAN RANGE:105.247.220.232/29 | 105.247.222.105 | 105.247.222.106 | 105.247.220.232/29 |  |  | Vodacom\Mobax | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi | 2020-03-13 | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | No | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 11:00 Hrs- 17:00 Hrs | 13:00 Hrs. - 19:00 Hrs. | 48268 | Implemented as emergency change under incident | Approved | 41617 | CRQ000000651062 | Completed | Completed | Tested-Fail | It was a failure. However, there were exception approved to go ahead with the migration and it was continued. |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01
CKT-I-02-ZA-BOK01-0004-VOD-1 | I0215VOD1 | 1 | Yes | High | Africa | SOUTH AFRICA | Boksburg Factory | 2018_222 | un-amt-zafbbg-vpn002 | un-amt-zafbbg-vpn002 | Prasenjit Pal | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | S19090569337 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-03-18 | Complete | 2019-11-18 | 2020-03-16 | Complete | 13 Dec: No new update 06 Dec : Unilever has requested for a hardcopy of the H&S file on the 0212. H&S file will be submitted by 0612. 29 Nov : IDD: end Jan 20 22 Nov : Approvals received. IDD to be provided 2711 18 Nov : Target delivery date as Feb20 provided by VF. No site survey's done yet. 11-Nov : Site survey not done, no date provided by VF yet. | Complete | Circuit Migrated |  | Check dates | ZA-BOK01-0004 | SOUTH_AFRICA_BOKSBURG_COMMISSIONER_STREET_UNIFOODS |  |  |  |  | 511 Commissioner Street | Boksburg | 1460 |  | Louisa Maphuthaees | louisa.maphutha@unilever.com | +27794385224 | Louisa Maphuthaees | louisa.maphutha@unilever.com | 75MB75MB | 75 | -26.2197 | 28.2732 | 2019 | Nov | Internet | 2019-12-13 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Mathubamahle.Ntshangase@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | "Public IP Address: 105.242.122.72 Subnet Mask: 255.255.255.248 "Public IP Next Hop ": 105.242.122.73 "Usable IP Range ":74-78 | 105.242.122.73 | 105.242.122.74 | 105.242.122.72/29 |  |  | Vodacom\Mobax | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi | 2020-03-17 | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 07:00 Hrs. - 13:00 Hrs. | 09:00 Hrs. - 15:00 Hrs. | 48094 | Implemented as emergency change under incident | Approved | 41618 | CRQ000000650991 | Completed | Completed | Tested -Pass-First Time | Testing was successful. |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01
CKT-I-01-ZA-DUR06-0002-VOD-1 | I019487VOD1 | 1 | Yes | High | Africa | SOUTH AFRICA | Indonsa (Queen Nandi) | 2018_225 | un-amt-zafqnd-vpn001 | un-amt-zafqnd-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | L19090570108 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-06-10 | Complete | 2019-11-18 | 2020-06-18 | Complete | Action Item : Cisco to prepare for migration. Pending RFC approval and SHE approval for NTT FE. 18-JUn: There were issues with the second link at site on the day of migration, After this existing link issue was resolved, migration completed successfully. 0505-LLA doc resent to LCON for sign-off 0405-Schedule install once the secondary LLA is received 2304-Lockdown for South Africa will relaxed to level 4 as from the 0105 - this allows for restricted mobility. Vodacom to follow up with Unilever LCON if site will open as BAU, request for the pending landlord approvals and request if Unilever will allow for the project to progress. 13 Dec: No new update 06 Dec : No update 29 Nov : Vendor Letter of good standing 22 Nov : Certification submitted, pending final H&S approval 18 Nov : No update. 11-Nov : Site survey is not done, no date provided by VF yet. | Complete | Circuit Migrated | Cisco |  | ZA-DUR06-0002 | SOUTH_AFRICA_QUEEN_NANDI |  |  |  |  | 77 Riverhorse Road, Riverhorse Valley Business Estate | Durban | 4017 |  | Bheki Mdunge | Bheki.Mdunge@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 50MB50MB | 50 |  |  | 2019 | Nov | Internet | 2019-06-26 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Siraj.Williams@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | WAN RANGE: 105.247.209.208/30 - vlan 2608 WAN PE IP: 105.247.209.209/30 WAN CE IP: 105.247.209.210/30 LAN RANGE: 105.242.195.16/29 | 105.247.209.209/30 | 105.247.209.210/30 | 105.242.195.16/29 |  |  | Vodacom\Mobax | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 75338 | CRQ000000680339 | Approved | 41816 | CRQ000000654495 | Completed | Completed | Tested -Pass-First Time | Test was done on 29th May and was successful. Able to connect to internet with good speed and NO packet loss and also able to reach the correct Zscaler node. |  | Circuit Migrated |  |  |  | 2020-02-01 | 2020-04-01
CKT-I-01-ZA-BOK02-0005-VOD-1 | I0110914VOD1 | 1 | Yes | Medium | Africa | SOUTH AFRICA | Khanyisa (Waterfall) | 2018_233 | un-amt-zafabt-vpn001 | un-amt-zafabt-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | L19090570169 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-05-19 | Complete | 2019-11-18 | 2020-06-04 | Complete | Action Item: Proceed with migration. 4-Jun: VOdacom had to update the prefix to resolve connectivity issue. 1-Jun: Testing completed on 29 May. Schedule confirmed. 19-May: Link delivered. 18-May: Vodacom confirmed that the delivery is brought forward to 19 may. 0705-Additional H&S requirements have been advised by Unilever LCON due to COVID-19. Unilever to provide document template for compliance. 0405-Go ahead given from Unilever to progress with deliverables. LCON engagement for access in progress 2204-COVID-19 lockdown is scheduled to uplifted by 3004. Delivery to commence thereafter. 13 Dec: No new update 06 Dec : Unilever has requested for a hardcopy of the H&S file on the 0212. H&S file will be submitted by 0612.29 Nov : IDD end of Jan20 22 Nov : Approvals received. IDD to be provided 2711 18 Nov : Target delivery date as Jan20 provided by VF. No site survey's done yet. 11-Nov : Site survey not done, no date provided by VF yet. | Complete | Circuit Migrated | Cisco |  | ZA-BOK02-0005 | SOUTH_AFRICA_WATERFALL |  |  |  |  | 24 Francis Road, Anderbolt | Boksburg | 1460 |  | Angela Ramothata | Angela.Ramothata@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 40MB40MB | 60 |  |  | 2019 | Nov | Internet | 2019-12-13 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Thobeka.Mbuyazi@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | WAN RANGE: 105.247.222.100/30 - vlan 2245 WAN PE IP: 105.247.222.101/30 WAN CE IP: 105.247.222.102/30 LAN RANGE:105.247.220.224/29 | 105.247.222.101/30 | 105.247.222.102/30 | 105.247.220.224/29 |  |  | Vodacom\Mobax | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 69982 | CRQ000000677246 | Approved | 41819 | CRQ000000654719 | Completed | Completed | Tested -Pass-First Time | This will be considered as pass. however,was not done as it was an IP connect and will have VLAN and needs a router to connect. We need to do a Hot swop on the day of migration, which is planned on 4th june |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-04-01
CKT-I-02-ZA-BOK02-0005-VOD-1 | I0210914VOD1 | 1 | Yes | Medium | Africa | SOUTH AFRICA | Khanyisa (Waterfall) | 2018_234 | un-amt-zafabt-vpn002 | un-amt-zafabt-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | S19090569453 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-05-19 | Complete | 2019-11-18 | 2020-06-11 | Complete | Action Item: Proceed with migration. 11-Jun: Vodacom had to reboot the NTE device to fix connectivity issues. 1-Jun: Testing completed on 29 May. Schedule confirmed. 19-May: Link delivered 18-May: Vodacom confirmed that the delivery is brought forward to 19 may. 0705-Additional H&S requirements have been advised by Unilever LCON due to COVID-19. Unilever to provide document template for compliance. 0405-Go ahead given from Unilever to progress with deliverables. LCON engagement for access in progress 2204-COVID-19 lockdown is scheduled to uplifted by 3004. Delivery to commence thereafter. 13 Dec: No new update 06 Dec : Unilever has requested for a hardcopy of the H&S file on the 0212. H&S file will be submitted by 0612. 29 Nov : IDD end of Jan20 22 Nov : Approvals received. IDD to be provided 2711 18 Nov : Target delivery date as Jan20 provided by VF. No site survey's done yet. 11-Nov : Site survey not done, no date provided by VF yet. | Complete | Circuit Migrated | Cisco |  | ZA-BOK02-0005 | SOUTH_AFRICA_WATERFALL |  |  |  |  | 24 Francis Road, Anderbolt | Boksburg | 1460 |  | Angela Ramothata | Angela.Ramothata@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 55MB55MB | 75 |  |  | 2019 | Nov | Internet | 2019-07-18 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Thobeka.Mbuyazi@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | Public IP Address: 105.242.122.80 Subnet Mask: 255.255.255.248 "Public IP Next Hop ": 105.242.122.81 "Usable IP Range ": 82-86 | 105.242.122.81/30 | 105.242.122.82/30 | 105.242.122.80/29 |  |  | Vodacom\Mobax | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms not sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 71395 | CRQ000000678675 | Approved | 41818 | CRQ000000654599 | Completed | Completed | Tested -Pass-First Time | Test was done on 29th May and was successful. Able to connect to internet with good speed and NO packet loss and also able to reach the correct Zscaler node. |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-04-01
CKT-I-01-ZA-DUR03-0001-VOD-1 | I0127VOD1 | 1 | From Mark Robinson (UL - SA) Hi Ashritha, Yes, La Lucia is the same as The Ridge. The links to migrate are: un-amt-zafumh-vpn001 un-amt-zafumh-vpn002 We also have a separate Agile wifi link which is 50Mbps and is to be migrated and upgraded to 200Mbps – this is on un-amt-zafumh-agi001. Rgds Mark Renewed BW of 400MB ordered for other circuit on the same site. | Medium | Africa | SOUTH AFRICA | La-Lucia Ridge HO | 2018_231 | un-amt-zafumh-vpn001 | un-amt-zafumh-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | L19090570144 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-07-10 | Complete | 2019-11-18 | 2020-07-30 | Complete | Action Item: Vodacom to proceed with circuit delivery. 16-Jul: MIgration was not successful as the link was delivered on first floor but the router is on basement. ISP to extend the demarc to basement floor and then migration to be replanned for 30th July. 18-May: Consolidate Agile link 0505-LLA doc resent to LCON for sign-off. As per LCON - Site is closed 0405-As per LCON - Site is closed 2304-Lockdown for South Africa will relaxed to level 4 as from the 0105 - this allows for restricted mobility. Vodacom to follow up with Unilever LCON if site will open as BAU, request for the pending landlord approvals and request if Unilever will allow for the project to progress. 13 Dec -Survey has been completed, pending site survey doc TD 13. 06 Dec : No further update 29 Nov : Resource hospitalised, need to book a date again for survey 22 Nov : Fibre vendor available for site re survey 2711 18 Nov : Site visit is delayed due to weather constraint 11-Nov : Recticulation dispute - Feedback for reticulation issue to be recevide by 0811. Need to check with AK | Complete | Circuit Migrated | Circuit Provider |  | ZA-DUR03-0001 | SOUTH_AFRICA_UMHLANGA_RIDGE_HEAD_OFFICE |  |  |  |  | 15 Nollsworth Crescent, La Lucia, Umhlanga | Durban | 4051 |  | Bheki Mdunge | Bheki.Mdunge@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 200MB200MB | 200 | -29.7852 | 31.0402 | 2019 | Oct | Internet | 2019-12-12 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | tsebo.technical@unilever.com | N | Head Office - low impact after 5pm | /29 | Head office for the South Africa business. Circa 1200 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. |  | WAN RANGE: 105.247.209.188/30 - vlan 2083 WAN PE IP: 105.247.209.189/30 WAN CE IP: 105.247.209.190/30 LAN RANGE:105.242.195.88/29 | 105.247.209.189/30 | 105.247.209.190/30 | 105.242.195.88/29 |  |  | Vodacom | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | In Progress |  | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression | Window Date agreed - End user Comms not sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 93524 , latest 105853 | CRQ000000688978 CRQ000000695237 (30 Jul) | Approved |  | CRQ000000687966 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-04-01
CKT-I-01-ZA-DUR01-0001-VOD-1 | I0120VOD1 | 1 | Yes | High | Africa | SOUTH AFRICA | MWF Factory (Maydon Wharf) | 2018_223 | un-amt-zafmwf-vpn001 | un-amt-zafmwf-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | L19090570096 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-07-10 | Complete | 2019-11-18 | 2020-07-29 | Complete | Action Item : Vodacom to proceed with circuit delivery 20-Jul: Migration rescheduled to 29 Jul due to delay in circuit delivery by ISP. 0405-Installation to be schdeuled with LCON. LCON engagement in progress for access. 2204-COVID-19 lockdown is scheduled to uplifted by 3004. Delivery to commence thereafter. 13 Dec : H&S docs resubmitted 0912, pending customer approval. Survey to then be scheduled for next year due to year end freeze. 06 Dec : No further update 29 Nov : Vendor Letter of good standing 22 Nov : Unilever requested for the updated TAX certificate. Will be handed by 2211 CoB, with letter of good standing 18 Nov : Letter of good understanding pending. No date provided by VF yet 11-Nov : Site survey not yet done, no date provided by VF. | Complete | Circuit Migrated | Circuit Provider |  | ZA-DUR01-0001 | SOUTH_AFRICA_DURBAN_MAYDON_WHARF |  |  |  |  | 73 Maydon Road, Maydon Wharf | Durban | 4001 |  | Nomfundo.Ndlanya | Nomfundo.Ndlanya@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 50MB50MB | 50 | -29.8699 | 31.0065 | 2019 | Nov | Internet | 2019-12-12 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | jabulani.cebekhulu@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | WAN RANGE: 105.247.209.204/30 - vlan 2085 WAN PE IP: 105.247.209.205/30 WAN CE IP: 105.247.209.206/30 LAN RANGE: 105.242.195.8/29 | 105.247.209.205/30 | 105.247.209.206/30 | 105.242.195.8/29 |  |  | Vodacom\Mobax | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression | Window Date agreed - End user Comms sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 87304 | CRQ000000687068 | Approved | 41814 | CRQ000000654712 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-04-01
CKT-I-02-ZA-DUR01-0001-VOD-1 | I0220VOD1 | 1 | Yes | High | Africa | SOUTH AFRICA | MWF Factory (Maydon Wharf) | 2018_224 | un-amt-zafmwf-vpn002 | un-amt-zafmwf-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | S19090569360 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-07-24 | Complete | 2019-11-18 | 2020-07-29 | Complete | Action Item: Action Item : Vodacom to proceed with circuit delivery 20-Jul: Migration rescheduled to 29 Jul due to delay in circuit delivery by ISP. 0405-Installation to be schdeuled with LCON. LCON engagement in progress for access. 2204-COVID-19 lockdown is scheduled to uplifted by 3004. Delivery to commence thereafter. 13 Dec -H&S docs resubmitted 0912, pending customer approval. Survey to then be scheduled for next year due to year end freeze. 06 Dec : No further update 29 Nov : Vendor Letter of good standing 22 Nov : Unilever requested for the updated TAX certificate. Will be handed by 2211 CoB, with letter of good standing 18 Nov : Letter of good understanding pending. No date provided by VF yet 11-Nov : Site survey not yet done, no date provided by VF. | Complete | Circuit Migrated | Circuit Provider |  | ZA-DUR01-0001 | SOUTH_AFRICA_DURBAN_MAYDON_WHARF |  |  |  |  | 73 Maydon Road, Maydon Wharf | Durban | 4001 |  | Nomfundo.Ndlanya | Nomfundo.Ndlanya@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 70MB70MB | 70 | -29.8699 | 31.0065 | 2019 | Nov | Internet | 2019-06-18 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | jabulani.cebekhulu@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | Public Ip's 105.247.170.168 Next Hop 105.247.170.169 Subnet 255.255.255.248 Usable IP's 170-174 | 105.247.170.169/30 | 105.247.170.170/30 | 105.247.170.168/29 |  |  | Vodacom\SAAB Grintek | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression | Window Date agreed - End user Comms sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 87304 | CRQ000000687068 | Approved |  | CRQ000000689219 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-04-01
CKT-I-01-ZA-DUR05-0166-VOD-1 | I011226VOD1 | 1 | Yes | Medium | Africa | SOUTH AFRICA | Phoenix Factory | 2018_216 | un-amt-zafpxl-vpn001 | un-amt-zafpxl-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | S19090570049 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-07-10 | Complete | 2019-11-18 | 2020-07-22 | Complete | Action Item: ISP to deliver circuit 0405-As per LCON - Site is closed 2204-COVID-19 lockdown is scheduled to uplifted by 3004. Delivery to commence thereafter. 13 Dec -Build doc approvals not received, by customer (LLA). H&S Approved, including Letter of Good Standing. 06 Dec : No further update 29 Nov : Build doc approvals not received 22 Nov : Build documents to be submitted to Unilever by 2111 CoB. IDD to be provided by 0412 18-Nov : Survey completed but no date provided by VF yet. 11-Nov : Site survey scheduled for 8th Nov | Complete | Circuit Migrated | Circuit Provider |  | ZA-DUR05-0166 | SOUTH AFRICA_PHOENIX_166 HUNSLETT ROAD_PHOENIX HPC FACTORY |  |  |  |  | 166 Hunslett Road, Phoenix Industrial Park | Durban | 4068 |  | Nomfundo.Ndlanya | Nomfundo.Ndlanya@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 4096Kbps20MB | 20 | -29.7039 | 31.0028 | 2019 | Nov | Internet | 2019-06-11 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Phumi.Nene@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | WAN RANGE: 105.247.222.96/30 - vlan 2612 WAN PE IP: 105.247.222.97/30 WAN CE IP: 105.247.222.98/30 LAN RANGE: 105.242.194.248/29 | 105.247.222.97/30 | 105.247.222.98/30 | 105.242.194.248/29 |  |  | Vodacom\Mobax | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created | Window Date agreed - End user Comms sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 99604 | CRQ000000692197 | Approved | 41813 | CRQ000000654645 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-04-01
CKT-I-02-ZA-DUR05-0166-VOD-1 | I021226VOD1 | 1 | Yes | Medium | Africa | SOUTH AFRICA | Phoenix Factory | 2018_217 | un-amt-zafpxl-vpn002 | un-amt-zafpxl-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | S19090569290 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-08-28 | Red | 2019-11-18 | 2020-10-14 | Red | Action Item: ISP to deliver circuit 0405-As per LCON - Site is closed 2204-COVID-19 lockdown is scheduled to uplifted by 3004. Delivery to commence thereafter. 13 Dec :Pending further inputs. 06 Dec : No further update 29 Nov : Survey completed. 22 Nov : To be re-surveyed, as MAST is saturated. 18-Nov : Survey completed but no date provided by VF yet. 11-Nov : Site survey scheduled for 8th Nov | Pink | Circuit Order Accepted | Circuit Provider |  | ZA-DUR05-0166 | SOUTH AFRICA_PHOENIX_166 HUNSLETT ROAD_PHOENIX HPC FACTORY |  |  |  |  | 166 Hunslett Road, Phoenix Industrial Park | Durban | 4068 |  | Nomfundo.Ndlanya | Nomfundo.Ndlanya@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 25MB25MB | 25 | -29.7039 | 31.0028 | 2019 | Nov | Internet | 2019-12-12 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Phumi.Nene@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | Public Ip's 105.244.22.56 Next Hop 105.244.22.57 Subnet 255.255.255.248 Usable IP's 58-62 | 105.244.22.57/30 | 105.244.22.58/30 | 105.244.22.56/29 |  |  | Vodacom\SAAB Grintek | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 99604 and new CR CHG000000000041639 | CRQ000000692197 (not implemented for this circuit) CRQ000000706296 |  |  | CRQ000000687788 | Completed | Completed | [7 empty] | 2020-02-01 | 2020-04-01
CKT-I-01-ZA-JNB05-0001-VOD-1 | I0110965VOD1 | 1 | Yes | High | Africa | SOUTH AFRICA | Allandale, Gauteng | 2018_229 | un-amt-zafspl-vpn001 | un-amt-zafspl-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | L19090570132 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-06-12 | Complete | 2019-11-18 | 2020-07-02 | Complete | Action Item: GEO IT to confirm schedule. 2105-Escalated for the Letter of good will proof of submission to be shared with Uniliever to progress with delivery. Renewal release is delayed due to COVID19 - lockdown 0705-Additional H&S requirements have been advised by Unilever LCON due to COVID-19. Unilever to provide document template for compliance. 0405-Go ahead given from Unilever to progress with deliverables. LCON engagement for access in progress 2204-COVID-19 lockdown is scheduled to uplifted by 3004. Delivery to commence thereafter. 13 Dec :Pending further inputs. 06 Dec : Build docs pending approvals 29 Nov : Same as below. 22 Nov : Approvals pending. 18 Nov : Target delivery date as Feb 20 provided by VF. No site survey's done yet. 11-Nov : Site survey not done, no date provided by VF yet. | Complete | Circuit Migrated | Unilever Geo-IT |  | ZA-JNB05-0001 | SOUTH_AFRICA_SOUTH POLE_ALLENDALE ROAD_MIDRAND_JOHANNESBURG |  |  |  |  | Lordsview Industrial Park - Chloorkop Extension 66 - Allandale Road | Johannesburg | 1682 |  | Angela Ramothata | Angela.Ramothata@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 40MB40MB | 40 |  |  | 2019 | Nov | Internet | 2019-07-19 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Keri.Grewan@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | WAN RANGE: 105.247.209.212/30 - - vlan 2220 WAN PE IP: 105.247.209.213/30 WAN CE IP: 105.247.209.214/30 LAN RANGE:105.242.195.80/29 | 105.247.209.213/30 | 105.247.209.214/30 | 105.242.195.80/29 |  |  | Vodacom\Mobax | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created | Window Date agreed - End user Comms sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 85298 | CRQ000000685513 | Approved |  | CRQ000000681531 | Completed | Completed | Tested -Pass-First Time | This will be considered as pass. however,was not done as it was an IP connect and will have VLAN and needs a router to connect. We need to do a Hot swop on the day of migration. |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-04-01
CKT-I-02-ZA-JNB05-0001-VOD-1 | I0210965VOD1 | 1 | Yes | Medium | Africa | SOUTH AFRICA | Allandale, Gauteng | 2018_230 | un-amt-zafspl-vpn002 | un-amt-zafspl-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | S19090569430 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-06-12 | Complete | 2019-11-18 | 2020-07-09 | Complete | Action Item: GEO IT to confirm schedule. 2105-Escalated for the Letter of good will proof of submission to be shared with Uniliever to progress with delivery. Renewal release is delayed due to COVID19 - lockdown 0705-Additional H&S requirements have been advised by Unilever LCON due to COVID-19. Unilever to provide document template for compliance. 0405-Go ahead given from Unilever to progress with deliverables. LCON engagement for access in progress 2204-COVID-19 lockdown is scheduled to uplifted by 3004. Delivery to commence thereafter. 13 Dec :Pending further inputs. 06 Dec : Build docs pending approvals 29 Nov : Same as below. 22 Nov : Approvals pending. 18 Nov : Target delivery date as Feb 20 provided by VF. No site survey's done yet. 11-Nov : Site survey not done, no date provided by VF yet. | Complete | Circuit Migrated | Unilever Geo-IT |  | ZA-JNB05-0001 | SOUTH_AFRICA_SOUTH POLE_ALLENDALE ROAD_MIDRAND_JOHANNESBURG |  |  |  |  | Lordsview Industrial Park - Chloorkop Extension 66 - Allandale Road | Johannesburg | 1682 |  | Angela Ramothata | Angela.Ramothata@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 55MB55MB | 75 |  |  | 2019 | Nov | Internet | 2019-12-13 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Keri.Grewan@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | "Public IP Address: 105.242.123.8 Subnet Mask: 255.255.255.248 "Public IP Next Hop ": 105.242.123.9 "Usable IP Range ":10-14 | 105.242.123.9/30 | 105.242.123.10/30 | 105.242.123.8/29 |  |  | Vodacom\Mobax | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression | Window Date agreed - End user Comms sent |  |  |  | 86381 | CRQ000000686984 | Approved |  | CRQ000000681722 | Completed | Completed | Tested -Pass-First Time | Test was done on 24 June and was successful. Able to connect to internet with good speed and NO packet loss and also able to reach the correct Zscaler node. |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-04-01
CKT-I-01-ZA-PZB01-0007-VOD-1 | I0122VOD1 | 1 | Yes | Medium | Africa | SOUTH AFRICA | PMB Factory (Pietermaritzburg) | 2018_218 | un-amt-zafpmb-vpn001 | un-amt-zafpmb-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | L19090570069 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-06-15 | Complete | 2019-11-18 | 2020-07-27 | Complete | Action Item: GEO IT to advise when migration can be planned after site reopens. 22-Jun: Migration cancelled last minute as the site is closed due to COvid-19. 18-May: Vodacom looking to schedule installation for 30 or 31 may. Need confirmation on schedule. 0405-Schedule install once LLA received. LCON engagement in progress for access. 2204-COVID-19 lockdown is scheduled to uplifted by 3004. Delivery to commence thereafter. 13 Dec-Awaiting site survey doc, from vendor TD 13, for submission to Unilever. Risk freeze. H&S Approved, including Letter of Good Standing. 06 Dec : No further update 29 Nov : Letter of good understanding pending from UL 22 Nov : H&S file dropped off, pending approvals 18 Nov : UL requested for a hardcopy of the H&S to be delivered to site. TD is 1511 or later due to weather constraints. No FCDD provided by VF yet. 11-Nov : Site survey is done, no date provided by VF yet. | Complete | Circuit Migrated | Unilever Geo-IT |  | ZA-PZB01-0007 | SOUTH AFRICA_PIETERMARITZBURG_7 GRIX ROAD_PIETERMARITZBURG FACTORY |  |  |  |  | 7 Grix Road, Willowton | Pietermaritzburg | 3201 |  | Helena Blythen | Helena.Blythen@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 20MB20MB | 20 | -29.5972 | 30.4157 | 2019 | Nov | Internet | 2019-06-22 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | stuart.taylor@unilever.com sanele.mkulisi2@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | WAN RANGE: 105.247.209.200/30 - vlan 2113 WAN PE IP: 105.247.209.201/30 WAN CE IP: 105.247.209.202/30 LAN RANGE: 105.242.195.0/29 | 105.247.209.201/30 | 105.247.209.202/30 | 105.242.195.0/29 |  |  | Vodacom\Mobax | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression | Window Date agreed - End user Comms not sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 78356 | CRQ000000684948 | Approved | 41815 | CRQ000000654494 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-04-01
CKT-I-02-ZA-PZB01-0007-VOD-1 | I0222VOD1 | 1 | Yes | Medium | Africa | SOUTH AFRICA | PMB Factory (Pietermaritzburg) | 2018_219 | un-amt-zafpmb-vpn002 | un-amt-zafpmb-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | S19090569314 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-06-15 | Complete | 2019-11-18 | 2020-07-27 | Complete | Action Item: GEO IT to advise when migration can be planned after site reopens. 24-Jun: Migration rescheduled as the site is closed due to COvid-19. 18-May: Vodacom looking to schedule installation for 30 or 31 may. Need confirmation on schedule. 0405-Schedule install once LLA received. LCON engagement in progress for access. 2304-Lockdown for South Africa will relaxed to level 4 as from the 0105 - this allows for restricted mobility. Vodacom to follow up with Unilever LCON if site will open as BAU, request for the pending landlord approvals and request if Unilever will allow for the project to progress. 13 Dec-Awaiting site survey doc, from vendor TD 13, for submission to Unilever. Risk freeze. H&S Approved, including Letter of Good Standing. 06 Dec : No further update. 29 Nov : Letter of good understanding pending from UL 22 Nov : H&S file dropped off, pending approvals 18 Nov : UL requested for a hardcopy of the H&S to be delivered to site. TD is 1511 or later due to weather constraints. No FCDD provided by VF yet. 11-Nov : Site survey is done, no date provided by VF yet. | Complete | Circuit Migrated | Unilever Geo-IT |  | ZA-PZB01-0007 | SOUTH AFRICA_PIETERMARITZBURG_7 GRIX ROAD_PIETERMARITZBURG FACTORY |  |  |  |  | 7 Grix Road, Willowton | Pietermaritzburg | 3201 |  | Helena Blythen | Helena.Blythen@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 25MB25MB | 25 | -29.5972 | 30.4157 | 2019 | Nov | Internet | 2019-12-12 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | stuart.taylor@unilever.com sanele.mkulisi2@unilever.com | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | Public IP Address: 105.242.22.32 Subnet Mask: 255.255.255.248 "Public IP Next Hop ": 105.242.22.33 "Usable IP Range ": 34-38 | 105.242.22.33/30 | 105.242.22.34/30 | 105.242.22.32/29 |  |  | Vodacom\Mobax | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression | Window Date agreed - End user Comms not sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 78356 | CRQ000000684948 | Approved | 41817 | CRQ000000654660 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-04-01
CKT-I-01-TZ-DAR01-0001-VOD-1 | I012149VOD1 | 1 | Yes; Deepak confirms to migrate on 2921 as ISR4K was damaged and circuit rolled back to old device and is operational | Medium | Africa | TANZANIA | Dar es salaam HO | 2018_254 | un-amt-tzadar-vpn001 |  | Prasenjit Pal | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQM-00012 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2019-11-26 | Complete | 2019-11-18 | 2020-01-30 | Complete | 30 Jan: Migration complete 19 Jan: Testing successful. Migration schedule confirmed for 30th Jan 6-Jan: Router needs to be updated as it is old model. Algosec and Zscaler request to be resubmitted as IP details changed by Vodafone. 13-Dec : No new update 06 Dec : Awaiting approval from Geo IT. 02 Dec : Migration planned for 19th Dec. 27 Nov : Circuit delivered 22 Nov : Supplier has completed the link deployment. Pending the handover from supplier to test the delivered service 18 Nov : Estimated handover for this site is in early January 11-Nov : Order in progress with local partner. Will be able to advise EDD in a week. | Complete | Circuit Migrated |  |  | TZ-DAR01-0001 | TANZANIA_DAR_ES_SALAAM_NYERERE_ROAD |  |  |  |  | Plot No. 4A , Nyerere Road | Dar Es Salaam | 255 |  | Musa Adeka | Musa.Adeka@unilever.com | 256755534850 | Dees Rampartab | Dees.Rampartab@unilever.com | 20MB | 20 | -6.8095 | 39.274 | 2019 | Nov | Internet | 2019-09-06 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Sigisbert.Soka@unilever.com Tel: 255789496650 | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | Wan IP Address 41.221.61.246 Lan IP Address 41.221.54.249 | 41.221.50.45/30 | 41.221.50.46/30 | 41.221.61.72/29 |  |  | Green Telecom | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | 2020-01-31 |  | Standard site type - Dual DMVPN | Complete |  |  | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 14:00 Hrs – 20:00 Hrs. | 17:00 Hrs. – 23:00 Hrs. | 29187 | CRQ000000635399 | Approved | 40796 | CRQ000000632054 | Completed | Completed | Tested -Pass-First Time | Testing was successful |  | Circuit Migrated - First Time right |  |  |  |  | 2019-12-01
CKT-I-02-TZ-DAR01-0001-VOD-1 | I022149VOD1 | 1 | Yes | Medium | Africa | TANZANIA | Dar es salaam HO | 2018_255 | un-amt-tzadar-vpn002 |  | Prasenjit Pal | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQM-00013 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2019-11-26 | Complete | 2019-11-18 | 2020-01-24 | Complete | 24 Jan : Migration completed successfully. 19 Jan: Testing successful. Migration scheduled confirmed 24th Jan 14 Jan: IP Issue yet to be resolved. Testing and migration may get delayed. 10-Jan: Cisco proposed Testing on 14th Jan and Migration on 20th Jan. Geo IT confirmation awaited 6-Jan: Algosec and Zscaler request to be resubmitted as IP details changed by Vodafone. 13-Dec : No new update 06 Dec : All good for 8th Jan, approved by Geo IT. 02 Dec : Migration planned for 8th Jan 27 Nov : Circuit delivered 22 Nov : No further update. 18 Nov : Estimated handover for this site is in early January 11-Nov : Order in progress with local partner. Will be able to advise EDD in a week. | Complete | Circuit Migrated |  |  | TZ-DAR01-0001 | TANZANIA_DAR_ES_SALAAM_NYERERE_ROAD |  |  |  |  | Plot No. 4A , Nyerere Road | Dar Es Salaam | 255 |  | Musa Adeka | Musa.Adeka@unilever.com | 256755534850 | Dees Rampartab | Dees.Rampartab@unilever.com | 25MB | 25 | -6.8095 | 39.274 | 2019 | Nov | Internet | 2019-09-05 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Ramadhani.Jallana@unilever.com Einoth.Christopher@unilever.com +255768575539 +255754524524 | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | Your vEdge WAN IP: 41.221.50.42 Subnet Mask: 255.255.255.252 Default Gateway: 41.221.50.41 Additional Routed subnet for LAN: 41.221.54.248/29 (routed to 41.221.50.42) | 41.221.50.41/30 | 41.221.50.42/30 | 41.221.54.248/29 |  |  | Green Telecom | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | 2020-01-27 |  | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 14:00 Hrs – 20:00 Hrs. | 17:00 Hrs. – 23:00 Hrs | 21687 | CRQ000000628648 | Approved | 40798 | CRQ000000632019 | Completed | Completed | Tested -Pass-First Time | Testing was successful |  | Circuit Migrated - First Time right |  |  |  |  | 2020-01-01
CKT-I-01-TZ-IRI01-0002-VOD-1 | I0128VOD1 | 1 | Yes | High | Africa | TANZANIA | Mufindi Plantations | 2018_256 | un-amt-tzamuf-vpn002 |  | Vishal Joshi | WAN Circuit Migration | Soft Upgrade | Vodafone Local | Vod |  | 2-18805762078 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-08-04 | Complete | 2019-11-18 | 2020-08-04 | Complete | 18-May: Novation to be effective 4th Aug. 8-Sep: Rework planned on 19th Sep to swap the links to align with ISP BW mapping. 29-Apr: These are move out of WAN migration scope to SNT. These circuits will only have change in ownership and no circuit migration required. 13-Dec : No new update 06 Dec : No further update 29 Nov : Same as below. 22 Nov : Pending documents submitted - Sign-off expected by 2211. Physical site survey to then be scheduled. IDD to be provided by 0412. 18 Nov : Additional information requested from Vodacom Teams, for final review. No FCDD provided yet. 11-Nov : Site survey is not done, no date provided by VF yet. | Complete | Circuit Migrated | Circuit Provider | Check dates | TZ-IRI01-0002 | TANZANIA_MUFINDI_LUGODA_COMPLEX |  |  |  |  | Lugoda, Iringa Region (Southern Highlands), PO Box 40 | Iringa | 255 |  | Musa Adeka Emmanuel Kiwaya | Musa.Adeka@unilever.com Emmanuel.Kiwaya@unilever.com | 256755534850 '255763759005 | Dees Rampartab | Dees.Rampartab@unilever.com | 25MB | 25 | -8.5163 | 35.2606 | 2019 | Nov | Internet | 2019-08-15 | Commercial Benefit | 1 | Congested Link | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | Ramadhani.Jallana@unilever.com Einoth.Christopher@unilever.com +255768575539 +255754524524 | N | Plantation 8x 5 - low impact after 5pm | /30 | [8 empty] | Vodacom Tanzania | [5 empty] | Fat Nela | Fat Nela | Fat Nela |  | Copper - RJ45 | [12 empty] | 107850 | CRQ000000709722 (19 Sep) | Approved | [7 empty] | Circuit Migrated |  |  |  | 2020-04-01
CKT-I-01-UG-KLA02-0001-VOD-1 | I0112011VOD1 | 1 | Yes | Top | Africa | UGANDA | Kampala HO | 2018_273 | un-amt-ugakam-vpn001 |  | Prasenjit Pal | WAN Circuit Migration | Circuit | Vodafone Local | Vod |  | 2-18805196092 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2019-10-31 | Complete | 2019-11-18 | 2019-11-28 | Complete | 29 Nov : Migration Successful, no post migration issues reported. 22 Nov : Migration re-scheduled for 28 Nov. Comments from Geo IT "Due to some urgent issues in Tanzania Mufindi, my flight was shifted we can only do testing and cut over on Wednesday 27th November 2019 and 28th November 2019 respectivley." 18 Nov: Circuit delivered. Migration planned for 26 Nov 11-Nov : Circuit handed over 31 Oct. Migration scheduled on 26 Nov. Dates agreed by Geo IT. | Complete | Circuit Migrated |  |  | UG-KLA02-0001 | UGANDA_UNILEVER_HEAD_OFFICE |  |  |  |  | Plot No. 26, Kyadondo Road | Kampala | 256 |  | Musa Adeka | Musa.Adeka@unilever.com | 256755534850 | Dees Rampartab | Dees.Rampartab@unilever.com | 15MB15MB | 15 | 0.32644 | 32.5825 | 2019 | Oct | Internet | 2019-08-13 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | Jude.Muhaya@unilever.com Tel:256753108219 | N | Head Office - low impact after 5pm | /29 | 25/10/19: Original order was /30, existing is /29, requested vodacom for /29 IP |  | WAN Block : 41.79.254.38/31 CE IP (WAN): 41.79.254.39/31 PE IP (WAN) : 41.79.254.38/31 LAN Block : 41.79.254.80/29 | 41.79.254.38/31 | 41.79.254.39/31 | 41.79.254.81/29-41.79.254.86/29 |  |  | Vodacom\DataNet | [5 empty] | Karthik Ravi | Karthik Ravi | Karthik Ravi |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | [5 empty] | Assessment Complete | Window Date agreed - End user Comms sent |  |  |  | 16585 | CRQ000000620578 | Approved | 39808 | CRQ000000620383 | Completed | Completed | Tested -Pass-First Time | Testing was successful |  | Circuit Migrated - First Time right |  |  |  | 2019-11-01 | 2019-11-01
CKT-I-02-UG-KLA02-0001-VOD-1 | I0212011VOD1 | 1 | Yes | Top | Africa | UGANDA | Kampala HO | 2018_274 | un-amt-ugakam-vpn002 |  | Prasenjit Pal | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQM-00001 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-02-17 | Complete | 2019-11-18 | 2019-12-10 | Complete | 13 Dec : Migration successful as planned on 10th Dec 06 Dec : Migration planned for 10th Dec, pre migration testing had few issues; Expereo engineer joined and sorted. Seems to be all good now for tomorrow's migration. 02 Dec : Geo IT confirmation received. Migration planned for 10th Dec. Pre migration testing to be done on 9th Dec. 22 Nov : Not yet confirmed by Geo IT. Re-scheduling needs to be done. 18 Nov: Circuit delivered. Migration planned for 05 Dec 11-Nov : Order placed with local partner and pending acceptance. 24/10 (AP) tech team requested change from /30 to /29. Email sent to Welington and Deepak. Vishal to raise this with VOD. | Complete | Circuit Migrated |  | Check dates | UG-KLA02-0001 | UGANDA_UNILEVER_HEAD_OFFICE |  |  |  |  | Plot No. 26, Kyadondo Road | Kampala | 256 |  | Musa Adeka | Musa.Adeka@unilever.com | 256755534850 | Dees Rampartab | Dees.Rampartab@unilever.com | 20MB | 20 | 0.32644 | 32.5825 | 2019 | Oct | Internet | 2019-08-07 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | Jude.Muhaya@unilever.com Tel:256753108219 | N | Head Office - low impact after 5pm | /29 | 25/10/19: Original order was /30, existing is /29, requested vodafone for /29 IP |  | WAN 41.191.79.14 LAN 41.77.79.81 | 41.191.79.13/30 | 41.191.79.14/30 | 41.77.79.80/29 |  |  | ROKE Telkom | [5 empty] | Karthik Ravi | Karthik Ravi | Karthik Ravi |  |  | Standard site type - Dual DMVPN | Complete | [6 empty] | Window Date agreed - End user Comms sent |  |  |  | 17921 | CRQ000000622376 | Approved | 40300 | CRQ000000622877 | Completed | Completed | Tested-Pass | There was no spare router and even unable to connect to \30. We are doing our next testing on 9th Dec. 29th Nov: ISP link was terminated to an additional expereo device which created confusion because of which we weren't able to continue testing on the same day. Concern was raised to the stakeholders 9th Dec: Testing was done bypassing the additional expereo router and the testing was successful. ISP link should be terminated on the Unilever production router and not on the Expereo router. This is being discussed with the stakeholders. |  | Circuit Migrated - First Time right |  |  |  | 2019-11-01 | 2019-12-01
CKT-I-01-ZM-LUN01-7136-VOD-1 | I0146VOD1 | 1 | Yes | High | Africa | ZAMBIA | Lusaka HO | 2018_337 | un-amt-zmblus-vpn001 | un-amt-zmblus-vpn001 | Vishal Joshi | WAN Circuit Migration | Soft Upgrade | Vodafone Local | Vod |  | S19090425189 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-08-24 | Complete | 2019-11-18 | 2020-08-25 | Complete | Action Item : Vodacom to proceed with delivery 2904-Project approval to progress was recevied on the 2804. LCON engagement in progress. 28-04-2020 Hi All – Please could we resume Zambia circuit delivery and liaise with local Geo IT team to confirm the earliest delivery date. Thanks Deepak 23-April : Request you to suspend Zambia circuit deliveries until further notice from either myself or Nand. Please avoid any further discussion/follow up with Unilever local Geo IT team/Site Contacts on this topic. Thanks Deepak 13-Dec : No new update 06 Dec : PO's expected by CoB 0612 29 Nov : On track for PO. 22 Nov : Vendor PO creation in progress. Expecting PO'sby 0612 18 Nov : No change in status 11-Nov : VF is expecting the PO from vendor by mid-Nov. Site survey not yet done | Complete | Circuit Migrated | Circuit Provider | Check dates | ZM-LUN01-7136 | ZAMBIA_LUSAKA_MWEMBESHI_ROAD |  |  |  |  | Stand No.7136, Mwembeshi Road off west side of Lumumba Road, Heavy Industrial Area | Lusaka |  |  | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 20MB | 20 | -15.4088 | 28.2824 | 2019 | Nov | Internet | 2019-10-02 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | Collins.Hamakala@unilever.com Phone: +260950551511 | N | Head Office - low impact after 5pm | /30 | [8 empty] | Vodacom\Africonnect | [5 empty] | Fat Nela | Fat Nela | Fat Nela |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | No |  | No | Assessment Complete CMSP ticket raised MOP created & config created Prep documents uploaded to central storage |  |  |  |  | 116570 |  | Approved | [7 empty] | Circuit Migrated |  |  |  | 2020-03-01
CKT-I-02-ZM-LUN01-7136-VOD-1 | I0246VOD1 | 1 | Yes | Top | Africa | ZAMBIA | Lusaka HO | 2018_338 | un-amt-zmblus-vpn002 | un-amt-zmblus-vpn002 | Vishal Joshi | WAN Circuit Migration | Soft Upgrade | Vodafone Local | Vod |  | S19090425811 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-08-24 | Complete | 2019-11-18 | 2020-08-25 | Complete | Action Item : Vodacom to proceed with delivery 2904-Project approval to progress was recevied on the 2804. LCON engagement in progress. Tue 28-04-2020 16:00 Hi All – Please could we resume Zambia circuit delivery and liaise with local Geo IT team to confirm the earliest delivery date. Thanks Deepak 23-April : Thu 23-04-2020 14:44 Hi All, Request you to suspend Zambia circuit deliveries until further notice from either myself or Nand. Please avoid any further discussion/follow up with Unilever local Geo IT team/Site Contacts on this topic. Thanks Deepak 13-Dec : No new update 06 Dec : PO's expected by CoB 0612 29 Nov : On track for PO. 22 Nov : Vendor PO creation in progress. Expecting PO'sby 0612 18 Nov : No change in status 11-Nov : VF is expecting the PO from vendor by mid-Nov. Site survey not yet done | Complete | Circuit Migrated | Circuit Provider | Check dates | ZM-LUN01-7136 | ZAMBIA_LUSAKA_MWEMBESHI_ROAD |  |  |  |  | Stand No.7136, Mwembeshi Road off west side of Lumumba Road, Heavy Industrial Area | Lusaka |  |  | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 25MB | 25 | -15.4088 | 28.2824 | 2019 | Nov | Internet | 2019-11-12 | Commercial Benefit |  |  | 0 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 5pm with UAT happening between 5pm and 6pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 5pm - 6pm - cutover to Vodacom kit. 5pm - 6pm - UAT testing | Collins.Hamakala@unilever.com Phone: +260950551511 | N | Head Office - low impact after 5pm | /30 |  |  |  | 41.222.17.254/30 | 41.222.17.255/30 | 41.222.16.40/29 |  |  | Vodacom\Africonnect | [5 empty] | Fat Nela | Fat Nela | Fat Nela |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | No |  | No | Assessment Complete CMSP ticket raised MOP created & config created Prep documents uploaded to central storage |  |  |  |  | 116570 |  | Approved |  | CRQ000000691435 | Completed | Completed |  |  |  | Circuit Migrated |  |  |  | 2020-03-01
CKT-I-01-ZW-HRE01-0001-VOD-1 | I0147VOD1 | 1 | Yes | Top | Africa | ZIMBABWE | Harare | 2018_342 | un-amt-zwehar-vpn001 |  | Prasenjit Pal | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQM-00005 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-02-20 | Complete | 2019-11-18 | 2019-12-03 | Complete | 06 Dec : Migration successful on 3rd Dec. 02 Dec : Migration planned for 3rd Dec. Pre migration testing is planned for 2nd Dec. 18 Nov : Circuit Delivered. Migration planned for 3 Dec 11-Nov : Order placed with local partner and pending acceptance. | Complete | Circuit Migrated |  | Check dates | ZW-HRE01-0001 | ZIMBABWE_HARARE_STIRLING_ROAD_HEAD_OFFICE |  |  |  |  | 2, Stirling Road | Harare |  |  | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 70MB (under tunnel) and 50MB (under physical) | 50 | -17.85 | 31.0167 | 2019 | Oct | Internet | 2019-09-05 | Commercial Benefit |  |  | SC4 | Week day excluding month end. Installation of new kit and lines where required can happen between 9am and 5pm. Existing lines must not be touched during these times. Connection of new lines to routers must happen at 6pm with UAT happening between 6pm and 7pm - local time. Training required must be provided by SHE officer. | 9am to 5pm for installation of new lines and new kit. 6pm - 7pm - cutover to Vodacom kit. 6pm - 7pm - UAT testing | Itai.Mlambo@unilever.com Phone: +263772997807 | N | Factory 24x7 - low impact between 6pm and 7pm as during shift change | /30 |  |  | WAN 196.43.113.110 LAN 196.43.113.73 | 196.43.113.109/30 | 196.43.113.110/30 | 196.43.113.72/29 |  |  | YoAfrica | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual DMVPN | Complete |  | No | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  |  |  | 17923 | CRQ000000622375 CMSP 17923 | Approved | 40299 | CRQ000000623062 | Completed | Completed | Tested-Pass | 29th Nov: ISP link was terminated to an additional expereo device which created confusion because of which we weren't able to continue testing on the same day. Concern was raised to the stakeholders 2nd Dec: LAN segment was tested with the expereo router as per the instructions from the RFS document, however WAN testing couldnt be done as we were confused of the additional router from expereo. 3rd Dec: Testing was done bypassing the additional expereo router and the testing was successful. ISP link should be terminated on the Unilever production router and not on the Expereo router. This is being discussed with the stakeholders. |  | Circuit Migrated - First Time right |  |  |  | 2019-11-01 | 2019-12-01
CKT-I-01-FR-RUE05-0001-GTT-1 | I0111012GTT1 | 1 | Yes | High | Europe | FRANCE | FRANCE_RUEIL_GREENSTATION | 2019_164 | un-uen-frarue1-vpn001 |  | Agnieszka Pajak | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01695108 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-20 | Complete | 2019-10-28 | 2019-11-21 | Complete | 2019-11-11 | 2019-11-26 | Complete | 26/11 Migration completed successfully. There was an issue with corporate NAT pool. (/30 working, /29 not). This has been fixed by the Cisco team but needs further investigation internally. 21/11 The feedback received from Welington was to go ahead with the migration. Cisco team is ammending the change request to ensure we can go ahead with the migration, as planned, with changed scope (internet instead of MPLS) 21/11 Pascal - local GeoIT - informed Cisco that the new MPLS circuit was installed in the internet entry instead of MPLS one. The MPLS room is located in a different building. As such, the recommendation is to postpone the migration and migrate first the internet line. Waiting for the feedback from Welington and Deepak. The scope of the migration is changed from MPLS to internet 20/11 GTT confirmed that the installation of the new circuit has been completed successfully and they are waiting for the handover now. This has been already escalated with the supplier a couple of times. The new circuit needs to be tested prior to the migration 23/10 COLT changed the delivery date to 6/11 | Complete | Circuit Migrated |  |  | FR-RUE05-0001 | FRANCE_RUEIL_GREENSTATION |  |  |  |  | 20 Rue des 2 Gares | Rueil Malmaison Cedex | 92500 |  | Pascal Busseau | Pascal.Busseau@unilever.com | 33612048240 Site desk number : +33141966200 |  |  | 60M | 400 | 48°53'24.4"N | 2°10'37.0"E | 2019 | Nov | Internet | 2015-12-23 | Commercial Benefit | 1 | Congested over 12 months | SC2 | NA | 1700 - 2300 UTC | NA | NA | NA | /29 | Head office for the France business. Circa 1000 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | Basement, Datacentre Room located in the basement of the building - see plans provided. | 87.119.85.208/28 Network - 87.119.85.208 First usable - 87.119.85.209 Last usable - 87.119.85.222 Broadcast - 87.119.85.223 Subnet Mask - 255.255.255.240 | 87.119.85.209/28 | 87.119.85.210/28 | 87.119.85.211/28-87.119.85.222/28 |  |  | Colt Technology Services | GTT Paris | AS 3257 |  |  |  | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde | 2019-11-27 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | [5 empty] | Assessment Complete | Window Date agreed - End user Comms sent |  | 1700 - 2300 | 1800 - 2400 | 16324 | CRQ000000620301 | Approved | 40067 | CRQ000000620149 | Completed | Completed | Tested-Pass | Testing failed on 22 Nov. Issue fixed and successfully tested on 25 Nov |  | Circuit Migrated - First Time right | NA | NA | NA |  | 2019-11-01
CKT-I-02-FR-RUE05-0001-BT-1 | I0211012BT1 | 1 | Yes. Hostname from BT sheet and on login is "un-uen-frarue1-vpn001" | High | Europe | FRANCE | FRANCE_RUEIL_GREENSTATION | 2019_165 | un-uen-frarue1-vpn001 |  | Eloise Shepheard | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-02-28 | 2020-02-28 | Green | 2020-03-06 | 2020-03-09 | Red | 2020-05-15 | 2020-10-10 | Red | 2020-05-29 | 2020-11-09 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process 21/11 The scope of the migration is changed from internet to MPLS. The first circuit delivered was installed in the internet entry instead of MPLS as initially planned. | Yellow | Circuit not ordered | Unilever SNT |  | FR-RUE05-0001 | FRANCE_RUEIL_GREENSTATION |  |  |  |  | 20 Rue des 2 Gares | Rueil Malmaison Cedex | 92500 |  | Pascal Busseau | Pascal.Busseau@unilever.com | 33612048240 Site desk number : +33141966200 |  |  | 400M | 400 | 48°53'24.4"N | 2°10'37.0"E | 2019 | Nov | MPLS | 2019-07-13 | Commercial Benefit | 1 | Congested over 12 months | SC2 | [5 empty] | /29 | Head office for the France business. Circa 1000 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | [13 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde
CKT-I-01-DE-AUB01-0021-VOD-1 | I01322VOD1 | 1 | Yes | Top | Europe | GERMANY | Auerbach | 2019_170 | un-uen-deuaue1-rtr001 | un-uen-deuaue1-vpn002 | Eloise Shepheard | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | 3C03806620 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-09-07 | Red | 2019-11-18 | 2020-09-11 | Red | 21/08: ADVA device to be installed on 2nd September. Hisham to confirm this next week. 16/07 - still in progress with Vodafone provisioning team 09/07 - PO approved on Vodafone and working on placing the order to send ADVA to site - still no view of dates 06/07 - Vodafone have raised a PO and it is with dispatch team – Julian requested Mohammed for ETA 02/07 - still in progress with commercials - hoping for mid-July delivery 01/07 - Mohammed confirmed Vodafone are still trying to sort out the commercials for the missing ADVA router and cannot confirm delivery date. 26/06 - Jo Parsons (Vodafone) confirmed they are working on this internally and will keep me posted 25/06 - Daniela confirmed all ADVAs we had here before had integrated power supplies so it’s impossible to have a power supply at site. – This is a “detail” Vodafone have to know (from customers perspective). AC Power Cables are available – of course. 24/06 - email to Mohammed stating it is not Daniela's responsiblity to know whether the Vodafone engineer left power supply and power cable on site and that Mohammed needs to ensure all of the correct equipment is delivered to site at the earliest. This will be raised on the Vodafone call on Friday 26th June 24/06 - email from Mohammed asking if the Vodafone engineer left power supply on site 22/06 - email from Dehmel, Thomas asking for this to be escalated with Vodafone - response sent 22/06 - confirmed that CCTV is not available 21/06 - Email sent to Mohammed as Lars, Brian will have to confirm CCTV on site but that is likely not going to identify the devices and serial numbers removed 19/06 - Mohammed emailed asking if CCTV on site that could be reviewed 18/06 - Mohammed emailed confirming Vodafone carrier engineer put ADVA in LBADVA71192400955 package but device inside the package is LBADVA71190801281. For this reason I escalated them for not providing accurate information. 17/06 - Email sent to Mohammed questioning why he was expecting a device with different serial number delivered to site 17/06 - Brian Lars confirmed to Vodafone ADVA device with s/n LBADVA71190801281 delivered to site 17/06 16/06 - Vodafone confrimed at 15:16 BST that ADVA will be delivered to site on 17/06 15/06 - Vodafone tried to return the ADVA to Auerbach but were turned away by Daniela Hertrich - new date for kit drop off being arranged 12/06 - Missing ADVA device found - had been removed by Vodafone engineer 09/06 - Issue with missing ADVA - what is going on with it? - Eloise and Voda emailed 04/05 Local GeoIT provided green light to test the circuit. Circuit to be tested this week. Cisco project team to initiate preparations for the migration 03/03 Carrier issue is resolved and ADVA is installed at the site without any issues. Pending final installation and activation of the circuit. 14/02 Testing unsuccessful. The ADVA device is probably faulty and Vod we have requested NCR to replace the ADVA device. 20/12 Circuit scheduled to be delivered 27 Jan 12/12 Delivery of AVDA devices confirmed by the local contact - this was communicated with the order manager. | Yellow | Circuit Order Accepted | Circuit Provider |  | DE-AUB01-0021 | GERMANY_AUERBACH_DR_WILHELM_KULZ_STRASSE |  |  |  |  | Dr. Wilhelm-Kuelz-Strasse 21 | Auerbach | 8209 |  | Daniela Hertrich | Daniela.Hertrich@unilever.com | 494034934431 | Thomas Dehmel, Stefan Hahnkamm | Thomas.Dehmel@unilever.com; Stefan.Hahnkamm@unilever.com | 8MB | 40 | 50.507 | 12.4038 | 2019 | Oct | MPLS | 2013-08-08 | Service Issues |  |  | SC2 | [5 empty] | /30 |  |  |  | 217.161.81.41/30 | 217.161.81.42/30 | [9 empty] | Sedat Citaku | Damian Dabros | Damian Dabros |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO | Yes | No | No |  | Assessment Complete |  |  |  |  | CHG000000000042187 |  |  |  | CRQ000000708783 | Completed | Completed
CKT-I-02-DE-AUB01-0021-CTL-1 | I02322CTL1 | 1 | Device migrated, but 400M under physical and 40M under tunnel. To be rectified. | Top | Europe | GERMANY | Auerbach | 2019_171 | un-uen-deuaue1-pio001 | un-uen-deuaue1-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006825963 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-08-29 | Complete | 2019-10-21 | 2019-12-12 | Complete | 2019-11-04 | 2019-12-18 | Complete | 24/11 Date and time confirmed for the migration by local GeoIT 20/11 Provider confirmed that the missing elements for the circuit were successfully delivered. Circuit is now ready for activation. Awaiting response from Daniela on the proposed migration date. 31/10 Circuit delivered, installation not completed. HW missing - this has been ordered by provider. Awaiting further details. | Complete | Circuit Migrated |  |  | DE-AUB01-0021 | GERMANY_AUERBACH_DR_WILHELM_KULZ_STRASSE |  |  |  |  | Dr. Wilhelm-Kuelz-Strasse 21 | Auerbach | 8209 | Factory | Daniela Hertrich | Daniela.Hertrich@unilever.com | +49 3744 257 433 | Thomas Dehmel, Stefan Hahnkamm | Thomas.Dehmel@unilever.com; Stefan.Hahnkamm@unilever.com | 400M under physical, 40M under tunnel | 40 | 50.507 | 12.4038 | 2019 | Oct | Internet | 2018-12-18 | Service Issues |  |  | SC2 | factory (running permanently from 22:00 on Sunday till 22:00 on Saturday) Local site contact will be available during migration – but no specific knowledge and permissions on WAN components (it’s the only IT staff on site) Engineer will be escorted by Daniela. Daniela do the tests after migration. | 0700 - 1300 UTC | engineer has to complete a safety training (video) before entering site no extra insurance required | NA | NA | /30 |  |  | 62.67.19.168/30 CTL: 62.67.19.169/30 UNI: 62.67.19.170/30 | 62.67.19.169/30 | 62.67.19.170/30 | [9 empty] | Damian Dabros | Damian Dabros | Damian Dabros | 2019-12-19 |  | Standard site type - Hybrid (MPLS + IEN) | Complete | RJ45 on ISR4k | No | No | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 0700 - 1300 | 0800 - 1400 | 19021 | RCQ000000626752 | Approved | 39980 | CRQ000000623934 | Completed | Completed | Tested -Pass-First Time | Test completed by Cisco. CenturyLink didnt have availability for testing as per the proposed timeslots shared by GeoIT |  | Circuit Migrated | Issues reported related to Zscaler. | INC000106638127 |  | 2019-11-01 | 2019-12-01
CKT-I-01-GR-ATH03-0001-BT-1 | I0110670BT1 | 1 | Yes | High | Europe | GREECE | Athens HO | 2019_184 | un-uen-grcath2-rtr001 |  | Eloise Shepheard | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-22 | 2020-05-20 | Red | 2020-07-31 | 2020-07-20 | Green | 2020-08-14 | 2020-12-07 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process 27/10 Check WAN Block requirement for Athens HO when placing the order (for previous circuit: /28) | Yellow | Circuit not ordered | Unilever SNT |  | GR-ATH03-0001 | GREECE_ATHENS_KIFISSIA HO |  |  |  |  | Kymis Avenue and 10 Seneka Street Kifissia | Athens | 14564 |  | Andreas Spertos | Andreas.Spertos@unilever.com | 6944522609 |  |  | 20MB17MB20MB | 100 | 38.517 | 23.478 | 2019 | Nov | MPLS | 2014-09-01 | Commercial Benefit | 1 | Congested over 7 months | SC2 |  |  | Notify Andreas Spertos with the field engineer details. |  |  | /29 | Head office for the Greece business. Circa 1000 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | [13 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde
CKT-I-02-GR-ATH03-0001-GTT-1 | I0210670GTT1 | 1 | Migrated | High | Europe | GREECE | Athens HO | 2019_185 | un-uen-grcath2-vpn001 |  | Agnieszka Pajak | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01699967 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-22 | Complete | 2019-10-28 | 2019-09-13 | Complete | 2019-11-11 | 2019-11-08 | Complete | 19-Nov: Cease Request: UNL00023764. Approval Date: Nov 12nd. 8-Nov: Circuit successfully migrated. There was an issue with corporate NAT pool. (/30 working, /29 not). This has been fixed by the Cisco team but needs further investigation internally. 5-Nov: Circuit testing failed and was resolved by GTT. 30-Oct: GEO IT confirmed 8th Oct date starting at 1400 local time. 25/10 Local GeoIT suggested to move the migration date from 09 Nov to 08 Nov. The migration window should start 1400 Greek Time. The date will be re-confirmed by the GeoIT by 29 Oct. 24/10 change in wan block size requested by tech team from /30 to /28. Email with information shared with Welington/Deepak. Provider shared /28 with Cisco 23/10 | Complete | Circuit Migrated |  |  | GR-ATH03-0001 | GREECE_ATHENS_KIFISSIA HO | 12/11/2019 |  | UNL00023764 | 2019-11-12 | Kymis Avenue and 10 Seneka Street Kifissia | Athens | 14564 |  | Andreas Spertos | Andreas.Spertos@unilever.com | +6944522609 |  |  | 60M (100mb soft upgrade) | 100 | 38.517 | 23.478 | 2019 | Nov | Internet | 2019-04-19 | Commercial Benefit | 1 | Congested over 7 months | SC2 | NA | 8 Nov | Notify Andreas Spertos with the field engineer details. | NA | NA | /29 | Head office for the Greece business. Circa 1000 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | Ground Floor, Main Computer Room | 87.119.82.160/28 LAN Network - 87.119.82.160 First usable - 87.119.121.217 Last usable - 87.119.121.218 Broadcast - 87.119.121.219 Subnet Mask - 255.255.255.252 | 87.119.82.161/28 | 87.119.82.162/28 | 87.119.82.163/28-87.119.82.174/28 |  |  | Forthnet | GTT Sofia | AS 3257 |  |  |  | Rajesh Dagde | Rajesh Dagde | Karthik Ravi | 2019-11-11 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  | No | No | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 1200 -1800 | 1400 - 2000 | 13482 | CRQ000000613809 | Approved | 39943 | CRQ000000615822 | Completed | Completed | Tested-Pass | First iteration of testing failed. GTT fixed issues and testing was successful. | Andreas | Circuit Migrated - First Time right | NA | NA | NA | 2019-09-01 | 2019-11-01
CKT-I-01-DE-MHG01-0001-GTT-1 | I011360GTT1 | 1 | Yes | Top | Europe | GERMANY | MANNHEIM_RHENANIASTRASSE | 2019_177 | un-uen-deuman1-vpn001 | un-uen-deuman1-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01690201 | 2019-08-12 | 2019-08-09 | Complete | 2019-08-19 | 2019-08-12 | Complete | 2019-10-28 | 2020-01-17 | Complete | 2019-11-11 | 2020-09-10 | Complete | 20/02 Migration confirmed by local team for 14 Mar, starting 1400 CET. Test has been completed successfully today. 23/01 2nd link has been ordered from CenturyLink and will be delivered in February. Cisco project team has been instructed to go ahead with the migration of the GTT link. 21/01 The local team requires to have two diverse paths (two physical entry points) for the circuits in the network in the Mannheim site to ensure they are physically independent in case there are any failovers. This is not part of the current solution, as such it is seen by the local team as a showstopper for the migration as per the current plans. 20/12 Circuit delivery as scheduled. Circuit to be delivered with 50Mbps and will be upgraded to 100Mbps at a later stage as a separate project. 12/12 the client has requested an upgrade on the bandwidth from 40Mbps to 100Mbps. Please note that 17th January was a date provided prior to the request for upgrade. This date is most likely to change given the fact that the bandwidth will need to be upgraded to 100 Mbps. 10/12: Vendor informed that they will have to postpone this until 17th January due to the freeze period. 09/12: The site contact informed us that no one will be on site between 13th December and 10th January. 10/12 The hub is in process of being built. 28/11: DTAG wanted to deliver on 29th Nov, however, there are difficulties with HUB extensions. 15/11 Versatel confirmed that they are on track and the circuit is going to be delivered by 30/12 11/11 Need to confirm FOC for circuit delivery 23/10 Request received to upgrade to 300MB | Complete | Circuit Migrated |  |  | DE-MHG01-0001 | GERMANY_MANNHEIM_RHENANIASTRASSE |  |  |  |  | Rhenaniastrasse 76-102 | Mannheim | 68219 |  | Bernd Graf, Denis Rogausch | Sebastian.Bossler@unilever.com, bernd.graf@unilever.com, Thomas.Dehmel@unilever.com | +49 621 8049 549 | Thomas Dehmel, Stefan Hahnkamm | Thomas.Dehmel@unilever.com; Stefan.Hahnkamm@unilever.com | 10000Kbps10000Kbps | 40 | 49.442 | 8.5112 | 2019 | Oct | MPLS | 2012-11-28 | EWM Rollout |  |  | SC2 | Safety glasses and shoes required from the FE. Additional restrictions due to Covid-19 - engineer required to complete health questionnaire on 25/03. This will be reviewed by the Unilever local management and a decision will be given whether we can go ahead with the migration | 1300 - 1900 UTC | Induction training required on the day of the migration. Safety glasses and shoes required from the FE. Additional restrictions due to Covid-19 - engineer required to complete health questionnaire on 25/03. This will be reviewed by the Unilever local management and a decision will be given whether we can go ahead with the migration | NA | NA | /30 |  | 2nd Floor, Building 32, Room 1103 | 87.119.82.252/30 LAN Network - 87.119.82.252 First usable - 87.119.82.253 Last usable - 87.119.82.254 Broadcast - 87.119.82.255 Subnet Mask - 255.255.255.252 | 87.119.82.253/30 | 87.119.82.254/30 |  |  |  | 1&1 Versatel Deutschland | GTT Frankfurt | AS 3257 |  |  |  | Fat Nela | Fat Nela | Fat Nela | 2020-03-30 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO | No | No | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 1300 - 1900 | 1400 - 2000 | 45045 | CRQ000000654351 | Approved | 40874 | CRQ000000634784 | Completed | Completed | Tested-Pass | Test passed. Test failed initially due to : Problem with the line which is already resolved. Test to be re-scheduled | Bernd Graf | Circuit Migrated - First Time right | NA | NA | NA | 2020-01-01 | 2020-02-01
CKT-I-01-IT-CAS99-9999-BT-1 | I011278BT1 | 1 | Hostname according to BT sheet is un-uen-rtr_guest_casale with IP "145.55.251.2" which is not accessible Devices at site are: un-uen-itacas1-rtr001 - no nat pool, /30 wan mask, 15M existing BW, 4351 device un-uen-itacas1-vpn001(accessible via telnet and TACACS) - 2 nat pools /30, /30 wan mask, 60M existing BW, 4351 device | High | Europe | ITALY | Cas/Pusterlengo | 2019_452 | un-uen-itacas1-rtr001 |  | Eloise Shepheard | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-22 | 2020-05-20 | Red | 2020-07-31 | 2020-07-20 | Green | 2020-08-14 | 2020-12-30 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | IT-CAS99-9999 | ITALY_CASALPUSTERLENGO_FACTORY |  |  |  |  | via Lever Gibbs, 3 | Lodi | 26841 |  | Alberto Caserini | alberto.caserini@unilever.com | +39 3318153480 |  |  | 15M | 100 |  |  | 2019 | Nov | MPLS | 2016-07-18 | Commercial Benefit | 1 | Congested over 12 months | SC2 | [5 empty] | /30 | [14 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde
CKT-I-01-IT-CHI99-9999-BT-1 | I0110056BT1 | 1 | Yes | High | Europe | ITALY | Chieti | 2019_481 | un-uen-itagio1-rtr001 |  | Eloise Shepheard | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-22 | 2020-05-20 | Red | 2020-07-31 | 2020-07-20 | Green | 2020-08-14 | 2020-12-30 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | IT-CHI99-9999 | ITALY_SAN GIOVANNI TEATINO_5 VIA TEVERE_CHIETI |  |  |  |  | VIA TEVERE, 5 66020 San Giovanni Teatino (CH) | Chieti | 66020 | office | Sandra Ranalletta | sandra.ranalletta@unilever.com | + 39 3488572885 |  |  | 1024Kbps1024Kbps | 10 | 42°24'33.4"N | 14°09'37.9"E | 2019 | Nov | Internet | 2009-03-31 | Service | 1 | Congested link | SC2 | work hours: 8x5 |  |  |  |  | /30 | [14 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde
CKT-I-01-IT-CHI99-9999-ORA-1 | I0110056ORA1 | 1 | Yes | High | Europe | ITALY | Chieti | 2019_482 | un-uen-itagio1-ien001 | un-uen-itagio1-vpn001 | Eloise Shepheard | WAN Circuit Migration | Circuit | Orange | Ora |  | LO0048VE45 | 2019-08-19 | 2019-09-13 | Complete | 2019-08-26 | 2020-01-14 | Complete | 2019-11-04 | 2020-04-24 | Complete | 2019-11-18 | 2020-08-05 | Complete | 05/08: Migration successful 28/07: Migration unsuccessful. NTT FE unplugged power cable.Re-planned for 5th August at 09:30 local time. 16/07 - MIgration on 28/07 - Field Engineer Required 14/07 - Issues resolve and line successfully tested at 21Mbps - Migration to be fast tracked due to issue with existing MPLS line 13/07 - ES confirmed engineer details for 14th July - Orange confirmed their support will be available on the testing dates 09/07 - ES sent follow up mail chasing engineer 08/07 - Orange confirmed they checked with carrier and require 1 day prior notice for the testing with LCON/Engineer. 08/07 - 3rd test attempt - waiting for NTT to confirm engineer and Orange support on day 06/07 - local carrier confirmed they can reach their line – Eloise to arrange field engineer as no local IT – Orange will arrange testing when engineer is on site. 01/07 - Eloise updated Ruth as to problems with circuit - As circuit delivered in November the issue needs to be dealt with through an incident raised with Chris Hobbs to get this addressed - Ruth confirmed incident will be raised by Chris Hobbs (Orange). 01/07 - Testing failed again - need to arrange Orange on site to test and mark-up correct port - testing will have to be re-planned - try to get Orange engineer to visit site and carry out testing with NTT on phone. 01/07 - NTT engineer over 30 mins late to 1.5 hour meeting - escalated by Cisco to NTT 29/06 - Sandra confirmed Jul 1st at 9am 26/06 - Aga confirmed quick response from partner and it seems we can go ahead with testing Jul 1st @9am - pending confirmation from Sandra (LCON) 26/06 - Aga confirmed she has confirmed with Cisco engineer and is waiting for confirmation from NTT 26/06 - LCON Ranalletta, Sandra <Sandra.Ranalletta@unilever.com> requested testing on Wed 1st July as cannot do Tue 30th June - Cisco to review and confirm 23/06 - Marco confirmed local contact won't know if there are isseus and that will have to be confirmed by Cisco - Eloise emailed to update her that it will have to be adressed on next site visit. 23/06 - Marco confirmed he is not able to confirm if there is an issue on site - I have asked him to check with local user 22/06 - Marco emailed to find out if there is an ongoing MPLS issue on site? 22/06 - Marco replied to confirm the Cisco work was unsuccessful and expect Cisco to provide an action plan. 18/06 - Andrew Colley replied that he believes there is an open MPLS issue for site and has asked Parise, Marco for an update 17/06 - email sent to MIke Keenan who forwareded it on to Andrew Colley (service lead) to see if he is aware of failed MPLS 17/06 - Circuit testing failed - NTT Engineer arrived 40 mins late and Languague issues when addressing technical issues. NTT Engineer was using his mobile as hotspot for testing speed - Eloise escalated with NTT 17/06 - Circuit testing underway 16/06 - Circuit testing planned for 17 June June 2nd: Not found on providers list; but in t 04/05 Circuit delivered. As per the feedback from the GeoIT, testing will be able to take place mid May due to current restrictions related to covid-19. Cisco team to initiate the prep work for the migration 04/12 Local team did not respond to the validation Email from Orange. It has been over 10 days now. Orange asked for help Welington. The delivery dates are dependent on when the confirmation email will be sent by the local team to Orange. | Complete | Circuit Migrated | Circuit Provider Cisco |  | IT-CHI99-9999 | ITALY_SAN GIOVANNI TEATINO_5 VIA TEVERE_CHIETI |  |  |  |  | VIA TEVERE, 5 66020 San Giovanni Teatino (CH) | Chieti | 66020 |  | Sandra Ranalletta | sandra.ranalletta@unilever.com | + 39 3488572885 |  |  | 7000Kbps | 10 | 42°24'33.4"N | 14°09'37.9"E | 2019 | Nov | Internet | 2015-04-27 | Service | 1 | Congested link | SC2 | work hours: 8x5 | 09:00am to 15:00pm local time |  |  |  | /30 |  |  | Subnet pubblica IPV4 2.228.234.132/30 | 2.228.234.133 | 2.228.234.134 |  |  |  | FASTWEB | [5 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde | [10 empty] | Window Date agreed - End user Comms not sent |  | 07:00am to 13:00pm | 09:00am to 15:00pm local time | 108804 | CRQ000000695987 | Approved |  | CRQ000000682658 | Completed | Completed |  |  |  | Circuit Migrated |  |  |  |  | 2020-06-01
CKT-I-01-IT-CAG99-9999-ORA-1 | I012766ORA1 | 1 | Yes | High | Europe | ITALY | Filiale Cagliari | 2019_443 | un-uen-itacag1-ien001 |  | Eloise Shepheard | WAN Circuit Migration | Circuit | Orange | ORA |  | GO0AUPEY48 | 2020-05-15 | 2020-05-15 | Green | 2020-05-22 | 2020-05-20 | Red | 2020-07-31 | 2020-10-15 | Red | 2020-08-14 | 2020-11-14 | Red | 09/07 - order in progress with carrier 11/06 - Cisco no reference - check with Supplier June 2nd: Not found on providers list 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | IT-CAG99-9999 | ITALY_CAGLIARI_DEPOT |  |  |  |  | Viale Marconi | Cagliari | 09131 |  | Veronica Deidda | veronica.deidda@unilever.com | +39 3488573654 |  |  | 7000Kbps | 10 |  |  | 2019 | Nov | MPLS | 2014-10-19 | Commercial Benefit | 1 | Congested over 12 months | SC2 | [5 empty] | /30 | [14 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde
CKT-I-02-IT-CAG99-9999-GTT-1 | I022766GTT1 | 1 | Yes | Top | Europe | ITALY | Filiale Cagliari | 2019_444 | un-uen-itacag1-rtr001 | un-uen-itacag1-vpn001 | Eloise Shepheard | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01706101 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-12 | Complete | 2019-10-28 | 2020-02-25 | Complete | 2019-11-11 | 2020-08-14 | Complete | 14/08: Migration successful 04/08: Migration planned for 14th August. Field engineer assigned and webex sent out 16/07 - Testing confirmed successful - FE engineer required for migration - Migration date to be confirmed 15/07 - FE - Damiano Sanna +39 320 5798831 - for 16th 13/07 - Mauro confirmed site agreed 10.00 AM on 16th of July for visit of TIM engineer 08/07 - Site confirmed they can do 16th July - Gerganan mailed by ES for FE confirmation 07/07 - ES chased Mario and Veronica Deidee for suitability of 16th July for FE to attend site for testing 06/07: Eloise reached out to Veronica about date for TIM engineer to come to site. She said any date next week is ok. Sent email to GTT regarding this - awaiting date and time for TIM engineer. 30/06 - Mauro confirmed that Telco FTE is now at the site checking the line/circuit/cabling - Carlo GTT to follow up and arrange new testing date 29/06 - Mauro chasing Veronica for an update 26/06 - Carlo chased Veronica for update on when TIM engineer can attend site 26/06 - Giuseppe requested LCON Veronica to provide information to Carlo about local contact in Cagliari and business work hour. 25/06 - Carlo confirms Retelit need to sent TIM engineer to site to check their device 24/06 - email sent to Mauro Biso 24/06 - Testing not successful - GTT need to take up with local Telecoms as device not reachable 24/06 - Field Engineer delayed getting to site, no contact details provided and trying to arrange contact when they get to site 22/06 - Gergana email - agrred to send out invite Wed 24th June - 09:30 local time (08:30 UK time). 19/06 - circuit testing confirmed for Wednesday June 24th at 9.30am June 2nd: Requested support to Mauro to define a date for testing the circuit June 1st: COVID - Need to wait until June 30 04/05 Covid-19 restrictions still in place. Further update from local GeoIT will be provided by mid May. 12/03 Circuit testing in Cagliari not possible due to coronavirus. Further information will be available by the local team after April 3rd, as per the general government guidance. Before the migration a FAILOVER TEST is required. 31/01 ETA for delivery end of Feb 13/01 Vendor delivery estimated 20 Jan 21/11 that the delivery of the circuit in Cagliari has been put on hold as there are some additional activities required to be completed. The supplier is waiting for digging permissions form the local authorities. The municipal permit should be received in the end of December and so the new date for circuit delivery has been estimated for end of January 2020 24/10 FOC not confirmed. GTT chasing the vendor for updates following the site survey. | Complete | Circuit Migrated | Circuit Provider |  | IT-CAG99-9999 | ITALY_CAGLIARI_DEPOT |  |  |  |  | Viale Marconi | Cagliari | 09131 |  | Veronica Deidda | veronica.deidda@unilever.com | +39 3488573654 |  |  | 1024Kbps1024Kbps | 10 |  |  | 2019 | Nov | Internet | 2014-10-19 | Service | 1 | Congested over 12 months | SC2 | [5 empty] | /30 |  | 1st floor, Comms Room | 154.14.7.36/30 Network - 154.14.7.36 First usable - 154.14.7.37 Last usable - 154.14.7.38 Broadcast - 154.14.7.39 Subnet Mask - 255.255.255.252 | 154.14.7.37 | 154.14.7.38 |  |  |  | Retelit | GTT Milan | AS 3257 |  |  |  | Lalhmunsanga Fanai | Lalhmunsanga Fanai | Lalhmunsanga Fanai | 2020-03-26 |  | Standard site type - Hybrid (MPLS + IEN) | Complete |  | No |  |  | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 0800 - 1400 | 0900 - 1500 | 112656 | CRQ 116086 | Approved | 41085 | CRQ000000639727 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  |  | 2020-06-01
CKT-I-01-IT-GEN99-9999-GTT-1 | I0111039GTT1 | 1 | Yes | High | Europe | ITALY | Genova 3PL | 2019_459 | un-uen-itagen1-rtr001 | un-uen-itagen1-vpn002 | Eloise Shepheard | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01723703 | 2019-08-19 | 2019-08-19 | Complete | 2019-08-26 | 2019-09-03 | Complete | 2019-11-04 | 2020-01-21 | Complete | 2019-11-18 | 2020-08-19 | Complete | 19/08: Migration successful 11/08: Migration planned for 19th August. Alberto confirm SFP's have arrived., 16/07 - Check with Julian on SFP Order - cannot progress without SFPs 09/07 - ES confirmed block order of SFP being delivered to site so can be internally shipped to other Italy sites if required. 29/06: Migration been rescheduled for 7th July - SFP sourced locally 08/06: Migration cancelled as we require SFP. Local team looking into getting locally or NTT order will need to be placed. 29/05 Migration planned for 09/06. 19/05: Eloise suggesting migration w/c 1st June 04/05 Covid-19 restrictions still in place. Further update from local GeoIT will be provided by mid May. 24/01 Meeting with GeoIT rescheduled twice due to GeoIT unavailability. 23/01 Project introduction meeting planned for Friday 24 Jan. testing arrangement - in progress. Local contact doesnt have admin rights atm. 10/01 Circuit delivery ETA end of next week 03/12 The Vendor will complete the activities and will handover into January. 24/10 FOC not confirmed. Chasing the vendor for further updates. | Complete | Circuit Migrated | Circuit Provider |  | IT-GEN99-9999 | ITALY_GENOVA_4 VIA GUALCO_GENOVA 3PL |  |  |  |  | via Gualco 4, 16165 | Genova | 16165 |  | Alberto Caserini | Caserini, Alberto <Alberto.Caserini@unilever.com> | +39 3318153480 |  |  | 1024Kbps1024Kbps | 10 |  |  | 2019 | Nov | MPLS | 2009-04-16 | Commercial Benefit | 1 | Congested link | SC2 | 05/06: Cisco established SFP required NA | 08:30-16:00 | NA | NA |  | /30 |  | Ground floor, Comms room, Co.gel. Srl Concessionaria Gelati, Via Gualco, 4, 16165 Genova | 154.14.6.56/30 Network - 154.14.6.56 First usable - 154.14.6.57 Last usable - 154.14.6.58 Broadcast - 154.14.6.59 Subnet Mask - 255.255.255.252 | 154.14.6.57 | 154.14.6.58 | 154.14.6.56/30 |  |  | FASTWEB SpA | GTT Milan - MIL2T |  |  |  |  | Rajesh Dagde | Adrian Lazar | Adrian Lazar |  |  | Standard site type - Hybrid (MPLS + IEN) | Complete | 1000Base-LX/LH with GLC-LH-SMD on ISR4k | No | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 08:00-14:00 | 09:00-15:00 | 32897 (OLD), 108255 New | CRQ000000701111 | Approved | 40873 | CRQ000000634753 | Completed | Completed | Tested-Fail | Line not working. Ping not going. GTT to connect with the vendor. |  | Circuit Migrated |  |  |  |  | 2020-02-01
CKT-I-02-IT-GEN99-9999-ORA-1 | I0211039ORA1 | 1 | Yes | High | Europe | ITALY | Genova 3PL | 2019_460 | un-uen-itagen-pio001 | un-uen-itagen-vpn001 | Eloise Shepheard | WAN Circuit Migration | Circuit | Orange | Ora |  | LO0048VC43 | 2019-08-19 | 2019-09-13 | Complete | 2019-08-26 | 2020-01-16 | Complete | 2019-11-04 | 2020-07-20 | Complete | 2019-11-18 | 2020-08-04 | Complete | 04/08 : Migration successful 08-Jul-20: Installation on going, expecting confirmation on the fibre installation by 10th July. Still should be mid july - placed 20th July as circuit deivery date 01-Jul-20: Carrier have advised that they have encountered issues with the fibre installation. They expect to finish this part by the end of next week (10th July) and install equipment and complete by mid-July. 31/05:Permits delayed until mid-June by the Town Council as the last flooding of the Bisagno River caused infrastructural problems to a bridge under renovation through which this connection cable should be laid 04/05 Delays with delivery due to covid-19 - new ETA TBC 20/12 Orange has not received validation email from the local contact yet 04/12 Local team did not respond to the validation Email from Orange. This is being escalated. The delivery dates will be confirmed only when the validation email is sent back to Orange. | Complete | Circuit Migrated | Circuit Provider |  | IT-GEN99-9999 | ITALY_GENOVA_4 VIA GUALCO_GENOVA 3PL |  |  |  |  | via Gualco 4, 16165 | Genova | 16165 |  | Marco Magatti | Caserini, Alberto <Alberto.Caserini@unilever.com> | +39 3318153480 |  |  | 7M | 10 |  |  | 2019 | Nov | Internet | 2014-05-18 | Service | 1 | Congested link | SC2 | [5 empty] | /30 |  |  | "LAN: 45.89.180.100/30 IP Retelit: 45.89.180.101 IP Orange : 45.89.180.102" | 45.89.180.101 | 45.89.180.102 |  |  |  | Retelit | [5 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN) |  |  | No | No | Yes |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 09:00:00 to 17:00:00 | 11 to 19:00 | 108255 | CRQ000000696311 | Approved |  | CRQ000000694726 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-IT-SAS99-9999-BT-1 | I0111037BT1 | 1 | Yes | High | Europe | ITALY | Sassari 3PL | 2019_483 | un-uen-itasas1-rtr001 | un-uen-itasas1-vpn001 | Eloise Shepheard | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-22 | 2020-05-20 | Red | 2020-07-31 | 2020-07-20 | Green | 2020-08-14 | 2020-12-30 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | IT-SAS99-9999 | ITALY_SASSARI_102 VIA CANIGA_SASSARI 3PL |  |  |  |  | VIA CANIGA 102 | Sassari | 07100 |  | Veronica Deidda | veronica.deidda@unilever.com | +39 3488573653 |  |  | 1024Kbps1024Kbps | 10 |  |  | 2019 | Nov | MPLS | 2009-03-31 | Service | 1 | Congested link | SC2 | [5 empty] | /30 | [14 empty] | Lalhmunsanga Fanai | Lalhmunsanga Fanai | Lalhmunsanga Fanai |  |  | Standard site type - Hybrid (MPLS + IEN) |  | 1000Base-LX/LH with GLC-LH-SMD on ISR4k | No | No | No |  | Partner MOP created Received tunnel IP or LAN IP (if required)
CKT-I-02-IT-SAS99-9999-ORA-1 | I0211037ORA1 | 1 | Yes | Top | Europe | ITALY | Sassari 3PL | 2019_484 | un-uen-itasas1-ien001 | un-uen-itasas1-vpn001 | Eloise Shepheard | WAN Circuit Migration | Circuit | Orange | Ora |  | LO0048V535 | 2019-08-19 | 2019-09-13 | Complete | 2019-08-26 | 2019-10-22 | Complete | 2019-11-04 | 2020-06-10 | Complete | 2019-11-18 | 2020-07-30 | Complete | 30/07: Migration successful 16/07 - 30/07 migration date - Field Engineer Required 09/07 - new migration date required - Cisco do not have network diagram 06/07 - migration on 17th July? - this is dependent on getting answer to network diagram question on 10th July 28/06: Testing successfully took place on 26th June. Migration can be planned for July 2020 31/05: Carrier have completed the Fibre installation and are now working to complete the installation at the PoP. This is expected to be completed by 12th June and then carrier will need to install router on site. IP address info provided to Unilever and Cisco 19/05: Eloise suggesting migration w/c 8th June 04/05 Delays with delivery due to covid-19 - new ETA TBC 04/03: No change - Carrier still waiting for authorization to excavate. 25/02: we have a delay The Carrier is waiting for authorizaton for an excavation permits that are required for 10/01 New ETA for circuit delivery. We were targetting 08/01 but Orange provided new ETA today for Feb 24 10/01 Network diagram requested from Darren Carr. IP address requested from Orange. Confirmation on delivery requested from Orange. 08/01 circuit to be delivered today. Network diagram / info on local PoC requested from Welington. IP address requested from Orange.. 20/12 Expected delivery date 4 Jan | Complete | Circuit Migrated | Circuit Provider |  | IT-SAS99-9999 | ITALY_SASSARI_102 VIA CANIGA_SASSARI 3PL |  |  |  |  | VIA CANIGA 102 | Sassari | 07100 |  | Veronica Deidda | veronica.deidda@unilever.com | +39 3488573653 |  |  | 2048Kbps | 10 |  |  | 2019 | Nov | Internet | 2015-05-01 | Service | 1 | Congested link | SC2 |  | 10am to 16:00pm local time |  |  |  | /30 |  |  | 37.186.203.56/30, where: 37.186.203.57 It will be the FW router 37.186.203.58 It will be the customer device. | 37.186.203.57 | 37.186.203.58 |  |  |  | FASTWEB | [5 empty] | Lalhmunsanga Fanai | Lalhmunsanga Fanai | Lalhmunsanga Fanai |  |  | Standard site type - Hybrid (MPLS + IEN) |  | NO | No | No | No | No | Assessment Complete MOP created & config created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms not sent |  | 08:00 to 14:00 | 10am to 16:00pm local time | 106299 |  |  |  | CRQ000000682357 | Completed | Completed | [7 empty] | 2020-01-01 | 2020-03-01
CKT-I-01-LV-RIX02-0310-UNL-1 |  | 1 | Not found in BT document or NP, No device access | Medium | Europe | LATVIA | LATVIA_RIGA_LV | 2019_510 | un-uen-lvarig1-rtr002 |  |  | SNT | Circuit | Unilever | Uni |  |  | 2019-07-05 | 2019-08-27 | Complete | 2019-07-12 | 2019-08-27 | Complete | 2019-09-20 | 2019-09-16 | Complete | 2019-11-11 | 2019-09-19 | Complete | Completed by UL/BT | Complete | Circuit Migrated |  | Check dates | LV-RIX02-0310 | LATVIA_RIGA_LV |  |  |  |  | Kronvalda 3-10 | Riga | LV-1010 |  | Mykolas Norvaisas | Mykolas.Norvaisas@unilever.com | +37069850977 |  |  | 100M | 40 | 56.9327 | 24.1361 | 2019 | Sep | MPLS | 2014-01-13 | Commercial Benefit |  |  | SC2 | [5 empty] | /30
CKT-I-02-LT-VNO02-0030-UNL-1 |  | 1 | Not found in NP, used old BW given. Not sure of IP address mask required Yes | Medium | Europe | LITHUANIA | LITHUANIA_VILNIUS | 2019_512 | un-uen-ltvilu1 |  | Agnieszka Pajak | BAU Projects | Circuit | Unilever | Uni |  |  | 2019-08-12 | 2019-08-28 | Complete | 2019-08-19 | 2019-08-28 | Complete | 2019-10-28 | 2019-09-17 | Complete | 2019-11-11 | 2019-11-15 | Complete | 15/11 Migration successful | Complete | Circuit Migrated |  |  | LT-VNO02-0030 | LITHUANIA_VILNIUS |  |  |  |  | Gabijos g. 30 | Vilnius | LT06110 |  | Mykolas Norvaisas | Mykolas.Norvaisas@unilever.com | 37069850977 |  |  | 10Mbps | 40 | 54.7336 | 25.2225 | 2019 | Nov | MPLS | 2013-12-13 | Commercial Benefit |  |  | SC2 | NA | 0730-1200 UTC | NA | NA | NA | /30 | [14 empty] | Adrian Lazar | Adrian Lazar | Adrian Lazar | 2019-11-17 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  | Yes |  |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms not sent |  | 0730-1200 | 1030 - 1500 |  | CRQ000000611769 | Approved | 39803 | CRQ000000615317 | Completed | Completed | Tested -Pass-First Time
CKT-I-01-PL-KTW01-0005-GTT-1 | I019903GTT1 | 1 | Yes | Medium | Europe | POLAND | KATOWICE_KIE_CENTRUM_BIZNESU_BUILDING | 2019_610 | un-uen-polkat1-pio001 | un-uen-polkat1-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01690236 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-20 | Complete | 2019-10-28 | 2019-11-07 | Complete | 2019-11-11 | 2020-03-05 | Complete | 06/03 Migration successfully completed. 21/02 New target migration date: 05 Mar. BT ALgosec team and Cisco TAC team to be in stand-by mode for the migration. Cisco working on arranging this. 06/02 Migration unsuccessful - roll back required. New configuration was being blocked by the firewall. Cisco team suspects this might be related to the Algosec request not being implemented successfully. An incident raised with BT for troubleshoot (INC000106796769). 23/01 New migration date requested from local GeoIT 22/01 Fix has been completed, Cisco NCE confirmed he can access the vpn001 router in Katowice. 20/01 Due to issues with vpn001 (Cisco has no access to the router) this migration is currently ON HOLD until the fix is completed. 08/01 Date and time for the migration re-confirmed by the local team. 12/11 10 Jan 2020 has been confirmed by the local business as a migration date. 07/11 A letter of service has been received from GTT today. IP address has been provided. 04/11 GeoIT requested to reschedule the migration to January 2020 - As one of the main reasons why Geo IT requested moving implementation from 30th November to January 2020. is because KCB is very large site (around 850 employee’s) and finance team is heavily involved at that time in month closure and very fast after this date they will start year closing and we want to avoid any potential problems with WAN. One more possible problem would be global red zone for core services at the end of each month. 31/10 We need to get more details. Local GeoIT requested to move this date out 24/10 No migration possible beg/end of month. Current proposed migration date not accepted by local IT. Request to move forward. This is being checked with GTT. | Complete | Circuit Migrated |  |  | PL-KTW01-0005 | POLAND_KATOWICE_KIE_CENTRUM_BIZNESU_BUILDING |  |  |  |  | Katowickie Centrum Biznesu ul. Chorzowska 6 | Katowice | 40-101 |  | Arkadiusz Lach | Arkadiusz.lach@unilever.com | +48 663630613 |  |  | 200MB | 350 | 50.261 | 19.0975 | 2019 | Nov | MPLS | 2017-11-01 | Commercial Benefit |  |  | SC2 | NA | 1600 - 2200 UTC | NA | NA | NA | /29 | Service Centre for Europe. Circa 1500 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | Floor No. 1, Server room on the south wing of the 1st floor. | 87.119.85.16/28 LAN Network - 87.119.85.16 First usable - 87.119.85.17 Last usable - 87.119.85.30 Broadcast - 87.119.85.31 Subnet Mask - 255.255.255.240 | 87.119.85.17/28 | 87.119.85.18/28 | 87.119.85.19-30/28 |  |  | Netia | GTT Warsaw | AS 3257 |  |  |  | Damian Dabros | Damian Dabros | Adrian Lazar | 2020-03-06 |  | Complex site type - requires redesign | In Progress | NO | No | No | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 1600 - 2200 | 1700 - 2300 | 28073 | CRQ000000647104 | Approved | 40842 | CRQ000000633629 | Completed | Completed | Tested-Pass | 1. Test passed in second attempt. 2. First test failed due to : Local Unilever contact (Arkadiusz Lach) was unable to connect over Windows Meeting due to his laptop mic issues. The testing would be rescheduled. | Arkadiusz Lach | Circuit Migrated | IP Loopback not showing Up |  |  |  | 2020-01-01
CKT-I-01-PL-WAW08-0001-UNL-1 |  | 1 | Not found in NP, used old BW given. Not sure of IP address mask required Yes | High | Europe | POLAND | WARSAW_EUROCENTRUM | 2019_613 | un-uen-polwar1-rtr001 |  |  | SNT | Circuit | Unilever | Uni |  |  | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-27 | Complete | 2019-10-28 | 2019-09-16 | Complete | 2019-11-11 | 2019-10-10 | Complete | Completed by UL/BT | Complete | Circuit Migrated |  |  | PL-WAW08-0001 | POLAND_WARSAW_EUROCENTRUM |  |  |  |  | AL.Jerozolimskie 134 | Warszawa | 02-305 |  | Jan Dolega | Jan.dolega@unilever.com | +48 601363213 |  |  | 30Mbps | 200 | 52.2212 | 20.9738 | 2019 | Oct | MPLS | 2015-07-24 | Commercial Benefit | 1 | Congested Link | SC3 | [5 empty] | /29 | Head office for the Poland business. Circa 700 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. |  | Network - 87.119.85.16 | [31 empty] | 39702 |  | Completed
CKT-I-02-PL-WAW08-0001-GTT-1 |  | 1 | Not found in BT document or NP, Not sure of hostname un-uen-polwar-vpn002 - 2 /28 nat pool, 200M existing tunnel BW, /28 WAN mask, 4431 device un-uen-polwar-vpn001 - no nat pool, 200M tunnel BW, /28 WAN mask, 4431 device | High | Europe | POLAND | WARSAW_EUROCENTRUM | 2019_614 | un-uen-polwar1-vpn001/un-uen-polwar1-vpn002 |  |  | SNT | Circuit | GTT | GTT |  | DIA/01699203 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-20 | Complete | 2019-10-28 | 2019-10-08 | Complete | 2019-11-11 | 2019-10-10 | Complete | Completed by UL/BT | Complete | Circuit Migrated |  | Check dates | PL-WAW08-0001 | POLAND_WARSAW_EUROCENTRUM |  |  |  |  | AL.Jerozolimskie 134 | Warszawa | 02-305 |  | Jan Dolega | Jan.dolega@unilever.com | +48 601363213 |  |  |  | 200 | 52.2212 | 20.9738 | 2019 | Oct | Internet | 2019-09-26 | Commercial Benefit | 1 | Congested Link | SC3 | [5 empty] | /29 | Head office for the Poland business. Circa 700 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | 3rd Floor, Server Room | 87.119.80.0/28 LAN Network - 87.119.80.0 First usable - 87.119.80.1 Last usable - 87.119.80.14 Broadcast - 87.119.80.15 Subnet Mask - 255.255.255.240 | [5 empty] | Netia | GTT Warsaw | AS 3257 |  |  |  | Already done | Already done | Already done | [20 empty] | Completed
CKT-I-01-PT-LIS01-0001-GTT-1 | I01608GTT1 | 1 | Yes | High | Europe | PORTUGAL | Lisbon Head Office | 2019_615 | un-uen-prtlis1-rtr001 | un-uen-prtlis1-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit | GTT | GTT |  | " DIA/01690248" | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-12 | Complete | 2019-10-28 | 2019-10-15 | Complete | 2019-11-11 | 2020-05-07 | Complete | 27/04 Santa Iria Migration scheduled for 5 May. If successful, we are going ahead with the migration in Lisnon 7 May 06/03 This is on hold until the migration in Santa Iria happens, and Santa Iria becomes independent network 17/12 This is being escalated by GTT in order to speed up the delivery date if possible. 22/11 Due to the complexity of the planned migration and the results after the testing, the decision was taken to postpones the migration in Lisbon HO until the migrations in Santa Iria take place - to make this site independent as it is part of the same network at the moment. 20/11 Expedited RFC approved by CAB. Pre-migration testing to take place 21 Nov. 18/11 Additional testing required in order to test whether Santa Iria (which is on the same network) will be able to connect to global network while the migration activity takes place in Lisbon HO. An expedited RFC to be raised. | Complete | Circuit Migrated | Cisco |  | PT-LIS01-0001 | PORTUGAL_LISBON_JERONIMO_MARTINS_LDA |  |  |  |  | Largo Monterroio Mascarenhas N1 | Lisboa | 1099-081 | headoffice | Joaquim Camoes | Joaquim.camoes@unilever.com | +351 93 251 0466 | Joaquim Camoes | Joaquim.camoes@unilever.com | 60MB60MB | 100 | 38.7207 | -9.1442 | 2019 | Nov | MPLS | 2017-04-26 | Commercial Benefit |  |  | SC2 | Migration between 7:00AM-9:00AM Local time, applications to be tested: SAP; email, Internet, Skype, OutSystems, Remedy; Local IT available | 0600-1200 | NA | NA | NA | /30 |  | First Floor, Datacentre, Unilever Fima, Lda. Largo Monterroio Mascarenhas, 1, 1099-081 Lisboa | 87.119.82.44/30 Network - 87.119.82.44 First usable - 87.119.82.45 Last usable - 87.119.82.46 Broadcast - 87.119.82.47 Subnet Mask - 255.255.255.252 | 87.119.82.45 | 87.119.82.46 |  |  |  | NOS (fka Optimus and ZON) | GTT Madrid | AS 3257 |  |  |  | Damian Dabros | Damian Dabros | Damian Dabros | 2020-05-08 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO |  |  | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 0600-1200 | 0600-1200 | 62997 | CRQ000000668554 CRQ000000619704 - change cancelled due to the results from the redundancy test CRQ000000620221 - test redundancy | Approved | 42578 | CRQ000000665115 | Completed | Completed | Tested-Pass |  | Joaquim Camoes | Circuit Migrated |  |  |  | 2019-10-01 | 2019-11-01
CKT-I-01-PT-SIA01-0001-GTT-1 | I012821GTT1 | 1 | Yes | High | Europe | PORTUGAL | Santa Iria Factories | 2019_616 | un-uen-prtsan1-rtr001 | un-uen-prtsan1-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Router | GTT | GTT |  | DIA/01690252 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-27 | Complete | 2019-10-28 | 2020-01-30 | Complete | 2019-11-11 | 2020-05-05 | Complete | 20/04 A new router has been delivered, Migration has been agreed for 5 May. 06/03 Awaiting additional router to be deliverred by Unilever. ETA 2-3 months. 31/01 Circuit delivered and ready for testing 20/01: The Vendor is keep trying to obtain the necessary approval. Their team is trying other contacts to overcome this issue and their high management is involved too. 08/01: After the holiday season the Vendor can finally get the approval to get this circuit installed. Once they have more info they will let us know. 17/12: The fiber licensing is in progress and the Vendor's team really knows the urgency in this circuit delivery and is truly engaged to be able to get the approval as soon as possible to carry on with the fiber deployment that needs to be done. They will share more information as soon as we have more developments. 20/12 The fiber licensing is in progress and the Vendor's team really knows the urgency in this circuit delivery and is truly engaged to be able to get the approval as soon as possible to carry on with the fiber deployment that needs to be done. They will share more information as soon as we have more developments. 17/11 changes in fiber path required. New delivery date to be provided by GTT | Complete | Circuit Migrated | Cisco |  | PT-SIA01-0001 | PORTUGAL_SANTA_IRIA_DE_AZOIA_JERONIMO_MARTINS_LDA |  |  |  |  | Fima Olá, Lda., Marinhas de D. Pedro | Santa Iria de Azoia | 2695-361 |  | Joaquim Camoes | Joaquim.camoes@unilever.com | +351 93 251 0466 |  |  | 45MB45MB | 100 | 36.0911 | -18.7277 | 2019 | Nov | MPLS | 2017-04-26 | Commercial Benefit | 1 | No resilience | SC2 | NA | 0600-1200 | NA | NA | NA | /30 |  | First Floor, Central building FimaOlá, Datacentre | 154.14.7.40/30 Network - 154.14.7.40 First usable - 154.14.7.41 Last usable - 154.14.7.42 Broadcast - 154.14.7.43 Subnet Mask - 255.255.255.252 | 154.14.7.41 | 154.14.7.42 |  |  |  | ONI Communications | GTT Madrid | AS 3257 |  |  |  | Damian Dabros | Damian Dabros | Damian Dabros | 2020-05-06 |  | Standard site type - Hybrid (DMVPN + IEN) | Complete |  |  |  | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 0600-1200 | 0600-1200 | 62702 | CRQ000000668134 | Approved | 42577 | CRQ000000664894 | Completed | Completed | Tested-Pass |  | Joaquim Camoes | Circuit Migrated - First Time right |  |  |  | 2019-12-01 | 2020-03-01
CKT-I-02-PT-SIA01-0001-VOD-1 | I022821VOD1 | 1 | Yes | Medium | Europe | PORTUGAL | Santa Iria Factories | 2019_617 | un-uen-prtsan1-rtr001 | un-uen-prtsan1-vpn001 | Eloise Shepheard | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQM-00014 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-10-31 | Red | 2019-11-18 | 2020-10-03 | Red | 16/07 - still local approvals pending - likely to be delivered by end of October - LMP will provide a wireless solution until the circuit is installed - to be checked back by Vodafone with last mile provider to see if capcity will be sufficient 09/07 - still pending approvals with City council - expected circuit delivery by end of August 02/07 - Still pending with local city coucil for permits 25/06 - Vodafone tracker Final approval should be in 1 week. External fiber build is currently ongoing and now 18/06 - Expected delivery date externally is 1st week of August - late August for delivery into building 04/06 - Initial approval received from local conuncil and external fibres work started 28/05 - Last mile provider still pending permits from council to proceed with external fibre build works 27.04 Awaiting circuit delivery. 06/03 ETA for delivery of new router 2-3 months 09/12 Welington to confirm the decision by end of week on whether the a router will be re-used from the currently available at Unilever or a new one will be ordered 21/11 [Update from VOD] Order is placed on-hold. Commercial charges for AR telecom and NOS have been presented to Vodafone. 18/11 No further update on the delivery dates for the new router, To be confirmed with Welington. 17/11 Additional router to be ordered from a different provider? Welington to advise on the status/next steps. | On Hold | Circuit Order Accepted | Circuit Provider | Check dates | PT-SIA01-0001 | PORTUGAL_SANTA_IRIA_DE_AZOIA_JERONIMO_MARTINS_LDA |  |  |  |  | Fima Olá, Lda., Marinhas de D. Pedro | Santa Iria de Azoia | 2695-361 |  | Joaquim Camoes | Joaquim.camoes@unilever.com | +351213892229 | Dees Rampartab | Dees.Rampartab@unilever.com | 45MB45MB | 100 | 36.0911 | -18.7277 | 2019 | Nov | 0 | Not Applicable | 0 | 1 | No resilience | SC2 | [5 empty] | /30 |  |  | Subnet Mask - 255.255.255.240 | [5 empty] | Vodafone | [5 empty] | Adrian Lazar | Adrian Lazar | Adrian Lazar
CKT-I-01-RO-BUH01-4244-BT-1 | I023744BT1 | 1 | Yes un-uen-roubuc1-pio001( 145.55.227.7) - existing bw 200M; un-uen-roubuc1-rtr001( 145.55.227.5) - existing BW 30M | Medium | Europe | ROMANIA | Bucharest HO | 2019_620 | un-uen-roubuc1-rtr001 |  | Eloise Shepheard | WAN Circuit Migration | Circuit | BT | BT |  |  | 2019-09-02 | 2019-11-30 | Complete | 2019-09-09 | 2019-09-30 | Complete | 2019-11-18 | 2020-05-28 | Red | 2019-12-02 | 2020-09-25 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process 28/04 Circuit hasn't been ordered yet. 10/12 will be included in Wave 2 orders for delivery in Q1 2020. 22/11 Deepak confirmd the MPLS circuits havent been ordered yet 21/11 Migration date confirmed by local GeoIT. Time of migration - start12.00pm local time 21/11 Discussion around the migration plan for Romania is taking place today Migration date TBC | Yellow | Circuit Order Accepted | Unilever SNT |  | RO-BUH01-4244 | ROMANIA_BUCHAREST_HEAD_OFFICE |  |  |  |  | 42-44 Sos. Bucuresti-Ploiesti, 4th Floor | Bucharest | 13696 |  | Andrei Costache | Andrei.costache@unilever.com | 0040727531060 |  |  | 30M | 100 | 44.4389 | 26.0975 | 2019 | Nov | MPLS | 2017-07-28 | Commercial Benefit |  |  | SC2 | [5 empty] | /30 | [14 empty] | Adrian Lazar | Adrian Lazar | Adrian Lazar |  |  | Complex site type - requires redesign | Complete | NO | No |  | Yes
CKT-I-01-RO-PLT02-0001-BT-1 | I021404BT1 | 1 | Yes | Medium | Europe | ROMANIA | Ploiesti Factory | 2019_621 | un-uen-rouplo1-rtr001 |  | Eloise Shepheard | WAN Circuit Migration | Circuit | BT | BT |  |  | 2019-09-02 | 2019-11-30 | Complete | 2019-09-09 | 2019-09-30 | Complete | 2019-11-18 | 2020-05-21 | Red | 2019-12-02 | 2020-12-16 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process 10/12 will be included in Wave 2 orders for delivery in Q1 2020. 22/11 Deepak confirmed that the MPLS circuits havent been ordered yet 21/11 Migration date confirmed by GeoIT. Start of migration: 830AM local time (until 400PM locla time) 21/11 Discussion around the migration plan for Romania is taking place today Migration date TBC 12/11 this is factory working in 3 shifts and heavily depending on internet and can cope without internet for max 1-2 hrs during the working days. Aga to schedule a meeting with the local team to discuss requirements and agree on migration plan. The migration to take place on Fri or during the weekend. | Yellow | Circuit Order Accepted | Unilever SNT |  | RO-PLT02-0001 | ROMANIA_PLOESTI_FACTORY_REPUBLICII_291 |  |  |  |  | 291 Bd. Republicii | Ploiesti | 100072 |  | Irinel Matei | Irinel.matei@unilever.com | 0040727736342 |  |  | 30MB30MB30MB | 100 | 44.9412 | 26.0225 | 2019 | Nov | MPLS | 2009-03-31 | Commercial Benefit |  |  | SC2 | [5 empty] | /30 | [14 empty] | Adrian Lazar | Adrian Lazar | Adrian Lazar |  |  | Complex site type - requires redesign | Complete | NO | No |  | Yes
CKT-I-01-ES-BCN04-0001-VOD-1 | I019610VOD1 | 1 | Yes | High | Europe | SPAIN | BCN-Viladecans HO | 2019_644 | un-uen-espbar1-vpn002 |  | Eloise Shepheard | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQS-00002 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-05-19 | Complete | 2019-11-18 | 2020-07-15 | Complete | 15/07: Migration successful 08/07: Migration has been re-planned for 15th July starting at 12 local time. 26/06: Migration was unsuccessful due to speed issue. 05/06: Migration had to be postpone due to issue with the line 29/05 Migration planned for 05/06. 04/05 Due to covid-19 installation cancelled by local GeoIT until further notice. 05/12 This is on hold pending confirmation from Unilever 21/11 No further update on FOC 15-Nov: Still no estimate delivery date from VF. To reschedule in 1-2 weeks if there's still no response. 12-Nov: Local GeoIT confirmed the migration date 14 Dec. Raul Burgos and Jose will escort and perform testing. No special requirements re onsite visit 29-Oct: Deepak sent request to VF to expedite delivery and advise if paid expedite option is available. Priority raised to High. | Complete | Circuit Migrated | Circuit Provider |  | ES-BCN04-0001 | SPAIN_BARCELONA_VILADECANS_HEAD_OFFICE |  |  |  |  | Calle Tecnología 19 | Viladecans | 08840 |  | Raul.Burgos Jose-Manuel.Garrobo | Raul.Burgos@unilever.com,Jose-Manuel.Garrobo@unilever.com | +34 647872861 +34 690646682 | Dees Rampartab | Dees.Rampartab@unilever.com | 100MB | 100 | 41°18'52.1"N | 2°01'54.6"E | 2019 | Nov | MPLS | 2017-02-20 | Commercial Benefit |  |  | SC3 | NA | New : 12 to 18 15:00-21:00 | NA | NA |  | /29 | Head office for the Spain business. Circa 500 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. |  |  | 216.172.71.233 | 216.172.71.234 | [9 empty] | Arijon Alija | Adrian Lazar | Adrian Lazar |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress |  | No | No | No | No |  | Window Date agreed - End user Comms sent |  | New: 10:00 to 16:00 13:00-19:00 | New 12:00 to 18:00 15:00-21:00 | 71414 | CRQ000000677850 | Approved |  | CRQ000000676667 | Completed | Completed |  |  |  | Circuit Migrated |  |  |  |  | 2020-06-01
CKT-I-01-CH-HHM01-0030-CTL-1 | I012447CTL1 | 1 | Yes | Medium | Europe | SWITZERLAND | FS6 Steinhausen | 2019_650 | un-uen-cheste-rtr001 |  | Agnieszka Pajak | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006828806 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2019-10-28 | Complete | 2019-11-04 | 2019-11-19 | Complete | 19/11 Migration successfully completed with one task outstanding. LoopBack Issue identified, which enables CMS team to monitor the new circuit. This has been raised with BT and is being escalated | Complete | Circuit Migrated |  |  | CH-HHM01-0030 | SWITZERLAND_STEINHAUSEN |  |  |  |  | Hinterbergstrasse 30 CH-6312 Steinhausen Switzerland interbergstrasse 30 | Steinhausen | CH 6312 | Office | Raphael Rutar | Raphael.Rutar@unilver.com | +41 77 408 33 35 +41 41 749 91 18 | Peter Gretsch | Peter.Gretsch@unilever.com | 40MB | 40 | 47.1874 | 8.4786 | 2019 | Nov | MPLS | 2016-10-25 | Commercial Benefit |  |  | SC2 | None, IT available onsite, applications suggested for testing: BisonERP, Email, SharePoint, Abacus, Internet Access | 0630-1630 UTC | None, accces via Site Contact | NA | NA | /30 |  |  | WAN: 213.242.83.72/30 CTL: 213.242.83.73/30 UNI: 213.242.83.74/30 | 213.242.83.73/30 | 213.242.83.74/30 | [9 empty] | Damian Dabros | Damian Dabros | Damian Dabros | 2019-11-20 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO | No |  |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 0630 - 1630 | 0730 - 1730 | 15665 | CRQ000000617415 | Approved | 40065 | CRQ000000617790 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right | NA | NA | NA | 2019-10-01 | 2019-11-01
CKT-I-01-CH-SCH01-0005-CTL-1 | I013819CTL1 | 1 | Require to order additional /28 | Medium | Europe | SWITZERLAND | Schaffhausen | 2019_649 | un-uen-chesch1-rtr001 |  | Agnieszka Pajak | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006828810 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2019-11-29 | Complete | 2019-11-04 | 2019-12-20 | Complete | 02/12 Ping test has been completed successfully by CenturyLink / local GeoIT (Birgit) 22/11 Migration date confirmed by GeoIT. Test b/w provider and local contact agreed for Dec 2nd at 11:30 to 13:30 CET 20/11 Circuit delivered and ready to be activated. GeoIT to confirm the migraton date. | Complete | Circuit Migrated |  |  | CH-SCH01-0005 | SWITZERLAND_SCHAFFHAUSEN_LANDHAUS |  |  |  |  | Spitalstrasse 5 | Schaffhausen | 8200 |  | Birgit Schalow | Birgit. Schalow@Unilever.com | 41787698130 | Birgit Schalow | Birgit. Schalow@Unilever.com | 100M | 100 | 47.6971 | 8.6312 | 2019 | Nov | MPLS | 2017-06-27 | Commercial Benefit |  |  | SC2 | Safety and Security training required Risk assessment required | 1400 - 2000 UTC | Safety and Security training required Risk assessment required | NA | NA | /30 |  |  | WAN: 213.242.83.76/30 CTL: 213.242.83.77/30 UNI: 213.242.83.78/30 | 213.242.83.77/30 | 213.242.83.78/30 | [9 empty] | Damian Dabros | Damian Dabros | Damian Dabros | 2019-12-23 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO RJ45 on ISR4k | No | Yes |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 1400 - 2000 | 1500 - 2100 | 19262 | RCQ000000626566 | Approved | 40364 | CRQ000000624758 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right | NA | NA | NA |  | 2019-12-01
CKT-I-01-GB-CEG01-0002-GTT-1 | I019982GTT1 | 1 | Not found in NP, used old BW given. Not sure of IP address mask required Detailed discussion needed, Aga to set it up alongwith Adrian | Top | Europe | UNITED KINGDOM | Chester Gates Data Centre | 2018_278 | un-uen-isp-gbcgt1 | un-uen-isp-gbcgt1 | Eloise Shepheard | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01699279 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-12 | Complete | 2019-10-28 | 2020-02-29 | Complete | 2019-11-11 | 2020-09-08 | Red | 22/08: Migration unable to take place on 25th - GTT sent wrong engineer for final installation 21/08: Migration on track 15/07 - SSRAMS survey taking place today by TTB Engineer 10/07 - pending site survey and no supplier delivery date provided 02/07 - Gergana confirmed site survey will be required 01/07 - Gergana confirmed new address space issued for BRB / CGT / PSL 30/06: If it is possible to arrange for circuit delivery any day next week 6th to 10th July or the week of 20th to 24th July it is expected that it will be possible for Unilever to have someone on site to host the engineers. (from GTT tracker) 06/03 Data Centers are currently not in scope for Cisco WAN migration team. The next steps are discussed between Zoe/David C 20/01 Awaiting confirmation on the installation date 10/12: It turns out that the below update is an Openreach internal planning update which states that they have discovered ducting that is full. There are no further updates on this as the order is currently progressing through planning stages but Openreach will be discussing a resolution. 04/12: Results from the survey will be available by the end of the week. 28/11: New Site survey will be on 02/12/19. | Green | Circuit Delivered | Unilever SNT |  | GB-CEG01-0002 | UK_CHESTERGATES_DATA_CENTRE |  |  |  |  | Unit 2, Chester Gates | Chester (GB-CHS) | CH1 6LT |  | Kim Newton | Kim.Newton@unilever.com | +44 (0) 7557 986245 |  |  | 800 Mbit/s | 1000 | 53.2463 | -2.9312 | 2019 | Oct | Internet | 2019-08-31 | Commercial Benefit |  |  | SC1 | [5 empty] | /29 | Data centre, will need to review existing BGP configuration | Ground Floor, Chestergate CGT HR-2, Row 1, Cab Location HR2-05, Position 7. | 154.14.114.44/30 Network - 154.14.114.44 First usable - 154.14.114.45 Last usable - 154.14.114.46 Broadcast - 154.14.114.47 Subnet Mask - 255.255.255.252 154.14.114.56/29 Network - 154.14.114.56 First usable - 154.14.114.57 Last usable - 154.14.114.62 Broadcast - 154.14.114.63 Subnet Mask - 255.255.255.248 | 154.14.114.45 | 154.14.114.46 | 154.14.114.56/29 |  |  | Talk Talk | GTT London | AS 3257 |  |  |  | Arijon Alija | Arijon Alija | Arijon Alija |  |  | Complex site type - requires redesign | Complete |  |  | Yes |  |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression SSR approved |  |  | 22:00 to 02:00 | 23:00 to 03:00 | 114412 -1st visit, 114754 - 2nd visit |  |  |  | CRQ000000702576 | Completed | Completed
CKT-I-02-GB-CEG01-0002-VOD-1 | I029982VOD1 | 1 | Not found in BT document or NP Detailed discussion needed, Aga to set it up alongwith Adrian | Medium | Europe | UNITED KINGDOM | Chester Gates Data Centre | 2019_761 | un-uen-isp-gbcgt1 | un-uen-isp-gbcgt1 | Eloise Shepheard | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | 3C03789775 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-07-10 | Complete | 2019-11-18 | 2020-09-08 | Red | 25/08: Migration unsuccessful - issue with BGP - rescheduled for 8th September 21/08: Migration on track z 16/07 - Cisco can test but not essential 15/07 - Mohammad Hisham asked to confirmedtesting was carried out when the engineer was on site and included throughput 09/07 - Mohammed confirmed installation was completed successfullly today 02/07 - Vodafone ADVA device name confirmed as CH16AAD01 02/07 - Discussed with Kim - Jatin Sharma requested to raised CRQ000000682341 for 09/07 01/07 - email received from Vodafone claiming install to non-strategice room - I advised them to put on hold whilst clarified 01/07 - Gergana confirmed new address space issued for BRB / CGT / PSL 22/06 - email from Vodafone confirming they have requested Site Specific RAMS 21/06 - meeting invite sent for 23/06 to review CGT demarc location 19/08 - email sent to Deepak regards identfying new decmarc location 19/08 - email set to Hisham explaing what is needed from Vodafone and that I will setup a meeting next week if he is still not able to provide the required details 16/06 - Hisham, Mohammed emailed with RAMS and Covid-19 doc Vodafone will supply 16/06 - Meeting invite sent to Kim for Friday to discuss delivery requirements and that the circuit is set to terminate in non-strategic room which is not possible. 16/06 - Hisham, Mohammed advised that internal DC cabling responsibility of Unilever and highlighted an email from 21/05 where Kim has identified the install of this is in a non-stratgic part of the DC 16/06 - Kim Newton emailed to see if the details provided by Vodafone RAMS are sufficient 16/06 - Hisham, Mohammed, Vodafone Group confirmed 3 days notice needed to arrange site visit 16/06 - Hisham, Mohammed, Vodafone Group asked if internal cablng was complete on site to avoid wasted visit? 06/03 Data Centers are currently not in scope for Cisco WAN migrations team. The next steps are discussed between Zoe/David C. 10/12 Pending further confirmations on demark point from Unilever. 15-Nov: Circuit Delivery on-hold. No access to site demarc point. | Green | Circuit Delivered | Unilever SNT |  | GB-CEG01-0002 | UK_CHESTERGATES_DATA_CENTRE |  |  |  |  | Unit 2, Chester Gates | Chester (GB-CHS) | CH1 6LT |  | Kim Newton | Kim.Newton@unilever.com | +44 (0) 7557 986245 | Dees Rampartab | Dees.Rampartab@unilever.com |  | 1000 | 53.2463 | -2.9312 | 2019 | Oct | 0 | Not Applicable | 0 |  |  | SC1 | [5 empty] | /29 | Data centre, will need to review existing BGP configuration |  | You have been provided with a 1000Mb bearer, throttled to 1000Mb. The WAN range is 217.161.79.236/30 with the Vodafone IER IP being 217.161.79.237 and your CE IP being 217.161.79.238. The circuit has been presented as VLAN tag: 100 For DNS please use DNS Primary: 141.1.1.1 and DNS Secondary: 195.27.1.1 ===================================================================== Activation notes - Unmanaged Static ===================================================================== Bearer Size: 1000Mb Bandwidth: 1000Mb WAN Range: 217.161.79.236/30 Vodafone IP: 217.161.79.237 Customer IP: 217.161.79.238 CE VLAN ID: 100 Adva Port: Access Port 2 DNS Primary: 141.1.1.1 DNS Secondary: 195.27.1.1 | 217.161.79.237 | 217.161.79.238 | [9 empty] | Adrian Lazar | Adrian Lazar | Adrian Lazar |  |  | Complex site type - requires redesign | Complete |  |  | Yes |  |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 22:00 to 02:00 | 23:00 to 03:00 | 114412 -1st visit, 114754 - 2nd visit | CRQ000000702349 | Approved |  | CRQ000000703102 | Completed | Completed |  |  |  | Circuit - Failed Go Live | Issue with BGP - ISP looking into it
CKT-I-01-GB-PSU01-0001-GTT-1 | I011407GTT1 | 1 | Device does not have a WAN circuit. Need to check. Detailed discussion needed, Aga to set it up alongwith Adrian | Top | Europe | UNITED KINGDOM | Port Sunlight Office & Factories | 2019_765 | un-uen-gbrpsl1-rtr003 | un-uen-gbrpsl1-vpn002 | Eloise Shepheard | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01699315 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-12 | Complete | 2019-10-28 | 2020-02-29 | Complete | 2019-11-11 | 2020-08-04 | Complete | 04/08: Migration was successful 17/07 - Circuit confirmed deployed and PSL router relocated and accessible via the network - East Wing Computer Room - Cabinet 2 - Pending formal handover to Unilever in order to plan testing and then migration 08/07: Circuit delivery organised for 17th July. 02/07 - Carlo -> VM confrimed “Andrew Grice is the PSE attending tomorrow afternoon. He has Paul’s contact details and will be in touch directly.” 02/07 - Paul confirmed his availability on site - 7th,8th, 16th or 17th July - and still no contact from VM regards PSE vist on 03/07 - GTT emailed and requested to chase 01/07 - email sent to Darren Carr, Paul Hunt, Gergana, Carlo and Eloise about getting the work done on 7th or 17th July 30/06 - Meeting with Paul Hunt / GTT to discuss how we can progress - VM should be speaking with Paul Hunt this week. 08/07: Circuit delivery organised for 17th July. 02/07 - Carlo -> VM confrimed “Andrew Grice is the PSE attending tomorrow afternoon. He has Paul’s contact details and will be in touch directly.” 02/07 - Paul confirmed his availability on site - 7th,8th, 16th or 17th July - and still no contact from VM regards PSE vist on 03/07 - GTT emailed and requested to chase01/07: VM informed us that they can attend the site on 3rd of July. Paul's contacts were provided to them. (from gtt tracker) 04/05 Awaiting for Virgin Media to complete installation of the modem. An approval from the local GeoIT required for Virgin Media to come onsite- this is being discussed internally by Unilever. 04/03 Vendor informed GTT that they are approaching their 90 day limit for unresolved orders and will cancel the order on the 13th March if no agreement has been reached by then on allowing them to complete their installation. 21/02 Pending confirmation of site contact to arrange the Virgin Media SSRAMS survey so that every Unilever requirement is captured and we have no further problems arranging access for Virgin Media to complete their final installation. 10/01 ETA for SFP delivery 31 Jan 28/11: Virgin: "Your order is in Delivery with BT.Signed SSRAMS has been received." Openreach are still contacting the customer to book in the B end access. 27/11: Unilever confirmed that SSRAMS are required. Virgin are going to prepare them and send to Unilever for approval. Once approved, installation can be scheduled. | Complete | Circuit Migrated | Unilever SNT |  | GB-PSU01-0001 | UK_PORT_SUNLIGHT_LEVERHOUSE&FACTORY |  |  |  |  | Lever House, Wood Street, Port Sunlight, Wirral | Port Sunlight Office & Factories | CH62 4ZD |  | Ceri Samuel-Jones | Ceri.Samuel-Jones@unilever.com, Darren.Carr@unilever.com | +44 (0) 151 6414000 |  |  |  | 1000 | 53.3495 | -2.9956 | 2019 | Nov | 0 | Not Applicable | Strategic Design |  |  | SC1 | [5 empty] | /29 | European tecnology services site and four factories. Circa 1600 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a wo | Ground floor, East Wing Computer Room, Rack LH-EW0HR1-R02 | 154.14.114.128/30 Network - 154.14.114.128 First usable - 154.14.114.129 Last usable - 154.14.114.130 Broadcast - 154.14.114.131 Subnet Mask - 255.255.255.252 154.14.114.136/29 Network - 154.14.114.136 First usable - 154.14.114.137 Last usable - 154.14.114.142 Broadcast - 154.14.114.143 Subnet Mask - 255.255.255.248 | 154.14.114.129 | 154.14.114.130 | 154.14.114.136/29 |  |  | Virgin Media | GTT London | AS 3257 |  |  |  | Adrian Lazar | Adrian Lazar | Adrian Lazar |  |  | Complex site type - requires redesign | Complete |  | Yes | Yes |  | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 07:00am to 22:00:00 | 08:00 to 21:00 | 108769 | CRQ000000696469 | Approved |  | CRQ000000690518 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-GB-BHK01-0002-GTT-1 | I019987GTT1 | 1 | There are two WAN links associated with this router Both have 80 MB BW and /30 WAN subnet Detailed discussion needed, Aga to set it up alongwith Adrian | Top | Europe | UNITED KINGDOM | Bromborough Data Centre | 2018_276 | un-uen-isp-gbbmb1 | un-uen-isp-gbbmb1 | Eloise Shepheard | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01699262 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-12 | Complete | 2019-10-28 | 2020-05-21 | Complete | 2019-11-11 | 2020-08-20 | Complete | 21/08: Migration successful 17/07 - Testing arranged for 23/07 at 1pm 16/07 - Trying to arrange for 23rd July, at 13:00 local time - Gergana to come back once FE confirmed 15/07 - KN and MH mailed again 13/07 - KN and MH mailed to find out date for testing w/c 20/07 10/07 - Gigabit link so GTT need to provide engineer for testing 01/07 - Gergana confirmed new address space issued for BRB / CGT / PSL 17/06 - Circuit testing required 04/05 Installation should be completed 06/05 04/03: Installation will be on 11/03. That order will be cancelled by 20th March if that installation not happen. 26/02: Unilever to confirm that they'll complete the RFC also to confirm the engineers access for installation. 20/01 Site survey planned for Jan 21. Internal RFS form required 03/12: Order is committed by the Vendor: Customer Commited Date is 03/01/2019. Estimated : Jointing 12/12/2019, Estimated: Fit & Test 31/12/2019. | Complete | Circuit Migrated | Circuit Provider Unilever SNT |  | GB-BHK01-0002 | UK_BROMBOROUGH_DATACENTRE |  |  |  |  | Unit 2 Georgia Avenue, Wirral International Business Park | Bromborough | CH62 3RG |  | Kim Newton | Kim.Newton@unilever.com | +44 (0) 7557 986245 |  |  | 800Mbps | 1000 | 53.3383 | -2.9745 | 2019 | Oct | Internet | 2019-09-01 | Commercial Benefit |  |  | SC1 | [5 empty] | /29 | Data centre, will need to review existing BGP configuration | Ground Floor, Bromborough Unit 2, Comms Room 1, Row 1, Cab Location CR1-04 position 20. | 154.14.114.40/30 Network - 154.14.114.40 First usable - 154.14.114.41 Last usable - 154.14.114.42 Broadcast - 154.14.114.43 Subnet Mask - 255.255.255.252 154.14.114.48/29 Network - 154.14.114.48 First usable - 154.14.114.49 Last usable - 154.14.114.54 Broadcast - 154.14.114.55 Subnet Mask - 255.255.255.248 | 154.14.114.41 | 154.14.114.42 |  |  |  | SSE Telecoms | GTT London | AS 3257 |  |  |  | Adrian Lazar | Adrian Lazar | Adrian Lazar |  |  | Complex site type - requires redesign | [6 empty] | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 22:00 to 02:00 | 23:00 to 03:00 | 114752 | CRQ000000701846 / CRQ000000698012 | Approved |  | CRQ000000702264 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01
CKT-I-01-GB-LEH01-0001-GTT-1 | I013745GTT1 | 1 | Yes | Medium | Europe | UNITED KINGDOM | Leatherhead | 2019_686 | un-uen-gbrlea-pio001 | un-uen-gbrlea-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Agile wifi consolidation | GTT | GTT |  | DIA/01690268 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-12 | Complete | 2019-10-28 | 2020-01-08 | Complete | 2019-11-11 | 2020-05-14 | Complete | 20/05: Failover testing organised for today at 18:00pm UK time 14/05 Migration successful - scope was changed during migration due to wrong link being decommissioned the same day.Instead of MPLS we need to use PIO link. We have faced issue with Agile wifi during testing but this has been resolved. Fail over test is organised for w/c 18th May. 12/05 Migration didn't start due to testing being unable to be completed. There was no internet traffic and internet carrier needed to be involved. Troubleshooting session took 5/6 hours to resolve so we ran out of time for migration. Rescheduled for 14/5 04/05 Migration scheduled for 12 May 18/04 Approval received from Unilever to go ahead with the migration. Awaiting response from NTT on resource availability. This is a key dependency here - availability of NTT to support the migration - local GeoIT wont be physically onsite during the migration. Circuit will be re-tested before the migration window starts, as such a stand-by support from GTT is required, in case we run into any issues. 12/03 2 support tickets submitted with GTT. This has been escalated to GTT account team. Carrier and the provider checked the links and confirmed the speed is, as expected. There is another test session scheduled for Tuesday 17 March to ensure the links is operating as expected. 21/02 There is a fix for the 2nd issue observed during the migration. Cisco chasing GTT and Local GeoIT to get the latest status on issue 1. GTT awaiting response from local GeoIT - screenshots are required with the issue. 07/02 Migration unsuccessful. Two issues: 1) circuit speed unsatisfactory - 50M instead of 400M - an incident has been created during migration window, no GTT engineers available to join the bridge. 2) new configuration being blocked by the firewall. This needs to be troubleshoot internally by Cisco 16/01 Testing arranged between Cisco/Unilever for 27 January. We have pencilled in 31 Jan as the date for the migration, as per the local contact request. 10/01 Circuit testing to be arranged by GTT - engineer to support the lcoal team onsite - pending commercial discussion with Unilever 08/01 Circuit installation successful. Awaiting official handover from GTT. 20/12 Virgin Media will install their equipment in the New year. Visit to be scheduled. 16/12 No further update on the status of delivery, GTT is escalating this with Virgin 27/11 Local GeoIT confirmed that the installation is completed. GTT to confirm this information with OpenReach. | Complete | Circuit Migrated | Cisco |  | GB-LEH01-0001 | UK_LEATHERHEAD | 14/05/20 | Completed |  |  | Unilever House, Springfield Drive, Leatherhead | Leatherhead | KT22 7GR | Office | Josh Mackinnon | Josh.Mackinnon@unilever.com | +44 (0) 7342 063818 | Josh Mackinnon | Josh.Mackinnon@unilever.com | 70MB70MB | 400 | 51.2964 | -0.32942 | 2019 | Nov | MPLS | 2019-08-14 | Commercial Benefit |  |  | SC2 | Phil Brinklow is site Building Services manager. If the engineers have not been to site before, they will need to complete a health and safety induction, which takes about 15 mins (which Phil can sort when they arrive). I will need their van/car registration along with the engineers names so parking in the loading bay can be arranged. | 0900 - 1300 | Safety and Security training required | NA | NA | /29 | UK corporate centre. Circa 1200 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | The fibres will come in to the undercroft -1 level car park and then get blown up from there. The equipment will need to sit in the Main Equipment Room (MER) at site, which is on Ground floor West. | 154.14.0.80/28 Network - 154.14.0.80 First usable - 154.14.0.81 Last usable - 154.14.0.94 Broadcast - 154.14.0.95 Subnet Mask - 255.255.255.240 |  |  | 154.14.0.80/28 |  |  | Virgin Media | GTT London | AS 3257 |  |  |  | Arijon Alija | Arijon Alija | Arijon Alija | 2020-05-15 |  | Standard site type - Hybrid (MPLS + IEN) | Complete | NO | Yes | Yes | Yes | No |  | Window Date agreed - End user Comms not sent |  | 0800-1400 | 0900-1500 |  | CRQ000000666141 | Approved | 40668 | CRQ000000632180 | Completed | Completed | Tested-Pass |  | Josh Mackinnon | Circuit Migrated | Issue with circuit speed; IP loopback didn't come up |  |  |  | 2020-01-01
CKT-I-01-GB-LBA02-0001-PCCW-1 | I011346PCCW1 | 1 | As per network diagram there are vpn001 and pio001 at the site. Pio001 has 2 circuit (MPLS/PIO)connected to it. There is a ISR4231-(un-uen-gbrlee1-agi001) and 1841 (UNIL_GB_FWR_LED1) agile router at the site. UNIL_GB_FWR_LED1 has seperate internet link for agile. | High | Europe | UNITED KINGDOM | Leeds Factory | 2019_689 | un-uen-gbrlee-pio001 | un-uen-gbrlee-vpn002 | Eloise Shepheard | WAN Circuit Migration | Circuit | PCCW | PCCW |  | LON(PCG) GI006657 | 2019-08-19 | 2019-09-03 | Complete | 2019-08-26 | 2019-09-18 | Complete | 2019-11-04 | 2020-06-30 | Complete | 2019-11-18 | 2020-08-31 | Complete | 31/08: Migration successful - Agile need to be completed 20/08: Peter Gaw successful tested the link. He got speeds of 191 mb/s and upload was varied between 175 – 185mb/s. Peter Gaw to confirm start time for 31st August - 08:00am or 08:30am 17/07 - SSRAMS survey confirmed for Thursday 23/07 at 9am - Openreach Engineers: Peter Burrow 07483 337770 and Matt Allsop 07483 369002 - Peter Gaw to confirm date and time ok 14/07 - confirmed that circuit to go ahead with BT using the Seacroft Exchange and PCCW circuit using the Hunslet New TE Exchange 13/07 - GTT delivered using Openreach Seacroft Exchange - PCCW delivered using Openreach Hunslet New TE exchange - Peter Gaw emailed asking him to confirm we can now go ahead with PCCW circuit delivery 10/07 - PCCW confirmed it is not possible to guarantee truly diverse routes due to circuits being supplied thorugh differnt provers and BT OR as last mile not offering that service. Deepak is giong to check with GTT what their POP is and if different to PCCW then he believes it will be good enough to go even though it will mean there is probably a single line cross at point of entry to site | Complete | Circuit Migrated | Unilever Geo-IT |  | GB-LBA02-0001 | UK_LEEDS_SEACROFT_FACTORY |  |  |  |  | Unilever UK Ltd, Coal Road, Seacroft | Leeds | LS14 2AR | Factory | Peter Gaw | Peter.Gaw@unilever.com | +44 (0) 7801 135271 |  |  | 100MB45MB45MB | 200 |  |  | 2019 | Nov | MPLS | 2017-07-26 | Commercial Benefit | 1 | Congested link | SC1 | -restriction on access times, Access to be pre arrange through myself and subject to my availability My Normal hours are 08:30 – 16:45 Mon- Fri, but can adjust for early starts if necessary, (which they usually are for commissioning). - notice period for access, To be arrange through myself, lead time depending on work to be carried out, as intrusive works must be aligned with factory maintenance activities Non intrusive work such as surveys I can arrange without formal procedure but would require 48 hours notice so I can plan my time. Intrusive work requires engineering change process, I need a week to raise and get approval for this, All engineering work goes through our weekly engineering control meetings which occur on Thursday mornings and cover works to be carried out from the next Saturday through to the following Friday. - any requirements for engineer’s induction Site Safety Induction can take between 20 and 40 minutes, ideally they would be done in advance of any works to they do not detract from the planned work start time. Surveys may be carried out with a visitor induction as long as anyone on site is accompanied and there is no engineering work carried out. - requirements for Site-Specific Risk Assessment or Method Statements Risk assessments and method statements should be provided ahead of the weekly Engineering control meeting ads works cannot be carried out without this being submitted in advance. Where possible all RA/MS should be specific to the job. Smaller works can be carried out with an on-site Job evaluation at the discretion of the host. Factory Maintenance typically takes place on Monday mornings from 08:00 (alternating weeks have 3 hours or 6 hours for factory downtime). Maintenance is move the Tuesday mornings after a bank holiday, and start time shifted to 07:00 following a non-working Sunday. | Factory Maintenance typically takes place on Monday mornings from 08:00 (alternating weeks have 3 hours or 6 hours for factory downtime). Maintenance is move the Tuesday mornings after a bank holiday, and start time shifted to 07:00 following a non-working Sunday. | Site Safety Induction can take between 20 and 40 minutes, ideally they would be done in advance of any works to they do not detract from the planned work start time. Surveys may be carried out with a visitor induction as long as anyone on site is accompanied and there is no engineering work carried out. |  |  | /29 | European factory and research site. Circa 1000 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | Main Office block. Ground Floor. Main Computer Room. Cab 8 & 9. | PCCW: 209.9.81.49/29 Customer: 209.9.81.50/29 | 209.9.81.49 | 209.9.81.50 |  |  |  | Exponential-E / Openreach | [5 empty] | Arijon Alija | Arijon Alija | Arijon Alija |  |  | Standard site type - Hybrid (DMVPN + IEN) |  |  | No | Yes |  | No | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 07:00 to 17:00 | 08:00 to 18:00 | 119400 | CRQ000000704535 | Approved |  | CRQ000000702690 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-02-GB-LBA02-0001-GTT-1 | I021346GTT1 | 1 | There are 4 devices at site - PIO1, RTR001, RTR002, AGI001 as per network diagram. Need confirmation from Geo-IT on the two circuits to be migrated for Wave 1. | High | Europe | UNITED KINGDOM | Leeds Factory | 2019_690 | un-uen-gbrlee1-rtr002 | un-uen-gbrlee1-vpn002 | Eloise Shepheard | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01701025 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-12 | Complete | 2019-10-28 | 2019-12-12 | Complete | 2019-11-11 | 2020-06-28 | Complete | 28/06: Migration was successful today. 17/02 Migration unsuccessful. We have rolled back. Not enough time to conduct rootcause analysis on the bridge. Skype not working. Failover test to be performed as next step before we agree on next steps and re-schedule the migration. 23/01 Carrier visited onsite to complete installation and testing. Local GeoIT to confirm the results from the visit. 20/01 Onsite visit to complete installation on 20 Jan unsuccessful due to limited availability of the UL local contact. This has been rescheduled for 23 Jan. 16/01 Testing unsuccessful. Despite the fact the circuit has been handed over by the carrier, the installation hasnt been completed. There is a SFP missing which needs to be supplied by the carrier. GTT to contact the carrier and agree on the new installation date. A meeting has taken place with the locla team to discuss the migration approach. 3 Feb has been pencilled in as a migration date for Leeds Factory. 10/01 Due to local's contact unavailability, circuit testing rescheduled to 16 Jan 08/01 Circuit testing to be arranged for 10/01 06/01: SFP to be delivered 08/01/2020 12/12 Circuit Handover Certificate received 03/12: The Vendor confirmed that the fibre will be installed on 09/12/2019 all day. 06/11 Local GeoIT informed that there is a strict change control in the office in Leeds. 09/11 we cannot support this interface – Vendor states they can only provide fibre presentation. Request change of SFP on the router. Adrian to confirm the additional HW | Complete | Circuit Migrated | Unilever Geo-IT |  | GB-LBA02-0001 | UK_LEEDS_SEACROFT_FACTORY |  |  |  |  | Coal Road, Seacroft | Leeds | LS14 2AR | Factory | Peter Gaw | Peter.Gaw@unilever.com | +44 (0) 7801 135271 |  |  | 45MB | 200 |  |  | 2019 | Nov | Internet | 2017-07-26 | Commercial Benefit |  |  | SC1 | Leeds work 24/7 so the only time they could accommodate would be on a Monday morning from the close of production circa 07:00 GMT. They have alternative ‘long and short’ maintenance windows which last between 2 hours and up to 6. Pete Gaw would be the best person to confirm.Leeds is Amanda Lee's home town and she is happy to help us liaise with the local team. | 0700 - 1500 | Safety and Security Training Required Risk Assessment Required Field engineer to arrive 1 hour before the migration to complete those two tasks | NA | NA | /29 | European factory and research site. Circa 1000 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | Ground Floor, Main Office Block, Main Computer Room, Cab 8 & 9. | 154.14.117.100/30 Network - 154.14.117.100 First usable - 154.14.117.101 Last usable - 154.14.117.102 Broadcast - 154.14.117.103 Subnet Mask - 255.255.255.252 154.14.117.160/29 Network - 154.14.117.160 First usable - 154.14.117.161 Last usable - 154.14.117.166 Broadcast - 154.14.117.167 Subnet Mask - 255.255.255.248 | 154.14.117.101 | 154.14.117.102 | 154.14.117.160/29 |  |  | Talk Talk | GTT London | AS 3257 |  |  |  | Adrian Lazar | Adrian Lazar | Adrian Lazar | Astrit Kadriu |  | Complex site type - requires redesign | Complete | 1000Base-LX/LH with GLC-LH-SMD on ISR4k | Yes | No | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms not sent |  | 0700 - 1500 | 0700 - 1500 | 43075 (OLD) | CRQ000000685244 | Approved | 40667 | CRQ000000632292/CRQ000000683860 | Completed | Completed | Tested-Pass | No proper setup, test to be done in Jan 2020. Testing could not be completed as Copper Access port on the NTE was not enabled and no fibre cables were available to check connection with another port. GTT are to arrange for an engineer in new year who will be able to bring correct cables to site to complete the testing. Testing Passed | Peter Gaw | Circuit Migrated |  |  |  |  | 2020-01-01
CKT-I-01-GB-SRK01-0102-GTT-1 | I01689GTT1 | 1 | Yes | Medium | Europe | UNITED KINGDOM | R&D Colworth | 2019_677 | un-uen-gbrcol1-vpn001 | un-uen-gbrcol1-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01696502 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-11-18 | Complete | 2019-10-28 | 2019-11-18 | Complete | 2019-11-11 | 2020-02-24 | Complete | 20/02 Design for migration prepared for DMVPN migration. There was a discrepancy in Cisco trackers. MPLS migration was discussed with local GeoIT. Local GeoIT agreed to proceed with DMVPN migration, as planned. 09/01 Welington confirmed we can get GTT involved in testing (an engineer needs to be sent onsite). Abhnishek to reach out to GTT. 06/01 SFP to be delivered 08 Jan 09/11 Vendor states they can only provide fibre presentation. Request change of SFP on the router. Adrian to determine the additional HW | Complete | Circuit Migrated |  |  | GB-SRK01-0102 | UK_COLWORTH_RESEARCH_LABORATORY |  |  |  |  | Colworth Science Park, Sharnbrook, Bedfordshire | R&D Colworth | MK44 1LQ |  | Jacob Masih | Jacob.Masih@unilever.com | +44 (0) 7824 538699 |  |  | 200MB | 200 | 52.2299 | -0.55971 | 2019 | Nov | Internet | 2018-04-10 | Commercial Benefit |  |  | SC2 | NA | 1730 - 2330 UTC | NA | NA | NA | /29 | European research site. Circa 2000 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | Ground Floor, Main House – PABX Room, building number 01/01 | 154.14.0.128/28 Network - 154.14.0.128 First usable - 154.14.0.129 Last usable - 154.14.0.142 Broadcast - 154.14.0.143 Subnet Mask - 255.255.255.240 | 154.14.0.129 | 154.14.0.130 | 154.14.0.128/28 |  |  | TalkTalk | GTT Manchester | AS 3257 |  |  |  | Sedat Citaku | Sedat Citaku | Sedat Citaku | 2020-02-25 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 1730 - 2330 | 1730 - 2330 | 36629 | CRQ000000642839 | Approved | 40670 | CRQ000000632359 | Completed | Completed | Tested-Pass | Comment from Jacob Masih (Local Unilever) "Given that the hand-off is fibre I have no means to test the circuit." Proper setup not available for testing. Testing approach where the hand off is fibre and not copper is not clear. Will move ahead when approach is cleared. Testing Passed | Jacob Masih | Circuit Migrated - First Time right | NA | NA | NA |  | 2020-01-01
CKT-I-01-GB-PSU02-0001-GTT-1 | I011406GTT1 | 1 | Detailed discussion needed, Aga to set it up alongwith Adrian According to network diagram - hostname can be 1. un-uen-gbrrps-isp001(130.24.248.47) - Telnet with local user creds (very slow connection) Dialer interface, 8M BW, /30, ISR 4321 OR 2. un-uen-gbrrps1-rtr001(130.24.248.46) ISR4451-x, no clear WAN interface on the device, 1GB link but is ISR4K, should it be ASR1k ? | Top | Europe | UNITED KINGDOM | R&D Port Sunlight | 2019_766 | un-uen-gbrrps1-rtr001 | un-uen-gbrrps1-vpn001 | Eloise Shepheard | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01699344 | 2019-08-12 | 2019-08-12 | Complete | 2019-08-19 | 2019-08-12 | Complete | 2019-10-28 | 2020-02-27 | Complete | 2019-11-11 | 2020-08-04 | Complete | 05/08: Migration successful 29/06: Still pending modem delivery 25/06 - Carlo confirmed back to Deepak that between himself and Stuart Tritton they were able to establish that Virgin Media had enabled a copper port and this is what we were able to successfully test to. 24/06 - Gergana provided evidence over email of successful circuit testing 04/05 Dependency: delivery of the circuit in Port Sunlight offices. Next step: Cisco to arrange a meeting Cisco/local GeoIT to present the agreed strategy for the migration 06/03 Meeting to discuss strategy for Port Sunlight scheduled for 10 Mar. Darren and Mike not available this week. 28/02 Circuit start of service certificate provided to Cisco 17/01: The details preventing site survey was cleared with the customer. He is awaiting Openreach to call them and schedule site survey. 08/01: Openreach will contact LCON again to arrange appointment. 30/12: Awaiting VM to schedule site survey. 10/12 Order placed with the vendor by GTT | Complete | Circuit Migrated | Cisco |  | GB-PSU02-0001 | UK_PORT_SUNLIGHT_RESEARCH_LAB |  |  |  |  | Lever House, Wood Street, Port Sunlight, Wirral | R&D Port Sunlight | CH62 4XN |  | Ceri Samuel-Jones Darren Carr | Ceri.Samuel-Jones@unilever.com, Darren.Carr@unilever.com | +44 (0) 151 6414000 |  |  | Gig link | 1000 | 53.3383 | -2.9745 | 2019 | Nov | 0 | Not Applicable | Strategic Design |  |  | SC2 | We need both sites ready for migration. R&D and Factory | 09:00am to 15:00pm local time |  |  |  | /29 | European research site. Circa 2000 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | East Wing Computer Room, Rack LH-EW0HR1-R02 | 154.14.122.24/29 Network - 154.14.122.24 First usable - 154.14.122.25 Last usable - 154.14.122.30 Broadcast - 154.14.122.31 Subnet Mask - 255.255.255.248 154.14.122.48/30 Network - 154.14.122.48 First usable - 154.14.122.49 Last usable - 154.14.122.50 Broadcast - 154.14.122.51 Subnet Mask - 255.255.255.252 | 154.14.122.49 | 154.14.122.50 | 154.14.122.24/29 |  |  | Virgin Media | GTT London | AS 3257 |  |  |  | Adrian Lazar | Adrian Lazar | Adrian Lazar |  |  | Complex site type - requires redesign | Complete |  | Yes | Yes |  | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms not sent |  | 08:00 to 14:00pm | 09:00 to 15:00pm | 108769 | CRQ000000696469 | Approved | 41790 | CRQ000000654261/CRQ000000683253 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  |  | 2020-06-01
Out of Scope |  | 1 | Out of scope - No Device Access | Medium | Latin America | Argentina | Planta La Rioja | 2019_54 | un-ula-branat1-rtr001 |  | Juan Simon | WAN Circuit Migration | Circuit | TI Sparkle | TIS |  | #NO MATCH | 2019-08-19 | 2019-08-19 | Out of Scope | 2019-08-26 | #NO MATCH | Out of Scope | 2019-11-04 | #NO MATCH | Out of Scope | 2019-11-18 |  | Out of Scope | Out of Scope | Out of Scope | Circuit not ordered |  |  | AR-IRJ01-0001 | ARGENTINA_LA_RIOJA |  |  |  |  | Ruta Nacional 38 km 429, Parque Industrial La Rio | La Rioja | 5300 |  | Ramiro Fernandez | ramiro.fernandez@unilever.com | 5493804718314 | Ricardo Caldes | Ricardo.caldes@unilever.com | 2Mbps | 20 | -29.2918 | -66.7557 | 2019 | Nov | MPLS | 2019-11-15 | Commercial Benefit | 2 | 0 | SC2 | [5 empty] | /30 |  | #NO MATCH | #NO MATCH |  |  |  | #NO MATCH | #NO MATCH | #NO MATCH | [9 empty] | #NO MATCH
Out of Scope |  | 1 | Out of scope - No Device Access | Medium | Latin America | Argentina | Planta La Rioja | 2019_54 | un-ula-branat1-rtr001 |  | Juan Simon | WAN Circuit Migration | Circuit | TI Sparkle | TIS |  | #NO MATCH | 2019-08-19 | 2019-08-19 | Out of Scope | 2019-08-26 | #NO MATCH | Out of Scope | 2019-11-04 | #NO MATCH | Out of Scope | 2019-11-18 |  | Out of Scope | Out of Scope | Out of Scope | Circuit not ordered |  |  | AR-IRJ01-0001 | ARGENTINA_LA_RIOJA |  |  |  |  | Ruta Nacional 38 km 429, Parque Industrial La Rio | La Rioja | 5300 |  | Ramiro Fernandez | ramiro.fernandez@unilever.com | 5493804718314 | Ricardo Caldes | Ricardo.caldes@unilever.com | 2Mbps | 20 | -29.2918 | -66.7557 | 2019 | Nov | Internet | 2019-08-01 | Commercial Benefit | 2 | 0 | SC2 | [5 empty] | /30 |  | #NO MATCH | #NO MATCH |  |  |  | #NO MATCH | #NO MATCH | #NO MATCH | [9 empty] | #NO MATCH
CKT-I-01-5098-TIS-1 |  | 1 | BW already 230Mb on live configuration | High | Latin America | Argentina | Bouchard - Argentina Head Office |  | un-ula-argmar1-vpn001 | un-ula-argmar1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | TI Sparkle | TIS |  |  | 2020-02-28 | 2020-02-28 | Green | 2020-03-06 | 2020-03-09 | Red | 2020-05-15 | 2020-08-31 | Red | 2020-05-29 | 2020-10-30 | Red | 27-Jul: Site also called Martinez and Munro. 29-Apr: Pending circuit order to provider. 23-Mar; Renamed the circuit and site name | Yellow | Circuit not ordered | Unilever SNT |  | AR-BUE04-0001 | ARGENTINA_BUENOS_AIRES_HEAD_OFFICE |  |  |  |  | Descartes 4020, Parque Industrial Tortuguitas | Malvinas Argentinas | 1667 |  | Hernan Gonzalez | hernan.gonzalez@unilever.com | 5491136175768 | Ricardo Caldes | Ricardo.caldes@unilever.com | 230 | 230 | -34.4685 | -58.7493 | 2019 | Oct | MPLS | 2019-10-01 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /29 | Head office for the Argentina business. Circa 1400 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | [13 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress |  | Yes |  | No |  | Assessment Complete
CKT-I-01-AR-MDZ01-1015-GTT-1 | I011848GTT1 | 1 |  | Medium | Latin America | Argentina | Plante Mendoza | 2019_9 | un-ula-argmen1-drt001 | un-ula-argmen1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01699929 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-22 | Complete | 2019-10-28 | 2019-12-27 | Complete | 2019-11-11 | 2020-08-07 | Complete | 7-Aug: Migration successful 24-Jul: Migration approved for August 7th 9AM. 8-Jul: Circuit tested successfully. 26-Jun: Circuit installation now moved to correct location. Pending circuit testing, and then migration. 28-May: Site survey completed. Pending GTT to complete the move of the circuit. 29-Apr: Pending GTT to provide documents to acces plant and move circuit installation to the correct room and rack. Mar-19:No update. GTT has already escalated to circuit vendor. Jan-31: Circuit still pending to be moved to correct location. Jan-9: Geo IT Manager informed us that the circuit was installed in the middle of the plant and not in the computer room, and that the installation has to be moved to the computer room. Will need to discuss with Welington on best approach. | Complete | Circuit Migrated | Unilever Geo-IT |  | AR-MDZ01-1015 | ARGENTINA_Mendoza |  |  |  |  | Godoy Cruz 10155, Dpto. Guaymallén | Mendoza | 5525 |  | Jorge Bartolome | jorge.bartolome@unilever.com | 5492634272472 | Ricardo Caldes | Ricardo.caldes@unilever.com | 4MB | 30 | -37.1615 | -56.8998 | 2019 | Nov | MPLS | 2019-06-01 | Commercial Benefit | 2 | 0 | SC2 |  | 9AM |  |  |  | /30 |  | Low-level, Godoy Cruz KM 11 CP 5525 Guaymallén, Mendoza, Computer Centre | WAN: Network: 67.73.141.240/30 Default Gateway: 67.73.141.241 (PE CTL) Host: 67.73.141.242 LAN: Network - 201.234.156.88/29 First usable - 201.234.156.89 Last usable - 201.234.156.94 Broadcast - 201.234.156.95 Subnet Mask - 255.255.255.248 | 67.73.141.241 | 67.73.141.242 | 201.234.156.88/29 |  |  | Neutrona Networks | Local ISP | AS 3257 |  |  |  | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Standard site type - Hybrid (MPLS + IEN) | In Progress | NO | Yes |  | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) |  |  | 12hrs UTC | 9AM | 108808 | CRQ000000697062 | Approved |  | CRQ000000696347 | Completed | Completed | Tested -Pass-First Time | 8-Jul: Circuit tested successfully. |  | Circuit Migrated - First Time right
CKT-I-01-BO-SRZ04-0001-PCCW-1 | I0120357PCCW1 | 1 | Device is accessible now.No access to device on CMS for un-ula-bolpai1-pio001 and un-ula-bolpai1-drt001 . Telnet and SSH refused. No access via connected interface. FRom BT configs given, can confirm 10M and /30 for PIO001 and 6M and /30 for DRT001. No access to either device. Need confirmation from on-site tech. | High | Latin America | Bolivia | Centro de Distribución Paititi | 2019_37 | un-ula-bolpai1-dtr001 | un-ula-bolpai1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | PCCW | PCCW |  | CBM(IFX) GI006265 | 2019-08-19 | 2019-09-03 | Complete | 2019-08-26 | 2019-10-17 | Complete | 2019-11-04 | 2020-01-10 | Complete | 2019-11-18 | 2020-06-19 | Complete | 19-Jun: Migration successfully completed. WiFi netwwork issue after migration (apparently not related to the migration); will follow up on Monday. 12-Jun: Circuit to be migrated on June 19th. 11-Jun: Pending new migration date. 4-Jun: Migration postponed since FE cancelled due to having COVID-19 symptoms. 16-May: Migration confirmed for June 5th. 22-May: Migration proposed for June 4th or 5th. NTT FE available on any of those dates. Pending GeoIT to confirm date. 18-May: Migration failed; rolled back. No Internet connection available after migration configuration on new migrated circuit. No apparent error found. TAC ticket to be raised; possibly a bug or a physical interface issue. 13-May: Migration pushed to May 18th at 8:30AM. 11-May: Migration approved for May 15th at 13hrs. 8-May: Still pending NTT's availability. Another tech will go to the site on May 15th for another change; we might be able to assign same tech to support the migration; Ricardo will confirm. 29-Apr: Pending NTT to have tech availability for the migration during the pandemic. 16-Apr: Migration cancelled due to not having a field engineer available to go to the site for the migration. 7-Apr: Migration approved on April 17th. 19-Mar: Circuit testing successful. Pending approved migration date. 31-Jan: Pending routers to be onboarded to CMS. 24-Jan: Routers were not transitioned to CMS by mistake. We will be informed once it is under CMS management to gain access to them. 13-Jan: No access to the device. 15-Nov: PCCW informed us that due to the current political situation (now at a ‘critical’ level), there is significant unrest in the country. As such all activities are currently on hold . | Complete | Circuit Migrated |  |  | BO-SRZ04-0001 | BOLIVIA_PAITITI_CD |  |  |  |  | Complejo Industrial del Norte - Carretera Norte Km. 23 | Santa Cruz (Bo-S) | 000 |  | Luis Rocha/Ricardo Caldes | Luis.rocha@unilever.com Ricardo.caldes@unilever.com | 59175495715 | Ricardo Caldes | Ricardo.caldes@unilever.com | 6M | 10 | -17.5724 | -63.1675 | 2019 | Nov | MPLS | 2020-01-20 | Commercial Benefit | 2 | 0 | SC2 | [5 empty] | /30 |  |  | Service Network IP: 177.222.40.81/29 | 177.222.40.81 | 177.222.40.82 | 177.222.40.83 - 177.222.40.86 |  |  | Neutrona Networks | [5 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Hybrid (MPLS + IEN) | In Progress | NO | Yes | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 13:00hrs UTC | 9AM | 75292 (new) 55938 (old) | CRQ000000679553 (new) CRQ000000661862 (old) | Approved | 42106 | CRQ000000659836 | Completed | Completed | Tested -Pass-First Time | March 3rd |  | Circuit Migrated | No Internet connection available after migration configuration on new migrated circuit. No apparent error found. |  |  |  | 2020-06-01
CKT-I-01-BO-CBB01-0001-PCCW-1 | I011859PCCW1 | 1 | Device upgrade needed ? ula-bocbbr3-agile (192.223.122.12)- CISCO1941/K9 , 8MB, /29 on WAN but can order /30 - only agile ula-bocbbr1-mpls (192.223.122.32) - CISCO2911/K9 , Frame relay on Se interface - unable to find ip address, BW 20M Separate Agile router on site. Should this be collapsed into secondary of site ? | High | Latin America | Bolivia | Head Office Cochabamba | 2019_34 | ula-bocbbr1-mpls | ula-bocbbr1-pccw-vpn001 | Juan Simon | WAN Circuit Migration | Circuit + Router | PCCW | PCCW |  | CBM(IFX) GI006262 | 2019-08-19 | 2019-09-03 | Complete | 2019-08-26 | 2019-10-17 | Complete | 2019-11-04 | 2020-01-10 | Complete | 2019-11-18 | 2020-06-29 | Complete | 29-Jun: Migration successfully completed: 25-Jun: Migration scheduled on June 29th at 9AM local time. 12-Jun: GeoIT to choose and approve migration date. 9-Jun: Migration cancelled due to FE not having insurance. 22-May: Migration proposed for June 9th. Pending confirmation from GeoIT. NTT FE available on this date. 8-May: Still pending NTT's availability. Ricardo will check if he can get a tech to go instead. 29-Apr: Pending NTT to have tech availability for the migration during the pandemic. 16-Apr: Migration cancelled due to not having a field engineer available to go to the site for the migration. 7-Apr: Migration approved on April 19th. 19-Mar: Circuit testing successful. Pending approved migration date. Jan-31: GeoIT looking for migration date. Jan-24: Circuit already delivered. Pending testing and migration date. 15-Nov: PCCW informed us that due to the current political situation (now at a ‘critical’ level), there is significant unrest in the country. As such all activities are currently on hold . | Complete | Circuit Migrated | Cisco |  | BO-CBB01-0001 | BOLIVIA_COCHABAMBA |  |  |  |  | Av. Blanco Galindo Km. 10.4, S/N Zona Irquicollo | Cochabamba | 508 |  | Luis Rocha/Ricardo Caldes | Luis.rocha@unilever.com Ricardo.caldes@unilever.com | 59175495715 | Ricardo Caldes | Ricardo.caldes@unilever.com | 20MB | 60 | -17.3862 | -66.1601 | 2019 | Nov | MPLS | 2020-01-14 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  |  | Service Network IP: 190.104.31.233/29 • DNS: o 200.73.96.146 Primary o 190.104.12.42 Secondary | 190.104.31.233 | 190.104.31.234 | 190.104.31.232/29 |  |  | Neutrona Networks | [5 empty] | Emir Jukovic | Emir Jukovic | Emir Jukovic |  |  | Complex site type - requires redesign | Complete | NO | Yes | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  |  | 8AM local | 56996 | CRQ000000661269 | Approved | 41077 | CRQ000000692831/CRQ000000640033/CRQ000000687333 | Completed | Completed | Tested -Pass-First Time | March 3rd |  | Circuit Migrated - First Time right |  |  |  |  | 2020-06-01
CKT-I-01-BR-AGU01-0001-BT-1 | I0110692BT1 | 1 | Yes | High | Latin America | Brazil | Aguai | 2019_60 | un-ula-braagu1-rtr001 | un-ula-braagu1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-22 | 2020-05-20 | Red | 2020-07-31 | 2020-07-20 | Green | 2020-08-14 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | BR-AGU01-0001 | BRAZIL_SAOPAULO_AGUAI |  |  |  |  | Estrada Aguaí - Pirassunu S/N, | Aguai | 13860-000 |  | Vagner Barcaro | Vagner.Barcaro@unilever.com | 55 19 9 8320 5922 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 1024kbps | 40 |  |  | 2019 | Oct | MPLS | 2018-07-31 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 | [14 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo |  |  |  | Complete
CKT-I-01-BR-RIO07-0001-CTL-1 | I0120130CTL1 | 1 | Yes | Medium | Latin America | Brazil | BARRA DA TIJUCA | 2019_59 | un-ula-brario3-rtr001 | un-ula-brario3-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006845615 / CID 500118214 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-01-24 | Complete | 2019-11-04 | 2020-04-09 | Complete | 9-Apr: Migration completed successfully. 1-Apr: GeoIT asked to migrate on April 9th at 9AM. 13-Mar: Migratio cancelled per Unilever due to the coronavirus situation. 9-Mar: GeoIT approved migration date of March 18th. 2-Mar: Migration still expected during Sprint 2. Pending confirmation from GeoIT and the site. 31-Jan: GeoIT looking for migration date. 24-Jan: Circuit already delivered. Pending testing and migration date. | Complete | Circuit Migrated |  |  | BR-RIO07-0001 | BRAZIL_RIODEJANEIRO_BARRADATIJUCA |  |  |  |  | Centro Empresarial Barra Shopping – Av das Americas, 4200, bloco 9, ala B, sala 112 a 116 | Rio de Janeiro | 22640-102 | Corporate Office | Soraya Aranha | Soraya.Aranha@unilever.com | +55 (21) 2480-2307 R.201 +55 (21) 9 9268-2469 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 2048Kbps | 10 | -22.9995 | -43.353 | 2019 | Oct | MPLS | 2016-06-29 | Commercial Benefit | 3 | 0 | SC2 |  | Business hours | RG (Registro Geral). Email sent to Tom with details. | N |  | /30 |  |  | WAN: 8.243.153.196/30 CTL: 8.243.153.197/30 UNI: 8.243.153.198/30 | 8.243.153.197/30 | 8.243.153.198/30 | [9 empty] | Sandor Jardon Vera | Sandor Jardon Vera | Sandor Jardon Vera |  |  | Standard site type - Hybrid (MPLS + IEN) | Complete | NO | Yes |  | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 11AM | 8AM | 54350 (new) 47215 (old) | CRQ000000658836 (new) CRQ000000651439 (old) | Approved | 41073 | CRQ000000639496 | Completed | Completed | Tested -Pass-First Time | Feb 11th, 2020 |  | Circuit Migrated - First Time right |  |  |  |  | 2020-02-01
CKT-I-01-BR-BSB02-0001-CTL-1 | I0120071CTL1 | 1 |  | High | Latin America | Brazil | BRASILIA_RV | 2019_42 | un-ula-brabra3-pio001 | un-ula-brabra3-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006845604 / CID500118208 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-02-12 | Complete | 2019-11-04 | 2020-03-06 | Complete | 27-Feb: GeoIT asked to migrate on March 6th at 8AM local time. 31-Jan: GeoIT looking for migration date. 24-Jan: Circuit already delivered. Pending testing and migration date. | Complete | Circuit Migrated |  |  | BR-BSB02-0001 | BRAZIL_BRASILIA_RV |  |  |  |  | R SIG QUADRA 4 - LOTE 75 BLOCO | Brasilia | 70.610-440 |  | Carolina Aranha | : Carolina.Aranha@unilever.com | +55 (62) 9920-9455 / +55 (61) 3441 4606 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 9M | 20 |  |  | 2019 | Nov | MPLS | 2019-08-31 | Commercial Benefit | 3 | 0 | SC2 |  |  | Yes. Email sent to Tom with details. |  |  | /30 |  |  | WAN: 200.186.241.72/30 CTL: 200.186.241.73/30 UNI: 200.186.241.74/30 | 200.186.241.73 | 200.186.241.74 | 200.186.241.72/29 | [8 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Complex site type - requires redesign | Complete | NO | Yes |  | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 11AM | 8AM | 45057 | CRQ000000648345 | Approved | 41164 | CRQ000000640195 | Completed | Completed | Tested -Pass-First Time | Feb 14h, 2020 |  | Circuit Migrated - First Time right |  |  |  |  | 2020-02-01
CKT-I-01-BR-MII01-0294-ORA-1 | I011915ORA1 | 1 | Yes | High | Latin America | Brazil | BRAZIL_MARILIA | 2019_53 | un-ula-bramar1-pio001 | un-ula-bramar1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | Orange | Ora |  | LO0048WL4C | 2019-08-05 | 2019-09-13 | Complete | 2019-08-12 | 2019-10-16 | Complete | 2019-10-21 | 2020-01-17 | Complete | 2019-11-04 | 2020-04-13 | Complete | 13-Apr: Migration successful 30-Mar: Migration approved on April 13th at 9AM local. 19-Mar: Migrations in Brazil on hold until further notice. 11-Mar: Second circuit testing successful. Pending approved migration date. 21-Feb: Circuit testing failed. Provider looking into issue. 31-Jan: GeoIT looking for migration date. 24-Jan: Circuit already delivered. Pending testing and migration date. 20-Dec: Expedited delivery requested with the provider | Complete | Circuit Migrated |  |  | BR-MII01-0294 | BRAZIL_MARILIA |  |  |  |  | ROD COMANDANTE JOAO RIBEIRO DE BARROS, nº 294, KM 443 + 20 METROS, PARQUE DAS INDUSTRIAS | Marilia | 17.519-780 | Distribution Center | Flavio Fedochenko | FLAVIO.FEDOCHENKO@unilever.com | +55 (14) 3417-6955 +55 (14) 99874-9101 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 2048kbps | 10 | -22204121 | -49949505 | 2019 | Oct | MPLS | 2019-03-31 | Commercial Benefit | 3 | 0 | SC2 |  | Business hours | RG (Registro Geral) | N |  | /30 |  |  | Subnet: 191.241.23.56/30 DefGW: 191.241.23.57 Host IP: 191.241.23.58 Mask: 255.255.255.252 DNS1: 191.5.164.2 DNS2: 191.5.164.3 | 191.241.23.57/30 | 191.241.23.58/30 |  |  |  | IG Networks | [5 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos |  |  |  | Complete | NO | Yes |  | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 12PM | 9AM | 54288 | CRQ000000658675 | Approved | 41163 | CRQ000000640523 | Completed | Completed | Tested-Pass | Test preformed on Feb 5 and 6, unsuccessfully; ports are on but we can not ping the gateway. Already contact Orange support. Rescheduled by March 5th. Failed. March 10th, last mile provider NOC contacted and issue resolved, there was restrictions on the configuration, MAC address info was required to allow the conection |  | Circuit Migrated - First Time right |  |  |  |  | 2020-02-01
CKT-I-01-BR-PPY02-0001-ORA-1 | I0110669ORA1 | 1 | Yes | Medium | Latin America | Brazil | BRAZIL_POUSOALEGRE_DC | 2019_55 | un-ula-brapou2-rtr001 | un-ula-brapou2-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | Orange | Ora |  | LO00480S53 | 2019-08-05 | 2019-09-13 | Complete | 2019-08-12 | 2020-02-17 | Complete | 2019-10-21 | 2020-05-25 | Complete | 2019-11-04 | 2020-09-30 | Red | Aug-6: Migration date to be approved on future date. Jul-31: Migration approved for August 17th at 9AM, pending results of circuit stress test. Jun-26: Pending circuit provider to confirm circuit issues are fixed before attempting a new migration. Jun-19: Migrated circuit with issues. It was decided that a rollback was needed, so circuit was rolled back to MPLS today. Jun-15: Migration successful. Jun-12: Internet router still with issues. If not resolved by Sunday June 14th, migration will be cancelled. Jun-5: Internet router at the site with issues and not reachable (tunnel is not coming up). Jun-4: Successful circuit testing. Migration approved for June 15th at 9AM local time. May-28: Circuit delivered. Pending circuit testing. Apr-30: Pending provider to deliver the circuit. Mar-19: No update. Migrations in Brazil on hold until further notice. Jan-31: Pending confirmation on FOC date. 20/12 Carrier has declined the order as site not served. 27/11 Unilever to chose the carrier | Pink | Circuit Delivered | Circuit Provider |  | BR-PPY02-0001 | BRAZIL_POUSOALEGRE_DC |  |  |  |  | RODOVIA BR 381 FERNÃO DIAS, S/N, KM 864 - PARTE A, BAIRRO ALGODÃO | Pouso Alegre | 37.550-000 | Distribution Center | Gilson Lima | Gilson.lima@unilever.com | 55 35 9 9851 9400 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 6000Kbps | 40 |  |  | 2019 | Nov | MPLS | 2019-10-31 | Commercial Benefit | 2 | 0 | SC2 |  | Business hours | RG e CPF ou CNH; Ficha de EPI´s; CPTS (parte da foto, qualificação civil e registro; Ficha de Registro; ASO – Atestado de Saúde Ocupacional; Certificado de Treinamento específico quando aplicável (Soldador, NR-10, NR-33, NR-35, etc). Obs. Para realizar trabalhos em altura / espaço confinado, além do certificado é necessário que no ASO esteja descrito que o colaborador está apto a exercer tais atividades. Todos os produtos químicos (limpeza, detergentes, tintas, etc), que forem ser utilizados no site devem obrigatoriamente estar acompanhados das FISPQ’s (Ficha de informação de Segurança de Produto Químico |  |  | /30 |  |  | Network: 138.185.22.24/30 IP: 138.185.22.26 Mask: 255.255.255.252 GW: 138.185.22.25 DNS: 138.185.23.254 | 138.185.22.25 | 138.185.22.26 |  |  |  | FulNet | [5 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Standard site type - Hybrid (MPLS + IEN) | Complete | [5 empty] | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms not sent |  | 12PM UTC | 9AM local | 78998 |  |  |  | CRQ000000679564 | Completed | Completed | Tested -Pass-First Time | 6/14/2020 |  |  | Rolled back 2 days after migration due to issues with the circuit. |  |  | 2020-05-01
CKT-I-01-BR-CWB01-0143-CTL-1 | I011884CTL1 | 1 | Yes | Medium | Latin America | Brazil | CURITIBA_HPC | 2019_46 | un-ula-bracur1-rtr001 | un-ula-bracur1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006845612 / CID500118212 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-03-15 | Complete | 2019-11-04 | 2020-04-24 | Complete | 24-Apr: Circuit successfully migrated. 13-Apr: Migration rescheduled for April 24th. 9-Apr: Migration postponed to a later date due to Covid-19 (possibly April 22-23). 3-April: GeoIT asked to migrate on April 16th. 19-Mar: Migrations in Brazil on hold until further notice. Jan-31: GeoIT looking for migration date. Jan-24: Pending confirmation on circuit delivery to schedule testing and migration date. | Complete | Circuit Migrated |  |  | BR-CWB01-0143 | BRAZIL_CURITIBA_HPC |  |  |  |  | Rua Comendador Araujo,143 -Ed. Center Everest - 16 and. - Conj. 161 e 162 | Curitiba | 80420-900 |  | Leda or Kamila | Leda.Osten@unilever.com Kamila.Moraes@unilever.com | +55 41 98843-5194 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 4M | 10 | -25.4347 | -49.2776 | 2019 | Oct | MPLS | 2018-08-31 | Commercial Benefit | 3 | 0 | SC2 | [5 empty] | /30 |  |  | WAN: 200.186.248.104/30 CTL: 200.186.248.105/30 UNI: 200.186.248.106/30 | 200.186.248.105/30 | 200.186.248.106/30 | [9 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Hybrid (MPLS + IEN) | In Progress | NO | Yes |  | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  |  |  | 55886 | CRQ000000661844 | Approved | 42111 | CRQ000000659864 | Completed | Completed | Tested -Pass-First Time | April 3rd |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01
Out of Scope |  | 1 | Out of scope - No Device Access | High | Latin America | Brazil | GOIANIA | 2019_54 | un-ula-branat1-rtr001 |  | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | #NO MATCH | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | #NO MATCH | Complete | 2019-10-21 | #NO MATCH | Out of Scope | 2019-11-04 |  | Out of Scope | Out of Scope | Out of Scope | Circuit Order Accepted |  |  | BR-GIA01-0002 | BRAZIL_GOIANIA |  |  |  |  | Rua Iza Costa- No 01, Chácaras Retiro | Goiania | 74.665-320 |  | Alexandra Nagy | Alexandra.Nagy@unilever.com | 55 62 9 81267997 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 2Mbps | 40 | -16689515 | -49285675 | 2019 | Nov | MPLS | 2019-03-31 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  | #NO MATCH | #NO MATCH |  |  |  | #NO MATCH | #NO MATCH | #NO MATCH | [9 empty] | #NO MATCH
CKT-I-01-BR-IGA01-0001-CTL-1 | I011899CTL1 | 1 | Require /29+ /30 | High | Latin America | Brazil | IGARASSU | 2019_49 | un-ula-braiga1-rtr001 | un-ula-braiga1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | Service ID: 81-1XG4VS5 Circuit ID: 500118218 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-06-15 | Red | 2019-11-04 | 2020-09-17 | Red | 8-Sep: Migration rolled back. Could not get circuit connectivity in router; only in laptop. Aug-27: Migration tentatively scheduled on September 7th. Apr-30: Pending provider to deliver the circuit. 19-Mar: Migrations in Brazil on hold until further notice. Jan-31: Pending confirmation on FOC date. 20-Dec: Requested CTL to change the order and provide a /29 with the circuit. | Pink | Circuit Order Accepted | Circuit Provider |  | BR-IGA01-0001 | BRAZIL_IGARASSU |  |  |  |  | ROD BR 101 NORTE, S/N, KM 43,6, CENTRO | Igarassu | 53.610-000 |  | Paulo Dionizio | Paulo.Dionizio@unilever.com | 55 81 9 9149 0160 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 40MB | 40 | -783354 | -34918985 | 2019 | Oct | MPLS | 2018-09-30 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  |  | LAN: 8.243.159.56/29 WAN: 8.243.159.52/30 IP CTL: 8.243.159.53/30 IP Unilever: 8.243.159.54/30 | 8.243.159.53/30 | 8.243.159.54/30 | [9 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  |  | Yes |  |  | Assessment Complete Received tunnel IP or LAN IP (if required) |  |  |  |  | CHG000000000042350 (New) CHG000000000042021 (Old) | CRQ000000708275 | Approved |  | CRQ000000708503 | Completed | Completed |  |  |  | Circuit - Failed Go Live | Circuit was not recognized in router but was responsive in laptop. Suspicion of MAC filtering. CTL to investigate.
CKT-I-01-BR-IDU01-0001-CTL-1 | I011900CTL1 | 1 | Yes | High | Latin America | Brazil | INDAIATUBA | 2019_50 | un-ula-braind1-rtr001 | un-ula-braind1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006845664 / CID500118220 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-06-15 | Complete | 2019-11-04 | 2020-08-20 | Complete | 24-Aug: Migration successful. Pending failover tests. 11-Aug: Migration pushed again, now to August 20th, due to a Go-Live happening on the 16th. 5-Aug: Migration pushed to August 13th (NTT engineer did not pass access requirement exam. 28-Jul: Migration approved for August 6th. 24-Jul: Circuit test successful. Migration tentatively scheduled on August 6th. Apr-30: Pending provider to deliver the circuit. 19-Mar: Migrations in Brazil on hold until further notice. Jan-31: Pending confirmation on FOC date. | Complete | Circuit Migrated | Circuit Provider |  | BR-IDU01-0001 | BRAZIL_INDAIATUBA |  |  |  |  | ROD ENGENHEIRO ERMENIO DE OLIVEIRA PENTEADO, S/N, KM 52,7 ITAICI | Indaiatuba | 13.340-600 |  | viviane Paula | viviane.paula@unilever.com | 55 019 3935 6989 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 20MB20MB | 70 | -23117122 | -472172 | 2019 | Oct | MPLS | 2019-03-31 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  | CenturyLink d-marc: Rack: Customer Rack – No label Equipment: NID ADVA Serial: NID077378 Port: 4 | Wan: 8.243.39.172/30 Lan: 8.243.39.176/29 IP Unilever - 8.243.39.174/30 Gateway - 8.243.39.173 | 8.243.39.173 | 8.243.39.174 | 8.243.39.176/29 | [8 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress |  | Yes | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved |  |  |  |  | 109151 | CRQ000000699233 (new) CRQ000000696845 (old) | Approved |  | CRQ000000696403 | Completed | Completed | Tested -Pass-First Time | 27-Jul: Test successful |  | Circuit Migrated - First Time right
CKT-I-01-BR-IPO01-0001-CTL-1 | I014887CTL1 | 1 | Yes | High | Latin America | Brazil | IPOJUCA | 2019_51 | un-ula-braipo1-rtr001 | un-ula-braipo1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | N/A | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-06-15 | Red | 2019-11-04 | 2020-10-15 | Red | Apr-30: Pending provider to deliver the circuit. 19-Mar: Migrations in Brazil on hold until further notice. Jan-31: Pending confirmation on FOC date. | Yellow | Circuit Order Accepted | Circuit Provider |  | BR-IPO01-0001 | BRAZIL_IPOJUCA |  |  |  |  | Complexo Industrial De Suape, ROD PE 60, KM 12, S/N, ENGENHO DO MEIO | Ipojuca | 55.590-000 | Manifacturing Plant | Andrezza Sales | Andrezza.Sales@unilever.com | 55 81 9 9929 5494 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 12MB | 40 | -805625 | -34941919 | 2019 | Oct | MPLS | 2018-04-30 | Commercial Benefit | 2 | 0 | SC2 |  | Business hours | ANÁLISE PRELIMINAR DE RISCO – APR CHECK LIST DE VERIFICAÇÃO DE DOCUMENTOS MAP ORDEM DE SERVIÇO (O.S.). POR ATIVIDADE SEGURANÇA DO TRABALHO (Ask PM for document templates) | Y |  | /30 | [14 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress | GLC-LX-SM | Yes |  | No |  | Assessment Complete
CKT-I-01-BR-LOZ01-0450-BT-1 | I012649BT1 | 1 | Devices on site un-ula-bralou1-rtr001 (192.223.120.40) 10M , /30 WAN, no nat pool , ISR4331/K9 un-ula-bralou1-vpn001 (192.223.120.67) 40M , /30 WAN, no nat pool , ISR4331/K9 Yes | High | Latin America | Brazil | Louveira | 2019_52 | un-ula-bralou1-rtr001 | un-ula-bralou1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-22 | 2020-05-20 | Red | 2020-07-31 | 2020-07-20 | Green | 2020-08-14 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | BR-LOZ01-0450 | BRAZIL_LOUVEIRA |  |  |  |  | AV JOSE LUIZ MAZZALI, Nº 450, SANTO ANTONIO | Louveira | 13.290-000 | Distribution Center | Jose Pereira Silva | Jose.P.Silva@unilever.com | 55 11 9 9754 1302 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 40MB | 40 | -3005371 | -512015 | 2019 | Oct | MPLS | 2018-06-30 | Commercial Benefit | 2 | 0 | SC2 |  | Business hours | RG | N |  | /30 | [19 empty] | Standard site type - Hybrid (MPLS + DMVPN) | In Progress | [14 empty] | CRQ000000705510 | In Progress | Completed
Out of Scope |  | 1 | Out of scope - No Device Access | Medium | Latin America | Brazil | NATAL | 2019_54 | un-ula-branat1-rtr001 |  | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | #NO MATCH | 2019-08-27 | 2019-08-27 | Out of Scope | 2019-08-27 | #NO MATCH | Out of Scope | 2019-08-27 | #NO MATCH | Out of Scope | 2019-08-27 |  | Out of Scope | Out of Scope | Out of Scope | Circuit not ordered |  |  | BR-NAT99-9999 | BRAZIL_NATAL |  |  |  |  | BR 101, KM 0,7 S/N, Única | Natal | 59149-070 |  | Joao Elias | Joao.elias@unilever.com | 55 81 9 8200 8706 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 2Mbps | 10 |  |  | 2019 | Nov | MPLS | 2019-03-31 | Commercial Benefit | 3 | 0 | SC2 | [5 empty] | /30 |  | #NO MATCH | #NO MATCH |  |  |  | #NO MATCH | #NO MATCH | #NO MATCH | [9 empty] | #NO MATCH
CKT-I-01-BR-PPY01-3701-CTL-1 | I011926CTL1 | 1 | Yes | High | Latin America | Brazil | POUSOALEGRE_PLANT | 2019_56 | un-ula-brapou1-rtr001 | un-ula-brapou1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006845677 / CID500118222 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-06-15 | Complete | 2019-11-04 | 2020-09-09 | Red | Sep-09: Migration successful. Sep-03: Migration rolled back. Circuit not responsive in router but it is in laptop. Suspecting MAC filtering in circuit CTL to investigate. Aut-13: Migration pushed to September 3rd at 9AM local time. Aug-6: Migration approved for August 17th 9AM. Pending successful circuit test same day before the migration as requested by Welington. Jul-30: Migration date still to be confirmed. Jul-27: Circuit migration approved for August 11th. Circuit testing pending. Apr-30: Pending confirmation that Cadastro registration has been completed. 19-Mar: Migrations in Brazil on hold until further notice. Jan-31: Pending confirmation on FOC date. | Complete | Circuit Delivered | Unilever SNT |  | BR-PPY01-3701 | BRAZIL_POUSOALEGRE_PLANT |  |  |  |  | Av. Prefeito Olavo Gomes, 3701, Jardim Mariosa | Pouso Alegre | 37.550-000 | Manifacturing Plant | Caroline Curiel Cyro Bastos | Caroline.A.Curiel@unilever.com cyro.bastos@unilever.com | 55 35 9 9217 0569 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 20MB20MB | 70 | -22285728 | -45911249 | 2019 | Oct | MPLS | 2018-07-31 | Commercial Benefit | 1 | 0 | SC2 |  | Business hours | RG e CPF ou CNH; Ficha de EPI´s; CPTS (parte da foto, qualificação civil e registro; Ficha de Registro; ASO – Atestado de Saúde Ocupacional; Certificado de Treinamento específico quando aplicável (Soldador, NR-10, NR-33, NR-35, etc). Obs. Para realizar trabalhos em altura / espaço confinado, além do certificado é necessário que no ASO esteja descrito que o colaborador está apto a exercer tais atividades. Todos os produtos químicos (limpeza, detergentes, tintas, etc), que forem ser utilizados no site devem obrigatoriamente estar acompanhados das FISPQ’s (Ficha de informação de Segurança de Produto Químico |  |  | /30 |  |  | WAN: 200.186.241.232/30 CTL: 200.186.241.233 UNI: 200.186.241.234 LAN 200.186.148.64/29 | 200.186.241.233 | 200.186.141.234 | [9 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress |  | Yes |  | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved |  |  |  |  | CHG000000000042165 | CRQ000000708103 (new) CRQ000000698919 (old) | Approved |  | CRQ000000696296 | Completed | Completed | Tested-Pass | Aug-13: Circuit test results delievered by CTL accepted by Welington. Jul-28: Tested again with CTL and we are not getting good speed results. CTL will escalate with last mile. Jul-23: Test failed. |  | Circuit Migrated | Circuit was not recognized in router but was responsive in laptop. Suspicion of MAC filtering. CTL to investigate.
CKT-I-01-BR-REC01-0025-CTL-1 | I0110941CTL1 | 1 | Yes Devices on site: un-ula-braboa1-drt001 - no nat pool, /30 wan mask, 10M existing BW, 4331 device un-ula-braboa1-vpn001 - /29 nat pool, /30 wan mask, 20M existing BW, 4331 device | High | Latin America | Brazil | RECIFE_BOAVIAGEM | 2019_57 | un-ula-braboa1-drt001 | un-ula-braboa1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | Circuit ID: 500118210 Service ID: 81-1XGCCC6 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-06-15 | Complete | 2019-11-04 | 2020-07-22 | Complete | Jul-22: Migration successful. Jul-14: FE did not arrive. Rescheduling for July 22th at 9AM. Jul-6: Migration approved for July 14th at 9AM local time. Jun-30: Circuit successfully tested. Jun-12: Circuit expected to be ready for testing on the week of June 15th. Apr-30: Pending provider to deliver the circuit. 19-Mar: Migrations in Brazil on hold until further notice. Jan-31: Pending confirmation on FOC date. 29-Dic: IP addresses not provided yet. Will need to push the migration. Need to push the migration for January. Might be able to bring to December if IP addresses are delivered by 4-Dec. 26-Nov: Circuit delivery date not defined. Proposing migration date of 18-Dec depending we get confirmation of circuit delivery no later than 3-December (to get CMSP ticket approved on Wed 4-Dec). 20-Nov: Migration date still pending confirmation that circuit is ready for activation. 8-Nov: Circuit still not fully delivered (waiting on confirmation for NID installation). Migration pushed to early December. | Complete | Circuit Migrated | Circuit Provider |  | BR-REC01-0025 | BRAZIL_RECIFE_BOAVIAGEM |  |  |  |  | R AGENOR LOPES, Nº 25, BOA VIAGEM | Recife | 51.021-110 | Corporate Office | Julio Cordeiro (HPC) Gabrielly Moiana (ICE) | Julio.cordeiro@unilever.com Gabrielly.Moiana@unilever.com | 55 81 98717-8480 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 20M | 20 | -8055384 | -34872004 | 2019 | Nov | MPLS | 2017-02-28 | Commercial Benefit | 2 | 0 | SC2 |  | Business hours | RG (Registro Geral) | No |  | /30 |  |  | LAN: 200.186.4.72/29 WAN: 200.186.7.176/30 CTL: 200.186.7.177 UNI: 200.186.7.178 | 200.186.7.177/30 | 200.186.7.178/30 | 200.186.4.72/29 | [8 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos | [9 empty] | Assessment Complete MOP created & config created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 12hrs UTC | 9AM | 97287 | CRQ000000689859 | Approved |  | CRQ000000689774 | Completed | Completed | Tested -Pass-First Time | Tested OK on June 30. |  | Circuit Migrated - First Time right
CKT-I-01-BR-VIN01-0001-CTL-1 | I011966CTL1 | 1 | Yes | High | Latin America | Brazil | VINHEDO | 2019_67 | un-ula-bravin1-rtr001 | un-ula-bravin1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006845681 / CID500118224 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-01-24 | Complete | 2019-11-04 | 2020-04-14 | Complete | 14-Apr: Migration completed successfully. 01-Apr: GeoIT asked to migrate on April 14th at 8AM local. 13-Mar: Migration cancelled pr Unilever due to the coronavirus situation. Mar-5: Rescheduled to March 16 since required documentation for site access wasn't received on time form NTT. Feb-27: GeoIT asked to migrate circuit on March 9th at 9AM. Jan-24: Circuit already delivered. Pending circuit testing and GeoIT to provide migration date. | Complete | Circuit Migrated |  |  | BR-VIN01-0001 | BRAZIL_VINHEDO |  |  |  |  | AV. DAS INDUSTRIAS, 315, DISTRITO INDUSTRIAL | Vinhedo | 13.280-000 |  | Cassio Benvenuto | cassio.benvenuto@unilever.com | +55 (19) 98136-8097 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 20MB | 70 | -7179447 | -34903763 | 2019 | Nov | 0 | 2020-03-07 | Commercial Benefit | 1 | 0 | SC2 | Review legacy contract end date to firm up delivery time table |  | Yes. Email sent to Tom with details. |  |  | /30 |  |  | WAN: 200.186.241.112/30 CTL: 200.186.241.113/30 UNI:200.186.241.114/30 LAN: 200.186.221.168/30 | 200.186.241.113/30 | 200.186.241.114/30 | 200.186.221.168/30 | [8 empty] | Sandor Jardon Vera | Sandor Jardon Vera | Sandor Jardon Vera |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO | Yes |  | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 11AM | 8AM | 45186 | CRQ000000648801 | Approved | 41074 | CRQ000000639921 | Completed | Completed | Tested -Pass-First Time | Feb 13th |  | Circuit Migrated - First Time right |  |  |  |  | 2020-03-01
CKT-I-01-CL-SCL05-0550-CTL-1 | I012687CTL1 | 1 | Yes | Medium | Latin America | Chile | Site Lampa | 2019_81 | un-ula-chllam1-rtr001 | un-ula-chllam1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006829532 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2019-12-13 | Complete | 2019-11-04 | 2020-06-14 | Complete | 14-Jun: Migration successful. 8-Jun: Migration rescheduled for June 14th 9AM local time. 7-Jun: Migration postponed. Unilever site contact did not have government authorization to be outdoors during quarantine. Pushed to next Sunday. 15-May: Migration approved for June 7th at 9AM. 8-May: Circuit testing successfu. Ricardo to get migration date. 29-Apr: Pending successful circuit testing now that CTL has confirmed the correct IP assignment. 9-Apr: Migration postponed for a later date in April; circuit testing failed this week. 6-Apr: GeoIT asked to migrate circuit on April 12th. 19-Mar: Activities (circuit testing & migration) in Chile on hold until further notice. 17-Jan:Geo IT Mgr informed us that the migration will need to be pushed to April, due to other two projects currently running at the site, as well as a change in their logistics operator (IDL). 13-Jan: Geo IT Mgr approved migration date of Feb-15 at 13hrs. 13-Dec: Circuit is now delivered. 29-Nov: Due to civil unrest in the country, Geo IT Team asked to push this migration until January. 27-Nov: NID still not installed. Pushing migration date to 18-Dec. 20-Nov: NID still not installed. Needs to be installed by 25-Nov or we will need to reschedule migration. 15-Nov: Confirmed with Fernando that /29 is not really needed. 8-Nov: Geo IT Team to confirm date of 7-Dec. 24/10 (AP) engineer requested a change from /30 to /29. Email for approval sent to UL. Juan to confirm with CTL. | Complete | Circuit Migrated |  |  | CL-SCL05-0550 | CHILE_SANTIAGO_LAMPA |  |  |  |  | La Estera No 550, Parque Industrial Valle Grande, Lampa | Santiago (CL-RM) | 939-0389 |  | Miguel Parada/Ricardo Caldesl Parada | miguel.parada@unilever.com / Ricardo.caldes@unilever.com | + 56 9 982191949 | Ricardo Caldes | Ricardo.caldes@unilever.com | 30MB | 30 | 33°18'58.1"S | 70°44'15.4"W | 2019 | Nov | MPLS | 2018-09-06 | Commercial Benefit | 2 | 0 | SC2 |  | 13HRS |  |  |  | /29 | 25/10/19: Original order was /30, existing is /29, requested vodacom for /29 IP |  | WAN: 67.73.178.0/30 CTL: 67.73.178.1/30 UNI: 67.73.178.2/30 | 67.73.178.1/30 | 67.73.178.2/30 | [9 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos |  |  | Standard site type - Hybrid (MPLS + IEN) | Complete | NO | Yes |  |  | No | Assessment Complete MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 18HRS | 13HRS | 55250 | CRQ000000659827 | Approved | 40069 | CRQ000000623636 | Completed | Completed | Tested-Pass | Could not get a connection. Asked CTL to look into issue. restest scheduled on April 21, 2nd test faild. CTL opened a ticket with last mile Provider Telefonica. UL asked CTL to sent out an FE. May 6th test passed, CTL provided wrong IP, which were corrected, also they corrected filters on the BW | Miguel Parada | Circuit Migrated - First Time right |  |  |  |  | 2020-01-01
CKT-I-01-CL-SCL06-0001-CTL-1 | I012688CTL1 | 1 | Yes | High | Latin America | Chile | Site Panamericana | 2019_83 | un-ula-chlpan1-rtr001 | un-ula-chlpan1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006829205 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2019-12-12 | Complete | 2019-11-04 | 2020-02-15 | Complete | 15-Feb: Circuit successfully migrated. 31-Jan: Site on track to be scheduled on Feb 15th. 17-Jan: Geo IT Mgr asked to push the migration to February 15th at 15hrs due to other changes happening at the site. 13-Dec:Geo IT Mgr approved migration dates of Jan-25 at 15hrs. 29-Nov: Geo IT Team asked to migrate on 15-Dec, but IP addresses are still not delivered; pending Welington to provide to CenturyLink IP Form. Site won't approve migration any other day in December. Pushing migration to January. 20-Nov: Pending confirmation on FOC date. | Complete | Circuit Migrated |  |  | CL-SCL06-0001 | CHILE_SANTIAGO_PANAMERICANA |  |  |  |  | Panamericana Norte 5981, Conchalí | Santiago (CL-RM) | 855-0187 |  | Miguel Parada/Ricardo Caldesl Parada | miguel.parada@unilever.com / Ricardo.caldes@unilever.com | + 56 9 982191949 | Ricardo Caldes | Ricardo.caldes@unilever.com | 25MB | 80 | 33°22'14.2"S | 70°41'48.7"W | 2019 | Oct | MPLS | 2019-11-01 | Commercial Benefit | 2 | 0 | SC2 |  | 15:00 | Safety training 30min before migration time. Safety shoes. |  |  | /30 |  |  | WAN: 67.73.178.220/30 CTL: 67.73.178.221/30 UNI: 67.73.178.222/30 | 67.73.178.221 | 67.73.178.222 | NA | [8 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos |  |  | Standard site type - Hybrid (MPLS + IEN) | Complete | NO | Yes | No |  | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 18:00 | 15:00 | 27939(Migration) | CRQ000000633497 | Approved | 40908 | CRQ000000633575 | Completed | Completed | Tested-Pass | January 21 to be on site. CTL supported us on test | Miguel Parada | Circuit Migrated - First Time right |  |  |  |  | 2020-01-01
CKT-I-01-CO-BOG01-0001-GTT-1 | I019940GTT1 | 1 | Yes | High | Latin America | COLOMBIA | Bogota Corporate | 2018_53 | un-ula-colbog1-vpn001 | un-ula-colbog1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | GTT | GTT |  | " DIA/01701016" | 2019-08-12 | 2019-08-09 | Complete | 2019-08-19 | 2019-08-12 | Complete | 2019-10-28 | 2020-10-31 | Red | 2019-11-11 | 2020-10-30 | Red | 15/06: Allan Morais to support identifying the requirements to complete the mgration to the new GTT circuit. (From GTT tracker) 19/03: No update 25/02: Order is on-hold with the vendor. Customer would like wait after the second 200Mbps circuit they ordered from another provider is implemented for this site. 18/02: On hold by Unilever until their new 200Mbps circuit is ready in mid-April. 31-Jan: GTT and Unilever are trying to reach a commercial agreement with current circuit provider to hand over their circuit installation and use it for te new circuit from GTT. 24-Jan: Site does not have any more room left to lay new fibers into the office. GTT looking for solution. 17/12 Waiting Unilever to decide if they will accept SW swap and when. | Yellow | Circuit Order Accepted | Unilever SNT | Check dates | CO-BOG01-0001 | COLOMBIA_BOGOTA_26 AVENIDA EL DORADO |  |  |  |  | Av. El Dorado # 69 B-45, Edificio Bogato Corporate | Bogota |  |  | Andrea Beltran | Andrea.Beltran@unilever.com | +57 1 4239727 | Luis.Rubio | Luis.Rubio@unilever.com | 200MB | 200 | 4.6597 | -74.1081 | 2019 | Oct | Internet | 2019-10-21 | Commercial Benefit | 1 | Resilience | SC2 | [5 empty] | /29 | Head office for the Columbia business. Circa 800 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | Ground floor, Avenida el Dorado #63B-45 piso 7. All the data cabling arrives to the building in a spot outside the building, but I can´t call it a Denmarc. | 208.116.210.128/28 Network - 208.116.210.128 First usable - 208.116.210.129 Last usable - 208.116.210.142 Broadcast - 208.116.210.143 Subnet Mask - 255.255.255.240 | 208.116.210.129/29 | 208.116.210.130/29 |  |  |  | Tigo | GTT Miami | AS 3257 |  |  |  | Hugo Trejo | Hugo Trejo | Hugo Trejo | [6 empty] | Yes | Yes |  | Assessment Complete
CKT-I-02-CO-BOG01-0001-CTL-1 | I029940CTL1 | 1 | Yes | High | Latin America | Colombia | Bogota Corporate | 2019_110 | un-ula-colbog1-rtr001 | un-ula-colbog1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006829214 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-06-19 | Complete | 2019-11-04 | 2020-09-22 | Red | Aug-24: Migration postponed until SFPs are delivered to the site. Aug-13: Migration pushed to August 20th at 8:30AM. Jul-31: Migration approved for August 18th at 9AM. Jul-30: Circuit test failed. Pending resolution. Jun-26: Pending circuit testing. Jun-12: GeoIT to provide migration date. Will be done on the same window as new circuit installation (NTE replaced). Apr-30: Pending GeoIT to inform when installation of the circuit can continue. 19-Mar: No update. 31-Jan: CTL working on the installation of the circuit. WIll provide update once they have ETA of completion. 24-Jan: Site does not have any more room left to lay new fibers into the office. CTL looking for workaround. | Pink | Circuit Delivered | Unilever Geo-IT |  | CO-BOG01-0001 | COLOMBIA_BOGOTA_26 AVENIDA EL DORADO |  |  |  |  | Av. El Dorado # 69 B-45, Edificio Bogato Corporate | Bogota |  |  | Andrea Beltran | Andrea.Beltran@unilever.com | +57 1 4239727 | Luis.Rubio | Luis.Rubio@unilever.com | 60MB | 200 | 4.6597 | -74.1081 | 2019 | Oct | MPLS | 2019-12-31 | Commercial Benefit | 1 | Resilience | SC2 | [5 empty] | /29 | Head office for the Columbia business. Circa 800 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. |  | 67.73.188.68/30 CTL: 67.73.188.69/30 UNI: 67.73.188.70/30 | 67.73.188.69/30 | 67.73.188.70/30 | [9 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo | [9 empty] | Assessment Complete |  |  |  | 8:30 | 113959 | CRQ000000700890 |  |  | CRQ000000701356 | Completed | Completed | Tested-Pass | Aug-13: Circuit test results delievered by CTL accepted by Welington.
CKT-I-01-CO-QPI01-0002-PCCW-1 | I019638PCCW1 | 1 | Require /29+ /30 | High | Latin America | Colombia | CALI HPC Plant | 2019_113 | un-ula-colcal1-vpn001 | un-ula-colcal1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | PCCW | PCCW |  |  | 2019-08-19 | 2019-09-03 | Complete | 2019-08-26 | 2019-10-17 | Complete | 2019-11-04 | 2020-06-30 | Red | 2019-11-18 | 2020-10-30 | Red | Apr-30: Pending provider to deliver the circuit. 19-Jan: Pending access to the site to install circuit. 24-Jan: Confirmation that circuit will be delivered as /29. 20-Dec: Requested PCCW to change the order and provide a /29 with the circuit. | Yellow | Circuit Order Accepted | Circuit Provider |  | CO-QPI01-0002 | COLOMBIA_CALI_VARELLA_HPC |  |  |  |  | Cra. 5 #5230, Valle del Cauca | Cali |  |  | Maria Victoria Mateus | Maria-Victoria.Mateus@unilever.com |  |  |  | 50MB | 50 | 3.5607 | -76.4252 | 2019 | Oct | MPLS | Assumed Monthly | Commercial Benefit | 1 | Resilience | SC2 | [5 empty] | /30 |  | First Floor, First Room, communications rack only one | [6 empty] | Brodynt | [5 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo | [6 empty] | Yes |  |  | Assessment Complete
CKT-I-01-CO-CLO01-0001-PCCW-1 | I011986PCCW1 | 1 | Yes | High | Latin America | Colombia | CALI Planta Foods | 2019_112 | un-ula-colcalf-rtr001 | un-ula-colcalf-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | PCCW | PCCW |  |  | 2019-08-19 | 2019-09-03 | Complete | 2019-08-26 | 2019-10-17 | Complete | 2019-11-04 | 2020-06-30 | Red | 2019-11-18 | 2020-10-30 | Red | Apr-30: Pending provider to deliver the circuit. 19-Jan: Pending access to the site to install circuit. 24-Jan: Confirmation that circuit will be delivered as /29. | Yellow | Circuit Order Accepted | Circuit Provider |  | CO-CLO01-0001 | COLOMBIA_CALI_FOODS |  |  |  |  | KM. 13 VIA CENCAR-AEROPUERTO, CORREGIMIENTO MATAPALO | Cali |  |  | Maria Victoria Mateus | Maria-Victoria.Mateus@unilever.com |  |  |  | 15M | 30 | 3.4631 | -76.4996 | 2019 | Oct | MPLS | 2018-10-31 | Commercial Benefit | 2 | 0 | SC2 | [5 empty] | /30 |  | Second Floor, First Room, communications rack only one | [6 empty] | Brodynt | [5 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo | [9 empty] | Assessment Complete
CKT-I-01-CR-SJO03-0001-ORA-1 | I012089ORA1 | 1 |  | High | Latin America | Costa Rica | Heredia HeadOffice | 2019_117 | un-ula-cribel1-rtr001 | un-ula-cribel1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | Orange | Ora |  | GO09XEV23D | 2019-08-19 | 2019-09-13 | Complete | 2019-08-26 | 2019-11-06 | Complete | 2019-11-04 | 2020-02-18 | Complete | 2019-11-18 | 2020-05-15 | Complete | May-15: Migration successful. May-4: Circuit testing and Migration approved on May 15th. Apr-30: Pending NTT to confirm date of avaialability for circuit migration. Apr-21: Orange confirms IP info is correct. Need to discuss best way to test the circuit. Migration has to be postponed to future date. Apr-20: IP information from Orange seems incorrect. Waiting on confirmation from Orange on correct IPs. Apr-17: GeoIT asked to migrate on April 24th at 9AM local. Mar-19: Pending circuit testing and agreement on migration date. Jan-30: GeoIT will look for migration date after circuit is delivered and tested. | Complete | Circuit Migrated |  |  | CR-SJO03-0001 | COSTA_RICA_SAN_JOSE_BELEN |  |  |  |  | Unilever, Heredia, Belén, Costa Rica 9°59'14.0"N 84°10'07.7"W 400m al Oeste y 800m al Norte Del Cruce Sobre El Puente Real Cariari,Fte A La Sede Testigos De Jehova / Heredia | San Jose | NA |  | Luis.Rubio | Luis.Rubio@unilever.com | +57 1 4239727 | Luis.Rubio | Luis.Rubio@unilever.com | 18MB | 40 | 9.9665 | -84.1053 | 2019 | Oct | MPLS | 2017-05-31 | Commercial Benefit | 1 | Resilience | SC2 |  | 9AM local |  |  |  | /30 |  |  | IP Address: 186.179.71.175 Subnet Maks: 255.255.255.254 Gateway: 186.179.71.174 Primary DNS IPv4: 167.250.220.220 Secondary DNS IPv4: 186.148.105.105 | 186.179.71.174 | 186.179.71.175 |  |  |  | UFINET LATAM SLU | [5 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress | NO | No |  | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 15:00 | 9AM | 65850 | CRQ000000672806 | Approved |  | CRQ000000672504 | Completed | Completed | Tested-Pass | May 15th |  | Circuit Migrated - First Time right |  |  |  | 2020-01-01 | 2020-05-01
CKT-I-01-CR-HER01-0002-ORA-1 | I013197ORA1 | 1 | Yes | High | Latin America | Costa Rica | Valencia Distribution Center | 2019_116 | un-ula-crival1-vpn001 | un-ula-crival1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | Orange | Ora |  | LO0048WP50 | 2019-08-19 | 2019-09-13 | Complete | 2019-08-26 | 2019-11-02 | Complete | 2019-11-04 | 2020-07-31 | Red | 2019-11-18 | 2020-09-28 | Red | May-28: Pending provider to get access to the building to install the circuit. Apr-30: Pending provider to deliver the circuit. Mar-19: Pending site access to install the circuit. Jan-30: GeoIT will look for migration date after circuit is delivered and tested. | Yellow | Circuit Order Accepted | Unilever Geo-IT |  | CR-HER01-0002 | COSTA_RICA_HEREDIA_VALENCIA |  |  |  |  | 1kilometro al este del cruce la valencia, calle a mano derecha frente a Extralum, ultimo almacen , Heredia | Valencia | NA |  | Luis.Rubio | Luis.Rubio@unilever.com | +57 1 4239727 | Luis.Rubio | Luis.Rubio@unilever.com | 10000Kbps | 10 | 9.9665 | -84.1053 | 2019 | Nov | MPLS | Assumed Monthly | Commercial Benefit | 1 | Resilience | SC2 | [5 empty] | /30 |  |  | IP Address: 190.61.84.91 Subnet Maks: 255.255.255.254 o 255.255.255.0 Gateway: 190.61.84.90 Primary DNS IPv4: 167.250.220.220 Secondary DNS IPv4: 186.148.105.105 | 190.61.84.90 | 190.61.84.91 |  |  |  | UFINET LATAM SLU | [5 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO | No |  | No | No | Assessment Complete Partner MOP created | [18 empty] | 2020-01-01
CKT-I-01-DO-SDQ04-0001-GTT-1 | I018533GTT1 | 1 | Yes | High | Latin America | Dominican Republic | Acropolis - Corporate | 2019_128 | un-ula-domacr1-rtr001 | un-ula-domacr1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01690190 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-10-30 | Complete | 2019-10-28 | 2019-10-30 | Complete | 2019-11-11 | 2020-01-17 | Complete | 17-Jan: Circuit successfully migrated. 14-Dec: CMS Change Management Team informed us that the CMSP ticket was rejected by mistake, and that they had to submit a new RFC ticket in UNL from scratch, and that it required an Expedite Approval if we wanted to maintain the Jan-17 migration date. Welington approved, and the Expedite was raised. 19-Dec: Migration rescheduled for January 17th at 4PM local time. 13-Dec: Migration cancelled midway as it was discovered that the Algosec request was raised with incorrect IPs. GTT provided incorrect IPs in one of the trackers, and in the delivery of their circuit the WAN and LAN IPs were swapped. Migration to be re-scheduled in January. 29-Nov: MOP ready for review. Migration date of 13-Dec fully approved by Geo IT Team. Waiting on agreement on time of day for the change window. 20-Nov: Need to further discuss the migration strategy for this topology (MPLS+IEN) since we are only migrating the MPLS circuit and not the IEN. Should have this strategy ready by next week. Migration date of 13-Dec tentative. 15-Nov: Waiting on Geo IT Team to confirm and approve Nov-29 as the migration date. 8-Nov. Geo IT Team wating on confirmation of time of day for migration on 22-Nov. | Complete | Circuit Migrated |  |  | DO-SDQ04-0001 | DOMINICAN_REPUBLIC_SANTO_DOMINGO_WINSTON_CHURCHILL |  |  |  |  | Acrópolis Center, Piso 17, Av. Winston Churchill 2 | Santo Domingo | 10127 |  | Vladimir.Mejia | Vladimir.Mejia@unilever.com | 829-904-2816 +1 809 405 3593 | Vladimir.Mejia | Vladimir.Mejia@unilever.com | 15MB | 30 | 18.4699 | -69.9396 | 2019 | Oct | MPLS | 2018-03-08 | Commercial Benefit | 1 | Congested Link | SC4 |  | 4PM |  |  |  | /30 |  | 17th Floor, Acropolis Center, Server Room | 208.116.200.108/30 Network - 208.116.200.108 First usable - 208.116.200.109 Last usable - 208.116.200.110 Broadcast - 208.116.200.111 Subnet Mask - 255.255.255.252 | 208.116.200.109 | 208.116.200.110 |  |  |  | Gold Data | GTT Miami | AS 3257 |  |  |  | Sandor Jardon Vera | Sandor Jardon Vera | Sandor Jardon Vera | 2020-01-20 |  | Standard site type - Hybrid (MPLS + IEN) | Complete | NO | No |  | Yes |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  |  | 6PM | 25936 (migration) 18950 (migration - old) 18958 (alarms supression) | CRQ000000634320 (new) CRQ000000625817 (original before rollback) | Approved | 40639 | CRQ000000631854 | Completed | Completed | Tested-Pass | Circuit testing failed on the first try. GTT to fix for second test on Dec 11. GTT coordinated the installation of the other CPE in the final customer. Waiting for GTT confirmation of configure, test and then back to us with circuit working and ready for us to set up the call with you to test again.The installation and testing on the link has been completed. Already given ping response, the final client performed speed tests and gives the contracted capacity. | Vladimir Mejia | Circuit Migrated | Incorrect IPs from provider. Algosec was implemented with these wrong IPs. |  |  |  | 2019-12-01
CKT-I-01-EC-GYQ01-0001-CTL-1 | I011992CTL1 | 1 | Yes | High | Latin America | Ecuador | Guayaquil Matriz (OASIS) | 2019_130 | un-ula-ecugua1-rtr001 | un-ula-ecguar1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006829551 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-07-15 | Red | 2019-11-04 | 2020-09-28 | Red | Apr-30: Pending provider to deliver the circuit. Mar-19: Still pending circuit delivery. Jan-30: GeoIT will look for migration date after circuit is delivered and tested. | Pink | Circuit Order Accepted | Circuit Provider |  | EC-GYQ01-0001 | ECUADOR_GUAYAQUIL_OASIS |  |  |  |  | Km. 25 Vía A Daule | Guayaquil | NA |  | Luis.Rubio | Luis.Rubio@unilever.com | T: +57 1 4239727, M: +57 3182062761 | Luis.Rubio | Luis.Rubio@unilever.com | 100MB100MB | 100 | -1.9947 | -79.9698 | 2019 | Oct | MPLS | 2019-09-30 | Commercial Benefit | 1 | Principal Site | SC2 | [5 empty] | /30 |  |  | 67.73.163.228/30 CTL: 67.73.163.229 UNI: 67.73.163.230 | 67.73.163.229/30 | 67.73.163.230/30 | [9 empty] | Fernando Ramos | Sandor Jardon Vera | Sandor Jardon Vera |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress | [14 empty] | CRQ000000708208 | Completed | Completed
CKT-I-01-SV-SAL10-0001-GTT-1 | I0110630GTT1 | 1 | Yes | High | Latin America | El Salvador | El Salvador - Head Office | 2019_146 | un-ula-slvsal-rtr001 | un-ula-slvsal-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | GTT | GTT |  | " DIA/01701014" | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-09-04 | Complete | 2019-10-28 | 2019-12-11 | Complete | 2019-11-11 | 2020-04-19 | Complete | 19-Apr: Circuit successfully migrated. 8-Apr: Geo IT asked to migrate on April 19th. 19-Mar: Pending circuit migration date. Jan-30: GeoIT will look for migration date after circuit testing which is now already scheduled. 17-Jan: Geo IT Mgr wants to wait for circuit testing before scheduling the migration. Migration not earlier than late-February. 13-Jan: Geo IT Mgr mentioned his preference of migrating all of the services that run over the current MPLS link gradually into the new circuit, of in a single migration window. We have informed him (cc' Welington) that this is not how we've been doing all other migrations, and that we are confident that a single migration window is enough. He asked to see the results of the circuit testing, as well as the MOP, before agreeing on a migration window date. 12-Jan: Trying to get the circuit scheduled back to January. Waiting on Geo IT for providing new date; possibly Jan 26 if approved before 15-Jan. 8-Jan: Concern regarding if the new circuit needs to be provisioned as /30 or /29. Internal review showed that /30 is enough. Will look for a new migration date with the site since migration was put on-hold due to this concern. 17-Dec: Geo IT and site confirm migration date of Jan-19 9AM. 28-Nov: FOC date needs to be re-issued by provider. Pushing migration to January. 20-Nov: FOC date pushed to 11-Dec. Tentative migration date pushed to 19-Dec. 24-Oct: Estimated vendor delivery date 22/11 | Complete | Circuit Migrated |  |  | SV-SAL10-0001 | EL_SALVADOR_SAN_SALVADOR_NEW_HOME |  |  |  |  | Calle El Mirador, Colonia Escalón, Torre Futura. Piso 19. | San Salvador | NA |  | Luis.Rubio | Luis.Rubio@unilever.com | T: +57 1 4239727, M: +57 3182062761 | Luis.Rubio | Luis.Rubio@unilever.com | 35mb | 100 | 13.7088 | -89.241 | 2019 | Oct | MPLS | Assumed Monthly | Commercial Benefit | 1 | Congested Link | SC2 |  | 9AM local |  |  |  | /30 |  | 19th Floor, Torre Futura, Computer centre | 168.232.37.4/30 Network - 168.232.37.4 First usable - 168.232.37.5 Last usable - 168.232.37.6 Broadcast - 168.232.37.7 Subnet Mask - 255.255.255.252 | 168.232.37.5 | 168.232.37.6 |  |  |  | Tigo | Local ISP | AS 262206 |  |  |  | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Complex site type - requires redesign | [6 empty] | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 12PM | 9AM | 56022 | CRQ000000661031 | Approved | 41071 | CRQ000000640036 | Completed | Completed | Tested-Pass | Feb 9th | Suleyma Platero | Circuit Migrated - First Time right |  |  |  | 2020-01-01 | 2020-01-01
CKT-I-01-HN-TGU01-0001-GTT-1 | I012175GTT1 | 1 | Yes | High | Latin America | Honduras | Tegucigalpa CORP & CD | 2019_202 | un-ula-honteg1-rtr001 | un-ula-honteg1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit + Router + DMVPN conversion | GTT | GTT |  | DIA/01690215 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-12-12 | Complete | 2019-10-28 | 2019-12-12 | Complete | 2019-11-11 | 2020-04-14 | Complete | 12-Jun: Allan Morais to reach out to Lourdes Ochoa to get new window date to complete the router upgrade. 4-Jun: DMVPN tunnel would not come up in the new router with the new circuit. Got Microland support on the land and showed us that it was not a FW/Algosec issue. Will have to analyze the logs and configurations to find the problem and schedule a new date for the new router installation. Router left racked and stacked. 25-May:New router installation and conversion to DMVPN with already migrated circuit scheduled to June 4th at 10AM (CMSP 72242 / RFC CRQ000000678722). 18-May: Pending confirmation from GeoIT for when we can return to the site to install new router and enable DMVPN. 14-Apr: Migration successful with old router. Pending to install new router and enable DMVPN. 9-Apr: Due to mobility restrictions at Honduras (because of Covid-19), migration has been moved ahead by one day on April 14th. Field Engineer support is not available on this day (also because of mobility restrictions), but we've escalated to get an exception. 8-Apr: Geo IT asked to migrate on April 15th. Pending migration strategy since current MPLS router (1941) does not support DMVPN, and there is no new router available at the moment. 19-Mar: Pending circuit migration date. 21-Feb: Circuit Testing failed. Provider looking into issue. Jan-30: GeoIT will look for migration date after circuit testing which is now already scheduled.. 17-Jan: Geo IT Mgr wants to wait for circuit testing before scheduling the migration. Migration not earlier than late-February. 13-Jan. Geo IT Mgr mentioned his preference of migrating all of the services that run over the current MPLS link gradually into the new circuit, of in a single migration window. We have informed him (cc' Welington) that this is not how we've been doing all other migrations, and that we are confident that a single migration window is enough. He asked to see the results of the circuit testing, as well as the MOP, before agreeing on a migration window date. | Complete | Circuit Migrated |  |  | HN-TGU01-0001 | HONDURAS-TEGUCIGALPA |  |  |  |  | Anillo periférico, Km 16. 1 Km adelante de puente las uvas. | Tegucigalpa | NA |  | Luis.Rubio | Luis.Rubio@unilever.com | T: +57 1 4239727, M: +57 3182062761 | Luis.Rubio | Luis.Rubio@unilever.com | 15M | 30 | 14.0467 | -87.2444 | 2019 | Nov | MPLS | Assumed Monthly | Commercial Benefit | 1 | Congested Link | SC2 | [5 empty] | /30 |  | 2nd Floor, Unilever CD, Data Centre | 208.116.224.164/30 Network - 208.116.224.164 First usable - 208.116.224.165 Last usable - 208.116.224.166 Broadcast - 208.116.224.167 Subnet Mask - 255.255.255.252 | 208.116.224.165 | 208.116.224.166 | 208.116.224.164/29 |  |  | Tigo | GTT Miami | AS 3257 |  |  |  | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress | NO | Yes | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 16hrs | 10AM | 57294 | CRQ000000661375 | Approved | 40841 | CRQ000000632998 | Completed | Completed | Tested-Pass | Friday 14 th, 2020. GTT has to escalate with local vendor and re schelude the visit. March 11th test passed, ipert perfomed |  | Circuit Migrated - First Time right |  |  |  |  | 2020-01-01
CKT-I-01-MX-CIU03-0001-CTL-1 | I0111049CTL1 | 1 | Yes | High | Latin America | Mexico | TALISMÁN | 2019_519 | un-ula-mextal1-drt001 | un-ula-mextal1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006829187 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-05-30 | Complete | 2019-11-04 | 2020-06-20 | Complete | 20-Jun: Migration successful. 12-Jun: Migration scheduled for June 20th. 10-Jun: Circuit testing failed. CTL to open a ticket with last mile provider. 4-Jun: Additional IP segment received. 28-May: Still waiting for CTL to provide new IP segment. ETA should be less than one week. 31-Apr: Pending CTL to change circuit order and deliver a /29 LAN segment additional to the already delivered /30 WAN segment. 3-Apr: Circuit to be installed next week. Schedule circuit testing by then, and migration later. 19-Mar: Pending circuit to be delivered. 30-Jan: It was agreed with Dave and Zoe that there needs to be a country-wide analysis done in Mexico before migrating hub site Tultitlan_Tepalcapa, and then, once we have a strategy, we will schedule the rest of the other migrations in Mexico. 17-Jan: IPT spoke site. Can't migrate MPLS until IPT strategy is defined. | Complete | Circuit Migrated | Circuit Provider |  | MX-CIU03-0001 | MEXICO_CIUDAD_DE_MEXICO_TALISMAN |  |  |  |  | Calle Talismán 210, CP 7820 Col 3 Estrellas, Ciudad de México | Ciudad de Mexico | 7820 |  | Karen.Soto | Karen.Soto@unilever.com | 525513844803 | Karen Soto | Karen.Soto@unilever.com | 8192Kbps8192Kbps | 40 | 19.3226 | -99.125 | 2019 | Nov | MPLS | 2016-10-21 | Commercial Benefit | 1 | Congested link | SC3 | [5 empty] | /30 |  |  | 64.208.169.152/30 CTL: 64.208.169.153 UNI: 64.208.169.154 LAN: 64.208.239.40/29 | 64.208.169.153 | 64.208.169.154 | 64.208.239.40/29 | [8 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | [9 empty] | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  |  |  | 79956 - Alarms 79960 - Hostname Change 79962 - CMS | CRQ000000682949 | Approved |  | CRQ000000680221 | Completed | Completed | Tested-Pass | Jun 19th: Circuit test passed after issues with new IP segment. April 23th, iPerf test performed |  | Circuit Migrated - First Time right
CKT-I-01-MX-TLC03-0001-CTL-1 | I012007CTL1 | 1 | Yes | High | Latin America | Mexico | LERMA | 2019_550 | un-ula-mexler1-vpn001 | un-ula-mexler1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006829259DIR | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-02-12 | Complete | 2019-11-04 | 2020-09-05 | Complete | 05-Sep: Migration successful. Agile redundancy did not work due to issue with NIM Card. Will have to go back to implement. 14-Aug: Migration cancelled due to CTL circuit not working. They could not fix the issue on time. To be rescheduled. 3-Aug: Migration pushed to August 15th. 27-Jul: Migration approved for August 8th. 10-Jun: Circuit testing successful. GeoIT ro provide migration date. 4-Jun: Additional IP segment received. 28-May: Still waiting for CTL to provide new IP segment. ETA should be less than one week. 30-Apr: Still waiting on CTL to provide ETA on new /29 IP assignments.. 12-Mar: Site needs additional IP pool. Waiting on CTL to provide ETA on change. 30-Jan: It was agreed with Dave and Zoe that there needs to be a country-wide analysis done in Mexico before migrating hub site Tultitlan_Tepalcapa, and then, once we have a strategy, we will schedule the rest of the other migrations in Mexico. 17-Jan: IPT spoke site. Can't migrate MPLS until IPT strategy is defined. | Complete | Circuit Migrated | Unilever Geo-IT |  | MX-TLC03-0001 | MEXICO_TOLUCA_CARRETERA_MEXICO |  |  |  |  | Km. 53.5 Carretera México Toluca Lerma | Toluca | 52000 |  | Karen.Soto | Karen.Soto@unilever.com | 525513844803 | Karen Soto | Karen.Soto@unilever.com | 50MB | 50 | 19.3547 | -99.4826 | 2019 | Nov | MPLS | 2017-07-29 | Commercial Benefit | 1 | Resilience | SC2 | [5 empty] | /29 |  |  | WAN: 64.208.239.60/30 CTL: 64.208.239.61/30 UNI: 64.208.239.62/30 LAN: 64.209.73.248/29 | 64.208.239.61/30 | 64.208.239.62/30 | 64.209.73.248/29 | [8 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO |  |  |  |  | Assessment Complete |  |  |  |  | CHG000000000041819 (new with NIM installs) 109361 (old) | CRQ000000706938 | Approved | 41536 | CRQ000000648143/CRQ000000680172 | Completed | Completed | Tested -Pass-First Time | Jun-11: Tested again successfully with new IP segment. Feb 25th |  | Circuit Migrated - First Time right
CKT-I-01-MX-TTN02-0001-ORA-1 | I012795ORA1 | 1 | Yes | High | Latin America | Mexico | MEXIQUENSE_CDU | 2019_553 | un-ula-mexcdu1-drt001 | un-ula-mexcdu1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | Orange | Ora |  | LO0048WH48 | 2019-08-19 | 2019-09-13 | Complete | 2019-08-26 | 2019-10-10 | Complete | 2019-11-04 | 2020-01-08 | Complete | 2019-11-18 | 2020-04-18 | Complete | 18-Apr: Circuit successfully migrated. 14-Apr: Migration confirmed for April 18th from 6AM to 12PM local time. 9-Apr: Welington informed that migration could be moved ahead by one day (April 18th). He will confirm next week. 8-Apr: Geo IT asked to migrate on April 19th. 3-Apr: Migration still on-hold until June; production in the country is too high now due to Covid-19, and do not want to risk any affectations. 18-Mar: Migrations in Mexico postponed due to coronavirus outbreak. 9-Mar: Migration planned for March 22. Pending final approval from GeoIT. Might get postponed due to coronavirus. 30-Jan: It was agreed with Dave and Zoe that there needs to be a country-wide analysis done in Mexico before migrating hub site Tultitlan_Tepalcapa, and then, once we have a strategy, we will schedule the rest of the other migrations in Mexico. 17-Jan: IPT spoke site. Can't migrate MPLS until IPT strategy is defined. 9-Jan: Circuit now delivered WAY ahead of forcasted time with no advance notice. Sep-30: Per Welington, Link capacity changed from 20 to 30Mbps | Complete | Circuit Migrated |  |  | MX-TTN02-0001 | MEXICO_TULTITLAN_LA_MEXIQUENSE |  |  |  |  | Av. La Mexiquense No. 5 Colonia Ex-Hacienda Los Portales | Tultitlan | 54900 |  | Karen.Soto | Karen.Soto@unilever.com | 5.25514E+11 |  |  | 6000Kbps6000Kbps | 30 | 19.6653 | -99.08 | 2019 | Nov | MPLS | 2017-06-05 | Commercial Benefit | 1 | Congested Link | SC2 | [5 empty] | /30 |  |  | 189.206.164.188 255.255.255.248 Gateway: 189.206.164.185 DNS: 207.248.224.71 DNS: 207.248.224.71 | 189.206.164.185 | 189.206.164.190 |  |  |  | AXTEL | [5 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos |  |  | Standard site type - Hybrid (MPLS + DMVPN) |  |  |  |  | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 11AM | 6AM | 48386 | CRQ000000652787 | Approved | 41503 | CRQ000000646837 | Completed | Completed | Tested -Pass-First Time | Feb 18th |  | Circuit Migrated - First Time right
CKT-I-01-MX-TTN01-0009-CTL-1 | I012794CTL1 | 1 | Yes | High | Latin America | Mexico | Tultitlan_Tepalcapa | 2019_554 | un-ula-mextul1-rtr001 | un-ula-mextul1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit + Router + Agile wifi consolidation | CenturyLink | CL |  | FRO2006829931 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-05-30 | Complete | 2019-11-04 | 2020-08-15 | Complete | 15-Aug: Migration successful. 3-Aug: Migration pushed to August 15th. 17-Jul: Circuit delivered but with low speeds. Will have to do migration separately. 6-Jul: Migration scheduled for July 19th along with the peer circuit migration. Apr-30: Pending cable extensions are run at the site by Unilever. 18-Mar: Migrations in Mexico postponed due to coronavirus outbreak. 30-Jan: It was agreed with Dave and Zoe that there needs to be a country-wide analysis done in Mexico before migrating hub site Tultitlan_Tepalcapa, and then, once we have a strategy, we will schedule the rest of the other migrations in Mexico. 17-Jan: IPT hub site. Can't migrate MPLS until IPT strategy is defined. | Complete | Circuit Migrated | Unilever Geo-IT |  | MX-TTN01-0009 | MEXICO_TULTITLAN_TEPALCAPA |  |  |  |  | Av. Tepalcapa No. 2, Col. Rancho Santo Domingo | Tultitlan | 54900 |  | Karen.Soto | Karen.Soto@unilever.com | 525513844803 | Karen Soto | Karen.Soto@unilever.com | 150MB150MB | 300 | 19.612 | -99.1569 | 2019 | Oct | MPLS | Assumed Monthly | Commercial Benefit | 1 | Resilience | SC2 | [5 empty] | /29 | Head office for the Mexico business. Circa 700 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. |  | LAN: 64.213.167.128/29 WAN: 64.209.8.228/30 CTL: 64.209.8.229 UNI: 64.209.8.230 | 64.209.8.229 | 64.209.8.230 | 64.213.167.128/29 | [8 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Complex site type - requires redesign |  |  | No |  |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  |  |  | 112047 | CRQ000000699270 | Approved |  | CRQ000000692172 | Completed | Completed | Tested-Pass | Jul-26: Circuit test results delievered by CTL accepted by Welington. Jul-16: Tested the circuit with fiber from modem to router and could not reach the ISP. |  | Circuit Migrated - First Time right
CKT-I-01-NI-MGA01-0001-CTL-1 | I0110666CTL1 | 1 | Yes | High | Latin America | Nicaragua | Head Office & CNd, Managua Nic | 2019_563 | un-ula-nicman1-rtr001 | un-ula-nicman1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006829196 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-01-29 | Complete | 2019-11-04 | 2020-03-07 | Complete | Mar-7: Circuit successfully migrated. Feb-28: GeoIT asked to migrate this circuit ASAP as urgent due to issues with the current circuit. Jan-30: Circuit is now delivered. GeoIT will look for migration date after circuit testing. | Complete | Circuit Migrated |  |  | NI-MGA01-0001 | NICARAGUA_MANAGUA_NEWHOME |  |  |  |  | Km 10.5 Carretera Nueva A León | Sandino | NA |  | Luis.Rubio | Luis.Rubio@unilever.com | +57 1 4239727 | Luis.Rubio | Luis.Rubio@unilever.com | 10000Kbps | 20 | 12.1505 | -86.3359 | 2019 | Nov | MPLS | Assumed Monthly | Commercial Benefit | 1 | Resilience | SC2 |  | 8AM local |  |  |  | /30 |  |  | WAN: 64.210.19.68/30 CTL: 64.210.19.69 UNI: 64.210.19.70 | 64.210.19.69/30 | 64.210.19.70/30 | [9 empty] | Sandor Jardon Vera | Hugo Trejo | Hugo Trejo |  |  | Standard site type - Hybrid (MPLS + IEN) | Complete |  | No | No | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 14hrs UTC | 8AM local | 45219 | CRQ000000648454 | Approved | 41436 | CRQ000000645136 | Completed | Completed | Tested-Pass | Feb 17th CTL escalated the issue with local vendor |  | Circuit Migrated - First Time right |  |  |  |  | 2020-03-01
CKT-I-01-PA-PTY04-0001-GTT-1 | I0110116GTT1 | 1 |  | High | Latin America | Panama | Panamá Ofcs Order Factory TDLA | 2019_566 | un-ula-panpan1-drt001 | un-ula-panpan1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01689458 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-09-05 | Complete | 2019-10-28 | 2020-01-29 | Complete | 2019-11-11 | 2020-05-07 | Complete | May-7: Circuit successfully migrated. Apr-30: Pending final circuit testing with a non-Unilever laptop on May 4th. Apr-27: Migration pushed to one hour later (9AM). Apr-23: GeoIT asked to migrate on May 7th at 8AM local time. Mar-19: Pending circuit testing and migration. Jan-30: Circuit is now delivered. GeoIT will look for migration date after circuit testing. 27/11 This site is on hold at the moment. Awaiting further details from Deepak on the site's status. 20-Nov: Pending confirmation on FOC date. | Complete | Circuit Migrated |  |  | PA-PTY04-0001 | PANAMA_CIUDAD_DE_PANAMA_ORDER_FACTORY |  |  |  |  | Torres de las Américas / Torre C /Piso 32 /Ave. Punta Darien / Punta Pacífica | Ciudad De Panama | NA |  | Luis.Rubio | Luis.Rubio@unilever.com | +57 1 4239727 | Luis.Rubio | Luis.Rubio@unilever.com | 24Mb | 50 | 8.9829 | -79.5092 | 2019 | Oct | MPLS | 2017-02-27 | Commercial Benefit | 1 | Resilience | SC2 |  | 8AM |  |  |  | /30 |  | 32nd Floor, URSP Building, Computer Centre. | 38.87.208.102/30 Network - 38.87.208.100 First usable - 38.87.208.101 Last usable - 38.87.208.102 Broadcast - 38.87.208.103 Subnet Mask - 255.255.255.252 | 38.87.208.101 | 38.87.208.102 | 38.87.208.100/30 |  |  | GOLD DATA | Local ISP | AS 28007 |  |  |  | Emir Jukovic | Emir Jukovic | Emir Jukovic |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO | Yes |  | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 14:00 | 9AM | 62494 | CRQ000000667657 | Approved | 42683 | CRQ000000667167 | Completed | Completed | Tested -Pass-First Time | April 13th, BW is asymmetric., we were expecting 50/50 Mb. GTT reviewed with last mile provider, restes on April 17th. last mile provider Gold Data on site to troubleshooting. Unilever laptop still showing BW dicrepances while external laptop showing proper BW. GD states that Zscaler firewall its affecting speed test. May 4th, we use a UL laptop with different configurations and we got better speed test results, also testes with external laptop (provider) and got the same results, all agreed to move forward to migration activities |  | Circuit Migrated - First Time right |  |  |  |  | 2020-05-01
CKT-I-01-PY-ASU01-0001-CTL-1 | I0112023CTL1 | 1 | Yes | High | Latin America | Paraguay | Asunción Head Office | 2019_567 | un-ula-pryasu1-drt001 | un-ula-pryasu1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006829272 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2019-12-13 | Complete | 2019-11-04 | 2020-01-17 | Complete | 17-Jan: Migration successful. IPT works over DMVPN. There is an issue with outgoing calls that cannot be established. Issue needs to be reviewed and resolved in the week after migration. 16-Jan: It was agreed that we will continue with the plan and do the migration for this site on Jan-17, and test that IPT works over DMVPN. Still pending SR with BT; will have to cancel migration if SR is not raised in time. 14-Jan. IPT site. UNL to confirm if we can proceed with this migration or if we need to reschedule until we've completed the strategy for moving the IPT traffic from MPLS to DMVPN. 19-Dec: Migration date approved to Jan-17 at 13hrs. 15-Nov: Migration date pushed due to high probability of circuit not delivered on time. Will review date once CL provides an update. 14-Nov: Circuit delivery might be delay due to possible vendor change. 13-Nov: Site approved migration date of Dec-6 starting 1PM. 8-Nov: Geo IT Team to confirm date and time in the afternoon | Complete | Circuit Migrated |  |  | PY-ASU01-0001 | PARAGUAY_ASUNCION_H.O. |  |  |  |  | Calle Roque Centurion Miranda C/ San Martin | Asunción | 1749 |  | Miguel Samaniego /Ricardo Caldés | Miguel.samaniego@unilever.com ; Ricardo.caldes@unilever.com | +595971900700 | Ricardo Caldes | Ricardo.caldes@unilever.com | 5000Kbps | 40 | 25.2858 | 57.5787 | 2019 | Oct | MPLS | 2019-08-07 | Commercial Benefit | 2 | 0 | SC2 |  | 1PM |  |  |  | /30 |  |  | WAN: 170.83.240.48/30 CTL: 170.83.240.49 UNI: 170.83.240.50 | 170.83.240.49 | 170.83.240.50 | NA | [8 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos | 2020-01-20 |  | Standard site type - Hybrid (MPLS + IEN) | Complete | NO | Yes | No | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  |  | 1PM | 23937 | CRQ000000632321 | Approved | 40072 | CRQ000000623852 | Completed | Completed | Tested -Pass-First Time |  | Miguel Samaniego | Circuit Migrated - First Time right | IPT issue with outgoing calls. |  |  | 2019-12-01 | 2020-01-01
CKT-I-01-PY-VLL02-0001-CTL-1 | I0120189CTL1 | 1 | Yes | High | Latin America | Paraguay | CD Villeta | 2019_569 | un-ula-pryvil1-pio001 | un-ula-pryvil1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006829526 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2019-12-13 | Complete | 2019-11-04 | 2020-01-18 | Complete | Jan 31: GeoIT Manager still trying to agree on a maintenance window to migrate the MPLS circuit. Jan 20: Due to wrong mapping of circuits against routers in one of our trackers, we migrated the Internet circuit instead of the MPLS circuit. Will need to go back to the site and migrate the MPLS circuit with the old Internet circuit (and convert to DMVPN). Jan 19: Migration successful. All services up and running after migration, except for a doc share server in Asuncion. Welington agreed to consider the migration successful, and get the issue with the server fixed separately. Jan 14: RFC raised with incorrect time and dates. CMS CM already modified the date and asked UNL CM to move the RFC back to approval phase. Jan 8: Geo IT and site asked to schedule this migration for January 18th at 9AM. Welington approves and is aware of the risks of scheduling with this short notice. | Complete | Circuit Migrated |  |  | PY-VLL02-0001 | PARAGUAY_VILLETA |  |  |  |  | Ruta Ypane-Villeta Km 3,5., Abay | Villeta | 2680 |  | Miguel Samaniego /Ricardo Caldés | Miguel.samaniego@unilever.com ; Ricardo.caldes@unilever.com | +595971900700 | Ricardo Caldes | Ricardo.caldes@unilever.com | 25MB | 30 | 25.4964 | 57.5434 | 2019 | Oct | MPLS | 2019-07-07 | Commercial Benefit | 2 | 0 | SC2 |  | 9AM |  |  |  | /30 |  |  | WAN: 170.83.240.84/30 CTL: 170.83.240.85 UNI: 170.83.240.86 | 170.83.240.85 | 170.83.240.86 | NA | [8 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | 2020-01-20 |  | Standard site type - Hybrid (MPLS + IEN) | Complete | NO | Yes | No | No | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  |  | 9AM | 25941 (Migration) 26015 (Alarm suppression) | CRQ000000633318 | Approved | 40799/41662 | CRQ000000632212/CRQ000000651486 | Completed | Completed | Tested -Pass-First Time |  | Miguel Samaniego | Circuit Migrated - First Time right |  |  |  |  | 2020-01-01
CKT-I-01-PE-LIM04-0001-CTL-1 | I0111059CTL1 | 1 | Yes. Login via telnet and local credentials. Very slow connection. Gig 0/0/1 configured with CTL IP (50M, but admin shutdown. Se 1/0/0.101 currently used for BT GMPLS and active - 12M, FR interface. No nat pools configured as of now. Migration attempted already. Issues and rolled back. | High | Latin America | Peru | Miraflores | 2019_573 | un-ula-permir1-rtr001 | un-ula-permir1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | FRO2006829189 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2019-11-08 | Complete | 2019-11-04 | 2020-02-21 | Complete | 21-Feb: Circuit successfully migrated. 18-Dec: Migration approved for 21-Feb 2020 at 13hrs. 13-Dec: On the second migration attempt the same issues as before were present. Internet traffic was not allowed in the MPLS router. We believe the cause of this is some configuration in the core switch is preventing this type of traffic. 6-Dec: First migration attempt failed for unknown issues. By the time the engineer realized of the issue, it was too late to rollback, so all of the traffic (both coporate and internet) was sent to the Internet router. MPLS router was left with no traffic, so the redundancy was lost. 27-Nov: Migration re-scheduled for 6-Dec (same time as before) to allow for circuit testing/activation on 4-Dec with CenturyLink support. 22-Nov: Circuit testing failed. Migration needs to be re-scheduled. Tentatively to 29-Nov. 13-Nov: Site approved migration date of Nov-22 starting 1PM. STILL DEPENDING ON ALGOSEC & ZSCALER REQUESTS. 8-Nov: Geo IT to confirm 22-Nov migration date and time | Complete | Circuit Migrated |  |  | PE-LIM04-0001 | Peru_Miraflores |  |  |  |  | Av. Paseo de la Republica 5895 Edificio Leuro 4to piso, Miraflores Lima | Lima | Lima18 |  | Miguel Lister | Miguel.lister@unilever.com | Work+ 51 1 4111667 / Mobile+51 993520248 | Ricardo Caldes | Ricardo.caldes@unilever.com | 12Mbps | 50 |  |  | 2019 | Nov | MPLS | 2019-05-25 | Commercial Benefit | 1 | 0 | SC2 |  | 1PM | CSRT coverage (insurance) | Yes |  | /30 |  | 4th Floor , Computer Center | WAN: 67.73.169.164/30 CTL: 67.73.169.165/30 UNI: 67.73.169.166/30 | 67.73.169.165/30 | 67.73.169.166/30 | NA | [8 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos | 2020-02-24 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO | Yes | No |  | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 6:00 PM | 1:00 PM | 39736 | CRQ000000642549 CRQ000000627384 (old) | Approved | 40074 | CRQ000000620297 | Completed | Completed | Tested-Pass | Testing again on Dec 4th and it was successful. Testing failed on 22 Nov and migration had to be cancelled at last minute. | Miguel Lister | Circuit Migrated | Core switch changes were required for successful migration. |  |  | 2019-11-01 | 2019-12-01
CKT-I-02-PE-LIM04-0001-PCCW-1 | I0211059PCCW1 | 1 | Yes | High | Latin America | Peru | Miraflores | 2019_574 | un-ula-permir1-vpn001 | un-ula-permir1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | PCCW | PCCW |  | LIM(BRD) GI006242 | 2019-08-19 | 2019-09-03 | Complete | 2019-08-26 | 2019-09-18 | Complete | 2019-11-04 | 2019-11-28 | Complete | 2019-11-18 | 2020-02-07 | Complete | 7-Feb: Circuit successfully migrated. 18-Dec: Migration approved for 7-Feb 2020 at 13hrs. 13- Dec: Migration of this circuit depends on the discussions regarding the failed migration of the MPLS circuit (the other link in the site) today. 5-Dec: Circuit already delivered. Site contact will be on PTO from Dec 22 to February 3rd. Trying to get the migration pulled into December. | Complete | Circuit Migrated |  |  | PE-LIM04-0001 | Peru_Miraflores |  |  |  |  | Av. Paseo de la Republica 5895 Edificio Leuro 4to piso, Miraflores Lima | Lima | 15047 |  | Miguel Lister | Miguel.lister@unilever.com | Work+ 51 1 4111667 / Mobile+51 993520248 | Ricardo Caldes | Ricardo.caldes@unilever.com | 30MB30MB | 50 |  |  | 2019 | Nov | Internet | 2019-08-28 | Commercial Benefit | 1 | Congested link | SC2 |  | 1PM | CSRT coverage (insurance) | Yes |  | /30 |  | 4th Floor , Computer Center | Public IP Range: 161.132.180.144/29 Gateway: 161.132.180.145 Free Usable IP(s): 161.132.180.146-150 Broadcast IP: 161.132.180.151 Subnet Mask: 255.255.255.248 DNS1: 161.132.5.133 DNS2: 161.132.1.133 | 161.132.180.145/29 | 161.132.180.150/29 | NA |  |  | Brodynt | [5 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos | 2020-02-10 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO | Yes | No |  | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 6:00 PM | 1:00 PM | 31292 | CRQ000000637734 CRQ000000627864 (old) | Approved | 40579 | CRQ000000625489 | Completed | Completed | Tested -Pass-First Time |  | Miguel Lister | Circuit Migrated - First Time right |  |  |  | 2019-12-01 | 2020-02-01
CKT-I-01-TT-CHF01-0001-GTT-1 | I012027GTT1 | 1 | Yes. Other router on site - un-ula-ttopos1-vpn001 - 19M,/28 LAN, /30 WAN, ISR4331. | High | Latin America | Trinidad and Tobago | Champs Fleurs - Corporate | 2019_652 | un-ula-ttopor1-rtr001 | un-ula-ttopos1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | GTT | GTT |  | " DIA/01703554" | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-20 | Complete | 2019-10-28 | 2019-10-17 | Complete | 2019-11-11 | 2020-05-03 | Complete | 3-May: Circuit successfully migrated. 23-Apr: Migration approved for May 3rd after NTT informed us of their availability on this date. GeoIT has approved. 17-Apr: Migration cancelled due to unavailability of field engineer. 8-Apr: Geo IT asked to migrate on April 18th (still to be confirmed, but Welington asked us to proceed as if it was confirmed). 3-Apr: Migration still on-hold until Covid-19 situation improves. 18-Mar: Migrations in the Caribbean postponed indefinitely due to coronavirus. 13-Mar: Migration postponed due to lack of confirmation from GeoIT, since they are still waiting on country-specific directions regarding the coronavirus threat response. 9-Mar: Migration planned for March 18th. Pending final approval from GeoIT. 31-Jan: Still waiting on the successful results in the IPT fix in Asuncion to get this migration re-scheduled. 24-Jan: IPT issue seems that it will not be an issue after all, since voice traffic goes to Trumbull, where there is DMVPN now. Will wait for the results in the IPT fix for Asuncion, and if successful, will replicate here. 16-Jan: Welington confirmed that the migration has to be rescheduled due to the IPT issue. Will agree on a migration date with GeoIT once we have a clear solution or workaround. 14-Jan. IPT site. UNL to confirm today if we can proceed with this migration or if we need to reschedule until we've completed the strategy for moving the IPT traffic from MPLS to DMVPN. 10-Jan: Migration pushed to 3hrs later: 5PM. 19-Dec: Migration rescheduled for January 16th at 2PM local time. 11-Dec: Migration not approved for Dec-13 since site contact will be out on holiday. Will need to reschedule for January. 6-Dec: During Geo IT meeting the migration date was approved for Dec 13th (instead of the 15th) since no weekend work is allowed in the site. 29-Nov: Pending confirmation from Geo IT that 15-Dec has been approved for circuit migration date. This confirmation will be provided on Dec-4th. 21-Nov: Confirmation that circuit was in fact already delivered. 8-Nov: According to the site circuit appears to not be delivered yet. Need to push migration for mid-December. Could bring back to earlier date if installation status is resolved. 31/10 Letter of start of service delivered 17 Oct. | Complete | Circuit Migrated |  |  | TT-CHF01-0001 | TRINIDAD_AND_TOBAGO_PORT_OF_SPAIN_EASTERN_MAIN_ROAD |  |  |  |  | Eastern Main Road P.O. Box 295 | Port Of Spain | 150123 |  | Kimberly.Yee-Ken | Kimberly.Yee-Ken@unilever.com | T: +1(868) 663-1787 ext.2000 M: +1(868) 280-3087 |  |  | 14MB | 50 | 10.6509 | -61.4277 | 2019 | Oct | MPLS | 2018-08-15 | Commercial Benefit | 1 | Congested Link | SC2 |  | 5PM |  |  |  | /30 |  | 2nd floor, IT Room, Unilever Administrative building | 190.58.0.200/30 WAN Network - 190.58.0.200 First usable - 190.58.0.201 Last usable - 190.58.0.202 Broadcast - 190.58.0.203 Subnet Mask - 255.255.255.252 190.58.0.208/29 LAN Network - 190.58.0.208 First usable - 190.58.0.209 Last usable - 190.58.0.214 Broadcast - 190.58.0.215 Subnet Mask - 255.255.255.248 | 190.58.0.201/30 | 190.58.0.202/30 | 190.58.0.209/29-190.58.0.214/29 |  |  | Comsol | Local ISP | 0 |  |  |  | Hugo Trejo | Hugo Trejo | Hugo Trejo |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  |  | No |  | Yes-Onboarding file created for CMS | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 13hrs | 9AM | 18964 | CRQ000000626812 | Approved | 39770 | CRQ000000624317 | Completed | Completed | Tested -Pass-First Time | Tested the circuit on Dec 11th with no issues. | Kimberly Yee-Ken | Circuit Migrated - First Time right |  |  |  | 2019-10-01 | 2019-12-01
CKT-I-01-UY-MVD01-0001-PCCW-1 | I0120069PCCW1 | 1 | Yes | Top | Latin America | Uruguay | Montevideo DC | 2019_759 | un-ula-urycam1-pio001 | un-ula-urycam1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit + Switch | PCCW | PCCW |  | MVD(BRD) GI006295 | 2019-08-19 | 2019-09-03 | Complete | 2019-08-26 | 2019-09-18 | Complete | 2019-11-04 | 2020-01-27 | Complete | 2019-11-18 | 2020-06-06 | Complete | 6-Jun: Migration successfully completed. 1-Jun: Start time changed to 15hrs. 28-May: Only circuit migration will be done on June 6th. 15-May: Migration planned for June 6th. Pending definition of activities on site + LAN changes. 8-May: Pending restrictions at the site to be lifted to schedule migration. 19-Mar: Pending confirmation from Welington on what change needs to be done in the migration. 31-Jan: Clarification that this circuit is not in the same site as in the circuit with RFP_REF 2019_758. Need to check pending SR with BT for switch installation, and after this, we will migrate circuit. 12-Dec: Need to get clarification on the topology, since the diagram doesn't match the configuration. | Complete | Circuit Migrated | Cisco |  | UY-MVD01-0001 | URUGUAY_MONTEVIDEO_DC |  |  |  |  | Camino Bajo de la Petisa 5205 12800 | Montevideo | 12800 |  | Mauro Repetto | Mauro.repetto@unilever.com | 59895685241 | Ricardo Caldes | Ricardo.caldes@unilever.com | 10000Kbps | 25 | -34.8195 | -56.0687 | 2019 | Nov | MPLS | 2019-07-09 | Commercial Benefit | 2 | 0 | SC2 | [5 empty] | /30 |  |  | Public IP Range 190.0.145.1/27 DNS1 200.40.30.245 DNS2 200.40.220.245 | 190.0.145.2 | 190.0.145.3 | 190.0.145.1 - 190.0.145.30 |  |  | Brodynt | [5 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Standard site type - Hybrid (DMVPN + IEN) | Complete | NO |  | No | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 18hrs | 15hrs | 71475 | CRQ000000677775 | Approved |  | CRQ000000677575 | Completed | Completed | Tested -Pass-First Time | First action in migration window |  | Circuit Migrated - First Time right |  |  |  |  | 2020-06-01
CKT-I-01-UY-MVD01-0001-ORA-1 | I01943ORA1 | 1 | Yes | High | Latin America | Uruguay | Montevideo HO | 2019_758 | un-ula-urymon1-rtr001 | un-ula-urymon1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit + Router + DMVPN conversion | Orange | Ora |  | LO0048WN4E | 2019-08-19 | 2019-09-13 | Complete | 2019-08-26 | 2019-10-15 | Complete | 2019-11-04 | 2019-11-11 | Complete | 2019-11-18 | 2020-03-21 | Complete | 8-Jul: 22-May: RAVB to DMVPN router upgrade successul. Failover corrected. 22-May: RAVB to DMVPN router upgrade failed. Algosec request raised with incorrect IPs. Will need to reschedule. 19-Mar: RAVB to DMVPN conversion on already migrated circuit to fix Internet redundancy scheduled for May 22. 13-Mar: Migration scheduled for March 21. NIM card not needed for this migration (but will need it for 2nd circuit migration). 9-Mar:Migration pending delivery of NIM Card. 6-Mar: GeoIT approved migration on March 19th. 31-Jan: Clarification that this circuit is not in the same site as in the circuit with RFP_REF 2019_758. Need to check pending SR with BT for switch installation, and after this, we will migrate circuit. 12-Dec: Need to get clarification on the topology, since the diagram doesn't match the configuration. 5-Dec: Had a discussion with UNL Design Team. Need to further analize topology and feedback. 29-Nov: IP info has just been provided. Pushed to January, but might be pulled into December if AlgoSec and Zscaler can be implemented before freeze, and design questions are resolved in time for CMSP ticket. 27-Nov: Need additional design discussions about the site before having MOP ready. Tentative migration date of 20-Dec; will need to push to January if MOP is not defined by 6-Dec. 12-Nov: Physical circuitt for Montevideo has been delivered, awaiting for Carrier testing completion and hand over of Certificate. | Complete | Circuit Migrated |  |  | UY-MVD01-0001 | URUGUAY_MONTEVIDEO |  |  |  |  | Camino Carrasco 5975 | Montevideo | 12100 |  | Mauro Repetto | Mauro.repetto@unilever.com | 59895685241 | Ricardo Caldes | Ricardo.caldes@unilever.com | 100MB90MB2000Kbps2000Kbps2000Kbps6000Kbps | 30 | -34.8195 | -56.0687 | 2019 | Nov | MPLS | 2019-11-18 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  |  | IPs Cliente 179.27.183.224 Máscara 255.255.255.224 Gateway 179.27.183.225 Menor IP Cliente 179.27.183.226 Mayor IP Cliente 179.27.183.254 DNS 1 200.40.30.245 DNS 2 200.40.220.245 | 179.27.183.225 | 179.27.183.226 | 179.27.183.227-179.27.183.254 |  |  | ANTEL |  |  | Yes |  |  | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  | Copper - RJ45 | Complex site type - requires redesign | Complete | NIM-1GE-CU-SFP | Yes | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 12hrs | 9AM | 48412 | CRQ000000653437 | Approved | 40929/41663 | CRQ000000636116/CRQ000000651747/CRQ000000677357 | Completed | Completed | Tested -Pass-First Time | March 4th first time |  | Circuit Migrated - First Time right |  |  |  |  | 2020-01-01
CKT-I-01-DZ-ALG02-0089-VOD-1 | I012134VOD1 | 1 | Not able to access the device. via Telnet/ssh not able to ping. | Medium | NAME | ALGERIA | Algiers Office | 2018_2 | un-amt-dzaalg-vpn001 |  | Eloise Shepheard | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQM-00007 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-01-08 | Complete | 2019-11-18 | 2020-06-01 | Complete | 02/06: Migration was successful - both WAN and CMS parts 29/05 Migration scheduled for 01/06. Everything is ready for Monday. 08/05 Router delivered onsite. A meeting to be arranged UL GeoIT/CMS/Cisco project team to discuss next steps. Cisco project team would like to complete router installation and link migration within one day. 27/04 Router HW issue. Incident raised with CMS. 21/04 Migration agreed for 27 Apr. - this is when the FE was arranged for. VOD confirmed they will also provide a stand-by support - this is critical for testing, since there was no opportunity to perform circuit testing prior the migration - there is no tech people onsite. 14/01 No access to vpn001 router. Working with CMS to resolve this issue. 08/01 Circuit has been delivered. Testing to be arranged. 12/12 Order is in progress. Order is in the deployment phase and may be delayed to January. The delay is due to the diversity requirement and last mile provider is currently studying availability of an alternative backhaul link between customer location and their POP. 04/12 Order is placed on hold as requested by Unilever due to local requirements for internal cabling. On-hold period to expire on 20th December. | Complete | Circuit Migrated | Cisco |  | DZ-ALG02-0089 | ALGERIA_ALGIERS_89 RUE DES TROIS FRERES DJILLALI_ALGIERS OFFICE |  |  |  |  | ABC Tour, hôtel Hilton pins maritimes- el Mohammadia- Alger | Algiers | 16330 |  | Azzedine Kebbati | Azzedine.Kebbati@Unilever.com | +213770979007 | Dees Rampartab | Dees.Rampartab@unilever.com | 15Mbps | 15 | 36°44'15.36" | 3°9'17.28" | 2019 | Nov | Internet | Assumed Monthly | Commercial Benefit |  |  | SC2 | FE needs to bring console cable and USB. | 08:45-16:45 local time | NA | NA | NA | /30 |  |  | Primary DNS 196.41.246.210 Secondary DNS 196.41.225.210 Static 197.140.14.72 255.255.255.248 Additional /29 subnet routed to 197.140.14.82 Static 197.140.14.80 255.255.255.252 Network Address Static 197.140.14.81 255.255.255.252 LAN IP / Default gateway Static 197.140.14.82 255.255.255.252 IP free to use Static 197.140.14.83 255.255.255.252 Broadcast Address Lan IP Address Lan Interface 197.140.14.81 FastEthernet 100BaseT | 197.140.14.81 | 197.140.14.82 | 197.140.14.72/29 |  |  | Icosnet | [5 empty] | Rahul Durugkar | Rajesh Dagde | Rajesh Dagde | 2020-06-02 |  | Standard site type - Dual DMVPN |  |  |  | Yes |  |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression SSR approved |  |  | 07:45-15:45 UTC | 08:45-16:45 local time | 60204 New CMSP 69995 | CRQ000000664267 | Approved | 41810 | CRQ000000654644 | Completed | Completed |  |  | Azzedine Kebbati | Circuit - Failed Go Live | Router HW issue |  |  | 2019-12-01 | 2020-04-01
CKT-I-02-DZ-ALG02-0089-VOD-1 | I022134VOD1 | 1 | Yes | Medium | NAME | ALGERIA | Algiers Office | 2018_1 | un-amt-dzaalg-vpn002 |  | Agnieszka Pajak | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIPX-IPQM-00006 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2019-12-04 | Complete | 2019-11-18 | 2020-04-27 | Complete | 21/04 Migration agreed for 27 Apr. - this is when the FE was arranged for. VOD confirmed they will also provide a stand-by support - this is critical for testing, since there was no opportunity to perform circuit testing prior the migration - there is no tech people onsite. 20/01 No access to router vpn-001 19/12 Incorrect design provided by Expereo. This has been escalated and a discussion with Expereo on a way forward to take place today. This has an impact on the migration date as we are not able to move forward with any activity unless a new design is provided to Cisco. 12/12 Incomplete IP address provided | Complete | Circuit Migrated |  |  | DZ-ALG02-0089 | ALGERIA_ALGIERS_89 RUE DES TROIS FRERES DJILLALI_ALGIERS OFFICE |  |  |  |  | ABC Tour, hôtel Hilton pins maritimes- el Mohammadia- Alger | Algiers | 16330 |  | Azzedine Kebbati | Azzedine.Kebbati@Unilever.com | +213770979007 | Dees Rampartab | Dees.Rampartab@unilever.com | 15MB | 15 | 36°44'15.36" | 3°9'17.28" | 2019 | Nov | Internet | Assumed Monthly | Commercial Benefit |  |  | SC2 | No tech resource onsite. | 0800-1400 local time | NA | NA | NA | /30 |  |  | Primary DNS 196.41.246.210 Secondary DNS 196.41.225.210 Static 197.140.14.84 255.255.255.252 Network Address Static 197.140.14.85 255.255.255.252 Default gateway for Customer Static 197.140.14.86 255.255.255.252 IP free to use Static 197.140.14.87 255.255.255.252 Broadcast Address Static 197.140.14.64 255.255.255.248 Additional /29 Routed to 197.140.14.86 Lan IP Address Lan Interface 197.140.14.85 FastEthernet 100BaseT | 197.140.14.85 | 197.140.14.86 | 197.140.14.64/29 |  |  | Icosnet | [5 empty] | Rahul Durugkar | Rajesh Dagde | Rajesh Dagde | 2020-04-28 |  | Standard site type - Dual DMVPN | [6 empty] | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression | Window Date agreed - End user Comms sent |  | 0800-1401 | 0800-1401 | 60204 | CRQ000000664267 | Approved | 41809 | CRQ000000654483 | Completed | Completed |  |  | Azzedine Kebbati | Circuit Migrated - First Time right | NA | NA | NA | 2019-12-01
CKT-I-01-BH-MAN01-0161-GTT-1 | I011205GTT1 | 1 | Yes | Medium | NAME | BAHRAIN | UNILEVER_BAHRAIN | 2018_30 | un-amt-bhrman-vpn001 | un-amt-bhrman-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01689388 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-21 | Complete | 2019-10-28 | 2019-12-18 | Complete | 2019-11-11 | 2020-01-24 | Complete | 24/01 Like for like migration successful 20/01 End user comms shared by local team and attached to RFC. RFC to be reviewed during CAB on 23 Jan 17/01 Pending: RFC approval - missing local user comms 08/01 Date and time for the migration confirmed with the customer. There are no site access requirements. 10/12 GTT waiting the Vendor to complete the delivery and to send us the Handover by Thursday 12th of December. 08/12 Local provider confirmed the end customer doesn`t now need to complete internal wiring; tentative RFS date 02/12. 27/11 Pending update from the provider on the status of the order. 18/11 Pending completion of the internal cabling. Lyuben the GTT service delivery coordinator is working with Maksud Hussain and the Vendor in order to finish this wiring and he is waiting for confirmation when this will be completed. 24/10 Estimated vendor handover 8 Nov | Complete | Circuit Migrated |  |  | BH-MAN01-0161 | BAHRAIN_MANAMA_UNILEVER_BAHRAIN |  |  |  |  | 161, Sh Salman Highway, Block number 358, Bldg # 1 | Manama | 1274 |  | Lakis,Maksud | Lakis.Dharmarajan@unilever.com,Maksud.hussain@unilever.com | 973 17253252 Ext. 144, Mob: 973 66309594 | Lakis Maksud |  | 8000Kbps | 8 | 26.2143 | 50.5807 | 2019 | Nov | Internet | Assumed Monthly | Commercial Benefit |  |  | SC4 | NA | 900 - 1500 local time | NA | NA | NA | /30 |  | Ground Floor, Bulding 161. Ground Floor Comms Room | 80.95.221.192/29 Network - 80.95.221.192 First usable - 80.95.221.193 Last usable - 80.95.221.198 Broadcast - 80.95.221.199 Subnet Mask - 255.255.255.248 | 80.95.221.193 | 80.95.221.194 | 80.95.221.192/29 |  |  | CMC Networks | Local ISP | TBC |  |  |  | Astrit Kadriu | Astrit Kadriu | Astrit Kadriu | 2020-01-27 |  | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 0600 - 1200 | 0900 - 1500 | 27408 | CRQ000000633493 | Approved | 40665 | CRQ000000632505 | Completed | Completed | Tested -Pass-First Time |  | Lakis Dharmarajan | Circuit Migrated - First Time right | NA | NA | NA |  | 2020-01-01
CKT-I-01-SA-JED02-0001-VOD-1 | I013752VOD1 | 1 | Yes | Medium | NAME | SAUDI ARABIA | Binzagr Unilever Factory | 2018_207 | un-amt-sabzlpio01 | un-amt-sabzlpio-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIAP-IPQM-00007 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2019-12-17 | Complete | 2019-11-18 | 2020-03-20 | Complete | 13/02 Country strategy agreed with the customer. Migration in factory to be scheduled for 10 Mar. Unilever House Jeddah to be targeted for 14 Mar. 20/01 IP address confirmed by the provider. 19/12 Incorrect design provided by Expereo. This has been escalated and a discussion with Expereo on a way forward to take place today. This has an impact on the migration date as we are not able to move forward with any activity unless a new design is provided to Cisco. 12/12 Pending router installation schedule from last mile provider. 9/12 Order is in progress. Telco has confirmed to activate the service by today/ tomorrow. Post service activation our local partner will schedule the router installation for final handover. Next update will be provided on: 16-Dec-2019 26/11 Migration date changed to 20 Dec as per the local contact request 20/11 Migration date confirmed by local GeoIT | Complete | Circuit Migrated |  |  | SA-JED02-0001 | SAUDI_ARABIA_JEDDAH_BINZAGR_UNILEVER_FACTORY |  |  |  |  | P.O. Box 5694, Road No 35, Phase 1 Industrial City | Jeddah | 21432 | Factory | Mohammad Alwan | Mohammad.alwan@unilever.com | 966536669982 | Dees Rampartab | Dees.Rampartab@unilever.com | 30MB | 30 | 21.5187 | 39.1695 | 2019 | Nov | Internet | 2019-07-17 | Commercial Benefit |  |  | SC4 | This service should be delivered using Fiber. Also internet traffic should be routed to Headoffice during outage | 0600-0900 | Safety tools including safety choose, there will be safety training on site that will take around 15 min | NA | NA | /30 |  |  |  | 188.117.122.77 | 188.117.122.78 | 188.117.122.76/30 |  |  | Sahara | [5 empty] | Rahul Durugkar | Adrian Lazar | Adrian Lazar | 2020-03-23 |  | Complex site type - requires redesign |  |  | No |  | No |  |  | Window Date agreed - End user Comms sent |  | 0600-0900 | 0900-1200 | 49564 | CRQ000000653961 CRQ000000649904 | Approved | 41537 | CRQ000000648201 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated | Algosec assigned to the incorrect location | NA | NA |  | 2020-02-01
CKT-I-01-SA-JED01-0001-VOD-1 | I011213VOD1 | 1 | No access to device, unable to ping as well | High | NAME | SAUDI ARABIA | Unilever House Jeddah | 2018_208 | un-amt-sajedu01 | un-amt-saujed-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIAP-IPQM-00008 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2019-12-17 | Complete | 2019-11-18 | 2020-04-21 | Complete | 22/04 Cisco has successfully re-routed the traffic from Jeddah House to Binzagr factory. 21/04 Migration completed successfully. An additional change window required to redirect the traffic from Jeddah house to Binzagr factory - for binzagr users. This is planned for 22 Apr. 06/03 SR 45695 - chasing ETA 05/03 No access to router. HW hasnt been onboarded yet by CMS. CMS created SR and will provide ETA. Until this is completed, no migration can be planned. 19/12 Incorrect design provided by Expereo. This has been escalated and a discussion with Expereo on a way forward to take place today. This has an impact on the migration date as we are not able to move forward with any activity unless a new design is provided to Cisco. 12/12 Pending router installation schedule from last mile provider. 9/12 Order is in progress. Telco has activated the service at the site. This week the local partner will Schedule the router installation for final handover. Next update will be provided on: 16-Dec-2019 26/11 Migration date changed to 16 Dec as per the local contact request 20/11 Migration date confirmed by GeoIT | Complete | Circuit Migrated |  |  | SA-JED01-0001 | SAUDI_ARABIA_JEDDAH_UNILEVER_HOUSE |  |  |  |  | Al-Malik Road, Al-Hosn Building | Jeddah | 21432 | Head Office | Mohammad Alwan | Mohammad.alwan@unilever.com | 966536669982 | Dees Rampartab | Dees.Rampartab@unilever.com | 30Mb | 30 | 21.5187 | 39.1695 | 2019 | Nov | Internet | 2019-10-04 | Commercial Benefit | 1 | Congested Link | SC2 | This service should be delivered using Fiber. Also internet traffic should be routed to Factory during outage | 1200 - 1700 local time | No FE required | NA | NA | /30 |  |  |  | 188.117.122.73 | 188.117.122.74 |  |  |  | Nour Global | [5 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar | 2020-04-22 |  | Complex site type - requires redesign | [7 empty] | Window Date agreed - End user Comms sent |  | 1000-1600 | 1200-1700 | 57939 | CRQ000000663115 CRQ000000664317 - for traffic re-routing from Jeddah House to Binzagr Factory | Approved | 42113 | CRQ000000659869 | Completed | Completed | Tested -Pass-First Time |  | Mohammad Alwan | Circuit Migrated - First Time right | NA | NA | NA | 2019-12-01 | 2020-03-01
CKT-I-01-US-JAX01-0001-GTT-1 | I0110253GTT1 | 1 | Yes | High | North America | United States | Jacksonville | 2019_726 | un-una-usajac1-rtr001 | un-una-usajac1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01710081 | 2019-08-12 | 2019-08-09 | Complete | 2019-08-19 | 2019-09-03 | Complete | 2019-10-28 | 2020-04-30 | Complete | 2019-11-11 | 2020-07-07 | Complete | Jul-7: Migration successful. Jun-9: Migration approved for July 7th at 9AM (pending successful circuit test). May-28: New circuit testing scheduled for Tuesday June 2nd at 9AM. Apr-31: Pending successful circuit testing with a non-Unilever laptop. 04/03: Sy from Unilever confirmed the extension is complete. Level 3 has been informed and asked for a completion date. 26/02: We are still on hold until the LCON confirm the extension is ready. 14-Feb: JDA issues at the site. Migration to be scheduled after circuit delivery. 29-Jan: Migration date approved for February 20th. Pending demarc extension. 17-Jan: Site suggested to be the first JDA site to get circuit migrated. Waiting on approval. 8-Nov: JDA sites migrations not approved until January. | Complete | Circuit Migrated | Cisco |  | US-JAX01-0001 | USA_JACKSONVILLE_PRESIDENTS_COURT |  |  |  |  | 12200 Presidents Ct | Jacksonville | 32220 |  | Sy.Nguyen | Sy.Nguyen@unilever.com | O: 904-378-0298 x2005 C: 904-400-5486 |  |  | 8MB | 30 | 30.3692 | -81.8412 | 2019 | Oct | MPLS | 2018-07-13 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  | Ground floor, Demarc is in the computer room which is located in the main office building. Computer room is ~10' x 10?. Circuits are ~7-8 ft away from racks. | 208.116.197.152/30 Network - 208.116.197.152 First usable - 208.116.197.153 Last usable - 208.116.197.154 Broadcast - 208.116.197.155 Subnet Mask - 255.255.255.252 | 208.116.197.153/30 | 208.116.197.154/30 |  |  |  | L3 | GTT US | AS 3257 |  |  |  | Hugo Trejo | Hugo Trejo | Hugo Trejo |  |  | Standard site type - Hybrid (MPLS + IEN) | Complete |  |  | No |  |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 1PM UTC | 9AM local | CMSP | CRQ000000689255 | Approved | 41086 | CRQ000000639955 | Completed | Completed | Tested-Pass | Jun-23: Circuit now working as expected. Could not get a connection. Asked GTT to look into issue.pending of vendor feedback. GTT got feedback issue was fixed. 2nd test on April 28th, iPerf performed with GTT, we got connectivity, BW is what we expected, but we see some packet loss. GTT stated that Zscaler need to be complety disable as is affecting results |  | Circuit Migrated - First Time right |  |  |  |  | 2020-02-01
CKT-I-02-US-JAX01-0001-CTL-1 | I0210253CTL1 | 1 | Yes | High | North America | United States | Jacksonville | 2019_725 | un-una-usajac1-pio001 | un-una-usajac1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | 441616262 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-02-12 | Complete | 2019-11-04 | 2020-04-02 | Complete | 02-Apr: Migration successful. 27-Mar: Rescheduled to April 2nd at 10AM EST. 25-Mar: Circuit migration failed. Rescheduled for April 1st. 19-Mar: Circuit testing on March 20th. Migration on March 25th. 04-Mar: Sy from Unilever confirmed the extension is complete. 14-Feb: JDA issues at the site. Migration pushed until April. 29-Jan: Pending demarc extension. Migration date to be approved once we get FOC date. 8-Nov: JDA sites migrations not approved until January. | Complete | Circuit Migrated |  |  | US-JAX01-0001 | USA_JACKSONVILLE_PRESIDENTS_COURT |  |  |  |  | 12200 Presidents Ct | Jacksonville | 32220 |  | Sy.Nguyen | Sy.Nguyen@unilever.com | O: 904-378-0298 x2005 C: 904-400-5486 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 8000Kbps | 30 | 30.3692 | -81.8412 | 2019 | Nov | Internet | 2018-12-31 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  |  | WAN: 4.59.8.140/30 CTL: 4.59.8.141/30 UNI: 4.59.8.142/30 | 4.59.8.141/30 | 4.59.8.142/30 | 4.53.233.161/29-4.53.233.166/29 | [8 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo |  |  |  | Complete | [5 empty] | Assessment Complete MOP created & config created | Window Date agreed - End user Comms sent |  | 14:00 | 10AM local | 52356 51313 (old) | CRQ000000656170 CRQ000000655516 (old) | Approved | 41430 | CRQ000000644983 | Completed | Completed | Tested-Pass | Status Pending:Test passed, Speed test 20 MB on March 20th. New test on March 25th, Speed test of 10 MB. March 27, test results ok, CTL found a mis-matched duplex setting with their local provider, which was corrected |  | Circuit Migrated | Incorrect circuit connection (most likely), or router port failure (less likely). |  |  | 2020-01-01 | 2020-04-01
CKT-I-01-US-AAH01-0001-CTL-1 | I012130CTL1 | 1 | Yes | High | North America | United States | Covington | 2019_710 | un-una-usacov1-rtr001 | un-una-usacov1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | 441616749 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-08-29 | Complete | 2019-10-21 | 2020-01-31 | Complete | 2019-11-04 | 2020-09-10 | Complete | 10-Sep: Migration successful. 24-Aug: Migration approved on September 10th 8AM Eastern. 10-Aug: Migration on Sep 7 TBC 3-Aug: Migration still to be confirmed for September. 30-Jul: Migration date to be confirmed. 3-Jul: We tested the circuit again with remote support from CTL and could still not get a connection. Seems a misconfiguration on their core network. They will investigate and get back to us. Migration has to be postponed. 30-Jun: We tested the circuit but were not able to get a connection. Will test again with CTL on July 3rd at 11AM EST: 8-Jun: Migration confirmed on July 4th at 9AM. Circuit testing on June 24/25. 30-Apr: Pending GeoIT to complete demark extension and to agree on a migration date (site does not have downtime until July 4th). 7-Apr: Migration postponed until further notice. 3-Apr: Migration might need to be postponed. Debbie to confirm next week. 5-Mar: From GeoIT: Covington cutover on Saturday, April 11th starting at 7am CST. 31-Jan: CenturyLink has confirmed the new IPs are now provisioned with the circuit. GeoIT manager is looking for a migration date. 19-Dec: CenturyLink can't confirm yet the date on when the additional NAT pool will be ready. Pushing migration until February. Will look to bring up to January if CL responds by end of 2019. 27-Nov: Pushed to January per Geo IT Team. 21-Nov: During detailed assessment it was discovered that an additional NAT pool is required. Provider has already been informed. Migration date of Dec-20 tentative; to discuss with GEO IT. 19-Nov: Geo IT can't confirm migration date yet. Have to push tentatively to 6-Dec. 15-Nov: Geo IT Team to get confirm date ASAP. 8-Nov: Date of 29-Nov still not confirmed. Currently it is provisional until site confirms it or advises of new date. Date of 29/11 or 30/11 requested by Geo IT Team. Migration Date Requested to Geo IT Teams. | Complete | Circuit Migrated | Cisco |  | US-AAH01-0001 | USA_COVINGTON_HIGHWAY_51_NORTH |  |  |  |  | 2000 Highway 51 North | Covington (US-TN) | 38019 |  | Alwin.Davis | Alwin.Davis@unilever.com | (M)- 901-616-7174 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 50MB50MB | 50 | 35.6109 | -89.6287 | 2019 | Nov | MPLS | 2018-06-12 | Commercial Benefit | 1 | 0 | SC2 |  | 7AM CST |  |  |  | /30 |  |  | LAN: 4.30.79.180/30 WAN: 4.49.84.104/30 CTL: 4.49.84.105 Uni: 4.49.84.106 | 4.49.84.105/30 | 4.49.84.106/30 | 4.30.79.180/30 | [8 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  |  | Yes |  |  | Assessment Complete MOP created & config created |  |  | 13:00 | 7AM CST | CHG000000000041957 (New) 87636 (Old) | CRQ000000708173 (new) CRQ000000686817 (old) | Approved | 40062 | CRQ000000658930 | Completed | Completed | Tested-Pass | 28-Jul: Test successful with CTL. 23-Jul: Tested circuit again with CTL and it failed again. CTL to investigate. 3-Jul: Tested circuit again with CTL. Still we could not get a connection. Seems a problem in their core network, so CTL will investigate. 30-Jun: Could not get a connection. Could not ping the GW. |  | Circuit Migrated - First Time right |  |  |  | 2019-11-01 | 2019-11-01
CKT-I-01-US-ENG01-0700-CTL-1 | I011220CTL1 | 1 | Yes | High | North America | United States | EC700 | 2018_297 | un-una-usaec700-vpn001 | un-una-usaec700-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | 441616233 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-02-28 | Complete | 2019-11-04 | 2020-05-22 | Complete | 22-May: Migration successfully completed. 19-May: Migration rescheduled for May 22nd at 12PM EDT. 18-May: Migration postponed until further notice, due to the site contact having a higher priority activity assigned on the same day pre-approved for the migration. 8-May: Migration approved by GeoIT on May 19th at 9AM EST. 5-May: Circuit testing successful. 31-Apr: Pending successful circuit testing on the week of May 3rd. 3-Apr: Migration on hold unil the Covid-19 crisis is over in the region. 19-Mar: Migration failed. Pending re-testing of circuit and new migration date. 28-Feb: Migration confirmed on March 9th at 5PM. Still pending NID install from CenturyLink. 21-Feb: GeoIT to confirm migration on March 6th at 5PM. 19-Dec: CenturyLink can't confirm yet the date on when the additional NAT pool will be ready. Pushing migration until February. Will look to bring up to January if CL responds by end of 2019. Demarc extension also still pending. 27-Nov: Pushed to January per Geo IT Team. 15-Nov: Demarcation point extension work still pending. Welington to contract a vendor to do the works. Migration date of Dec-19 not approved yet. Still waiting on CL to provide additional NAT pool (1x /30 + 2x /29) 8-Nov: Geo IT Team informed us that the date of 27-Nov is no longer possible. Asking the site for a new site. Date of 14-Dec provisional. Proposed Migration Date pushed by two weeks (26/11) due to delays with CP, and additional /29 requested. Migration date of 12/11 proposed by Geo IT Team. Start time 6:30pm EST. | Complete | Circuit Migrated |  |  | US-ENG01-0700 | USA_ENGLEWOOD_CLIFFS_700_SYLVAN_AVENUE |  |  |  |  | 700 Sylvan Avenue | Englewood Cliffs | 07632-3301 |  |  |  |  | Debbie Clarke | Debbie.G.Clarke@unilever.com | 1000MB | 1000 | 40.8868 | -73.9462 | 2019 | Oct | Internet | 2019-06-16 | Commercial Benefit | 1 | 0 | SC1 |  | 11AM EST |  |  |  | /29 | Service Centre for US. Circa 2000 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. |  | WAN: 4.16.92.140/30 CTL: 4.16.92.141 UNI: 4.16.92.142 LAN: 4.59.18.240/29 | 4.16.92.141 | 4.16.92.142 | 4.59.18.240/29 | [8 empty] | Emir Jukovic | Emir Jukovic | Emir Jukovic |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 16hrs UTC | 12PM EDT | 66917 | CRQ000000673526 | Approved | 41079 | CRQ000000640111/CRQ000000677418 | Completed | Completed | Tested-Pass | May 5th, we tested and got conectivity through cbale RJ45, Speed tests showing results under 200 MB up and dow, We change for a Non UL laptop and got better results up to 700MB |  | Circuit Migrated | DMVPN |  |  |  | 2019-11-01
CKT-I-01-US-JEF04-0001-CTL-1 | I011050CTL1 | 1 | Yes | High | North America | United States | Jefferson City | 2019_727 | un-una-usajef1-rtr001 | un-una-usajef1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | 441584770 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-01-21 | Complete | 2019-11-04 | 2020-04-25 | Complete | 25-Apr: Migration completed successfully. 15-Apr: Migration (2nd attempt) scheduled for April 25th. 12-Apr: Migration failed (Algosec issue: tunnel comes up, but drops after a few seconds). 31-Jan: GeoIT proposes date of April 12th for migration (Easter Sunday) 19-Dec: CenturyLink can't confirm yet the date on when the additional NAT pool will be ready. Pushing migration until February. Will look to bring up to January if CL responds by end of 2019. 13-Nov: Still waiting on CL to provide additional NAT pool (1x /30 + 4x /31) Nov-8: Geo IT team asked to push the migration for either mid-December or January. Date of 12-Jan provisional. Migration date of 27/11 proposed by Geo IT Team. Tentative dates at this point - May be 28 Nov. | Complete | Circuit Migrated |  |  | US-JEF04-0001 | USA_JEFFERSON_CITY_WEST_TRUMAN_BOULEVARD |  |  |  |  | 2900 W Truman Blvd | Jefferson City | 65109-0544 |  | Rafe.Gamet | Rafe.Gamet@unilever.com | O: 573-893-3040 x2272 C: 573-644-4214 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 40MB40MB | 60 | 38.5741 | -92.2488 | 2019 | Nov | MPLS | 2018-12-31 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  |  | LAN: 4.17.128.100/30 WAN: 64.159.122.156/30 CTL: 64.159.122.157/30 UNI: 64.159.122.158/30 | 64.159.122.157/30 | 64.159.122.158/30 | 4.17.128.100/30 | [8 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO | Yes |  |  | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  |  |  | 54593 58103 - 2nd Attempt | CRQ000000663602 CRQ000000659342 (old) | Approved | 41080 | CRQ000000640002/CRQ000000662844 | Completed | Completed | Tested -Pass-First Time | March 30th Passed port 3 |  | Circuit Migrated | VPN Tunnel (comes up, but drops after a few seconds) |  |  |  | 2019-11-01
CKT-I-01-US-ZNE01-0001-CTL-1 | I019662CTL1 | 1 | Yes | High | North America | United States | Newville | 2019_731 | un-una-usanew1-rtr001 | un-una-usanew1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | 441513563 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-02-24 | Complete | 2019-11-04 | 2020-08-09 | Complete | 9-Aug: Migration successful. 13-Jul: Migration pushed to August 9th 8AM Easter time. 22-Jun: Migration approved for July 19th at 6:30AM. 31-Apr: Pending demark extension. 19-Mar: Pending circuit testing and migration date. 15-Nov: Site contact requested CTL to change hand-off from copper to fiber. 8-Nov: JDA sites migrations not approved until January. Migration Date Requested to Geo IT Teams. | Complete | Circuit Migrated | Cisco |  | US-ZNE01-0001 | USA_NEWVILLE_CENTERVILLE_ROAD |  |  |  |  | 952 Centerville Rd, Key Logistics Park Condominium | Newville | 17241 |  | Fernando.Padua | Fernando.Padua@unilever.com | O: 717-776-2702 C:717-961-1168 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 40M | 50 | 40.1193 | -77.3416 | 2019 | Nov | MPLS | 2018-12-31 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  |  | LAN: 4.49.32.40/29 WAN: 4.49.34.196/30 CTL: 4.49.34.197/30 UNI: 4.49.34.198/30 | 4.49.34.197/30 | 4.49.34.198/30 | 4.49.32.40/29 | [8 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo |  |  | Complex site type - requires redesign | In Progress | NO |  |  | No | No | Assessment Complete |  |  |  |  | 110857 | CRQ000000698193 | Approved |  | CRQ000000690670 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right |  |  |  | 2019-12-01
CKT-I-02-US-ZNE01-0001-GTT-1 | I029662GTT1 | 1 | Yes | High | North America | United States | Newville | 2019_731 | un-una-usanew1-pio001 | un-una-usanew1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01690281 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-12 | Complete | 2019-10-28 | 2020-03-25 | Complete | 2019-11-11 | 2020-09-26 | Red | 10-Sep: Migration re-attempt tentatively scheduled for Sep-26. 6-Sep:Migration not successful. Initial failover tests did not work. Need to investigat and re-schedule. 10-Aug: Migration approved for September 6th at 6:30AM. 30-Jul: Pending confirmation on migration date. 13-Jul: Migration approved for August 23 8AM Easter time. Circuit tested and had issues. Pending GTT to resolve. 22-Jun: Once first migration successful, we will agree on the date for this second circuit migration. Apr-30: Pending GeoIT to complete demark extension. 04/03: Pending Level 3 to install ADVA. 18/02: Pending Level 3 FOC. 06/02:LCON advised they need handoff MMF. This is the cause for the FOC delay. 29/01: The vendor Level 3 has acknowledged the change request to a fibre presentation - we're now waiting for a completion date. 08/01: Unilever has asked for the presentation to be changed to fiber. We have asked our vendor for a quote to change the interface and will place the revised order shortly. 06/01: PM is asking the customer if we can deliver on copper, because if we have to change to fiber, the order need to reissued with Level 3. This is impact the delivery date even more. 30/12: PM confirmed the customer is changing the handoff to GigE Fiber. SDC is checking with Level 3, if we need a new quote, because of this change. 27/11 Pending input from vendor on the status of the delivery 24/10 FOC date received 20/11 | Pink | Circuit Delivered | Unilever Geo-IT |  | US-ZNE01-0001 | USA_NEWVILLE_CENTERVILLE_ROAD |  |  |  |  | 952 Centerville Rd, Key Logistics Park Condominium | Newville | 17241 |  | Fernando.Padua | Fernando.Padua@unilever.com | O: 717-776-2702 C:717-961-1168 |  |  | 50 | 50 | 40.1193 | -77.3416 | 2019 | Nov | MPLS | 2018-12-31 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  | Ground floor, Demark is located in the center north side of the building ~ 1440 feet away from the computer room which is in the main building. | 208.116.197.100/30 LAN Network - 208.116.197.100 First usable - 208.116.197.101 Last usable - 208.116.197.102 Broadcast - 208.116.197.103 Subnet Mask - 255.255.255.252 | 208.116.197.101/30 | 208.116.197.102/30 |  |  |  | L3 | GTT Washington | AS 3257 |  |  |  | Hugo Trejo | Hugo Trejo | Hugo Trejo |  |  | Complex site type - requires redesign | In Progress | NO | Yes |  | No |  | Assessment Complete |  |  |  |  | CHG000000000041827 | CRQ000000707331 | Approved | 41078 | CRQ000000639780 | Completed | Completed | Tested-Pass |  |  | Circuit - Failed Go Live | Initial Failover failed. Did not get approval to continue.
CKT-I-01-US-PNB01-5620-GTT-1 | I0110907GTT1 | 1 | Yes | High | North America | United States | Pontoon Beach | 2019_712 | un-una-usapon1-vpn001 | un-una-usapon1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01709947 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-09-03 | Complete | 2019-10-28 | 2019-10-10 | Complete | 2019-11-11 | 2020-07-14 | Complete | 14-Jul: Migration successful 8-Jul: Circuit tested successfully. Jun-9: Migration approved for July 14th at 9AM. 1-Jun: Circuit testing scheduled for June 3rd. 31-Apr: Pending successful circuit testing with a non-Unilever laptop. 3-Apr: Migration rescheduled from May to June. 29-Jan: Migration approved for May 13th 8AM. 8-Nov: JDA sites migrations not approved until January. 31/10 Service Start Letter delivered 22 Oct Migration Date Requested to Geo IT Teams. | Complete | Circuit Migrated | Cisco |  | US-PNB01-5620 | USA_EDWARDSVILLE_PONTOON_BEACH_INNER_PARK_DRIVE |  |  |  |  | 5620 Inner Park Drive | Pontoon Beach | 62040 |  | Steve.Seidner | Steve.Seidner@unilever.com | O: 618-797-3705 C: 618-410-4174 |  |  | 15Mbps | 50 | 38.7243 | -90.1131 | 2019 | Oct | Internet | Assumed Monthly | JDA site |  |  | 1 |  | 8AM |  |  |  | /30 |  | Ground floor, Computer room is located in the main office area at main entrance (25ft away). Circuits are located on the opposite side of computer room from the rack; cabling length ~25ft | 208.116.197.148/30 LAN Network - 208.116.197.148 First usable - 208.116.197.149 Last usable - 208.116.197.150 Broadcast - 208.116.197.151 Subnet Mask - 255.255.255.252 | 208.116.197.149/30 | 208.116.197.150/30 |  |  |  | AT&T | GTT US | AS 3257 |  |  |  | Hugo Trejo | Hugo Trejo | Hugo Trejo |  |  |  | Complete | [5 empty] | Assessment Complete MOP created & config created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 2PM UTC | 9AM local | 98269 | CRQ000000690605 | Approved | 40063 | CRQ000000627287 | Completed | Completed | Tested-Pass | 8-Jul: Circuit now tested successfully with FE from GTT on site. Apr-23: Tested with GTT, AT&T joined the call, they stated that Zscaler is the cause of lower BW. Apr-7: BW too low 15MB of 50MB, GTT to rise ticket with vendor. |  | Circuit Migrated - First Time right |  |  |  | 2019-10-01 | 2019-11-01
CKT-I-02-US-PNB01-5620-CTL-1 | I0210907CTL1 | 1 | Yes | High | North America | United States | Pontoon Beach | 2019_711 | un-una-usapon1-rtr001 | un-una-usapon1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | 441616638 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-08-29 | Complete | 2019-10-21 | 2019-11-13 | Complete | 2019-11-04 | 2020-05-07 | Complete | May-7: Circuit successfully migrated. 23-Apr: Migration scheduled to May 7th 8AM. 15-Apr: Migration postponed. Site contact had emergency and cannot go to the site. 9-Apr: Migration scheduled back to April 15th. WIll have to raise urgent tickets. 3-Apr: Migration rescheduled from April to May/June. 19-Mar: Pending circuit testing and migration on April 15th 8AM. 29-Jan: Migration approved for April 15th 8AM. 8-Nov: JDA sites migrations not approved until January. Migration Date Requested to Geo IT Teams. | Complete | Circuit Migrated |  |  | US-PNB01-5620 | USA_EDWARDSVILLE_PONTOON_BEACH_INNER_PARK_DRIVE |  |  |  |  | 5620 Inner Park Drive | Pontoon Beach | 62040 |  | Steve.Seidner | Steve.Seidner@unilever.com | O: 618-797-3705 C: 618-410-4174 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 20Mbps | 50 | 38.7243 | -90.1131 | 2019 | Oct | MPLS | 2018-12-31 | Commercial Benefit |  |  | 1 |  | 8AM |  |  |  | /30 |  |  | WAN: 4.28.89.44/30 CTL: 4.28.89.45 Uni: 4.28.89.46 | 4.28.89.45/30 | 4.28.89.46/30 | [9 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo |  |  |  | Complete | [5 empty] | Assessment Complete | Window Date agreed - End user Comms sent |  | 13hrs UTC | 8AM | 56816 | CRQ000000661606 | Approved | 40064 | CRQ000000658833 | Completed | Completed | Tested -Pass-First Time | Passed first time, April 7th port 3 |  | Circuit Migrated - First Time right |  |  |  | 2019-11-01 | 2019-11-01
CKT-I-01-US-RFN01-0001-CTL-1 | I012068CTL1 | 1 | Yes | High | North America | United States | Raeford | 2019_735 | un-una-usarae1-rtr001 | un-una-usarae1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | 441513554 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-03-06 | Complete | 2019-11-04 | 2020-04-26 | Complete | 26-Apr: Circuit successfully migrated. 3-Apr: Debbie still looking for a migration date. 19-Mar: Migration postponed to an undefined date in the future due to the coronavirus outbreak. 10-Mar: GeoIT approved migration date of April 5th at 8AM EST. 19-Dec: CenturyLink can't confirm yet the date on when the additional NAT pool will be ready. Keeping migration until February. Will look to bring up to January if CL responds by end of 2019. 13-Nov: Still waiting on CL to provide additional NAT pool (1x /30 + 2x /29) 8-Nov: JDA sites migrations not approved until January. | Complete | Circuit Migrated |  |  | US-RFN01-0001 | USA_RAEFORD_FABERGE_BLVD |  |  |  |  | 100 Faberge Blvd | Raeford | 28376 |  | Nick.Lozano | Nick.Lozano@unilevercom | (M): 910-691-4115 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 15Mbps | 100 | 34.9898 | -79.2576 | 2019 | Oct | MPLS | 2018-12-31 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  |  | LAN: 4.71.162.120/29 WAN: 4.71.162.20/30 CTL: 4.71.162.21 UNI: 4.71.162.22 | 4.71.162.21 | 4.71.162.22 | 4.71.162.120/29 | [8 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress | NO | Yes |  |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 12PM | 8AM | 58095 | CRQ000000662816 | Approved | 42380 | CRQ000000662865 | Completed | Completed | Tested -Pass-First Time | April 22th |  | Circuit Migrated
CKT-I-01-US-RLO01-0001-CTL-1 | I0110262CTL1 | 1 | Yes | High | North America | United States | Rialto | 2019_704 | un-una-usaria1-rtr001 | un-una-usaria1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | 441616372 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-04-30 | Complete | 2019-11-04 | 2020-06-04 | Complete | 4-Jun: Migration successfully completed. 20-May: Migration approved for this circuit to replace the MPLS link on June 4th. 18-May: CenturyLink fixed upload speed. 15-May: Circuit delivered and tested. Good download speed, low upload speed. 31-Apr: Pending provider to deliver the circuit. 14-Feb: JDA issues at the site. Migration pushed until April. 29-Jan: Pending demarc extension. Migration date to be approved once we get FOC date. 6-Jan: IP addresses info fixed. IPs info were inverted with the ones for GTT. 19-Dec: Demarc extension still pending. 13-Dec: Demarcation extension works required 8-Nov: JDA sites migrations not approved until January. Migration Date Requested to Geo IT Teams. | Complete | Circuit Migrated |  |  | US-RLO01-0001 | USA_BLOOMINGTON_WEST_RESOURCE_DRIVE |  |  |  |  | 305 West Resource Drive | Rialto | 92316 |  | Natasha.Wilroy | Natasha.Wilroy@dhl.com | M: 661-755-3628 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 20MB | 30 | 34.0412 | -117.372 | 2019 | Nov | Internet | 2017-11-21 | JDA site | 1 | 0 | SC2 | [5 empty] | /30 |  |  | WAN: 4.7.101.64/30 CTL: 4.7.101.65/30 UNI: 4.7.101.66/30 | 4.7.101.65/30 | 4.7.101.66/30 | [9 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos |  |  | Standard site type - Hybrid (DMVPN + IEN) | In Progress | [5 empty] | Assessment Complete MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 16:00 | 9:00 | 36506 | CRQ000000643243 | Approved | 41084 | CRQ000000639875 | Completed | Completed | Tested-Fail | May 15th, Test failed download BW ok, upload BW not ok (half of contracted BW 14Mb) |  | Circuit Migrated - First Time right |  |  |  | 2019-12-01 | 2020-06-01
CKT-I-02-US-RLO01-0001-GTT-1 | I0210262GTT1 | 1 | Yes | High | North America | United States | Rialto | 2019_703 | un-una-usaria1-ien001 | un-una-usaria1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01690274 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-12 | Complete | 2019-10-28 | 2019-10-21 | Complete | 2019-11-11 | 2020-07-21 | Complete | 21-Jul: Migration successful. 9-Jul: Migration approved for July 21st. 22-Jun: Pending business approval on migration date. 4-Jun: Migration to be approved by early July. 15-May: CIrcuit testing successful. Pending migration date. 31-Apr: Pending successful circuit testing with located equipment. 21-Apr: Migration cancelled. Circuit could not be located. 9-Apr: Migration approved for April 21st. 14-Feb: JDA issues at the site. Migration pushed until April. 29-Jan: Migration date approved for February 20th. Pending demarc extension. 6-Jan: IP addresses info fixed. IPs info were inverted with the ones for CTL. 20/12 [AP] Please check the IP addresses with Aga 19-Dec: Demarc extension still pending. 13-Dec: Demarcation extension works required 8-Nov: JDA sites migrations not approved until January. Migration Date Requested to Geo IT Teams. | Complete | Circuit Migrated | Cisco |  | US-RLO01-0001 | USA_BLOOMINGTON_WEST_RESOURCE_DRIVE |  |  |  |  | 305 West Resource Drive | Rialto | 92316 |  | Natasha.Wilroy | Natasha.Wilroy@dhl.com | M: 661-755-3628 |  |  | 6000Kbps6000Kbps | 30 | 34.0412 | -117.372 | 2019 | Nov | MPLS | 2016-01-26 | JDA site | 1 | 0 | SC2 | [5 empty] | /30 |  | Ground floor, Comms room | 208.116.197.140/30 Network - 208.116.197.140 First usable - 208.116.197.141 Last usable - 208.116.197.142 Broadcast - 208.116.197.143 Subnet Mask - 255.255.255.252 | 208.116.197.141/30 | 208.116.197.142/30 |  |  |  | XO Comm | GTT LA | AS 3257 |  |  |  | Fernando Ramos | Fernando Ramos | Fernando Ramos |  |  | Complex site type - requires redesign | Complete | NO | Yes |  |  |  | Assessment Complete CMSP ticket raised MOP created & config created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  |  |  | 101631 | CRQ000000691953 | Approved | 41083 | CRQ000000640027 | Completed | Completed | Tested-Pass | May 15th, Tests succesfully performed |  | Circuit Migrated - First Time right |  |  |  | 2019-10-01 | 2019-11-01
CKT-I-01-US-STA01-0900-CTL-1 | I012128CTL1 | 1 | Check if hardcoded NAT translations will cause issue. Check with site PoC if the hardcoded IPs for NAT are in use elsewhere in the network. | High | North America | United States | St. Albans | 2019_738 | un-una-usasta1-rtr001 | un-una-usasta1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | 441616314 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-01-21 | Complete | 2019-11-04 | 2020-03-07 | Complete | Mar-7: Circuit successfully migrated. 14-Feb: Per GeoIT, migration to be pushed until April. 1-Feb: Additional NAT pool received. 12-Jan: No update. 19-Dec: CenturyLink can't confirm yet the date on when the additional NAT pool will be ready. Pushing migration until February. Will look to bring up to January if CL responds by end of 2019. 4-Dec: CenturyLink hasn't provided the new IP pool with its respective IP address, so we cannot create the MOP. Needs to be rescheduled to a later date TBD by Geo IT Team. 22-Nov: Geo IT and site approved the migration date of 14-Dec at 8AM EST. 15-Nov: Geo IT Team proposed the date of Dec 21. Need to verify we are allowed during freeze. 8-Nov: Geo IT asked to change the date to Nov-23. Migration date of 26/11 proposed by Geo IT Team. Start time 08:30am EST. | Complete | Circuit Migrated |  |  | US-STA01-0900 | USA_SAINT_ALBANS_INDUSTRIAL_PARK_ROAD |  |  |  |  | 900 Industrial Park Rd. | St. Albans | 05478-1880 |  | Stephen.Parent | Stephen.Parent@unilever.com | O-802-393-3622; C: 802-393 0206 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 8000Kbps8000Kbps | 40 | 44.8002 | -73.0988 | 2019 | Nov | MPLS | 2017-10-02 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  |  | LAN: 4.31.156.160/28 WAN: 4.16.12.128/30 CTL: 4.16.12.129/30 UNI: 4.16.12.130/30 | 4.16.12.129/30 | 4.16.12.130/30 | 4.31.156.160/28 | [8 empty] | Sandor Jardon Vera | Sandor Jardon Vera | Sandor Jardon Vera |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  |  | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 12hrs | 7AM | 46667 | CRQ000000650849 | Approved | 40075 | CRQ000000624211 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right |  |  |  | 2019-11-01 | 2019-11-01
CKT-I-02-US-STA01-0900-GTT-1 | I022128GTT1 | 1 | Require /29+ /30 | High | North America | United States | St. Albans | 2019_737 | un-una-usasta1-vpn001 | un-una-usasta1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01710096 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-09-03 | Complete | 2019-10-28 | 2019-11-15 | Complete | 2019-11-11 | 2020-04-11 | Complete | Apr-11: Circuit successfully migrated. Apr-9: Field Engineer not required at the site. Apr-3: Migration might not need support from field engineer. Debbie to advise next week. Mar-30: Migration to rescheduled for April 11th. Mar-27: Migration postponed for a future date in April. Mar-19: Pending circuit re-testing and migration. Mar-10: Circuit to be rescheduled for March 28th. Mar-7: Circuit testing failed. Will need to get migration date once circuit is tested successfully. 14-Feb: Per GeoIT, migration to be pushed until April. 1-Feb: Additional NAT pool received. 9-Jan: Requested GTT to change the order and provide a /28 with the circuit and keep already assigned IP addresses. 15-Nov: Geo IT to get migration date from site for this second circuit. Jan-10 proposed date. 8-Nov: Geo IT proposed 21-Dec as migration date. Still to be confirmed by Cisco. | Complete | Circuit Migrated |  |  | US-STA01-0900 | USA_SAINT_ALBANS_INDUSTRIAL_PARK_ROAD |  |  |  |  | 900 Industrial Park Rd. | St. Albans | 05478-1880 |  | Stephen.Parent | Stephen.Parent@unilever.com | O-802-393-3622; C: 802-393 0206 |  |  | 30MB | 40 | 44.8002 | -73.0988 | 2019 | Oct | Internet | 2018-12-31 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  | Ground floor, Demark is in the server room which is located in main corridor of the main office. Server room is ~10x12. Demarks are behind racks, ~3-4ft away. Cabling requirements may be 10-15ft. | 208.116.235.160/28 LAN Network - 208.116.235.160 First usable - 208.116.235.161 Last usable - 208.116.235.174 Broadcast - 208.116.235.175 Subnet Mask - 255.255.255.240 | 208.116.235.161/28 | 208.116.235.162/28 | 208.116.235.160/28 |  |  | Fairpoint Comms | GTT US | AS 3257 |  |  |  | Sandor Jardon Vera | Sandor Jardon Vera | Sandor Jardon Vera |  |  | Standard site type - Dual DMVPN | Complete |  | Yes | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 12hrs | 7AM | 50340 (new) 46667 (old) | CRQ000000654715 | Approved | 41081 | CRQ000000639827 | Completed | Completed | Tested-Pass | Testing and migration successful Testing failed on March 7th. Opened support ticket 4980518 with GTT. March 27 test failed again, Major alarm bliking on device. |  | Circuit Migrated | The circuit from GTT was not working on our first attempt to migrate this circuit. |  |  |  | 2020-01-01
CKT-I-01-US-HMN01-0002-BT-1 | I011043BT1 | 1 | Two tunnels seen - one for MPLS and one to Trumbull. Both with 20MB. Nat specified on a /32 pool. | High | North America | United States | Hammond | 2019_714 | un-una-usaham1-ien001 |  | Juan Simon | WAN Circuit Migration | Circuit | BT | BT |  |  | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-09-09 | Complete | 2019-10-28 | 2020-08-15 | Red | 2019-11-11 | 2020-08-15 | Red | 17/08: Moved from GTT to BT 10/06: On hold while significant excess costs from the Vendor are reviewed.(From GTT tracker) 01/04: Welington to advise on the status, can we proceed with vendor training or is the issue still re the certification which none of our vendors can provide. 30/03: Pending advise what we will do with the ISN certification client require from the vendor. 19/03: Pending circuit delivery. 26/02: Vendor's FOC is 07/04. 18/02:Pending PM to advise on the progress of Comcast techs training, requested by Unilever. 20/11 Waiting for the FOC date to be confirmed 15-Nov: Migration on Dec-13 still tentative date. Probably will have to be pushed to January since site might not accept migration in December. 8-Nov: Tentative date. Geo IT Team requesting confirmation from site to migrate on this date. Could be pushed to January since it is a JDA site. | On Hold | Circuit Order Accepted | Unilever SNT | Check dates | US-HMN01-0002 | USA_HAMMOND_CALUMET_AVE |  |  |  |  | 1200 Calumet Avenue | Hammond | 46320-1015 |  | Thomas.McFarland | Thomas.McFarland@unilever.com | O: 219 473 7412 C: 219 808-4776 |  |  | 20MB * 2 | 30 | 41.6914 | -87.5085 | 2019 | Oct | MPLS | 2017-11-17 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  |  |  | 208.116.197.145/30 | 208.116.197.146/30 |  |  |  |  | GTT US | AS 3257 |  |  |  | Fernando Ramos | Fernando Ramos | Fernando Ramos |  |  | Standard site type - Hybrid (MPLS + IEN) | In Progress |  | Yes | Yes
CKT-I-02-US-HMN01-0002-CTL-1 | I021043CTL1 | 1 |  | High | North America | United States | Hammond | 2019_713 | un-una-usaham1-rtr001 | un-una-usaham1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | 441513576 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-06-30 | Complete | 2019-11-04 | 2020-08-21 | Complete | 24-Aug: Migration successful. 30-Jul: Migration date to be confirmed. 13-Jul: Migration pushed to Augusto. 17-Jun: Migration approved for July 15th at 8AM CST. 30-Apr: Pending Deepak to approve installation costs or chose another provider. 19-Mar: Pending circuit delivery. 8-Nov: JDA sites migrations not approved until January. Migration Date Requested to Geo IT Teams. | Complete | Circuit Migrated | Unilever SNT |  | US-HMN01-0002 | USA_HAMMOND_CALUMET_AVE |  |  |  |  | 1200 Calumet Avenue | Hammond | 46320-1015 |  | Thomas.McFarland | Thomas.McFarland@unilever.com | O: 219 473 7412 C: 219 808-4776 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 10MB | 30 | 41.6914 | -87.5085 | 2019 | Nov | Internet | 2016-04-26 | JDA site | 1 | 0 | SC2 |  | 8AM |  |  |  | /30 |  |  | WAN: 4.59.24.12/30 CTL: 4.59.24.13/30 UNI: 4.59.24.14/30 | 4.59.24.13/30 | 4.59.24.14/30 | [9 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Hybrid (MPLS + IEN) | In Progress |  | Yes | Yes | Yes |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required) |  |  | 1PM UTC | 8AM CST | 114674 | CRQ000000701397 | Approved |  | CRQ000000687841 | Completed | Completed |  | Aug-14: To be tested on Aug 17th. |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01
CKT-I-01-US-TBL01-0080-GTT-1 | I0110936GTT1 | 1 | Login via telnet and local credentials. | High | North America | United States | Trumbull DC | 2019_750 | una-ustru80r4-isp2 | una-ustru80r4-isp2 | Juan Simon | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01689550 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-29 | Complete | 2019-10-28 | 2019-09-12 | Complete | 2019-11-11 | 2020-02-15 | Complete | 15-Feb: Circuit successfully migrated. 13-Feb: Circuit tested successfully. Switched migration date with circuit from CL since that one is still not ready. 31-Jan: Migration pushed to Feb 22th to allow for demarc extension to complete (Feb 6th).. 24-Jan: MIgration agreed on Feb 8th. 6-Dec: Demarc extension needs to be installed from the building's carriers room to the UNL computer room. Debbie and Welington working on this and pending to provide ETA. Circuit testing will be done after this. 15 Nov: Geo IT Team said that most likely both circuits in Trumbull will have to be migrated in January. Debbie still will look for approval for Dec 7. 14-Nov: GTT is saying that for the routing table service that we require in this circuit that they will need to create a new order with the vendor and that this will take a few weeks. Migration date of Dec-7 will most likely not be possible, so we're switching the migration order between the two new circuits in this site. 8-Nov: Geo IT asked to schedule for Dec 7th (or Dec 8th - TBC) 2nd Migration date of 7/12 proposed by Geo IT Team. Migration date of 16/11 proposed by Geo IT Team. Start time: 08:00am EST | Complete | Circuit Migrated |  |  | US-TBL01-0080 | USA_TRUMBULL_80MERRITT |  |  |  |  | 80 Merritt Boulevard | Trumbull | 06611 |  | Angelo.DeSimone | Angelo.Desimone@unilever.com | W(203) 816-3015 (M)(203)400-5398 |  |  | 200MB | 400 | 41.2431 | -73.1479 | 2019 | Nov | Internet | -1 | Commercial Benefit | 1 | 0 | SC1 | [5 empty] | /29 | Data centre, will need to review existing BGP configuration | 1st floor, POP Room, which is on the 1st floor. | 208.116.214.228/30 Network - 208.116.214.228 First usable - 208.116.214.229 Last usable - 208.116.214.230 Broadcast - 208.116.214.231 Subnet Mask - 255.255.255.252 | 208.116.214.229/30 | 208.116.214.230/30 | NA |  |  | Zayo | GTT NY | AS 3257 |  |  |  | Fernando Ramos | Fernando Ramos | Fernando Ramos |  |  | Complex site type - requires redesign | Complete | Not sure but single mode is most likely, need confirmation of what will be delivered | Yes | No |  | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 14:00 UTC | 9:00 | 32659 | CRQ000000641135 | Approved | 40310 | CRQ000000639227 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right |  |  |  | 2019-09-01 | 2020-02-01
CKT-I-01-US-TBL01-0080-CTL-1 | I0110936CTL1 | 1 | Login via telnet and local credentials. | High | North America | United States | Trumbull DC | 2018_310 | una-ustru80r3-isp1 | una-ustru80r3-isp1 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | 441571155 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-01-21 | Complete | 2019-11-04 | 2020-02-22 | Complete | 13-Feb: Circuit with issues (no BGP routes advertised). Switched migration date with circuit from GTT since that one is ready. 31-Jan: Demarc extension pending to complete. ETA Feb 6th. 24-Jan: MIgration agreed on Feb 15th. 11-Dec: Pending CenturyLink to confirm full routing table is being advertised with the internet link. 6-Dec: Demarc extension needs to be installed from the building's carriers room to the UNL computer room. Debbie and Welington working on this and pending to provide ETA. Circuit testing will be done after this. 15 Nov: Geo IT Team said that most likely both circuits in Trumbull will have to be migrated in January. Debbie still will look for approval for Dec 7. 8-Nov: Geo IT asked to schedule for mid-January Migration date of 23/11 proposed by Geo IT Team | Complete | Circuit Migrated |  |  | US-TBL01-0080 | USA_TRUMBULL_80MERRITT |  |  |  |  | 80 Merritt Boulevard | Trumbull | 06611 |  |  |  |  | Debbie Clarke | Debbie.G.Clarke@unilever.com | 200MB | 400 | 41.2431 | -73.1479 | 2019 | Oct | Internet | 2017-01-19 | Commercial Benefit | [8 empty] | /30 |  |  | WAN: 4.15.68.200/30 CTL: 4.15.68.201 Uni: 4.15.68.202 | 4.15.68.201/30 | 4.15.68.202/30 | [9 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos |  |  | Complex site type - requires redesign | Complete | Not sure but single mode is most likely, need confirmation of what will be delivered | Yes | No | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 17:30 UTC | 12:30 PM EST | 31574 | CRQ000000638171 | Approved | 40273 | CRQ000000638888 | Completed | Completed | Tested-Pass |  |  | Circuit Migrated - First Time right |  |  |  | 2019-11-01 | 2020-02-01
CKT-I-01-US-WXR01-0001-ORA-1 | I0110270ORA1 | 1 | Existing 40MB, ordered 30MB, Deepak has ordered the change. Vishal to follow up | High | North America | United States | Wilmer | 2019_755 | un-una-usawil1-rtr001 | un-una-usawil1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit | Orange | Ora |  | LO0048V838 | 2019-08-19 | 2019-09-13 | Complete | 2019-08-26 | 2020-05-27 | Complete | 2019-11-04 | 2020-08-31 | Red | 2019-11-18 | 2020-10-30 | Red | 01-Jul-20: Order signed by Deepak. Pending confirmation from the carrier regarding what is possible for IP address provision and possible additional costs (From Orange tracker) Apr-29: Pending circuit delivery. 19/03: Pending FOC date and circuit delivery. 19/12 Carrier has declined the order - a new Carrier will be chosen and advised. 05/12 Pending carrier to confirm delivery dates 8-Nov: JDA sites migrations not approved until January. | Yellow | Circuit Order Accepted | Circuit Provider |  | US-WXR01-0001 | USA_WILMER_SUNRIDGE_BLVD |  |  |  |  | 201 Sunridge Blvd | Wilmer | 75172 |  | Rick.Brazelton | Rick.Brazelton@unilever.com | (O) 972-290-8080 (M) 214-697-8377 |  |  | 40MB | 30 | 32.6077 | -96.6761 | 2019 | Nov | MPLS | 2018-12-31 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 | [8 empty] | LEC Frontier | [5 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Complex site type - requires redesign | Complete | NO | Yes | No | No | No | Assessment Complete Partner MOP created Received tunnel IP or LAN IP (if required)
CKT-I-02-US-WXR01-0001-CTL-1 | I0210270CTL1 | 1 | Yes | High | North America | United States | Wilmer | 2019_756 | un-una-usawil-IEN002 | un-una-usawil1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  | 441614312 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-09-01 | Complete | 2019-10-21 | 2020-07-07 | Red | 2019-11-04 | 2020-10-30 | Red | 30-Apr: Pending Deepak to approve installation costs or chose another provider. 19-Nov: Pending FOC date and circuit delivery. 8-Nov: JDA sites migrations not approved until January. | Yellow | Circuit Order Accepted | Unilever SNT |  | US-WXR01-0001 | USA_WILMER_SUNRIDGE_BLVD |  |  |  |  | 201 Sunridge Blvd | Wilmer | 75172 |  | Rick.Brazelton | Rick.Brazelton@unilever.com | (O) 972-290-8080 (M) 214-697-8377 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 30 Mbps | 30 | 32.6077 | -96.6761 | 2019 | Nov | Internet | 2017-01-19 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /30 |  |  | WAN: 4.59.117.36/30 CTL: 4.59.117.37/30 UNI: 4.59.117.38/30 | 4.59.117.37 | 4.59.117.38 | [9 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Complex site type - requires redesign | Complete | NO |  | No | No | No | Assessment Complete Partner MOP created Received tunnel IP or LAN IP (if required)
CKT-I-01-JP-TYO02-0211-GTT-1 | I012320GTT1 | 1 | This is a new router installation with complete DMVPN configuration. So the Ordered BW and NAT pool will used. | Medium | North Asia | Japan | Nakameguro Head Office | 2019_505 | un-sea-jpnmeg-vpn001 |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router | GTT | GTT |  | DIA/01699062 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-20 | Complete | 2019-10-28 | 2019-11-14 | Complete | 2019-11-11 | 2020-03-26 | Complete | 30-Mar: Migration to new DMVPN set up completed on 26th March. There was issue reported ON 27 MAR, related to user in china not able to access remote desktop in Japan which was resolved through an expedite change on 30 MAR. 9-Mar: Date rescheduled to 26th per request from Miho. Testing of parallel set up complete. Pending resolution of existing link issue which is being investigated by CMS. 2-Mar: Post discussion between Miho, Deepak and Cisco team new proposed date is 24th Mar. There is an existing issue with Osaka DMVPN link which is not working. CMS will be engaged to trouble shoot and fix the issue. INC000106912143 is raised. 14-Feb: NO GO Decision made in discussion with GEO IT for migration on 25 Feb. Deepak to further discuss with Miho to agree on next plan of action. 27-Jan: Proposed migration date of 25th Feb. Pending downtime confirmation. 19 Jan: Router configuration planned on 20th. Traffic routing tentative on 29-Jan. TRB approval will be taken on 20th 10 Jan : Test 2 and troubleshooting planned on 14th Jan'20 06 Dec : Pre migration testing planned for 19th Dec 29 Nov : Overall strategy for Japan to agreed before scheduling this migration. Moved to Feb 2020. 18 Nov : Technical discussions in progress. Migration postponed for 19 Dec 11-Nov: Technical discussions in progress. 31/10: Initial asses sment commenced. Need clarification from Unilever before continuing preparing for the migration. Migration Date has to be rescheduled. | Complete | Circuit Migrated |  |  | JP-TYO02-0211 | JAPAN_TOKYO_HEAD_OFFICE_NAKAMEGURO |  |  |  |  | 2-1-1 Kamimeguro, Meguro-Ku, Nakameguro GT Tower | Tokyo | 153-8578 |  | Miho.Sakurai | Miho.sakurai@unilever.com | +81 3-5723-2496 |  |  | 100Mbps | 100 | 35.6412 | 139.6971 | 2019 | Nov | Internet | 2019-10-09 | Commercial Benefit |  |  | SC1 |  | 18:30 hrs | Agreed with Miho that FE is not required for this migration. |  |  | /29 | Head office for the Japan business. Circa 600 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | Floor 24F, Nakameguro GT Tower, comms room 24F | 64.235.253.144/28 Network - 64.235.253.144 First usable - 64.235.253.145 Last usable - 64.235.253.158 Broadcast - 64.235.253.159 Subnet Mask - 255.255.255.240 | 64.235.253.145 | 64.235.253.146 | 64.235.253.144/28 |  |  | Colt Asia | GTT PoP | AS 1002 |  |  |  | Pawan Nandigama | Pawan Nandigama | Pawan Nandigama | [5 empty] | No |  |  | No |  | Window Date agreed - End user Comms sent |  | 9:30 am to 5:30 pm UTC | 6:30 pm to 2:30 am | 29992 | CRQ000000635594 (26 Mar) CRQ000000656201 (30 Mar) | Approved | 40615 | CRQ000000627280 | Completed | Completed | Tested-Pass | The test was incomplete Configuration changes made during the Testing: • Configured the CE router with IP - 64.235.253.146/30. (Inter Gi0/0/1) • Brought up the interface. • Tried to ping the PE IP- 64.235.253.145/30, it didn’t work. • Changed the cable and did not work. WAN & LAN subnet details used are as below : WAN: PE : - 64.235.253.145/30 CE: - 64.235.253.146/30 LAN: 64.235.253.144/28 GTT came back with the below update. We’ve checked with our provisioning team and on our end we have configured the service with LAN 64.235.253.144/28 [.145 for GTT]. Since this is a Direct routing, we don’t use any WAN IP’s it’s LAN IP’s configured on our end.we need to schedule another testing call with GTT in the new year-2020 Testing was done on 14th Jan everything worked fine, except the Zscaler where the node was going to los angeles rather than to Tokyo. It was corrected and tested on 16th Jan again and even Zscaler also worked fine. | Miho Sakurai | Circuit Migrated - First Time right |  | INC000107088361 | User in china not able to connect remotely to desktop in Japan. CIsco was not made aware of users in China accessing desktop in Japan during planning phase. Routing changes were applied during MW per request from Hendro during troubleshooting. THis was resolved by an expedited change which was implemented on 30 March |  | 2020-02-01
CKT-I-01-IL-IAD01-0012-GTT-1 | I011201GTT1 | 1 | Yes | High | RUB/ TUI&I | Israel | Arad | 2019_426 | un-amt-ilarah01 |  | Eloise Shepheard | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01696554 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-09-04 | Complete | 2019-10-28 | 2020-05-15 | Complete | 2019-11-11 | 2020-10-01 | Red | 20/08: New router will arrive in Israel 14th September. It will be at Unilever site for 21st September. Eloise has sent an email to Danny and Bashir for them to confirm migration date. Options are 25/28/29/30 September 06/08: Still awaiting 2nd router to be ordered/delivered. Local team can order themselves if lead time if shorter. 16/07 - Speed testing carried out successfully but Internal and External IP addresses are the wrong way round and need to be switched before migration - 2nd router also required for site 14/07 - Testing scheduled for 16th July 11am local time 01/07 - email sent to Deepak and Nand for progress update on required rooter 17/06 - New router purchase and installation being progressed with Nand / Deepak 09/06 - Cisco advise do not have two links on 1 router - needs new router if decided by Unilever 09/06 - Decision needed by Unilever David Collins on new router - if needed then expected end of July for migration at best 09/06 - moved from AB351 as refres to GTT circuit and not Orange ciruit - 'Ensure that site access is granted to deliver GTT circuit' 12 Hata'asiya Street, Arad - 30/09/19 12/03 Engineer from GTT not allowed onsite to perform installation due to coronavirus 04/03: The installation date is 12/03. 20/01 Feedback from Unilever on how to proceed with this order required 24/10 on hold. pending details from Deepak | On Hold | Circuit Delivered | Unilever Geo-IT |  | IL-IAD01-0012 | ISRAEL_ARAD_12 HATASIYA STREET_ARAD PLANT |  |  |  |  | 12 Hata'asiya Street | Arad | 8910001 |  | Danny Kornblit | Danny.Kornblit@unilever.com | +972 52 700 2124 |  |  | 10000Kbps10000Kbps | 50 | 31.6139 | 34.766 | 2019 | Nov | MPLS | 2019-12-31 | Service | 1 | Congested Link | SC2 | [5 empty] | /30 |  | Ground floor, Arad Offices Building, IT Network Room | 62.90.143.177/30 Network - 62.90.143.176 First usable - 62.90.143.177 Last usable - 62.90.143.178 Broadcast - 62.90.143.179 Subnet Mask - 255.255.255.252 | 62.90.143.177 | 62.90.143.178 |  |  |  | Cellcom Israel | Local ISP | AS 1680 |  |  |  | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar
CKT-I-02-IL-IAD01-0012-ORA-1 | I021201ORA1 | 1 | 2 circuits terminating on same device. Check for method of migration here, if collating both into one circuit in target. | High | RUB/ TUI&I | Israel | Arad | 2019_425 | un-amt-ilarah01 | un-amt-ilarah-vpn001# | Eloise Shepheard | WAN Circuit Migration | Circuit | Orange | Ora |  | GO09XEJL43 | 2019-08-19 | 2019-09-13 | Complete | 2019-08-26 | 2019-12-19 | Complete | 2019-11-04 | 2019-12-08 | Complete | 2019-11-18 | 2020-10-01 | Red | 20/08: New router will arrive in Israel 14th September. It will be at Unilever site for 21st September. Eloise has sent an email to Danny and Bashir for them to confirm migration date. Options are 25/28/29/30 September 06/08: Still awaiting 2nd router to be ordered/delivered. Local team can order themselves if lead time if shorter. 16/07 - Speed testing carried out successfully - 2nd router also required for site 14/07 - Testing scheduled for 16th July 11am local time 01/07 - email sent to Deepak and Nand regards required rooter 17/06 - Email send to Deepak and David Collins in follow up for decision as testing on hold 10/06 - Email sent to Deepak and David Collins for decision regards 2nd router 09/06 - Cisco advise do not have two links on 1 router - needs new router if decided by Unilever Decision needed by Unilever David Collins on new router - if needed then expected end of July for migration at best 12 Hata'asiya Street, Arad -06/12/19 06/03 New router required. Unilever submit order and provide ETA. 17/02 After network analysis of Hatasiya site, Cisco proposed two approached for the migration. Local team suggested to go ahead with option 2, as it seen as less risky. Additional router is required onsite. Welingotn to confirm next steps. Options presented to the local team for the migration in Arad Hatasiya:: 1. Decommision both MPLS links and install 1 x DMVPN. In this case the site will have no link redundancy. (This should be done after the Main sites are already migrated to DMVPN). 2. Get another router to install the DMVPN link on, this will insure proper redundancy with 1 x MPLS and 1 x DMVPN. 06/02 Migration cancelled. Incorrect router identified for the migration - designed has been prepared for the wrong site. This migration will be re-scheduled. 09/01 Circuit testing successful. Local team informed us about network configuration works scheduled at that site until end of Jan, as such we are only able to proceed with migration in Feb. 6th Feb has been initially secured as the migration date. The migration should take place during work hours. 12/12 Arad is part of the stand alone network. No complexity identified - we can go ahead and plan the migration. | On Hold | Circuit Delivered | Unilever SNT |  | IL-IAD01-0012 | ISRAEL_ARAD_12 HATASIYA STREET_ARAD PLANT |  |  |  |  | 12 Hata'asiya Street | Arad | 8910001 |  | Amir Hoberfeld | Amir.Hoberfeld@unilever.com | +972 52 8459748 |  |  | 10000Kbps10000Kbps | 50 | 31.6139 | 34.766 | 2019 | Nov | MPLS | 2019-12-31 | Service | 1 | Congested Link | SC2 | NA | 1100 - 1700 UTC | NA | NA | NA | /30 |  |  | IP range: 84.110.48.180-84.110.48.183 Ip Address: 84.110.48.181 Subnet mask: 255.255.255.252 Default gateway: 84.110.48.181 Primary DNS: 192.115.106.35 Secondary DNS: 62.219.186.7 | 84.110.48.181 | 84.110.48.182 | 84.110.48.180/30 |  |  | Bezeq |  | AS 6810 |  |  |  | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar | [5 empty] | No |  |  |  |  | Window Date agreed - End user Comms sent |  | 1100 - 1700 | 1300 - 1900 | 32075 | Yes | Approved | 40843 | CRQ000000633810 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit - Failed Go Live | Cisco identified incorrect router for the migration |  |  |  | 2020-01-01
CKT-I-01-IL-HFA01-0001-GTT-1 | I011210GTT1 | 1 | Login via telnet and local credentials. Additional LAN pool /24 needs to be ordered. | Top | RUB/ TUI&I | Israel | Haifa (food) | 2019_434 | un-amt-ilhaiu1 | un-amt-ilhaiu1-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01696536 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-20 | Complete | 2019-10-28 | 2019-09-22 | Complete | 2019-11-11 | 2020-05-06 | Complete | 27/04 Migration agreed for 6 May, starting 11 am local time 20/02 Unilever local team doesn't want to proceed with the migration due to the fact the migration in Keshet wasn't fully implemented (due to issues with firewall). This migration will need to be postponed to March. 12/12 Routers need to be exchanged, waiting further confirmation from Unilever on the delivery timelines 02/12 Technical workshop to be arranged to agree on the migration approach for Israel 18/11 A request has been received today by Mohammed Diab to reschedule the migration in Haifa food and Keshet to January, as per the business request 31/10: Initial assessment commenced. Need clarification from Unilever before continuing preparing for the migration. Migration Date has to be rescheduled. 22/10 No access to devices - move the migration out. | Complete | Circuit Migrated | Cisco |  | IL-HFA01-0001 | ISRAEL_HAIFA_BAY_JULIUS_SIMON |  |  |  |  | Julius Simon 52 | Haifa | 3126001 |  | Danny Kornblit | Danny.Kornblit@unilever.com | +972 52 700 2124 |  |  | 5Mbps | 100 | 32.8117 | 34.9987 | 2019 | Oct | MPLS | 2019-12-31 | Commercial Benefit |  |  | SC2 | Migration to go ahead under condition that migration in Keshet is successful on 18/02 | 1400 - 2000 UTC | NA | NA | NA | /30 |  | Floor No. 2, Offices Building, IT Servers Room | 84.110.42.238/30 Network - 84.110.42.236 First usable - 84.110.42.237 Last usable - 84.110.42.238 Broadcast - 84.110.42.239 Subnet Mask - 255.255.255.252 | 84.110.42.237 | 84.110.42.238/30 |  |  |  | Bezeq International | Local ISP | AS 8551 |  |  |  | Adrian Lazar | Adrian Lazar | Adrian Lazar | 2020-05-07 |  | Complex site type - requires redesign | Complete |  | Yes | Yes | No |  | MOP created & config created | Window Date agreed - End user Comms not sent |  | 1400 - 2000 | 1600 - 2200 | 62314 | CRQ000000662290 | Approved | 39736 | CRQ000000655762 | Completed | Completed | Tested -Pass-First Time |  | Danny Kornblit | Circuit Migrated - First Time right |  |  |  | 2019-09-01 | 2020-02-01
CKT-I-01-IL-HFA06-0001-GTT-1 | I01WC041GTT1 | 1 | Login via telnet and TACACS. SSH not enabled. Yes | High | RUB/ TUI&I | Israel | Haifa Warehouse | 2019_436 | un-amt-ilhicce02 |  | Agnieszka Pajak | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01696520 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-09-05 | Complete | 2019-10-28 | 2019-10-10 | Complete | 2019-11-11 | 2019-12-17 | Complete | 12/12 RFC not included on the agenda for CAB. As a recommendation from CAB this request will be raised by CMS change management team as urgent. 02/12 Technical workshop to be arranged to agree on the migration approach for Israel. We are OK to go ahead with the migration in Haifa Warehouse separately in December. 22/11 Migration date confirmed - 17 Dec 21/11 We are going ahead with the migration in December,. Exact date tbc by Mohamed. Circuit tests are being arranged with GTT. 03/11 Customer requested the migration for 25 Nov, 1000-1500 local time | Complete | Circuit Migrated |  |  | IL-HFA06-0001 | ISRAEL_HAIFA_ICE_CREAM_WAREHOUS |  |  |  |  | 21 Yaakov Moshli St., P.O.B 120 Check Post Haifa Israel | HAIFA | 26112 | Warehouse | Danny Kornblit | Danny.Kornblit@unilever.com | +972 52 700 2124 | Mohamed Diab | Mohamed.Diab@unilever.com | 10MB | 10 |  |  | 2019 | Nov | MPLS | 2019-12-31 | Service | 1 | Congested Link | SC2 | No training required. | 0800 - 1300 UTC | NA | NA | NA | /30 |  | 1st floor, Haifa Ice cream Marlog, Inetwork cabinet | 199.203.37.173/30 Network - 199.203.37.172 First usable - 199.203.37.173 Last usable - 199.203.37.174 Broadcast - 199.203.37.175 Subnet Mask - 255.255.255.252 DNS 1. 194.90.0.1 2. 212.143.0.1 | 199.203.37.174/30 | 199.203.37.173/30 |  |  |  | Cellcom Israel | Local ISP | AS 1680 |  |  |  | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar | 2019-12-18 | [9 empty] | Window Date agreed - End user Comms sent |  | 0800 - 1300 | 1000 - 1500 | 19186 | RCQ000000626647 | Approved | 40061 | CRQ000000623855 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right |  |  |  | 2019-10-01 | 2019-11-01
CKT-I-02-IL-HFA06-0001-ORA-1 | I02WC041ORA1 | 1 | Login via telnet and TACACS. SSH not enabled. Yes | High | RUB/ TUI&I | Israel | Haifa Warehouse | 2019_435 | un-amt-ilhicce01 | un-amt-ilhicce01-vpn002 | Eloise Shepheard | WAN Circuit Migration | Circuit | Orange | Ora |  | LO0048V434 | 2019-08-19 | 2019-09-13 | Complete | 2019-08-26 | 2019-10-31 | Complete | 2019-11-04 | 2019-11-07 | Complete | 2019-11-18 | 2020-07-02 | Complete | 02/07: Migration successful today 29/06: Migration confirmed for 2nd July. FE assigned 28/06: Migration was unsuccessful on 22nd June. Being rescheduled for 2nd July 06/03 No migration will be planned in this site until the migrations in key hubs are completed. 10/12 Pending confirmation from Unilever. GEO IT wants all the locations to have one local MPLS link in the first phase. In a second phase these will be replaced by DMVPN as well 05/12 Pending carrier to confirm delivery dates | Complete | Circuit Migrated | Cisco Unilever Geo-IT |  | IL-HFA06-0001 | ISRAEL_HAIFA_ICE_CREAM_WAREHOUS |  |  |  |  | 21 Yaakov Moshli St., P.O.B 120 Check Post Haifa Israel | HAIFA | 26112 |  | Danny Kornblit | Danny.Kornblit@unilever.com | +972 52 700 2124 |  |  | 6144Kbps | 10 |  |  | 2019 | Nov | MPLS | 2019-12-31 | Service | 1 | Congested Link | SC2 | FE required. | 11am to 17:00pm |  |  |  | /30 |  |  | IP: 82.166.25.213 / sbnet 255.255.255.252 IP: 82.166.25.214 / Subnet : 255.255.255.252 | 82.166.25.213 | 82.166.25.214 |  |  |  | CELLCOM | [5 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar | [10 empty] | Window Date agreed - End user Comms sent |  | 08:00am to 14:00pm | 11:00am to 17:00pm | 83516 | CRQ000000682946 | Approved |  | CRQ000000680021 | Completed | Completed |  |  |  | Circuit Migrated
CKT-I-01-IL-LOD01-0002-GTT-1 | I011214GTT1 | 1 |  | Top | RUB/ TUI&I | Israel | Keshet | 2019_422 | Decommision legacy IEN firewall am-ilapc-vam1 to free up ISR 4451 router. Plan to replace GMPLS with Internet using the ISR 4451 router |  | Agnieszka Pajak | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01689436 | 2019-08-12 | 2019-08-27 | Complete | 2019-08-19 | 2019-08-20 | Complete | 2019-10-28 | 2019-09-04 | Complete | 2019-11-11 | 2020-04-22 | Complete | 18/02 Migration partially implemented. 2nd migration window required in order to complete migration activities. Potential firewall problem that is filtering IKEv2 and IPSEC packets between the Spoke and the Hubs. We agreed together with the local contact to keep the DMVPN configuration on the router since there is no impact (MPLS circuit is on another router). 23/01 Traffic switch successful from Keshet to Haifa CRQ 28555 ¦¦ Internet traffic switchover from Keshet to Haifa sites in Israel ¦¦ CRQ000000634643 20/01 Migration cannot be scheduled for month end - local business requested to reschedule the migration to February. The new date for the migration is 11 Feb. 12/12 Routers need to be exchanged, waiting further confirmation from Unilever on the delivery timelines 18/11 A request has been received today by Mohammed Diab to reschedule the migration in Haifa food and Kashet to January, as per the business request 15/10: Initial assessment commenced. Need clarification from Unilever before continuing preparing for the migration. Migration Date has to be rescheduled. | Complete | Circuit Migrated |  |  | IL-LOD01-0002 | ISRAEL_AIRPORT_CITY |  |  |  |  | Gilboa St., Airport City, P.O.B. 208 | Lod | 70100 |  | Danny Kornblit | Danny.Kornblit@unilever.com | +972 52 700 2124 |  |  | 100 | 100 | 31.9588 | 34.8864 | 2019 | Oct | MPLS | 2019-12-31 | Commercial Benefit |  |  | SC4 | NA | 0800 - 1400 UTC | NA | NA | NA | /30 |  | Floor No. 2, IT Network Room, Main Offices Building | 84.110.40.250/30 WAN Network - 84.110.40.248 First usable - 84.110.40.249 Last usable - 84.110.40.250 Broadcast - 84.110.40.251 Subnet Mask - 255.255.255.252 |  | 84.110.40.250/30 |  |  |  | Bezeq International | Local ISP | AS 8551 |  |  |  | Adrian Lazar | Adrian Lazar | Adrian Lazar | 2020-02-19 |  | Standard site type - Dual MPLS | Complete |  | No |  | No |  | Assessment Complete | Window Date agreed - End user Comms not sent |  | 0800 - 1400 UTC | 1100 - 1700 | 57926 | CRQ000000662290 CRQ 32959 | Approved | 39736 | CRQ000000655762 | Completed | Completed | Tested-Pass |  | Danny Kornblit | Circuit Migrated |  |  |  | 2019-09-01 | 2020-02-01
CKT-I-01-ID-BOG03-0001-VOD-1 |  | 1 | Yes | Medium | SEAA | Indonesia | BGR | 2019_360 | un-sea-idnbgr-drt001 |  | Vishal Joshi | Soft Delete | Circuit | Vodafone Global | Vod |  | UNIAP-IPQM-00001 | 2020-02-28 | 2020-02-28 | Green | 2020-03-06 | 2020-05-22 | Red | 2020-05-15 | 2020-12-31 | Red | 2020-05-29 | 2020-09-30 | Red | Next Action: Finalise circuit ordering. 25-May: Order cancelled with Vodafone. 16-Oct: Local discussion to determine if the site needs to be closed. Currently on hold | Out of Scope | Circuit not ordered | Unilever SNT | Check dates | ID-BOG03-0001 | INDONESIA_BOGOR_FAASRI_DR |  |  |  |  | Jl.Pajajaran No.17 Baranangsiang, Kecamatan Bogor Timur, Kelurahan Baranangsiang, Bogor-16143 | Bogor | 16143 | DR Site | Edy Rohadi | Edy.rohadi@unilever.com | 62818911306, 622180827072 | Aditya Rizqi/ Devita Soendoro | aditya.rizqi@unilever.com devita.soendoro@unilever.com | 150 Mbps | 500 | -6.5911 | 106.7911 | 2019 | Oct | Internet | monthly contract | Commercial Benefit |  |  | SC2 | No Local support available at site. |  | This is a DR site and personnel will escort FE. |  |  | /29 | DR Site for Indonesia business. Needs to replicate head office | [7 empty] | Telekom Indonesia | [5 empty] | Pawan Nandigama | Pawan Nandigama | Pawan Nandigama
CKT-I-01-ID-TRG01-0001-VOD-1 |  | 1 | Two /30 needs to be ordered at minimum for the site | High | SEAA | Indonesia | HO | 2019_362 | un-sea-idnjkt-rtr001 |  | Vishal Joshi | Soft Delete | Circuit | Vodafone Global | Vod |  | UNIAP-IPQM-00002 | 2020-02-28 | 2020-02-28 | Green | 2020-03-06 | 2020-05-22 | Red | 2020-05-15 | 2020-12-31 | Red | 2020-05-29 | 2020-09-30 | Red | Next Action: Finalise circuit ordering. 25-May: Order cancelled with Vodafone. 16-Oct: Local discussion to determine if the site needs to be closed. Currently on hold | Out of Scope | Circuit not ordered | Unilever SNT | Check dates | ID-TRG01-0001 | INDONESIA_BSD HEAD OFFICE |  |  |  |  | BSD Green office park Kav 3 JL Boulevard Barat BSD City Tangerang | BSD | 15345 | Office | Edy Rohadi | Edy.rohadi@unilever.com | 62818911306, 622180827072 | Aditya Rizqi/ Devita Soendoro | aditya.rizqi@unilever.com devita.soendoro@unilever.com | 200M | 500 | 6.301 | 106.649 | 2019 | Oct | Internet | monthly contract | Commercial Benefit |  |  | SC1 | GEO IT support from 8 am to 5 pm |  |  |  |  | /29 | Head office for the Indonesia business. Circa 1100 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | [7 empty] | fibermedia | [5 empty] | Pawan Nandigama | Pawan Nandigama | Pawan Nandigama | [6 empty] | Yes
CKT-I-01-MY-KUL01-0001-VOD-1 | I01154VOD1 | 1 | Yes | Top | SEAA | MALAYSIA | Unilever Malaysia HQ | 2018_140 | un-sea-mysubs-vpn001 | un-sea-mysubs-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Global | Vod |  | UNIAP-IPQM-00003 | 2019-08-19 | 2019-08-27 | Complete | 2019-08-26 | 2019-09-01 | Complete | 2019-11-04 | 2020-08-03 | Complete | 2019-11-18 | 2020-09-08 | Red | Next Action: Vodafone's local supplier is working with GEO IT to get approval to schedule work at site. Pending confirmation from GEO IT. 25-May: Due to COvid - 19 site is closed until 9 Jun. Work to resume after this. 30-Apr: The lock down is extended until 12 May and activity can be planned only after that. 15-Apr: Financial approval received for performing cabling work by Vodafone. Activity on hold as site is under lock down due to covid-19. 3-Feb: Site survey completed. Pending FOC date from Vod | Complete | Circuit Delivered | Circuit Provider |  | MY-KUL01-0001 | MALAYSIA_KUALA_LUMPUR_PANTAI_BARU |  |  |  |  | Level 34, Menara TM, Jalan Pantai Bharu | Kuala Lumpur | 59200 |  | Jeff Ooi | Jeff.ooi@unilever.com | 60126646583 | Dees Rampartab | Dees.Rampartab@unilever.com | 100MB | 100 | 3.1407 | 101.6866 | 2019 | Oct | Internet | 2019-05-29 | Commercial Benefit |  |  | SC2 | Plan for week day migration after 6 pm. Plan between 10 to 20 Aug. | 6 pm local time | Health Declaration. Temp check. Photocopy copy of National ID to be provided for work permit approval. |  |  | /29 | Head office for the Malaysia business. Circa 600 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. |  | IP Address Subnet Mask Note Static 103.54.110.96 255.255.255.248 Network Address Static 103.54.110.97 255.255.255.248 LAN IP / Default gateway Static 103.54.110.98 255.255.255.248 First IP Free to use Static 103.54.110.102 255.255.255.248 Last IP free to use Static 103.54.110.103 255.255.255.248 Broadcast Address | 103.54.110.97 | 103.54.110.98 | 103.54.110.96/29 |  |  | Telekom Malaysia | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual DMVPN |  |  | No | Yes | No |  |  | Window Date agreed - End user Comms not sent |  | 2 am to 8 am UTC | 10am to 4 pm local time. | 113356(CMSP) CHG000000000041774(ServiceNow) | CRQ000000700489 (cancelled) CRQ000000700489 | Approved |  | CRQ000000697759 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-PH-CEB03-0211-PCCW-1 |  | 1 | Device upgrade needed ? Deepak confirms circuit is on hold | High | SEAA | PHILIPPINES | HPC Cebu Sales Office | 2018_183 | un-sea-phlces-drt001 |  | Vishal Joshi | Soft Delete |  | PCCW | PCCW |  | N/A | 2020-04-30 | 2020-04-30 | Green | 2020-05-07 | 2020-05-06 | Green | 2020-07-16 | 2020-07-30 | Red | 2020-07-30 | 2020-08-31 | Red | Next Action: New rows added with updated circuit reference. 14-Jan: This is moved to inscope. | Out of Scope | Circuit not ordered | Unilever SNT |  | PH-CEB03-0211 | PHILIPPINES_CEBU_HPC_SALES_OFFICE |  |  |  |  | THE QC PAVILLION UNIT 211-212 GORORDO AVENUE | Cebu City | 6000 |  | Sheryl Caballero | Cebu.Philippines@unilever.com | +639254521797 |  |  | 10000Kbps | 20 | 10.316944, | 123.9006 | 2019 | Nov | Internet | 2019-12-06 | Commercial Benefit |  |  | 0 | [5 empty] | /30 | [14 empty] | Pawan Nandigama | Pawan Nandigama | Pawan Nandigama
CKT-I-01-PH-CGY02-0001-PCCW-1 |  | 1 | Yes Deepak confirms circuit is on hold | High | SEAA | PHILIPPINES | NORTH MINDANAO SALES OFF (HPC) | 2018_181 | un-sea-phlcds-drt001 |  | Vishal Joshi | Soft Delete |  | PCCW | PCCW |  | N/A | 2020-04-30 | 2020-04-30 | Green | 2020-05-07 | 2020-05-06 | Green | 2020-07-16 | 2020-07-30 | Red | 2020-07-30 | 2020-08-31 | Red | Next Action: New rows added with updated circuit reference. 14-Jan: This is moved to inscope. | Out of Scope | Circuit not ordered | Unilever SNT |  | PH-CGY02-0001 | PHILIPPINES_CAGAYAN_DE_ORO_HPC_SALES_OFFICE |  |  |  |  | Insular Life Building 2F Velez Street Corner Akut Street | Cagayan de Oro City | 9000 |  | Sherly Amba | Cdo.philippines@unilever.com | +63 9553058325 |  |  | 10 Mbps | 10 | 8.4832 | 124.6461 | 2019 | Oct | Internet | 2019-12-07 | Commercial Benefit |  |  | 0 | [5 empty] | /30 | [14 empty] | Pawan Nandigama | Pawan Nandigama | Pawan Nandigama
CKT-I-01-PH-CGY04-0001-PCCW-1 |  | 1 | Deepak confirms circuit is on hold Rajeshware: natting using loopback interface; existing 40M, ordered 10M | High | SEAA | PHILIPPINES | URIC CDO Depot | 2018_180 | un-sea-phlcgy-vpn001 |  | Vishal Joshi | Soft Delete |  | PCCW | PCCW |  | N/A | 2020-04-30 | 2020-04-30 | Green | 2020-05-07 | 2020-05-06 | Green | 2020-07-16 | 2020-07-30 | Red | 2020-07-30 | 2020-08-31 | Red | Next Action: New rows added with updated circuit reference. 14-Jan: This is moved to inscope. | Out of Scope | Circuit not ordered | Unilever SNT |  | PH-CGY04-0001 | PHILIPPINES_CAGAYAN_DE_ORO_CITY_URICDEPOT |  |  |  |  | Jentec Cold Storage Tin-ao, Agusan | Cagayan de Oro City | 9000 |  | Jerwin Formoso | Jerwin.formoso@unilever.com | +639088805749 |  |  | 40Mbps | 10 | 8.4932 | 124.7442 | 2019 | Oct | Internet | 2019-12-08 | Commercial Benefit |  |  | 0 | [5 empty] | /30 | [14 empty] | Pawan Nandigama | Pawan Nandigama | Pawan Nandigama | [7 empty] | Yes
CKT-I-01-PH-CAM01-0001-PCCW-1 |  | 1 | Require discussion of site migration as this device does not terminate an ISP circuit as per network diagram | Medium | SEAA | PHILIPPINES | URIC General Santos Depot | 2018_198 | un-sea-phlges-drt001 |  | Vishal Joshi | Soft Delete |  | PCCW | PCCW |  | N/A | 2020-04-30 | 2020-04-30 | Green | 2020-05-07 | 2020-05-06 | Green | 2020-07-16 | 2020-07-30 | Red | 2020-07-30 | 2020-08-31 | Red | Next Action: New rows added with updated circuit reference. 14-Jan: This is moved to inscope. | Out of Scope | Circuit not ordered | Unilever SNT |  | PH-CAM01-0001 | PHILIPPINES_URIC_Santos City Gensen |  |  |  |  | Alzona compound Purok Malinawon, Conel | General Santos City | 9500 |  | Rhea Donasco | Rhea.Donasco@unilever.com | +639088805736 |  |  | 1024Kbps | 2 | 6.1824 | 125.1889 | 2019 | Nov | 0 | Not Applicable | Commercial Benefit |  |  | 0 | [5 empty] | /30 | [14 empty] | Pawan Nandigama | Pawan Nandigama | Pawan Nandigama
CKT-I-01-SG-SIN99-9999-PCCW-1 |  | 1 | Yes. Existing 500 MB. Require detailed discussion of migration strategy for the site. | Low | SEAA | SINGAPORE | 1 NET Data centre | 2018_209 | un-sea-ul_sg_1-net_gmpls_r |  | Vishal Joshi | Soft Delete | Circuit | PCCW | PCCW |  | N/A | 2020-05-30 | 2020-05-30 | Green | 2020-06-05 | 2020-06-08 | Amber | 2020-08-14 | 2020-08-10 | Green | 2020-08-28 | 2020-08-31 | Amber | Next Action: None 20-May: Moving out of scope as confirmed by Deepak. Will continue with the existing link for one more year. 18 Nov :order not yet released. No order in PCCW Project Management Team at this time | Out of Scope | Circuit not ordered |  |  | SG-SIN99-9999 | SINGAPORE_15 PIONEER WALK_EQUINIX SG2 DC |  |  |  |  | Equinix SG2 Data Centre;15 Pioneer Walk Singapore 627753 | SINGAPORE | 627753 |  | ENC helpdesk | enc@bt.com | 68232321 | Macapagal, Ramir-Asuncion | Ramir-Asuncion.Macapagal@unilever.com | 500M | 1000 | 1.3183 | 103.6926 | 2020 | TBA | Internet | 2020-07-03 | Commercial Benefit |  |  | SC1 | Plan delivery in early May-June 2020 |  | No one onsite, BT warm hands support only. |  |  | /29 | Data centre, will need to review existing BGP configuration
CKT-I-01-LT-VNO02-0030-UNL-1 |  | 1 | Not found in NP, used old BW given. Not sure of IP address mask required Yes | Medium | Europe | LITHUANIA | LITHUANIA_VILNIUS | 2019_513 | un-uen-ltuvil1-rtr001 |  | Agnieszka Pajak | BAU Projects |  | Unilever | Uni |  |  | 2019-08-12 | 2019-08-28 | Complete | 2019-08-19 | 2019-08-28 | Complete | 2019-10-28 | 2019-10-27 | Complete | 2019-11-11 | 2019-10-28 | Complete | 15/11 Migration successful | Complete | Circuit Migrated |  | Check dates | LT-VNO02-0030 | LITHUANIA_VILNIUS |  |  |  |  | Gabijos g. 30 | Vilnius | LT06110 |  | Mykolas Norvaisas | Mykolas.Norvaisas@unilever.com | 37069850977 |  |  | 10Mbps | 40 | 54.7336 | 25.2225 | 2019 | Nov | Internet | Assumed Monthly | New site |  |  | SC2 | [5 empty] | /30 | [14 empty] | Adrian Lazar | Adrian Lazar | Adrian Lazar | [17 empty] | 39803 | CRQ000000615317 | Completed | Completed
CKT-I-01-BE-BRU99-9999-VOD-1 |  | 1 | Yes, but device name is given for BELGIUM_BRUSSELS_HEAD_OFFICE | Top | Europe | Belgium | New Belgium Head Office | 2019_1001 | un-uen-belbru1-rtr001 |  |  | BAU Projects |  | Vodafone Global | VOD |  | 3C03779059 | 2019-09-02 | 2019-02-09 | Complete | 2019-09-09 | 2019-09-07 | Complete | 2019-11-18 | 2019-12-20 | Red | 2019-12-02 |  | Red |  | Pink | Circuit Order Accepted |  |  | BE-BRU99-9999 | [5 empty] | Industrielaan 9, 1070 | Anderlecht |  |  |  | Kees-C.Poot@unilever.com | 3223336666 | Kees-C Poot, Laura Beever | Kees-C.Poot@unilever.com; Laura.Beever@unilever.com | 45MB45MB | 500 |  |  | 2019 | Oct |  |  | New site |  |  |  | New Site - Circuit must be delivered in late September to allow readiness for go live in early October
CKT-I-02-BE-BRU99-9999-GTT-1 |  | 1 | Yes, but device name is given for BELGIUM_BRUSSELS_HEAD_OFFICE | Top | Europe | Belgium | New Belgium Head Office | 2019_1002 | un-uen-belbru1-vpn001 |  |  | BAU Projects |  | GTT | GTT |  | DIA/01696392 | 2019-08-12 | 2019-12-08 | Complete | 2019-08-19 | 2019-08-21 | Complete | 2019-10-28 | 2020-05-06 | Red | 2019-11-11 | 2020-06-30 | Red | 24/10 ETA 20/12 | Yellow | Circuit Order Accepted |  |  | BE-BRU99-9999 | [5 empty] | Industrielaan 9, 1070 | Anderlecht | 1070 |  | Kees-C Poot + Laura Beever | Laura.Beever@unilever.com, Erik.Kooy@unilever.com | + 31 6 53233150, +32 499586008 | Kees-C Poot, Laura Beever | Kees-C.Poot@unilever.com; Laura.Beever@unilever.com | 100MB | 500 | 50.8282 | 4.3143 | 2019 | Oct |  |  | New site |  |  |  | New Site - Circuit must be delivered in late September to allow readiness for go live in early October | [6 empty] | 5th floor, Citydox building. Server room. | 87.119.85.248/30 Network - 87.119.85.248 First usable - 87.119.85.249 Last usable - 87.119.85.250 Broadcast - 87.119.85.251 Subnet Mask - 255.255.255.252 | [5 empty] | Eurofibre | GTT Brussels | AS 3257
CKT-I-01-DE-HEN01-0001-GTT-1 |  | 1 | Require /29+ /30 | Top | Europe | GERMANY | Heilbronn | 2018_81 | un-uen-deuhei1-vpn002 |  |  | BAU Projects |  | GTT | GTT |  | DIA/01726392 | 2019-08-21 | 2019-09-20 | Complete | 2019-08-28 | 2019-10-05 | Complete | 2019-11-06 | 2020-03-23 | Complete | 2019-11-20 |  | Red | 24/10 FOC Jan, GTT trying to bring forward to Dec Deepak is awaiting order forms from GTT once final solution is confirmed. | Yellow | Circuit Delivered |  |  | DE-HEN01-0001 | GERMANY_HEILBRONN_KNORRSTRASSE |  |  |  |  | KNORRSTRASSE 1 | HEILBRONN | 74074 |  |  |  |  | Thomas Dehmel, Stefan Hahnkamm | Thomas.Dehmel@unilever.com; Stefan.Hahnkamm@unilever.com | 100MB | 100 | 49.1338 | 9.2103 | 2019 | Oct | Internet | 2000-01-01 | DC/Office Move |  |  | SC1 | [5 empty] | /30 |  | 1st Floor, DC4 Comms Room | 154.14.9.112/28 Network - 154.14.9.112 First usable - 154.14.9.113 Last usable - 154.14.9.126 Broadcast - 154.14.9.127 Subnet Mask - 255.255.255.240 | [5 empty] | DTAG
CKT-I-02-DE-HEN01-0001-GTT-1 |  | 1 | Require /29+ /30 | Top | Europe | GERMANY | Heilbronn | 2018_82 | un-uen-deuhei1-vpn001 |  |  | BAU Projects |  | GTT | GTT |  | DIA/01726381 | 2019-08-21 | 2019-09-20 | Complete | 2019-08-28 | 2019-10-05 | Complete | 2019-11-06 | 2020-04-21 | Complete | 2019-11-20 |  | Red | 24/10 FOC Jan, GTT working to bring delivery date to Dec Deepak is awaiting order forms from GTT once final solution is confirmed. | Yellow | Circuit Delivered |  |  | DE-HEN01-0001 | GERMANY_HEILBRONN_KNORRSTRASSE |  |  |  |  | KNORRSTRASSE 1 | HEILBRONN | 74074 |  |  |  |  | Thomas Dehmel, Stefan Hahnkamm | Thomas.Dehmel@unilever.com; Stefan.Hahnkamm@unilever.com | 100MB | 100 | 49.1338 | 9.2103 | 2019 | Oct | Internet | 2000-01-01 | DC/Office Move |  |  | SC1 | [5 empty] | /30 |  | 1st Floor, DC4 Comms Room | 154.14.8.240/28 Network - 154.14.8.240 First usable - 154.14.8.241 Last usable - 154.14.8.254 Broadcast - 154.14.8.255 Subnet Mask - 255.255.255.240 | [5 empty] | DTAG
CKT-I-01-DE-PEN99-9999-CTL-1 |  | 1 | Not found in BT document or NP, Not able to locate the device. | Top | Europe | GERMANY | Pensionskasse Berolina VVaG | 2019_1002 | ?? |  |  | BAU Projects |  | CenturyLink | CL |  | FRO2006828788 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-08-29 | Complete | 2019-10-21 | 2019-11-22 | Complete | 2019-11-04 |  | Red |  | Pink | Circuit Delivered |  |  | DE-PEN99-9999 | [5 empty] | Spitalerstrasse 16 | Hamburg | [5 empty] | Thomas Dehmel, Stefan Hahnkamm | Thomas.Dehmel@unilever.com; Stefan.Hahnkamm@unilever.com |  | 50 |  |  | 2019 | Oct |  |  | New site |  |  |  | New Site - Circuit must be delivered in late September to allow readiness for go live in early October |  |  |  |  | /30 |  |  | 212.162.29.224/30 CTL: 212.162.29.225/30 Uni: 212.162.29.226/30 | [11 empty] | -BAU- | -BAU- | -BAU-
CKT-I-02-DE-PEN99-9999-GTT-1 |  | 1 | Not found in BT document or NP, Not able to locate the device. | Top | Europe | GERMANY | Pensionskasse Berolina VVaG | 2019_1002 | ?? |  |  | BAU Projects |  | GTT | GTT |  | DIA/01714168 | 2019-08-21 | 2019-08-21 | Complete | 2019-08-28 | 2019-08-29 | Complete | 2019-11-06 | 2020-01-30 | Red | 2019-11-20 |  | Red |  | Yellow | Circuit Order Accepted |  |  | DE-PEN99-9999 | [5 empty] | Spitalerstrasse 16 | Hamburg |  |  | Thomas Dehmel + Stefan Hahnkamm | Thomas.Dehmel@unilever.com, Stefan.Hahnkamm@unilever.com | + 49 40 3493 4431, + 49 173 6142674 | Thomas Dehmel, Stefan Hahnkamm | Thomas.Dehmel@unilever.com; Stefan.Hahnkamm@unilever.com |  | 100 |  |  | 2019 | Oct |  |  | New site |  |  |  | New Site - Circuit must be delivered in late September to allow readiness for go live in early October |  |  |  |  | /30 |  | 1st floor, Spitalerstrasse 16 (Seeburg), Server Room | 154.14.0.204/30 Network - 154.14.0.204 First usable - 154.14.0.205 Last usable - 154.14.0.206 Broadcast - 154.14.0.207 Subnet Mask - 255.255.255.252 | [5 empty] | Versatel | HAM1IR
CKT-I-01-CL-SCL99-9999-CTL-1 |  | 1 | Not found in NP, used old BW given. Not sure of IP address mask required YES. Existing reported as 80 MB | Top | Latin America | Chile | Carrascal | 2019_1004 | un-ula-chlcar-rtr001 |  |  | BAU Projects |  | CenturyLink | CL |  | FRO2006829109 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-08-29 | Complete | 2019-10-21 | 2019-12-20 | Complete | 2019-11-04 |  | Red | 17/01 Carrier is waiting for the Electrical company approval of the project, after approval they'll work on the external route. Once this is finished they'll be able to deliver the service. Therefore any delivery date is suspect until Orange get the approval. | Pink | Circuit Delivered |  |  | CL-SCL99-9999 | [5 empty] | Avenida Carrascal 3551, Quinta Normal | Santiago (CL-RM) | 8530028 |  | Miguel Parada/Ricardo Caldes | miguel.parada@unilever.com / Ricardo.caldes@unilever.com | + 56 9 982191949 | Ricardo Caldes | Ricardo.caldes@unilever.com | 0 | 100 | -33.3793 | -70.5303 | 2019 | Nov |  |  | DC/Office Move |  |  | SC2 | New Site - Link required in October to allow go live in November |  |  |  |  | /29 | Head office for the Chile business. Circa 900 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. |  | 67.73.177.244/30 CTL: 67.73.177.245/30 UNI: 67.73.177.246/30 | 67.73.177.245/30 | 67.73.177.246/30 | [9 empty] | -BAU- | -BAU- | -BAU-
CKT-I-02-CL-SCL99-9999-ORA-1 |  | 1 | Existing 160MB and 80 MB | Top | Latin America | Chile | Carrascal | 2019_1004 | un-ula-chlcar1-vpn001 |  |  | BAU Projects |  | Orange | ORA |  | GO09XEJ13E | 2019-09-02 | 2019-02-09 | Complete | 2019-09-09 | 2019-10-10 | Complete | 2019-11-18 | 2020-03-27 | Red | 2019-12-02 |  | Red |  | Pink | Circuit Order Accepted |  |  | CL-SCL99-9999 | [5 empty] | Avenida Carrascal 3551, Quinta Normal | Santiago (CL-RM) | 8530028 |  | Miguel Parada/Ricardo Caldes | miguel.parada@unilever.com / Ricardo.caldes@unilever.com | + 56 9 982191949 | Ricardo Caldes | Ricardo.caldes@unilever.com | 160MB160MB | 100 | -33.3793 | -70.5303 | 2019 | Nov |  |  | DC/Office Move |  |  | SC2 | New Site - Link required in October to allow go live in November |  |  |  |  | /29 | Head office for the Chile business. Circa 900 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. |  | Default Gateway 186.67.33.97 255.255.255.248 Rango de IP’s 186.67.33.97 - 186.67.33.102 DNS 200.72.1.5 – 20.72.1.11 | [5 empty] | Entel | [15 empty] | Yes
CKT-I-01-CL-VIT99-9999-CTL-1 |  | 1 | Not found in BT document or NP, Not able to locate the device. | Top | Latin America | Chile | Oficina Vitacura | 2019_1003 | ?? |  |  | BAU Projects |  | CenturyLink | CL |  | FRO2006829121 | 2019-08-05 | 2019-08-27 | Complete | 2019-08-12 | 2019-08-29 | Complete | 2019-10-21 | 2019-12-03 | Complete | 2019-11-04 |  | Red | 16/10 (AP) Site criticality. Circuits to be delivered by Nov 20. This was raised with provider is now being escalated. | Pink | Circuit Delivered |  |  | CL-VIT99-9999 | [5 empty] | Av. las Condes 11000 | Vitacura | 7650777 |  | Miguel Parada/Ricardo Caldes | miguel.parada@unilever.com / Ricardo.caldes@unilever.com | + 56 9 982191949 | Ricardo Caldes | Ricardo.caldes@unilever.com |  | 60 |  |  | 2019 | Oct |  |  | New site |  |  | SC2 | New Site - Link required in October to allow go live 1st November |  |  |  |  | /29 | Head office for the Chile business. Circa 900 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. |  | 67.73.177.240/30 CTL: 67.73.177.241/30 UNI: 67.73.177.242/30 | 67.73.177.241/30 | 67.73.177.242/30 | [9 empty] | -BAU- | -BAU- | -BAU-
CKT-I-02-CL-VIT99-9999-ORA-1 |  | 1 | Not found in BT document or NP, Not able to locate the device. | Top | Latin America | Chile | Oficina Vitacura | 2019_1003 | ?? |  |  | BAU Projects |  | Orange | ORA |  | LO0048WK4B | 2019-09-02 | 2019-02-09 | Complete | 2019-09-09 | 2020-03-10 | Complete | 2019-11-18 | 2019-12-13 | Complete | 2019-12-02 |  | Red | 16/10 (AP) Site criticality. Circuits to be delivered by Nov 20. This was raised with provider is now being escalated. | Pink | Circuit Delivered |  |  | CL-VIT99-9999 | [5 empty] | Av. las Condes 11000 | Vitacura | 7650777 |  | Miguel Parada/Ricardo Caldes | miguel.parada@unilever.com / Ricardo.caldes@unilever.com | + 56 9 982191949 | Ricardo Caldes | Ricardo.caldes@unilever.com |  | 60 |  |  | 2019 | Oct |  |  | New site |  |  | SC2 | New Site - Link required in October to allow go live 1st November |  |  |  |  | /29 | Head office for the Chile business. Circa 900 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. |  | IP: 186.67.33.98 – 102 /29 Gateway: 186.67.33.97 DNS: 200.72.1.5 – 200.72.1.11 | [5 empty] | Entel | [5 empty] | -BAU- | -BAU- | -BAU- |  | Copper - RJ45
CKT-I-01-AU-NRC01-0001-GTT-1 | I0157GTT1 | 1 | Yes. Confirm if /30 ordered | Top | SEAA | Australia | North Rocks | 2018_24 | un-sea-ausnrk-p2p001 | un-sea-ausnrk-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | GTT | GTT |  | DIA/01728861 | 2019-08-23 | 2019-08-23 | Complete | 2019-08-30 | 2019-09-01 | Complete | 2019-11-08 | 2019-10-21 | Complete | 2019-11-22 | 2020-04-16 | Complete | 9-Apr: Agreed with Dane to schedule migration on 16th APril. 19-Mar: Due to Covid-19 situation, migration in Aus is on hold. 12-Mar: Migration date of 20 mar agreed with GEO IT. 9-Mar: Pending feedback from GEO IT on the migration date. 2-Mar: Circuit tested and pending confirmation on migration date 10-Feb: Pending confirmation on availability of GEO IT for circuit testing and confirmation on migration date. 3-Feb: GEO IT feedback to push the migration to end of March due to CBD site move. Welington to discuss further to confirm schedule in Feb. 27-Jan: Need to schedule testing for this link. Working with GEO IT to schedule testing. Proposed migration date is 13 Feb and need to be confirmed 10 Jan: Don't have router access. Requested access. TACACS config WIP | Complete | Circuit Migrated |  |  | AU-NRC01-0001 | [5 empty] | 219 North Rocks Road | North Rocks | 2141 |  | Chris.Sagadevan | Chris.Sagadevan@unilever.com |  | Dane Ryan | Dane.Ryan@unilever.com | 100M | 200 | -33.7766 | 151.014 | 2019 | Oct | Internet |  | CBD Office closure |  |  | SC1 | Plan migration mid of the month , around 15th and preferably on thursday. Option 1is to do on 13th Feb | 5 pm to 11 pm | Need to complete Online induction - 2 days before and SWMS document (SAfe Working Methods Statement) Online induction links to be provided by Dane SWMS is a standard requirement in Aus and follow up with NTT | Yes, Need liability insurance |  |  |  | Ground floor, Fibre connection for the bulk of the services in the MER Ground Floor. Computer Room. Cabinet 1. RU-32. Port 9 of the 72NO-H53-G000-F01-01. | 98.124.141.56/30 LAN Network - 98.124.141.56 First usable - 98.124.141.57 Last usable - 98.124.141.58 Broadcast - 98.124.141.59 Subnet Mask - 255.255.255.252 | 192.157.25.17/30 | 192.157.25.18/30 |  |  |  | Optus | SYD1OSN | AS 3257 |  |  |  | Karthik Ravi | Pawan Nandigama | Pawan Nandigama |  | Copper - RJ45 | Complex site type - requires redesign | Complete |  | No |  | No |  | Assessment Complete MOP created & config created Received tunnel IP or LAN IP (if required) |  |  | 7:00 am to 12:00 pm UTC | 5 pm to 11 pm local time | 34783 | CRQ000000640114 | Approved | 40909 | CRQ000000634739/CRQ000000685412 | Completed | Completed | Tested -Pass-First Time | Everything worked fine along with good speed and Pawan confirmed even the Zscaler is fine |  | Circuit Migrated - First Time right |  |  |  |  | 2020-02-01
CKT-I-01-AU-NRC01-0001-VOD-1 | I0157VOD1 | 1 | Yes. Confirm if /30 ordered | Top | SEAA | Australia | North Rocks | 2018_24 | un-sea-ausnrk-vpn001 |  | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Global | VODSG |  |  | 2019-09-02 | 2019-09-02 | Complete | 2019-09-09 |  | Complete | 2019-11-18 |  | Complete | 2019-12-02 | 2020-05-07 | Complete | Next Action: Cisco to submit RFC and proceed scheduling the migration. 28-Apr: GEO IT agreed on a migration date on 7th May. 24-Apr: Testing of vodafone link carried out, speed was satisfactory. 9-Apr: Dane will support local testing. Vodafone to schedule remote testing/troubleshooting and agree schedule with Dane. 19-Mar: Due to Covid-19 situation, all work in Aus is on hold. 9-Mar: Vodafone has agreed to dispatch FE to site for testing and fixing speed issue. Pending GEO IT availability to schedule the testing. 2-Mar: Issues with speed during testing of new link. 10-Feb: Pending confirmation on availability of GEO IT for circuit testing and confirmation on migration date. 3-Feb: GEO IT feedback to push the migration to end of March due to CBD site move. Welington to discuss further to confirm schedule in Feb. 27-Jan: Need to schedule testing for this link. Working with GEO IT to schedule testing. Proposed migration date is 20 Feb and need to be confirmed | Complete | Circuit Migrated | Cisco |  | AU-NRC01-0001 | [5 empty] | 219 North Rocks Road | North Rocks | 2141 |  | Chris.Sagadevan | Chris.Sagadevan@unilever.com |  | Dane Ryan | Dane.Ryan@unilever.com | 100Mbps | 200 | -33.7766 | 151.014 | 2019 | Oct | Internet |  | CBD Office closure |  |  | SC1 | Plan migration mid of the month , around 15th and preferably on thursday Option 1 is 20th Feb Option 2 is 12th Mar | 5 pm to 11 pm | Need to complete Online induction - 2 days before and SWMS document (SAfe Working Methods Statement) Online induction links to be provided by Dane SWMS is a standard requirement in Aus and follow up with NTT | Yes, Need liability insurance | [5 empty] | 58.96.16.1 | 58.96.16.2 | 115.70.224.96/29 |  |  | Telstra | [5 empty] | Pawan Nandigama | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Complex site type - requires redesign | Complete |  | No |  | Yes |  | Assessment Complete | Window Date agreed - End user Comms not sent |  | 7:00 am to 1:00 pm UTC | 5 pm to 11 pm local time | 40325 | CRQ000000643822 | Approved | 40973 | CRQ000000636186 | Completed | Completed | Tested-Fail | Everything worked fine except the speed test as it was nowhere closed to 200mbps with both download the upload speed. Hisham from vodafone with check with expereo and come back. Post that we will considered this as complete. | Dane Ryan | Circuit Migrated - First Time right |  | INC000107325434 | Internet traffic for corporate users was not working as the IP pool provided by Vodafone was not working. Summary of fix: “natting for corporate and guest users was done over the WAN interface instead of the IP pool provided by Vodafone as the users were unable to access the internet over the IP pool” | 2020-01-01 | 2020-02-01
Out of Scope |  | 1 | Out of scope - No Device Access | High | Latin America | Chile | Site Carrascal | 2019_54 | un-ula-branat1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | TI Sparkle | TIS |  | #NO MATCH | 2019-08-27 | 2019-08-27 | Out of Scope | 2019-08-27 | #NO MATCH | Out of Scope | 2019-08-27 | #NO MATCH | Out of Scope | 2019-08-27 |  | Out of Scope | Out of Scope | Out of Scope | Circuit not ordered |  |  | CL-SCL03-0002 | CHILE_CARRASCAL |  |  |  |  | Av Carrascal 3301, Quinta Normal | Santiago (CL-RM) | 8530075 |  | Miguel Parada/Ricardo Caldes | miguel.parada@unilever.com / Ricardo.caldes@unilever.com | + 56 9 982191949 | Ricardo Caldes | Ricardo.caldes@unilever.com | 2Mbps | 160 | 33°25'35.8"S | 70°40'56.0"W | 2019 | Oct | MPLS | 2019-10-01 | Commercial Benefit | 1 | 0 | SC2 | [5 empty] | /29 | Head office for the Chile business. Circa 900 users. Assumption is each user will be carrying three devices. Assumption is a total 100 concurrent TCP Internet sessions per-user. Users consume cloud services (O365, SalesForce, PowerBI, etc) on their work laptop, a work smartphone/tablet that is used for reporting, emails, etc and a personal smartphone. | #NO MATCH | #NO MATCH |  |  |  | #NO MATCH | #NO MATCH | #NO MATCH | [9 empty] | #NO MATCH
Out of Scope |  | 1 | Out of scope - No Device Access | Medium | North America | United States |  | 2019_54 | un-ula-branat1-rtr001 |  | Juan Simon | WAN Circuit Migration |  |  |  |  | #NO MATCH | 2019-08-27 | 2019-08-27 | Out of Scope | 2019-08-27 | #NO MATCH | Out of Scope | 2019-08-27 | #NO MATCH | Out of Scope | 2019-09-10 |  | Out of Scope | Out of Scope | Out of Scope | Circuit not ordered |  |  |  | USA_HENDERSON_EASTGATE_ROAD | [13 empty] | 2Mbps | 10 |  |  |  |  | MPLS | 2019-06-30 | Commercial Benefit |  |  | 0 | [5 empty] | /30 |  | #NO MATCH | #NO MATCH |  |  |  | #NO MATCH | #NO MATCH | #NO MATCH | [9 empty] | #NO MATCH
Under Review |  | 1 | Found the network Diagram but not able to locate the device. | High | SEAA | PHILIPPINES | URIC Cebu Depot | 2018_186 | ?? |  | Vishal Joshi | Soft Delete |  | Vodafone Global | Vod |  | #NO MATCH | 2020-04-30 | 2020-04-30 | Under Review | 2020-05-07 | #NO MATCH | Under Review | 2020-07-16 | #NO MATCH | Under Review | 2020-07-30 | 2020-08-31 | Under Review | Next Action: New rows added with updated circuit reference. 14-Jan: This is moved to inscope. | Out of Scope | Circuit not ordered | Unilever SNT | #INVALID OPERATION | PH-CEB01-0001 | PHILIPPINES_MANDAUE_CITY_URIC_DEPOT |  |  |  |  | PC Suico Street, Tabok | Mandaue city | 6014 |  | Doroteo Egoc | Doroteo.Egoc@unilever.com | +639088805748 | #N/A | #N/A |  | 10 | 10.345491, | 123.9448 | 2019 | Oct | Internet | 2019-12-07 | Commercial Benefit |  |  | 0 | [5 empty] | /30 |  | #NO MATCH | #NO MATCH |  |  |  | #NO MATCH | #NO MATCH | #NO MATCH | [5 empty] | Pawan Nandigama | Pawan Nandigama | Pawan Nandigama |  | #NO MATCH |  |  |  |  | Yes
Under Review |  | 1 | Found the network Diagram but not able to locate the device. | Medium | SEAA | Philippines | URIC Cebu Depot | 2018_186 | ?? |  | Vishal Joshi | Soft Delete |  | Vodafone Global | Vod |  | #NO MATCH | 2020-04-30 | 2020-04-30 | Under Review | 2020-05-07 | #NO MATCH | Under Review | 2020-07-16 | #NO MATCH | Under Review | 2020-07-30 | 2020-08-31 | Under Review | Next Action: New rows added with updated circuit reference. 14-Jan: This is moved to inscope. | Out of Scope | Circuit not ordered | Unilever SNT | #INVALID OPERATION | PH-CEB01-0001 | PHILIPPINES_MANDAUE CITY_PC SUICO STREET_CEBU |  |  |  |  | PC Suico Street, Tabok | Mandaue city | 6014 |  | Doroteo Egoc | Doroteo.Egoc@unilever.com | +639088805748 | #N/A | #N/A |  | 20 | 10.345491, | 123.9448 | 2019 | Nov | Internet | 2019-07-31 | Service | 1 | Congested Link | SC4 | [5 empty] | /30 |  | #NO MATCH | #NO MATCH |  |  |  | #NO MATCH | #NO MATCH | #NO MATCH | [5 empty] | Pawan Nandigama | Pawan Nandigama | Pawan Nandigama |  | #NO MATCH |  |  |  |  | Yes
CKT-I-01-BR-CGE03-1651-CTL-1 | I0110944CTL1 | 1 | Yes |  | Latin America | Brazil | Contagem | 2019_45 | un-ula-bracon1-pio001 | un-ula-bracon1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2006862127 / CID 500152653 | 2019-10-31 | 2019-10-31 | Complete | 2019-11-07 | 2019-11-08 | Complete | 2020-01-16 | 2020-01-31 | Complete | 2020-01-30 | 2020-04-06 | Complete | Apr-6: Migration successfully completed. Mar-23: Migration re-scheduled for 6-April at 9AM local. Mar-13: Migrations in Brazil postponed indefinitely due to coronavirus. Mar-12: Migration unsuccessful. DMVPN tunnel did not come up: firewall issue. Need to resolve issue. Mar-3: GeoIT asked to migrate on March 12th at 8AM local. Mar-2: Circuit testing OK. Migration date proposed for March 12, pending confirmation from site. Circuits replacement for site Natal | Complete | Circuit Migrated |  |  | BR-CGE03-1651 | BRAZIL_CONTAGEM_IC |  |  |  |  | AVENIDA WILSON TAVARES RIBEIRO | CONTAGEM | 32183-680 |  |  |  |  | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 3072 kbps | 10 | -18.5775 | -45.4513 | 2019 | Nov | Internet |  | Service | 1 | 0 |  |  | 8AM local | Field Engineer Full Name, CPF, RG (The local engineer knows what is these information). |  |  | /30 |  |  | WAN: 200.186.221.200/30 CTL: 200.186.221.201/30 UNI:200.186.221.202/30 | 200.186.221.201 | 200.186.221.202 | 200.186.221.200/30 | [8 empty] | Emir Jukovic | Emir Jukovic | Emir Jukovic |  |  | Complex site type - requires redesign | Complete | NO | Yes |  | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 12PM UTC | 9AM Local | 52438 46389 (old) | CRQ000000656075 CRQ000000650437 (old) | Approved | 41715 | CRQ000000653166 | Completed | Completed | Tested -Pass-First Time | March 2nd |  | Circuit Migrated - First Time right | DMVPN |  |  |  | 2020-03-01
CKT-I-01-BR-TSA01-4855-CTL-1 | I014886CTL1 | 2 | Yes. Could also be device name with 2MB and /30 (ISR4331), un-ula-bratab1-pio001 - 3MB, /30, ISR4331 | High | Latin America | Brazil | Taboao | 2019_64 | un-ula-bratab1-rtr001 | un-ula-bratab1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-22 | 2020-05-20 | Green | 2020-07-31 | 2020-07-20 | Green | 2020-08-14 | 2020-08-20 | Red | 29-Apr: Pending circuit order to provider. | On Hold | Circuit not ordered | Unilever SNT |  | BR-TSA01-4855 | BRAZIL_TABOAO |  |  |  |  | Rua Guilherme de Almeida, nº147, Jardim Salete (altura do Km 274,2 da Rod Regis Bittencourt, nº4855) | Taboao da Serra | 06.793-200 |  |  |  |  | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 2MB | 10 | -23.6209 | -46.7855 | 2019 | Nov | MPLS |  | Commercial Benefit | 3 | 0 | [6 empty] | /30 | [14 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo
CKT-I-01-GB-PAL99-9999-GTT-1 |  | 1 | Not found in BT document or NP | High | Europe | UNITED KINGDOM | Palm Court | 2019_1005 | ?? |  |  | BAU Projects |  | GTT | GTT |  | DIA/01746644 | 2019-09-19 | 2019-09-19 | Complete | 2019-09-26 | 2019-09-24 | Complete | 2019-12-05 | 2020-06-14 | Red | 2019-12-19 |  | Red | On hold until further notice | On Hold | Circuit Order Accepted |  |  | GB-PAL99-9999 | [5 empty] | 4 Heron Square | Richmond | TW9 1EW | [7 empty] | 100 | 51.4583 | -0.30839 | 2019 | Dec |  | Not Applicable | New site Integration | [17 empty] | Openreach
CKT-I-01-GB-SPR99-9999-GTT-1 |  | 1 | Not found in BT document or NP | High | Europe | UNITED KINGDOM | Springfield Road | 2019_1006 |  |  |  | BAU Projects |  | GTT | GTT |  | DIA/01746648 | 2019-09-19 | 2019-09-19 | Complete | 2019-09-26 | 2019-09-24 | Complete | 2019-12-05 | 2020-06-14 | Red | 2019-12-19 |  | Red | On hold until further notice | On Hold | Circuit Order Accepted |  |  | GB-SPR99-9999 | [5 empty] | cnr Bullsbrook Road | Hayes | UB4 0TP | [7 empty] | 100 | 51.5122 | -0.3998 | 2019 | Dec |  | Not Applicable | New site Integration | [17 empty] | Openreach
CKT-I-01-GB-TOL99-9999-GTT-1 |  | 1 | Not found in BT document or NP | High | Europe | UNITED KINGDOM | Tolldown Barn | 2019_1007 |  |  |  | BAU Projects |  | GTT | GTT |  | DIA/01746730 | 2019-09-19 | 2019-09-19 | Complete | 2019-09-26 | 2019-09-24 | Complete | 2019-12-05 | 2020-06-14 | Red | 2019-12-19 |  | Red | On hold until further notice | On Hold | Circuit Order Accepted |  |  | GB-TOL99-9999 | [6 empty] | Dyrham | SN14 8HZ | [7 empty] | 100 | 51.4912 | -2.3584 | 2019 | Dec |  | Not Applicable | New site Integration | [17 empty] | Talk Talk
CKT-I-01-GB-PAL99-9999-PCCW-1 |  | 1 | Not found in BT document or NP | High | Europe | UNITED KINGDOM | Palm Court | 2019_1005 |  |  |  | BAU Projects |  | PCCW | PCCW |  | N/A | 2020-02-28 | 2020-02-28 | Complete | 2020-03-06 | 2020-03-06 | Complete | 2020-05-15 | 2020-05-29 | Red | 2020-05-29 |  | Red |  | Yellow | Circuit Order Accepted |  |  | GB-PAL99-9999 | [5 empty] | 4 Heron Square | Richmond | TW9 1EW | [7 empty] | 100 | 51.4583 | -0.30839 | 2019 | Dec |  | Not Applicable | New site Integration
CKT-I-01-GB-SPR99-9999-PCCW-1 |  | 1 | Not found in BT document or NP | High | Europe | UNITED KINGDOM | Springfield Road | 2019_1006 |  |  |  | BAU Projects |  | PCCW | PCCW |  | N/A | 2020-02-28 | 2020-02-28 | Complete | 2020-03-06 | 2020-03-06 | Complete | 2020-05-15 | 2020-05-29 | Red | 2020-05-29 |  | Red |  | Yellow | Circuit Order Accepted |  |  | GB-SPR99-9999 | [5 empty] | cnr Bullsbrook Road | Hayes | UB4 0TP | [7 empty] | 100 | 51.5122 | -0.3998 | 2019 | Dec |  | Not Applicable | New site Integration
CKT-I-01-GB-TOL99-9999-PCCW-1 |  | 1 | Not found in BT document or NP | High | Europe | UNITED KINGDOM | Tolldown Barn | 2019_1007 |  |  |  | BAU Projects |  | PCCW | PCCW |  | N/A | 2020-02-28 | 2020-02-28 | Complete | 2020-03-06 | 2020-03-06 | Complete | 2020-05-15 | 2020-05-29 | Red | 2020-05-29 |  | Red |  | Yellow | Circuit Order Accepted |  |  | GB-TOL99-9999 | [6 empty] | Dyrham | SN14 8HZ | [7 empty] | 100 | 51.4912 | -2.3584 | 2019 | Dec |  | Not Applicable | New site Integration
CKT-I-01-EE-TLL03-0001-UNL-1 |  | 1 | Not found in NP, used old BW given. Not sure of IP address mask required Existing reported as 1984 kbps. Could also be un-uen-eetal2 reported as 8MB | Top | Europe | Estonia | Talinn | 2019_149 | un-uen-esttal1-rtr001 |  |  | SNT |  | Unilever | Uni |  |  | 2019-09-16 | 2019-09-16 | Complete | 2019-09-23 | 2019-09-21 | Complete | 2019-12-02 | 2019-11-20 | Complete | 2019-12-16 | 2019-10-10 | Complete | Completed by UL/BT on 10/10 | Complete | Circuit Migrated |  | Check dates | EE-TLL03-0001 | ESTONIA_TALINN |  |  |  |  | Sopruse pst 145 | Tallinn | 145 13417 |  |  |  |  | Mykolas Norvaisas | Mykolas.Norvaisas@unilever.com | 0 | 40 | 59.4153 | 24.7108 | 2019 | Oct | MPLS |  | Service | 1
CKT-I-01-MZ-MPM02-0001-VOD-1 | I011217VOD1 | 1 | Yes. Confirm if /30 ordered | Low | Africa | MOZAMBIQUE | Maputo | 2018_159 | un-amt-mozmap-vpn002 | un-amt-mozmap-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | VOD |  | 2-18805196097 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-07-27 | Complete | 2019-11-26 | 2020-08-12 | Complete | Action Item : ISP to proceed with circuit delivery 2904-Commercial clarification to be resolved by the 0805. Will then proceed with delivery. 2204- Project ON HOLD - due to COVID-19 lockdown. Feedback regarding lockdown regulations to be provided by Vodacom LCON on the 2904. 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Circuit Provider |  | MZ-MPM02-0001 | MOZAMBIQUE_MAPUTO_UNILEVER_MOCAMBIQUE_LDA |  |  |  |  | Av. 24 de Julho, Building 24 | MAPUTO | 1100 | [6 empty] | 20MB | 25 | -25.9662 | 32.5754 | 2020 | May | Internet |  | Commercial Benefit | [11 empty] | 197.235.19.36/30 197.235.17.208/29 | 197.235.19.37/30 | 197.235.19.38/30 | 197.235.17.208/29 |  |  | Vodacom Nigeria | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | Yes |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 08:00 Hrs. To 14:00 Hrs. | 10:00 Hrs. To 16:00 Hrs | 111463 | CRQ000000699031 | Approved |  | CRQ000000696298 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-03-01
CKT-I-02-MZ-MPM02-0001-VOD-1 | I021217VOD1 | 1 | No device access to validate | Low | Africa | MOZAMBIQUE | Maputo | 2018_159 | un-amt-mozmap-vpn001 | un-amt-mozmap-vpn001 | Vishal Joshi | WAN Circuit Migration | Soft Upgrade | Vodafone Local | VOD |  | 2-18805196096 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-09-01 | Complete | 2019-11-26 | 2020-09-16 | Red | 18-May: Novation to be effective 4th Aug. 29-Apr: These are move out of WAN migration scope to SNT. These circuits will only have change in ownership and no circuit migration required. 03-Feb - Site assessment & Design document verification in progress | Pink | Circuit Delivered | Circuit Provider |  | MZ-MPM02-0001 | MOZAMBIQUE_MAPUTO_UNILEVER_MOCAMBIQUE_LDA |  |  |  |  | Av. 24 de Julho, Building 24 | MAPUTO | 1100 | [6 empty] | 0 | 20 | -25.9662 | 32.5754 | 2020 | May | Internet |  | Commercial Benefit | [17 empty] | Vodacom\?? | [9 empty] | Copper - RJ45 |  |  |  |  | Yes |  |  | Assessment Complete | [18 empty] | 2020-03-01
CKT-I-02-ZA-DUR03-0001-VOD-1 | I0227VOD1 | 1 | Need to order /30 + /29 for this site. Other router at site um-amt-zafumh-vpn002(152.109.111.16) - 200MB, /29+/30,ISR4451-X, Also one Agile at site which is currently from 50Mbps and is to be migrated and upgraded to 200Mbps – this is on un-amt-zafumh-agi001. This is the circuit on which the Agile device will be collapsed into the secondary circuit on site. Revalidate which device is secondary during prep. | Medium | Africa | SOUTH AFRICA | Unilever La Lucia Ridge Office, Durban | 2018_232 | un-amt-zafumh-vpn002 | un-amt-zafumh-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | VOD |  | L19090570157 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-07-10 | Complete | 2019-11-26 | 2020-07-16 | Complete | Action Item : GEO IT to confirm if site is closed. 18-May: Consolidate Agile link 0505-LLA doc resent to LCON for sign-off. As per LCON - Site is closed 0405-As per LCON - Site is closed 2304-Lockdown for South Africa will relaxed to level 4 as from the 0105 - this allows for restricted mobility. Vodacom to follow up with Unilever LCON if site will open as BAU, request for the pending landlord approvals and request if Unilever will allow for the project to progress. 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Unilever Geo-IT |  | ZA-DUR03-0001 | SOUTH_AFRICA_UMHLANGA_RIDGE_HEAD_OFFICE |  |  |  |  | 15 NOLLSWORTH CRESCENT | DURBAN | 4051 | [6 empty] | 204.8MB400MB | 400 | -29.7333 | 31.05 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | WAN RANGE: 105.247.209.192/30 - vlan2150 WAN PE IP: 105.247.209.193/30 WAN CE IP: 105.247.209.194/30 LAN RANGE:105.242.195.96/29 | 105.247.209.193/30 | 105.247.209.194/30 | 105.242.195.96/29 |  |  | Vodacom | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes |  |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression | Window Date agreed - End user Comms sent |  |  |  | 93524 ,latest 105853 | CRQ000000688978 | Approved |  | CRQ000000687847 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-03-01
CKT-I-02-NG-AGB02-0001-VOD-1 | I0210VOD1 | 1 | Yes. Confirm if /30 ordered | Medium | Africa | NIGERIA | AGBARA FACTORY | 2018_171 | un-amt-ngaabg-vpn001 | un-amt-ngaabg-vpn001 | Vishal Joshi | WAN Circuit Migration | Soft Upgrade | Vodafone Local | VOD |  | 2-18805196102 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-08-04 | Complete | 2019-11-26 | 2020-08-05 | Complete | 18-May: Novation to be effective 4th Aug. 29-Apr: These are move out of WAN migration scope to SNT. These circuits will only have change in ownership and no circuit migration required. 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Circuit Provider | Check dates | NG-AGB02-0001 | NIGERIA_OREGUN_STATE_AGBARA |  |  |  |  | KM 32 Lagos Badagry Expressway, Agbara, Ogun State, Nigeria | Agbara | 112102 |  | Paul Anoruem | Paul.Anoruem@unilever.com | 2.34803E+12 | Dees Rampartab | Dees.Rampartab@unilever.com | 40MB | 40 | 6.4531 | 3.3958 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | 155.93.107.46 subnet 255.255.255.252 gw155.93.107.45 | [5 empty] | Vodacom Nigeria | [9 empty] | Copper - RJ45 | Standard site type - Dual DMVPN |  |  | No | No | No | No | [5 empty] | 107850 |  | Approved | [7 empty] | Circuit Migrated |  |  |  | 2020-04-01
CKT-I-02-TZ-IRI01-0002-VOD-1 | I0228VOD1 | 1 | Yes. Confirm if /30 ordered | Medium | Africa | TANZANIA | Mufindi Plantations | 2018_257 | un-amt-tzamuf-vpn001 | un-amt-tzamuf-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | VOD |  | 2-18805762077 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-08-12 | Complete | 2019-11-26 | 2020-08-31 | Complete | Action item: ISP working with last mile to progress delivery. 8-Sep: Rework planned on 19th Sep to swap the links to align with ISP BW mapping. 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Circuit Provider |  | TZ-IRI01-0002 | TANZANIA_MUFINDI_LUGODA_COMPLEX |  |  |  |  | LUGODA COMPLEX | MUFINDI | n.a. | [6 empty] | 20MB20MB | 30 | -8.5163 | 35.2606 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | WAN BLOCK: 41.223.6.244/30 VODA IP: 41.223.6.245 CLIENT IP: 41.223.6.246 VLAN: 580 LAN BLOCK: 41.217.202.88/29 DNS 01/02: 41.223.4.97 / 197.250.65.178 | 41.223.6.245 | 41.223.6.246 | 41.217.202.88/29 |  |  | Vodacom Tanzania | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression |  |  | 7 am to 1 pm UTC | 10 am to 4 pm local time | 114644 LINK SWAP SNOW TICKET: CHG000000000042209 | CRQ000000701465 CRQ000000709722 (19 Sep) | Submitted |  | CRQ000000703009/CRQ000000705240 | Completed | Completed |  |  |  | Circuit Migrated |  |  |  | 2020-04-01
CKT-I-02-NG-AGB01-0001-VOD-1 | I0210098VOD1 | 1 | Yes. Confirm if /30 ordered | Medium | Africa | NIGERIA | MEGA DC AGBARA | 2018_167 | un-amt-ngamdc-vpn001 | un-amt-ngamdc-vpn001 | Vishal Joshi | WAN Circuit Migration | Soft Upgrade | Vodafone Local | VOD |  | 2-18805196098 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-08-04 | Complete | 2019-11-26 | 2020-08-05 | Complete | 18-May: Novation to be effective 4th Aug. 29-Apr: These are move out of WAN migration scope to SNT. These circuits will only have change in ownership and no circuit migration required. 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Circuit Provider | Check dates | NG-AGB01-0001 | NIGERIA_MEGA DISTRIBUTION CENTER |  |  |  |  | Mega Distribution Center, Plot No. C20/3 Industrial Layout, Agbara Village via Igbesa, Ado-Odo/Otta South L.G.A. Ogun State. | Agbara | 112102 |  | Olufemi AKINGBEHIN | Olufemi.AKINGBEHIN@unilever.com | 2.34817E+12 | Dees Rampartab | Dees.Rampartab@unilever.com | 10000Kbps | 10 | 6.4531 | 3.3958 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | 155.93.107.18 subnet 255.255.255.252 gw 155.93.107.17 | [5 empty] | Vodacom Nigeria | [9 empty] | Copper - RJ45 | Standard site type - Dual DMVPN |  |  | No | No | No | No | [5 empty] | 107850 |  | Approved | [7 empty] | Circuit Migrated |  |  |  | 2020-04-01
CKT-I-01-ZW-UBK99-9999-VOD-1 | I0120067VOD1 | 1 | Yes. Confirm if /30 ordered | Medium | Africa | ZIMBABWE | Unibak | 2018_343 | un-amt-zweunb-vpn001 | un-amt-zweunb-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | VOD |  | 2-18805762080 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-06-12 | Complete | 2019-11-26 | 2020-06-22 | Complete | Action Item: Cisco to prepare for migration 22-Jun: Migration completed. How ever there were issues during the migration. Initially there were issues with locating the link and then there was issues with packet dropping which was a country wide issue not related to this migration. 1-Jun: Migration date agreed. 0605-Unilever LCON confirmed relaxtion of lockdown. Vodacom LCON to arrange for access and for works to be completed. 3004-It was agreed to wait until the extended locked period of the 050520, to progress for access request to complete, link activation and testing. 2204- L1 installation has been completed. Access to site for 2wds for the activation of the link and complaince testing has been refused due to COVID-19 lockdown extension. IP address information to be released once access is approved for the link activation and compliance testing. Unilever to advise if site is catergorised as ESSENTIAL SERVICES. Unilever to ascertain approval from local regulatory authotities and provide a LOA allowing for Vodacom and its partner to conclude link activation and compliance testing. 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Cisco |  | ZW-UBK99-9999 | ZIMBABWE_HARARE_UNIBAK_106 DARTFORD ROAD_INNOCENT KWANGWARE UNIBAK |  |  |  |  | Logistics (Pvt) Ltd, 106 Dartford Road, | Wllowvale |  |  | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 2000Kbps | 2 | -17.8862 | 30.9841 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | WAN - 196.43.113.232/30 LAN - 196.43.99.136/29 | 196.43.113.233/30 | 196.43.113.234/30 | 196.43.99.136/29 |  |  | Vodacom\Dandemutande | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms not sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 76847 | CRQ000000682598 | Approved |  | CRQ000000678352 | Completed | Completed | Tested -Pass-First Time | This will be considered as pass. however,was not done as it was an IP connect and will have VLAN and needs a router to connect. We need to do a Hot swop on the day of migration, which is planned on 4th june |  | Circuit Migrated - First Time right |  |  |  | 2020-04-01 | 2020-06-01
CKT-I-02-ZW-UBK99-9999-VOD-1 | I0220067VOD1 | 1 | Yes. Confirm if /30 ordered | Medium | Africa | ZIMBABWE | Unibak | 2018_344 | un-amt-zweunb-vpn002 | un-amt-zweunb-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | VOD |  | 2-18805762079 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-06-12 | Complete | 2019-11-26 | 2020-06-29 | Complete | Action Item: Cisco to prepare for migration. 1-Jun: Migration date agreed. 0605-Unilever LCON confirmed relaxtion of lockdown. Vodacom LCON to arrange for access and for works to be completed. 3004-It was agreed to wait until the extended locked period of the 050520, to progress for access request to complete, link activation and testing. 2204- L1 installation has been completed. Access to site for 2wds for the activation of the link and complaince testing has been refused due to COVID-19 lockdown extension. IP address information to be released once access is approved for the link activation and compliance testing. Unilever to advise if site is catergorised as ESSENTIAL SERVICES. Unilever to ascertain approval from local regulatory authotities and provide a LOA allowing for Vodacom and its partner to conclude link activation and compliance testing. 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Cisco |  | ZW-UBK99-9999 | ZIMBABWE_HARARE_UNIBAK_106 DARTFORD ROAD_INNOCENT KWANGWARE UNIBAK |  |  |  |  | Logistics (Pvt) Ltd, 106 Dartford Road, | Wllowvale |  |  | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 2000Kbps | 2 | -17.8862 | 30.9841 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | WAN - 196.43.113.236/30 LAN - 196.43.99.128/29 | 196.43.113.237/30 | 196.43.113.238/30 | 196.43.99.128/29 |  |  | Vodacom\Dandemutande | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 76851 | CRQ000000681231 | Approved |  | CRQ000000678460 | Completed | Completed | Tested -Pass-First Time | Test was done on 18th Jun and was successful. Able to connect to internet with good speed and NO packet loss and also able to reach the correct Zscaler node. |  | Circuit Migrated - First Time right |  |  |  | 2020-04-01 | 2020-06-01
CKT-I-01-ZW-BUQ01-0001-VOD-1 | I0120068VOD1 | 1 | Yes. Confirm if /30 ordered | Medium | Africa | ZIMBABWE | Bulawayo | 2018_339 | un-amt-zwebul-vpn001 | un-amt-zwebul-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | VOD |  | 2-18805762091 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-06-12 | Complete | 2019-11-26 | 2020-06-24 | Complete | Action Item: Cisco to prepare for migration. 1-Jun: Migration date agreed. 0605-Unilever LCON confirmed relaxtion of lockdown. Vodacom LCON to arrange for access and for works to be completed. 3004-It was agreed to wait until the extended locked period of the 050520, to progress for access request to complete, link activation and testing. 2204- L1 installation has been completed. Access to site for 2wds for the activation of the link and complaince testing has been refused due to COVID-19 lockdown extension. IP address information to be released once access is approved for the link activation and compliance testing. Unilever to advise if site is catergorised as ESSENTIAL SERVICES. Unilever to ascertain approval from local regulatory authotities and provide a LOA allowing for Vodacom and its partner to conclude link activation and compliance testing. 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Cisco |  | ZW-BUQ01-0001 | ZIMBABWE_BULAWAYO_8 CNR HERBERT CHITEPO STREET_INNOCENT KWANGWARE |  |  |  |  | Unilever Zimbabwe, Cnr 8th & Jason Moyo Avenue | City Centre |  |  | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 2M | 2 | -20.6265 | 28.6265 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | WAN - 168.253.58.88/30 LAN - 168.253.57.68/29 | 168.253.58.89/30 | 168.253.58.90/30 | 168.253.57.68/29 |  |  | Vodacom\Dandemutande | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 08:00 to 16:00 UTC | 10:00 to 18:00 local time | 76844 | CRQ000000683502 | Approved |  | CRQ000000678275 | Completed | Completed | Tested -Pass-First Time | Test was done on 19th June and was successful. Able to connect to internet with good speed and NO packet loss and also able to reach the correct Zscaler node. |  | Circuit Migrated - First Time right |  |  |  | 2020-04-01 | 2020-06-01
CKT-I-01-KE-LIM01-0001-VOD-1 | I012779VOD1 | 1 | Yes. Confirm if /30 ordered | Medium | Africa | KENYA | Mabrouki | 2019_128 | un-amt-kenmab-vpn002 | un-amt-kenmab-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Global | VOD |  | UNIPX-IPQM-00016 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-09-09 | Red | 2019-11-26 | 2020-09-14 | Red | Action Item :Vodafone to deliver circuit. Site survey to be scheduled. 0-Apr: Order is not progressing due to COVID-19 pandemic. Lockdown extended by 21 more days from 26th April. 15 Nov: Circuit Reference ID not present on any VOD tracker. 11 Nov : Updated the migration date based on FCDD provided by VF | Pink | Circuit Order Accepted | Circuit Provider |  | KE-LIM01-0001 | KENYA_LIMURU_MABROUKI |  |  |  |  | LIMURU-NAZARETH RD | LIMURU |  |  | Agnes Karani | agnes.karani@unilever.com | 254722401134 | Dees Rampartab | Dees.Rampartab@unilever.com | 10000Kbps10000Kbps | 10 | -1.1118 | 36.6437 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | Static 41.215.2.64 255.255.255.252 Network Address Static 41.215.2.65 255.255.255.252 LAN IP / Default gateway Static 41.215.2.66 255.255.255.252 IP free to use Static 41.215.2.67 255.255.255.252 Broadcast Address Static 41.215.20.72 255.255.255.248 Additional /29 subnet routed to 41.215.2.66 | 41.215.2.65/30 | 41.215.2.66/30 | 41.215.20.72/29 |  |  | MTN | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi |  |  | Standard site type - Dual DMVPN | Complete |  | No | Yes | No | No | Assessment Complete MOP created & config created | Window Date agreed - End user Comms not sent |  | 7 am to 1 pm UTC | 10 am to 4 pm Local time | CHG000000000042331 | CRQ000000709876 | Submitted |  | CRQ000000709728 | In Progress | Completed |  | Testing couldnt be done as circuit details were incorrect. | [5 empty] | 2020-06-01
CKT-I-01-MW-MWH99-9999-VOD-1 | I0111189VOD1 | 1 | Yes. Confirm if /30 ordered | Medium | Africa | MALAWI | Manica Warehouse | 2018_137 | un-amt-mwimwh-vpn002-new | un-amt-mwimwh-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Global | VOD |  | UNIPX-IPQM-00027 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-02-11 | Complete | 2019-11-26 | 2020-08-05 | Complete | Action Item: Vodafone to resolve faulty hardware and provide confirmation to replan. 5-Aug: Vodafone has delivered a new fibre link and was successfully migrated on 5th Aug 22-Jun: Migration rolled back. Vodafone had a faulty hardware. This was replaced on 18 Jun. 11-Jun: Vodafone has fixed the issue. They have removed all firewall rules from their end which was blocking the traffic. IOS upgrade of NTE device was carried out. 1-Jun: Pushed migration date to 31 July pending investigation from Vodafone. 18-May: Migration had to be rolled back as we see UDP packet drops. Vodafone to investigate further and provide RCA. 5-May: Schedule confirmed. OK to proceed with migration,. 29 April Pending schedule confirmation for migration date proposed by Cisco. 15 April: Migration on hold due to Covid. UL will advise new date 23 Mar: First Migration attempt on 20 Mar failed. The Migration has been rolled Back since we were able to ping the PE, but could not reach the internet.15 Nov: No FOC date from VOD. | Complete | Circuit Migrated | Circuit Provider |  | MW-MWH99-9999 | MALAWI_UNILEVER_MANICA_WAREHOUSE | 01-August-2020 | Open |  |  | ALI HASSAN MWINYI ROAD | BLANTYRE | FOREIGN | Warehouse | Wilfred Mauluka | Wilfred.Mauluka@unilever.com | +265 99 951 9446 | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com | 2000Kbps | 2 | -15.7851 | 35.0094 | 2019 | Nov | Internet |  | Commercial Benefit | [5 empty] | Need to carry Masks | [5 empty] | OLD IPS: Static 41.87.3.36 255.255.255.252 Network Address Static 41.87.3.37 255.255.255.252 LAN IP / Default gateway Static 41.87.3.38 255.255.255.252 IP free to use Static 41.87.3.39 255.255.255.252 Broadcast Address Static 41.87.3.208 255.255.255.248 Additional /29 subnet routed to 41.87.3.38 Wan IP Address 41.87.3.22 Lan IP Address 41.87.3.37 New IP received on 4 AUg: IP Address Subnet Mask Note Static 41.75.113.248 255.255.255.252 Network Address Static 41.75.113.249 255.255.255.252 LAN IP / Default gateway Static 41.75.113.250 255.255.255.252 IP free to use Static 41.75.113.251 255.255.255.252 Broadcast Address Static 41.75.113.96 255.255.255.248 Additional /29 Routed to 41.75.113.250 | 41.221.97.241/30 | 41.221.97.242/30 | 41.221.97.216/29 |  |  | Globe Internet | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi | 2020-04-24 |  | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 08:00 Hrs. To 16:00 Hrs. | 10:00 Hrs. To 18:00 Hrs | 4702(first iteration) 55625 (second iteration) 73956 (third iteration) 102207(forth iteration) 110584 (fifthIteration) Migrated succesfully | CRQ000000653324 (old) CRQ000000661112 (second attempt on 18 May) CRQ000000681362 (17 Jun) CRQ000000693341 (23 Jul) CRQ000000697850 (5 Aug) | Approved | 41362 | CRQ000000643839 | Completed | Completed | Tested -Pass-First Time | However, the IP is yet to be provisioned. We will do the testing once the provision is done and then will consider it as completely done. The IP address was enabled and asked the team to share the Ip.zscaler.com and the team shared it on 18th Feb and it was fine. Based on the screenshot and confirmation from Valdrin, we considered the testing as complete for the site. | Email: Kamanga, George GeorgePhillip.Kamanga@intoutsource.com Mobile: +26599188 6452 | Circuit Migrated | DMVPN did not come up in 2 failed attempts. UDP packet drop seen and traffic not able to reach DMVPN Hub router. Vodafone to provide RCA. 22-Jun: Migration on 17 Jun failed. This was due to faulty hardware which was replaced by Vodafone next day. | INCV00294085 |  | 2020-02-01 | 2020-03-01
CKT-I-02-ZW-BUQ01-0001-VOD-1 | I0220068VOD1 | 1 | Yes. Confirm if /30 ordered | Medium | Africa | ZIMBABWE | Bulawayo | 2018_340 | un-amt-zwebul-vpn002 | un-amt-zwebul-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | VOD |  | 2-18805762092 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-06-12 | Complete | 2019-11-26 | 2020-06-24 | Complete | Action Item :Cisco to prepare for migration 1-Jun: Migration date agreed. 0605-Unilever LCON confirmed relaxtion of lockdown. Vodacom LCON to arrange for access and for works to be completed. 3004-It was agreed to wait until the extended locked period of the 050520, to progress for access request to complete, link activation and testing. 2204- L1 installation has been completed. Access to site for 2wds for the activation of the link and complaince testing has been refused due to COVID-19 lockdown extension. IP address information to be released once access is approved for the link activation and compliance testing. Unilever to advise if site is catergorised as ESSENTIAL SERVICES. Unilever to ascertain approval from local regulatory authotities and provide a LOA allowing for Vodacom and its partner to conclude link activation and compliance testing. 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Cisco |  | ZW-BUQ01-0001 | ZIMBABWE_BULAWAYO_8 CNR HERBERT CHITEPO STREET_INNOCENT KWANGWARE |  |  |  |  | Unilever Zimbabwe, Cnr 8th & Jason Moyo Avenue | City Centre |  |  | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com |  | Dees Rampartab | Dees.Rampartab@unilever.com | 2M | 2 | -20.6265 | 28.6265 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | WAN - 168.253.58.92/30 LAN - 168.253.57.76/29 | 168.253.58.93/30 | 168.253.58.94/30 | 168.253.57.76/29 |  |  | Vodacom\Dandemutande | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 08:00 to 16:00 UTC | 10:00 to 18:00 local time | 76844 | CRQ000000683502 | Approved |  | CRQ000000678516 | Completed | Completed | Tested -Pass-First Time | Test was done on 19th June and was successful. Able to connect to internet with good speed and NO packet loss and also able to reach the correct Zscaler node. |  | Circuit Migrated - First Time right |  |  |  | 2020-04-01 | 2020-06-01
CKT-I-01-TZ-DAR99-9999-VOD-1 | I0120330VOD1 | 1 | Yes. Confirm if /30 ordered | Medium | Africa | TANZANIA | Vingunguti Warehouse | 2018_258 | un-amt-tzawar-vpn001 | un-amt-tzawar-vpn001 | Prasenjit Pal | WAN Circuit Migration |  | Vodafone Global | VOD |  | UNIPX-IPQM-00021 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-02-03 | Complete | 2019-11-26 | 2020-03-09 | Complete | 06 Feb: Circuit delivered. Physical device & circuit is yet to be located. 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated |  |  | TZ-DAR99-9999 | TANZANIA_VINGUNGUTI_WAREHOUSE |  |  |  |  | NYERERE ROAD | DAR ES SALAAM | 000255 | Warehouse | Danford Rugazia | Danford.Rugazia@unilever.com | 255768586176 | Musa Adeka | Musa.Adeka@unilever.com | 2000Kbps | 2 | -6.8229 | 39.2697 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | IP Address Subnet Mask Note Static 41.221.50.92 255.255.255.252 Network Address Static 41.221.50.93 255.255.255.252 LAN IP / Default gateway Static 41.221.50.94 255.255.255.252 IP free to use Static 41.221.50.95 255.255.255.252 Broadcast Address Static 41.221.50.128 255.255.255.248 Additional /29 subnet routed to 41.221.50.94 Brand CPE Type Wan IP Address Lan IP Address Lan Interface Cisco C881-K9 Not Applicable 41.221.50.70 41.221.50.93 FastEthernet 100BaseT [confirmed] | 41.221.50.93/30 | 41.221.50.94/30 | 41.221.50.128/29 |  |  | Green Telecom | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi | 2020-03-10 |  | Standard site type - Dual DMVPN | Complete | NO | No | No | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 14:00 Hrs. – 20:00 Hrs | 17:00 Hrs – 23:00 Hrs | 44705 | CRQ000000647583 | Approved | 41334 | CRQ000000642907 | Completed | Completed | Tested -Pass-First Time | All worked fine. It was passed first time along with the Zscaler | Valdrin Bismili | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-03-01
CKT-I-02-KE-LIM01-0001-VOD-1 | I022779VOD1 | 1 | Yes. Confirm if /30 ordered | Medium | Africa | KENYA | Mabrouki | 2018_127 | un-amt-kenmab-vpn001 | un-amt-kenmab-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | VOD |  | 2-18805196091 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-07-29 | Complete | 2019-11-26 | 2020-08-22 | Complete | Action Item: Vodacom to deliver the circuit. lockdown extended until 6 Jun. 0505-The insurance of the devices has been activated. Lockdown to be uplifted on the 1805. Will schedule for the installation thereafter. 2304-Device insurance confirmation has not yet been provided by Unilever GEO IT. Vodacom to escalate further to Unilver SNT. 06 Dec : Insurance not yet provided 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Circuit Provider |  | KE-LIM01-0001 | KENYA_LIMURU_MABROUKI |  |  |  |  | LIMURU-NAZARETH RD | LIMURU |  |  | Agnes Karani | agnes.karani@unilever.com | 254722401134 | Dees Rampartab | Dees.Rampartab@unilever.com | 10000Kbps | 10 | -1.1118 | 36.6437 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | 41.79.253.96/30 41.79.253.104/29 | 41.79.253.98 | 41.79.253.97 | 41.79.253.104/29 |  |  | Vodacom Kenya | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | No | No | Assessment Complete MOP created & config created Partner MOP created | Window Date agreed - End user Comms sent |  | 7 am to 1 pm UTC | 10 am to 4 pm local time | 114978 | CRQ000000702819 | Approved |  | CRQ000000701204 | Completed | Completed |  |  |  | Circuit Migrated |  |  |  | 2019-12-01
CKT-I-01-KE-MBA03-0001-VOD-1 | I012778VOD1 | 1 | Require /29+ /30 | Medium | Africa | KENYA | Mombasa | 2018_133 | un-amt-kenmom-vpn001 |  | Prasenjit Pal | WAN Circuit Migration |  | Vodafone Local | VOD |  | 2-18805196093 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2019-11-11 | Complete | 2019-11-26 | 2019-12-09 | Complete | 13 Dec : Migration successful on 09th Dec 06 Dec : On track as planned. 02 Dec : Migration planned for 09 Dec 11 Nov : Circuit delivered on 11 Nov | Complete | Circuit Migrated |  |  | KE-MBA03-0001 | KENYA_UNILEVER_KENYA_LTD_TEA_DIVSION |  |  |  |  | Imaara , Off-Nyerere Avenue, Opposite Pandya Hospital,Mombasa. | MOMBASA | 254 |  | Ngachi, Rhoda | Rhoda.Ngachi@unilever.com | +254 (709) 452700 /+254 (792) 765604 | Dees Rampartab | Dees.Rampartab@unilever.com | 10000Kbps | 10 | -4.053 | 39.6666 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | WAN Block : 41.79.252.192/31 CE IP (WAN) : 41.79.252.193/31 PE IP (WAN) : 41.79.252.192/31 LAN Block : 41.79.252.72/29 | 41.79.252.192/31 | 41.79.252.193/31 | 41.79.252.72/29 |  |  | Vodacom\Internet Solution | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CR raised Config created MOP created Raised an SR for alarm supression | Window Date agreed - End user Comms sent |  |  |  | 16296 | CRQ000000614583 | Approved | 39857 | CRQ000000620534 | Completed | Completed | Tested-Pass | Testing failed on 25 Nov and migration had to be cancelled at last minute. There is packet loss on new link. Packer drops were resolved on the same day but was too late to continue the migration and hence was cancelled |  | Circuit Migrated - First Time right |  |  |  | 2019-11-01 | 2019-12-01
CKT-I-02-KE-MBA03-0001-VOD-1 | I022778VOD1 | 1 | Require /29+ /30 | Medium | Africa | KENYA | Mombasa | 2018_134 | un-amt-kenmom-vpn002 |  | Prasenjit Pal | WAN Circuit Migration |  | Vodafone Local | VOD |  | 2-18805196094 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2019-11-11 | Complete | 2019-11-26 | 2019-12-02 | Complete | 06 Dec : Migration successful on 2nd Dec. 02 Dec : Migration planned for 2nd Dec. 11 Nov : Circuit delivered on 11 Nov | Complete | Circuit Migrated |  |  | KE-MBA03-0001 | KENYA_UNILEVER_KENYA_LTD_TEA_DIVSION |  |  |  |  | Imaara , Off-Nyerere Avenue, Opposite Pandya Hospital,Mombasa. | MOMBASA | 254 |  | Ngachi, Rhoda | Rhoda.Ngachi@unilever.com | +254 (709) 452700 /+254 (792) 765604 | Dees Rampartab | Dees.Rampartab@unilever.com | 15MB15MB | 15 | -4.053 | 39.6666 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | WAN Block : 41.79.253.92/31 CE IP (WAN) : 41.79.253.93/31 PE IP (WAN) : 41.79.253.92/31 LAN Block : 41.79.253.144/29 | 41.79.253.92/31 | 41.79.253.93/31 | 41.79.253.144/29 |  |  | Vodacom\Jamii Telcom | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete | NO | No | Yes | Yes | No | Assessment Complete CR raised Config created MOP created Raised an SR for alarm supression | Window Date agreed - End user Comms sent |  |  |  | 17461 | CRQ000000621654 | Approved | 39857 | CRQ000000620534 | Completed | Completed | Tested -Pass-First Time | No issues |  | Circuit Migrated - First Time right |  |  |  |  | 2019-11-01
CKT-I-02-ZA-DUR06-0001-VOD-1 | I029487VOD1 | 1 | Yes. Confirm if /30 ordered Second device on site - un-amt-zafqnd-vpn001 currenlty has 50MB BW | Medium | Africa | SOUTH AFRICA | Indonsa (Queen Nandi) | 2018_226 | un-amt-zafqnd-vpn002 | un-amt-zafqnd-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | VOD |  | S19090569383 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-06-10 | Complete | 2019-11-26 | 2020-07-15 | Complete | Action Item: Mark to work with BT to make required changes on FW and confirm. 15-Jul: MIgration successful and no issues during UAT. HOw ever the speed test results were not satisfactory. Upload speed less than 1MB and download speed was less than 20 MB. ISP to check further and if required another MW to be scheduled to perfom fail over test. 24-Jun: Mark identified additional technical dependencies. There was a 3rd party firewall at Indonsa which has an external IP address from MTN circuit provider’s IP range. This IP address is used for management of this firewall and is routed through the MTN DIA link.​ So if we move the link to Vodacom and use their IP addresses this interface won't be accessible anymore. As an action item, Mark would get the firewall port for external interface decommissioned and in future use the internal IP for firewall. Cisco would plan the migration to Vodacom circuit once this has been done. to internal interface. Migration cancelled last minute on 24th Jun. 0405-Schedule install once LLA received. LCON engagement in progress for access. 2304-Lockdown for South Africa will relaxed to level 4 as from the 0105 - this allows for restricted mobility. Vodacom to follow up with Unilever LCON if site will open as BAU, request for the pending landlord approvals and request if Unilever will allow for the project to progress. 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Unilever Geo-IT |  | ZA-DUR06-0001 | SOUTH_AFRICA_QUEEN_NANDI |  |  |  |  | RIVER HORSE VALLEY | DURBAN | 4093 | [6 empty] | 65MB65MB | 65 | -29.9321 | 30.8832 | 2019 | Nov | Internet |  | Commercial Benefit | [11 empty] | "Public IP's 105.244.11.240 Next Hop 105.244.11.241" Subnet 255.255.255.248 Usable IP's 242-246 | 105.244.11.241/30 | 105.244.11.242/30 | 105.244.11.240/29 |  |  | Vodacom\Mobax | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression | Window Date agreed - End user Comms sent |  | 08:00 to 14:00 UTC | 10:00 to 16:00 local time | 76853 | CRQ000000684049 (Cancelled) CRQ000000689330 (15 Jul) | Approved |  | CRQ000000679761 | Completed | Completed | Tested -Pass-First Time | This will be considered as pass. however,was not done as it was an IP connect and will have VLAN and needs a router to connect. We need to do a Hot swop on the day of migration, which is planned on 18th June |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-03-01
CKT-I-02-TZ-DAR99-9999-VOD-1 | I0220330VOD1 | 1 | Yes. Confirm if /30 ordered | Medium | Africa | TANZANIA | Vingunguti Warehouse | 2018_259 | un-amt-tzawar-vpn002 | un-amt-tzawar-vpn002 | Vishal Joshi | WAN Circuit Migration | Soft Upgrade | Vodafone Local | VOD |  | 2-18805762075 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-08-04 | Complete | 2019-11-26 | 2020-07-30 | Complete | Action Item: Moved to SNT as it owner transfer only. 2904-Project kick off in progress. 2204- Project ON HOLD - due to COVID-19 lockdown. Feedback regarding lockdown regulations to be provided by Vodacom LCON on the 2904. 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Circuit Provider | Check dates | TZ-DAR99-9999 | TANZANIA_VINGUNGUTI_WAREHOUSE |  |  |  |  | NYERERE ROAD | DAR ES SALAAM | 000255 | [6 empty] | 2000Kbps2000Kbps | 10 | -6.8229 | 39.2697 | 2019 | Nov | Internet |  | Commercial Benefit | [12 empty] | 0 | 0 | 0 |  |  | Vodacom Tanzania | [9 empty] | Copper - RJ45 | Standard site type - Dual DMVPN |  |  | No | Yes | Yes | No | [5 empty] | 107850 | [13 empty] | 2020-04-01
CKT-I-02-MW-MWH99-9999-VOD-1 | I0211189VOD1 | 1 | Yes. Confirm if /30 ordered | Low | Africa | MALAWI | Manica Warehouse | 2018_138 | un-amt-mwimwh-vpn001-new | un-amt-mwimwh-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Global | VOD |  | UNIPX-IPQM-00017 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-08-04 | Complete | 2019-11-26 | 2020-06-17 | Complete | Action Item: CIsco to Perform migration on 17 Jun. 11-Jun: Vodafone has fixed the issue. They have removed all firewall rules from their end which was blocking the traffic. IOS upgrade of NTE device was carried out. 1-Jun: Pushed migration date to 31 July pending investigation from Vodafone. 11-May: Migration had to be rolled back as we see UDP packet drops. Vodafone to investigate further and provide RCA. 5-May: Schedule confirmed. OK to proceed with migration,. 29 April Pending schedule confirmation for migration date proposed by Cisco. 18 Apr: ON HOLD due to lockdown 15 April: Migration on hold due to Covid. UL will advise new date 23 Mar: Migration attempt on 24 Feb failed. DMVPN did not come up. 02 Mar: Migration failed. Troubleshooting going on . Migration will be scheduled after troubleshooting is over. 13 Feb: Test successful. Migration scheduled on 24-February'20 11 - Feb: Device located. Test planned on 12-Feb'20. 04- Feb: Unable to locate device. Testing delayed Highlighted potential risk for migration timelines. (Local polictical issue going on) 31-Jan : Circuit and device could not be located physically. Testing getting delayed. 24 Jan: RFS Received. 15 Nov: No FOC date from VOD. | Complete | Circuit Migrated | Cisco | Check dates | MW-MWH99-9999 | MALAWI_UNILEVER_MANICA_WAREHOUSE | 01-August-2020 | Open |  |  | ALI HASSAN MWINYI ROAD | BLANTYRE | FOREIGN | Warehouse | Wilfred Mauluka | Wilfred.Mauluka@unilever.com | +265 99 951 9446 | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com | 2000Kbps | 2 | -15.7851 | 35.0094 | 2020 | Apr | Internet |  | Commercial Benefit | [5 empty] | Need to carry Masks | [5 empty] | IP Address Subnet Mask Note Static 41.221.97.240 255.255.255.252 Network Address Static 41.221.97.241 255.255.255.252 LAN IP / Default gateway Static 41.221.97.242 255.255.255.252 IP free to use Static 41.221.97.243 255.255.255.252 Broadcast Address Static 41.221.97.216 255.255.255.248 Additional /29 Subnet Routed to 41.221.97.242 Brand CPE Type Wan IP Address Lan IP Address Lan Interface MikroTik 951G-2HnD Router 41.221.97.214 41.221.97.241 FastEthernet 100BaseT | 41.75.113.249 | 41.75.113.250 | 41.75.113.96/29 |  |  | Globe Internet | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi | 2020-04-15 |  | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 08:00 Hrs. To 16:00 Hrs. | 10:00 Hrs. To 18:00 Hrs | 41293, (first iteration) 53169 (second iteration) 73956 (third iteration) | CRQ000000644066 (old) CRQ000000657725 (second attempt on 11 May) CRQ000000681362 (17 Jun) | Approved | 41001 | CRQ000000637022/CRQ000000698506 | Completed | Completed | Tested-Pass | First time(11th Feb), it didn't work as mikrotik router on the site had NATing disabled. Once it was enabled for service on the LAN side it worked fine. It was successful the following day-12th Feb | Email: Kamanga, George GeorgePhillip.Kamanga@intoutsource.com Mobile: +26599188 6452 | Circuit Migrated | DMVPN did not come up in 2 failed attempts. UDP packet drop seen and traffic not able to reach DMVPN Hub router. Vodafone to provide RCA. Below are support incident raised to Vodafone: INCV00282582 INCV00301394 |  |  |  | 2020-02-01
CKT-I-02-ET-DKM01-0002-VOD-1 | I0212012VOD1 | 1 | Yes. Confirm if /30 ordered | Low | Africa | ETHIOPIA | Ethiopia EIZ | 2018_69 | un-amt-etheiz-vpn002 | un-amt-etheiz-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | VOD |  | 2-18805196086 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-08-31 | Red | 2019-11-26 | 2020-10-30 | Red | Action Item: ISP to work with last mile to progress delivery of circuit. 2-Sep: This is moved out of scope as ISP is unable to deliver new circuit. UL will continue with existing ISP circuit. 0605-Site Access denied. Request intervention from global team. (mail sent to Welington and Mohan) 2904-LCON engagement has commenced to facilitate access requirement for a physical site survey. 2204- Project ON HOLD - due to COVID-19 lockdown. Feedback regarding lockdown regulations to be provided by Vodacom LCON on the 2904. Attempts to contact Vodacom LL partner and Unilever onsite contact was unsuccessful. Project is managed by our Kenya team, and the lockdown uplifting for Kenya is scheduled 03-Feb - Site assessment & Design document verification in progress | Out of Scope | Circuit Order Accepted | Circuit Provider |  | ET-DKM01-0002 | ETHIOPIA_MANUFACTURING_PLC |  |  |  |  | DUKEM - ADDIS ABABA | ADDIS ABABA | 0251 | [6 empty] | 15MB15MB | 15 | 8.4839 | 8.4839 | 2020 | Jun | Internet | [14 empty] | 0 | 0 | 0 |  |  | Vodacom Kenya\PCCW\Ethio | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi |  | Copper - RJ45 |  | In Progress |  |  | Yes | [21 empty] | 2020-04-01
CKT-I-02-ET-DKM02-0001-VOD-1 | I027687VOD1 | 1 | Yes. Confirm if /30 ordered | Low | Africa | ETHIOPIA | Ethiopia Addis Ababa | 2018_71 | un-amt-ethadd-vpn002 | un-amt-ethadd-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Local | VOD |  | 2-18805196084 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-08-31 | Red | 2019-11-26 | 2020-10-30 | Red | Action Item: ISP to work with last mile to progress delivery of circuit. 2-Sep: This is moved out of scope as ISP is unable to deliver new circuit. UL will continue with existing ISP circuit. 0605-Site Access denied. Request intervention from global team. (mail sent to Welington and Mohan) 2904-LCON engagement has commenced to facilitate access requirement for a physical site survey. 2204- Project ON HOLD - due to COVID-19 lockdown. Feedback regarding lockdown regulations to be provided by Vodacom LCON on the 2904. Attempts to contact Vodacom LL partner and Unilever onsite contact was unsuccessful. Project is managed by our Kenya team, and the lockdown uplifting for Kenya is scheduled 03-Feb - Site assessment & Design document verification in progress | Out of Scope | Circuit Order Accepted | Circuit Provider |  | ET-DKM02-0001 | ETHIOPIA_UNILEVER |  |  |  |  | Unilever Manufacturing plc woreda 8 Kirkos sub city,house P.O. Box 2396 Addis Abeba | [8 empty] | 30MB | 30 | 9.0336 | 38.7445 | 2020 | Jun | Internet | [14 empty] | 0 | 0 | 0 |  |  | Vodacom Kenya\PCCW\Ethio | [5 empty] | Valdrin Bislimi | Valdrin Bislimi | Valdrin Bislimi |  | Copper - RJ45 | Standard site type - Dual DMVPN | Complete |  | No | Yes | No | No | Assessment Complete | [18 empty] | 2020-04-01
CKT-I-01-NE-NIM02-0002-VOD-1 | I012355VOD1 | 1 | Yes. Could also be device name un-amt-nernai-vpn002 with 2MB | Low | Africa | NIGER | Niamey | 2018_166 | un-amt-nernai-vpn001 | un-amt-nernai-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Global | VOD |  | UNIPX-IPQM-00019 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-12-31 | Red | 2019-11-26 | 2020-12-31 | Red | Next Action: 3-Jul: As confirmed by Mohan this circuit is no longer in migration scope. 30-Apr: Awaiting confirmation from Deepak if the site will be relocated or not. 24 Feb: On hold confirmed by Deepak. Reason : Office move 15-Oct: The site is getting closed tentatively Q1 2020 and the users are moving to different location. Local GEO IT contact to confirm the targeted dates and advise if this order needs to be put on hold temporarily. | Out of Scope | Circuit Order Accepted | Unilever SNT | Check dates | NE-NIM02-0002 | NIGER_NIAMEY_AVENUE_DU_PROGRES |  |  |  |  | AVENUE DU PROGRES | NIAMEY | n.a. |  | Aichath Nzi-Akande |  |  | Dees Rampartab | Dees.Rampartab@unilever.com | 2048Kbps | 2 | 13.513 | 2.1184 | 2020 | Jun | Internet | [14 empty] | 0 | 0 | 0 |  |  | Sonitel | [11 empty] | In Progress |  |  | Yes
CKT-I-02-ZW-HRE01-0001-VOD-1 | I0247VOD1 | 1 | Yes. Could also be device name un-amt-zwehar-vpn001 with 50 MB | Low | Africa | ZIMBABWE | Harare | 2018_341 | un-amt-zwehar-vpn002 | un-amt-zwehar-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Vodafone Global | VOD |  | UNIPX-IPQM-00022 | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2020-02-19 | Complete | 2019-11-26 | 2020-06-25 | Complete | Action Item:Cisco to prepare for migration. 15-Jun: ISP confirmed issue is fixed. Root cause was a fibre cable cut. GEO IT has agreed for migration on 25 Jun. Need NTT FE to have PCR covid 19 negative report. 1-Jun: Pushed migration date to 31 July pending investigation from Vodafone. 19-May: Migration was rolled back as there was no internet connectivity once circuit was connected. Incident created with Vodafone to investigate further. 29 April : Geo IT (Tawanda.Matambanadzo2@unilever.com) to confirm the date to schedule migration. (Currently migration on Hold as requested by Geo IT due to Covid situation) 18 Apr: ON HOLD due to Covid situation 23 Mar: TRB failed. Migration rescheduled 19-Feb : Circuit delivered 03-Feb - Site assessment & Design document verification in progress | Complete | Circuit Migrated | Cisco |  | ZW-HRE01-0001 | ZIMBABWE_HARARE_STIRLING_ROAD_HEAD_OFFICE |  |  |  |  | STIRLING ROAD | HARARE | 950 |  | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com | +263 719425435 | Tawanda Matambanadzo | Tawanda.Matambanadzo2@unilever.com | 70MB | 70 | -17.85 | 31.0167 | 2020 | Jun | Internet | [7 empty] | Should go through the SHE induction and Medical induction if not done already. The Engineer coming onsite should have all the necessary PPE(Safety Shoes, Face Masks ) Should process a Work Permit on the day Approximately 1 hour to process the permit. Induction if not done already should be done 48hours before the day the works are scheduled. | N |  |  |  |  | IP Address Subnet Mask Note Static 196.43.113.168 255.255.255.252 Network Address Static 196.43.113.169 255.255.255.252 LAN IP / Default gateway Static 196.43.113.170 255.255.255.252 IP free to use Static 196.43.113.171 255.255.255.252 Broadcast Address Static 196.43.113.216 255.255.255.248 Additional /29 subnet routed to 196.43.113.170 Brand CPE Type Wan IP Address Lan IP Address Lan Interface Cisco ISR4331/K9 Router 196.43.99.62 196.43.113.169 GigabitEthernet 1000BaseT 950GS-40B Media Converter 0.0.0.0 0.0.0.0 | 196.43.113.169/30 | 196.43.113.170/30 | 196.43.113.216/29 |  |  | YoAfrica | [5 empty] | Kastriot Dragusha | Kastriot Dragusha | Kastriot Dragusha | 2020-05-20 |  | Standard site type - Dual DMVPN | Complete |  | No | Yes |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 08:00 Hrs. To 14:00 Hrs. | 10:00 Hrs. To 16:00 Hrs | 64981, SSR 66960 (first iteration) 73958 (secondary iteration) | CRQ000000673434 CRQ000000679372 (new) | Approved | 41501 | CRQ000000646834 | Completed | Completed | Tested -Pass-First Time | Everything worked fine and test was successful including the Zscaler and the speed is also very good. |  | Circuit Migrated | First attempt issues - No internet connectivity. Issue with circuit. |  |  | 2020-02-01 | 2020-03-01
CKT-I-02-LV-RIX02-0310-UNL-1 |  | 1 | Not found in NP, used old BW given. Not sure of IP address mask required Yes. Existing reported as 10 MB | Medium | Europe | LATVIA | LATVIA_RIGA_LV |  | un-uen-lvrig1-rtr001 |  |  | SNT | Circuit | Unilever | Uni |  |  | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2019-09-01 | Complete | 2019-11-26 | 2019-09-19 | Complete | Completed by UL/BT on 19/9 | Complete | Circuit Migrated |  |  | LV-RIX02-0310 | LATVIA_RIGA_LV |  |  |  |  | Kronvalda 3-10 | Riga | LV-1010 |  | Mykolas Norvaisas | Mykolas.Norvaisas@unilever.com | +37069850977 |  |  | 0 | 40 | 56.9327 | 24.1361 | 2019 | Sep | MPLS | 2014-01-13 | Commercial Benefit |  |  | SC2 | [5 empty] | /30 |  |  |  | 0 | 0 | 0
CKT-I-02-KZ-ALM99-9999-UNL-1 | I02WC042UNL1 | 1 | Discussed with customer and Rajesh Dagde has details. This is a new site. | Medium | Europe | Kazakhstan | Almaty |  | ?? | un-uaa-kzalm1-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  |  | 2019-08-27 | 2019-08-27 | Complete | 2019-09-03 | 2019-09-01 | Complete | 2019-11-12 | 2019-11-12 | Complete | 2019-11-26 | 2020-02-17 | Complete | 22/01 Meeting with local team took place today. Targetted date for migration 17 Feb. UL local team to provide required documentation. 12/12 Pending clarification on the IP address / confirmation on the local contact 10/12 Circuit has been delivered. | Complete | Circuit Migrated |  |  | KZ-ALM99-9999 | [5 empty] | 53, ABYLAI KHAN AVENUE | Almaty | 050000 | [7 empty] | 50 |  |  | 2019 | Nov |  |  | New site Integration |  |  | SC2 | New site, router requires to be installed | 1200 - 1800 UTC | NA | NA | NA | /30 |  |  |  | 212.76.6.97 | 212.76.6.99 | 212.76.6.96/28 212.76.6.97-212.76.6.102 | [8 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde | 2020-02-18 |  |  |  | NO | Yes |  |  | Yes-Onboarding file created for CMS | Assessment Complete Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms not sent |  | 1200 - 1800 | 1800 - 2400 | 36634 | No downtime, no RFC required | Approved | 41033 | CRQ000000638370 | Completed | Completed | Tested-Pass |  | Almas Batyrkhanov | Circuit Migrated - First Time right |  |  |  |  | 2020-02-01
CKT-I-01-GB-PUK99-9999-GTT-1 |  | 1 | Not found in BT document or NP | High | Europe | UNITED KINGDOM | Pukka Herbs |  | ?? |  |  | BAU Projects |  | GTT | GTT |  | GTT/001761419 | 2019-07-10 | 2019-07-10 | Complete | 2019-07-17 | 2019-07-15 | Complete | 2019-09-25 | 2020-06-14 | Red | 2019-10-09 |  | Red | Order cancelled | Out of Scope | Circuit Order Accepted |  |  | GB-PUK99-9999 | [5 empty] | Block C, The Chocolate Factory, The Chocolate Quarter, Via Traversus | Keynsham | [8 empty] | 100 |  |  | 2019 | Dec |  | Not Applicable | New site Integration | [12 empty] | 0 | 0 | 0 |  |  | BT Wholesale
CKT-I-02-GB-PUK99-9999-VOD-1 |  | 1 | Not found in BT document or NP | High | Europe | UNITED KINGDOM | Pukka Herbs |  | ?? |  |  | BAU Projects |  | Vodafone Global | VOD |  |  | 2019-11-10 | 2019-11-10 | Complete | 2019-11-15 | 2019-10-16 | Complete | 2020-01-24 | 2020-01-14 | Green | 2020-02-07 |  | Red |  | Yellow | Circuit Order Accepted |  |  | GB-PUK99-9999 | [5 empty] | Block C, The Chocolate Factory, The Chocolate Quarter, Via Traversus | Keynsham | BS31 2GN | [7 empty] | 100 |  |  | 2019 | Dec |  | Not Applicable | New site Integration | [12 empty] | 0 | 0 | 0
CKT-I-01-NL-HLD01-0015-GTT-1 | I011321GTT1 | 1 | Yes. Confirm if /30 ordered | High | Europe | Netherlands | Hellendoorn |  | un-uen-nldhel1-rtr001 | un-uen-nldhel1-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit | GTT | GTT |  | GTT/001764365 | 2019-11-10 | 2019-10-16 | Complete | 2019-11-15 | 2019-11-15 | Complete | 2020-01-24 | 2020-02-19 | Complete | 2020-02-07 | 2020-04-03 | Complete | 10/02: Vendors field engineer will attend to the site on 18-02-2020 to complete the delivery. 05/02: The fiber construction work should be ready before 13.02.2020. Field engineer will install the fiber Switch on the 18th of February. 29/01: Waiting the Vendor to give us an update on this order. 09/01: Blow - 09/01 and pre-existing route - 10/01. On 16/01 and 17/01 civil incl. Bore - Blow scheduled for 06/02 cable and the final work will be completed on 10/02. 09/01: Checking with the Vendor if they received permits for digging and if they can give us delivery date. 24/10 Pending order acknowledgement and placement with vendor | Complete | Circuit Migrated |  |  | NL-HLD01-0015 | NETHERLANDS_HELLENDOORN_SOURCING_UNIT |  |  |  |  | Ben & Jerry's Hellendoorn - Valkweg 2 - 7447 JL - HELLENDOORNeggeweg 15 | Hellendoorn | 7447 JL | Factory | Willem Flim | Jan-Willem.Flim@unilever.com | landline: + 31 655701563 mobile: + 31 655701563 |  |  | 10000Kbps | 40 | 52.3869 | 6.456 | 2020 | Jan | MPLS | [5 empty] | 8x5 work hour | 1000-1600 UTC | Induction training required. Health questionnaire to be completed by the FE | NA | NA |  |  | 1st Floor, Comms Room | 154.14.4.156/30 Network - 154.14.4.156 First usable - 154.14.4.157 Last usable - 154.14.4.158 Broadcast - 154.14.4.159 Subnet Mask - 255.255.255.252 | 154.14.4.157 | 154.14.4.158 | 154.14.4.156/30 |  |  | Vodafone Ziggo | [5 empty] | Fat Nela | Fat Nela | Fat Nela | 2020-04-06 |  | Complex site type - requires redesign | Complete |  | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 1000 - 1600 | 1100 - 1700 | 51398 | CRQ000000655425 | Approved | 41820 | CRQ000000654807 | Completed | Completed | Tested -Pass-First Time |  | Jan-Willem.Flim | Circuit Migrated | NA | NA | NA | 2020-03-01 | 2020-04-01
CKT-I-02-NL-HLD01-0015-BT-1 | I011321BT1 | 2 | Yes. Confirm if /30 ordered | High | Europe | Netherlands | Hellendoorn |  | un-uen-nldhel1-pio001 | un-uen-nldhel1-vpn002 | Eloise Shepheard | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-05-15 | 2020-04-30 | Complete | 2020-05-22 | 2020-04-30 | Complete | 2020-07-31 | 2020-05-15 | Complete | 2020-08-14 | 2020-05-20 | Complete | 21/05: Migration successful on 20 May. 28/04 Migration date suggested by local PoC May 13 or May 20. Cisco team to start prep work and submit a change request. | Complete | Circuit Migrated | Cisco |  | NL-HLD01-0015 | NETHERLANDS_HELLENDOORN_SOURCING_UNIT |  |  |  |  | Ben & Jerry's Hellendoorn - Valkweg 2 - 7447 JL - HELLENDOORNeggeweg 15 | Hellendoorn | 7447 JL | Factory | Willem Flim | Jan-Willem.Flim@unilever.com | landline: + 31 655701563 mobile: + 31 655701563 |  |  | 20/30 | 40 | 52.3869 | 6.456 | 2020 | Jan | Internet | [5 empty] | 8x5 work hour | 11:00am. to17:00pm. | [9 empty] | 0 | [8 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Complex site type - requires redesign |  |  |  | Yes | No |  |  |  |  | 09:00 to 15:00 | 10:00 to 16:00 | 65835 |  | Approved | 42823 | CRQ000000670945 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-IT-ROM01-0001-GTT-1 | I01550GTT1 | 1 | Yes. Confirm if /30 ordered | High | Europe | ITALY | Rome Head Office |  | un-uen-itarom1-rtr001 | un-uen-itarom1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001762251 | 2019-11-10 | 2019-10-10 | Complete | 2019-11-15 | 2019-11-15 | Complete | 2020-01-24 | 2020-01-14 | Complete | 2020-02-07 | 2020-06-03 | Complete | 29/05 Migration date confirmed for 03/06. 19/05: Eloise suggestion migration w/c 1st June. Customer mention end of May ? 05/05 Circuit testing required. Currently on hold due to civid-19 restrictions 20/02 Cisco was not aware that the handoff ordered was not Fibre.This wasn't highlighted in GTT trackers. This came out during testing. SFP needed to be ordered. The ETA for delivery is 05 Mar - Cisco chasing to have this delivered earlier. Potentially additional fiber cable required to connect HW between racks - this is owned by Unilever. 24/10 Pending order acknowledgement and order with vendor | Complete | Circuit Migrated | Circuit Provider |  | IT-ROM01-0001 | ITALY_ROME_HEAD_OFFICE |  |  |  |  | Via Paolo di Dono 3/A Roma | Roma | 00142 |  | Giuseppe Mangione |  |  |  |  | 40MB40MB | 200 | 45.8607 | 11.3388 | 2020 | Jan | MPLS | [5 empty] | NA | 09:00 - 17:00 | NA - this is office building, no special requirements | NA |  |  |  |  | 154.14.12.112/28 Network - 154.14.12.112 First usable - 154.14.12.113 Last usable - 154.14.12.126 Broadcast - 154.14.12.127 Subnet Mask - 255.255.255.240 | 154.14.12.113 | 154.14.12.114 | 154.14.12.112/28 |  |  | Colt | [5 empty] | Emir Jukovic | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | 1000Base-LX/LH with GLC-LH-SMD on ISR4k | No | Yes | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 07:00-15:00 | 09:00-17:00 | 42748 |  |  | 40988 | CRQ000000636397 | Completed | Completed | Tested-Fail | Media converter faulty, test to be redone with another one. Cable connectivity unclear, to be retested | [6 empty] | 2020-02-01
CKT-I-02-IT-ROM01-0001-CTL-1 | I02550CTL1 | 1 | Yes. Confirm if /30 ordered | High | Europe | ITALY | Rome Head Office | 2019_479 | un-uen-itarom1-vpn001 |  | Eloise Shepheard | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-05-15 | 2020-05-15 | Complete | 2020-05-22 | 2020-05-20 | Green | 2020-07-31 | 2020-07-20 | Green | 2020-08-14 | 2020-10-24 | Red | "16/07 - work is underway to move the comms room new location before circuit can be delievered. Hopefully end of August - Geo-IT need to confirm when work can start 15/07 - Provider has stated the site on hold as not ready - DC sent email to Mauro and Giuseppe to find out more whilst GY is following up with provider 09/07 - CTL tracker does not contain a delivery date 01/07 - waiting for FOC (Firm Order Commitment Date) from Provider - which is being escalated - Firm Order Commitment Date 11/06 - Circuit ordered - should arrive 20th July - migration august June 1st: Provider delivery date not informed" 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit Ordered | Unilever SNT |  | IT-ROM01-0001 | ITALY_ROME_HEAD_OFFICE |  |  |  |  | Via Paolo di Dono, 3a | Roma | 00142 | [6 empty] | 100MB100MB | 200 | 45.8607 | 11.3388 | 2020 | Jan | Internet | [14 empty] | 0 | 0 | 0 | [17 empty] | Yes
CKT-I-01-NL-RTM02-0004-GTT-1 | I01WC005GTT1 | 1 | Yes | High | Europe | NETHERLANDS | Nassaukade |  | un-uen-nlrotb1 | un-uen-nlrotb1-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Router | GTT | GTT |  | GTT/001769771 | 2019-10-18 | 2019-10-18 | Complete | 2019-10-25 | 2019-10-25 | Complete | 2020-01-03 | 2020-02-03 | Complete | 2020-01-17 | 2020-03-23 | Complete | 28/02 The router has been pre-configured by Cisco. Port switch has been configured by GNOC. Migration was cancelled - DMVPN tunnel was established and BGP routes received. All seems to be good from DMVPN perspective, but the customers didnt have fibers - Unilever couldn't connect to MPLS router and Core switch. A new date for the migration to be agreed once the cabling is arranged by the local team. 21/01: The order is delayed, because the fibres do not reach the customer location. The contractor will open a few handholes in week 5 to find the issue. 16/12 Vendor's delivery date changed to 03 Feb 2020 11/12 Vendor's delivery date 27/01/2020 08/12 FOC not confirmed yet | Complete | Circuit Migrated |  |  | NL-RTM02-0004 | NETHERLANDS_ROTTERDAM_NASSAUKADE_HEAD_OFFICE |  |  |  |  | Nassaukade 5 | Rotterdam | 3071 JL | [6 empty] | 150MB150MB | 200 | 51.915 | 4.5038 | 2020 | Jan | MPLS |  | Geo IT priority |  |  |  | NA | 0900 - 1500 UTC | NA | NA | NA | /29 |  | adjacent Upfield factory - Feijenoord, 3071 JL Rotterdam, Netherlands (51.9148243,4.5018233) | 154.14.6.96/28 Network - 154.14.6.96 First usable - 154.14.6.97 Last usable - 154.14.6.110 Broadcast - 154.14.6.111 Subnet Mask - 255.255.255.240 | 154.14.6.97 | 154.14.6.98 | 154.14.6.96/28 |  |  | KPN | [5 empty] | Damian Dabros | Damian Dabros | Damian Dabros | 2020-03-23 |  | Complex site type - requires redesign | In Progress |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 0900 - 1500 | 1000 - 1600 | 50461 44984 | CRQ000000654488 CRQ000000648172 | Approved | 41424 | CRQ000000644670 | Completed | Completed | Tested -Pass-First Time |  | Patrick De Bruin | Circuit Migrated | Customer didn't have fibres - cabling to be arranged before the new migration date is agreed. | NA | NA
CKT-I-02-NL-RTM02-0004-ORA-1 | I02WC005ORA1 | 1 | Login via local creds on SSH. Very slow connection. Yes Vishal to clarify if WAN circuit team to do the circuit migration after BAU is done with router replacement ? | High | Europe | NETHERLANDS | Nassaukade |  | un-uen-nldnas1-pio001 | un-uen-nlrotb1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | GO09ZMRT6B | 2019-01-11 | 2018-11-01 | Complete | 2019-01-18 | 2020-04-02 | Complete | 2019-03-29 | 2020-09-30 | Red | 2019-04-12 | 2020-12-31 | Red | Not in Unilever's tracker - 20th July 22-May-20: Unilever have confirmed that wireless is not a suitable option for this site and as Tele2 were requested for diversity and cannot provide the solution on their infrastructure, Unilever have decided to cancel this order. Cancellation is in progress in the tools (From orange tracker) 05/05 Delays with circuit delivery due to covid-19 20/12 Orange didn't receive validation email from local contact | On Hold | Circuit Order Accepted | Circuit Provider |  | NL-RTM02-0004 | NETHERLANDS_ROTTERDAM_NASSAUKADE_HEAD_OFFICE |  |  |  |  | Nassaukade 5 | Rotterdam | 3071 JL | [6 empty] | 150Mbps | 200 | 51.915 | 4.5038 | 2020 | Jan | Internet |  | Geo IT priority | [8 empty] | /29 |  |  |  | 0 | 0 | 0 |  |  | Tele2 | [5 empty] | Damian Dabros | Damian Dabros | Damian Dabros |  |  | Complex site type - requires redesign | In Progress |  | Yes |  | No
CKT-I-02-MM-RGN02-0001-UNL-1 |  | 1 | Not found in BT document or NP | Medium | SEAA | Myanmar | Unilever Myanmar Factory |  |  |  |  | SNT |  | Unilever | Uni |  |  | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-10-01 | 2019-10-01 | Complete | Completed by UL/BT | Complete | Circuit Migrated |  |  | MM-RGN02-0001 | [5 empty] | No.40, 41, 47 Min Thate Hti Kyaw Swar Road,39 Ward, Shwe Pyi Thar Zone (2) | Yangon |  | Factory | Ye Lin | Ye.lin@unilever.com | +959450951040 | Thiha Kyaw | Thiha.Kyaw@unilever.com |  | 30 |  |  | 2019 | Sep | Internet | [14 empty] | 0 | 0 | 0 | 0.925 | Within 4 hours | Telenor | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual DMVPN | Complete
CKT-I-01-MM-RGN02-0001-UNL-1 | I0120111UNL1 | 1 | Not found in BT document or NP | Medium | SEAA | Myanmar | Unilever Myanmar Factory |  | un-sea-mmryfc-vpn001 |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni |  | ENT0418 / TB1YN1312UNI | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2020-02-07 | Complete | 2019-10-01 | 2020-02-25 | Complete | 10-Feb:Brought forward migration to Feb and schedule needs to be confirmed 5-Feb: IP Details confirmed. 3-Feb: Pending IP details 10 Jan: Waiting for input from Geo IT to progress on site assessment | Complete | Circuit Migrated |  |  | MM-RGN02-0001 | [5 empty] | No.40, 41, 47 Min Thate Hti Kyaw Swar Road,39 Ward, Shwe Pyi Thar Zone (2) | Yangon | 11411 | Factory | Ye Lin | Ye.lin@unilever.com | +959450951040 | Thiha Kyaw | Thiha.Kyaw@unilever.com |  | 30 |  |  | 2019 | Nov | Internet | [6 empty] | 6:00 PM to 12:00 AM Local Time | "Local contact will escort the Field engineer. Training - None. Safety Gear - Helmet, Wear Boots, safety colour belt." | No | High |  |  |  | "Customer IP : 37.111.49.82 Subnet : 255.255.255.252 Gateway : 37.111.49.81 DNS : 8.8.8.8" | 37.111.49.81 | 37.111.49.82 | 0 | 0.925 | Within 4 hours | Telenor | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 11:30 to 17:30 UTC | 18:00 to 00:00 Local time | 40334 | CRQ000000644361 | Approved | 41302 | CRQ000000642039 | Completed | Completed | Tested -Pass-First Time | The test was successful. Everything worked fine without any issues. |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01
CKT-I-02-MM-RGN06-0001-UNL-1 |  | 1 | Yes. Confirm if /30 ordered | Medium | SEAA | Myanmar | Unilever Myanmar HQ |  | un-sea-mmrumm-vpn002 |  |  | SNT |  | Unilever | Uni |  |  | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-10-01 | 2019-10-01 | Complete | Completed by UL/BT | Complete | Circuit Migrated |  |  | MM-RGN06-0001 | [5 empty] | 196, Shwe Gon Daing (West) 5th St., Mimosa Tower, Saya San Ward, Bahan Township, Yangon Region | Yangon | 11201 | Office | Thang Sian Suan | ThangSian.Suan@unilever.com | +959777778685 | Thiha Kyaw | Thiha.Kyaw@unilever.com | 100MB | 100 |  |  | 2019 | Sep | Internet | [14 empty] | 0 | 0 | 0 | 0.925 | Within 4 hours | Telenor | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual DMVPN | Complete
CKT-I-01-MM-RGN06-0001-UNL-1 | I0120110UNL1 | 1 | Yes | Medium | SEAA | Myanmar | Unilever Myanmar HQ |  | un-sea-mmrumm-vpn001 |  | Vishal Joshi | WAN Circuit Migration | Circuit + Agile wifi consolidation | Unilever | Uni |  | ENT0417 / TB1YN2054UNI | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2020-01-15 | Complete | 2019-10-01 | 2020-03-04 | Complete | 5-Feb: New IP details provided and will need to redo algosec/zscaler changes. Migration moved to March 3-Feb: During testing, there were issues. Supplier provided new IP address and it was working with this IP. Algosec and Zscaler will need to be redone. MIgration on 7th Feb will need to be replanned after algosec and zscaler is reprocessed. 27-Jan: Migration date of 7th Feb per discussion with GEO IT. Testing planned on 3rd Feb. | Complete | Circuit Migrated |  |  | MM-RGN06-0001 | [5 empty] | 196, Shwe Gon Daing (West) 5th St., Mimosa Tower, Saya San Ward, Bahan Township, Yangon Region | Yangon | 11201 | Office | Thang Sian Suan | ThangSian.Suan@unilever.com | +959777778685 | Thiha Kyaw | Thiha.Kyaw@unilever.com | 100MB | 100 |  |  | 2019 | Nov | Internet | [6 empty] | 6:00 PM to 12:00 AM Local Time | "Local contact will escort the Field engineer. Training - None. Safety Gear - Helmet, Wear Boots, safety colour belt." | No | High |  |  |  | "IP : 37.111.49.22 Subnet : 255.255.255.252 Gateway : 37.111.49.21 DNS : 8.8.8.8" | 37.111.49.49/29 | 37.111.49.50/29 | 37.111.49.48/29 | 0.925 | Within 4 hours | Telenor | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 11:30 to 17:30 UTC | 18:00 to 00:00 Local time | 30707 | CRQ000000636771 | Approved | 41246 | CRQ000000640927 | Completed | Completed | Tested -Pass-First Time | The test was successful. However, the IP address changed. We are awaiting for the IP address to be provisioned. Post that will do the IP address testing |  | Circuit Migrated - First Time right |  |  |  | 2020-01-01 | 2020-02-01
CKT-I-01-MM-RGN99-9999-UNL-1 | I0110638UNL1 | 1 | Yes | Medium | SEAA | Myanmar | YGN Plant |  | un-sea-mmruey-vpn001 |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni |  | ENT0419 / TB1YN1872UNI | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2020-02-09 | Complete | 2019-10-01 | 2020-02-27 | Complete | 10-Feb: Received confirmation from Thiha that Circuit is delivered. Brought forward migration to Feb and schedule needs to be confirmed 5-Feb: IP details provided. 3-Feb: Pending IP details | Complete | Circuit Migrated |  |  | MM-RGN99-9999 | [5 empty] | Plot No. 28-31 and 31 , Zone 3, Hlaing Thar Yar Industrial Zone, Hlaing Thar Yar Township, Yangon | Yangon | 11401 | Factory | Zaw Lin Aung | Zawlin.aung@unilever.com | +959967610898 | Thiha Kyaw | Thiha.Kyaw@unilever.com | 30MB | 30 |  |  | 2019 | Sep | Internet | [6 empty] | 6:00 PM to 12:00 AM Local Time | "Local contact will escort the Field engineer. Training - None. Safety Gear - Helmet, Wear Boots, safety colour belt." | No | High |  |  |  | "User IP : 37.111.49.30 Subnet Mask : 255.255.255.252 Default Gateway : 37.111.49.29 DNS : 8.8.8.8" | 37.111.49.29/30 | 37.111.49.30/30 | 0 | 0.925 | Within 4 hours | Telenor | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 11:30 to 17:30 UTC | 18:00 to 00:00 Local time | 40354 | CRQ000000645166 | Approved | 41165 | CRQ000000641706 | Completed | Completed | Tested -Pass-First Time | The test was successful. Everything worked fine without any issues. |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01
CKT-I-02-MM-RGN99-9999-UNL-1 |  | 1 | Yes. Confirm if /30 ordered | Medium | SEAA | Myanmar | YGN Plant |  | un-sea-mmruey-vpn002 |  |  | SNT |  | Unilever | Uni |  |  | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-10-01 | 2019-10-01 | Complete | Completed by UL/BT | Complete | Circuit Migrated |  |  | MM-RGN99-9999 | [5 empty] | Plot No. 28-31 and 31 , Zone 3, Hlaing Thar Yar Industrial Zone, Hlaing Thar Yar Township, Yangon | Yangon | 11401 | Factory | Zaw Lin Aung | Zawlin.aung@unilever.com | +959967610898 | Thiha Kyaw | Thiha.Kyaw@unilever.com | 30MB | 30 |  |  | 2019 | Nov | Internet | [14 empty] | 0 | 0 | 0 | 0.925 | Within 4 hours | Telenor | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual DMVPN | Complete
CKT-I-02-NL-RTM02-9999-PCCW-1 |  | 1 | Not found in BT document or NP | Top | Europe | Netherlands | De-brug |  |  |  |  | BAU Projects |  | PCCW | PCCW |  | RTM(PCG) GI006504 | 2019-08-11 | 2019-01-11 | Complete | 2019-08-16 | 2019-08-11 | Complete | 2019-10-25 | 2020-05-29 | Red | 2019-11-08 |  | Red |  | Yellow | Circuit Order Accepted |  |  | NL-RTM02-9999 | [5 empty] | Hofplein 19 | Rotterdam | [8 empty] | 1000 |  |  | 2020 | Jan |  |  | Site Relocation | [12 empty] | 0 | 0 | 0
CKT-I-1-NL-RTM02-9999-GTT-1 |  | 1 | Not found in BT document or NP | Top | Europe | Netherlands | De-brug |  |  |  |  | BAU Projects |  | GTT | GTT |  | GTT/001777373 | 2019-10-24 | 2019-10-24 | Complete | 2019-10-31 | 2019-10-29 | Complete | 2020-01-09 | 2020-03-11 | Red | 2020-01-23 |  | Red | 03/12: Site survey was completed and GTT expecting the Vendor to send us the report. Unilever informed the Vendor that they don't want delivery until February 2020. | Yellow | Circuit Order Accepted |  |  | NL-RTM02-9999 | [5 empty] | Hofplein 19 | Rotterdam | [8 empty] | 1000 |  |  | 2020 | Jan |  |  | Site Relocation | [10 empty] | 6th floor, comms room | 154.14.6.112/28 Network - 154.14.6.112 First usable - 154.14.6.113 Last usable - 154.14.6.126 Broadcast - 154.14.6.127 Subnet Mask - 255.255.255.240 | 0 | 0 | 0 |  |  | Eurofiber Netherlands
CKT-I-01-AR-GHU01-0001-BT-1 | I011846BT1 | 1 | Already migrated from and also from 2921 to isr 4k. no open issues | Top | Latin America | Argentina | Gualeguaychú |  | un-ula-arggua1-pio001 | un-ula-arggua1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit + Router | BT | BT |  |  | 2019-12-01 | 2019-12-01 | Complete | 2019-12-06 | 2019-10-26 | Complete | 2020-02-14 | 2019-12-01 | Complete | 2020-02-28 | 2019-12-19 | Complete | 19-Dec: MIgration successfully completed on Dec-19th. 13-Dec: MOP has been completed. RFC and Webex details have been shared with BT for them to assign an engineer for the change. 6-Dec: Onboarding process has been agreed. BT has been informed of the changes that will be done ,and the ones they need to implement in the core switch. 29-Nov: Pending new device onboarding process to be agreed next week, as well as agreement with BT to make changes to core switch during migration. 27-Nov: New AlgoSec and Zscaler requests need to be re-issued (original requests were made with incorrect IP addresses) 26-Nov: Still pending info and details on how to onboard new router. 20-Nov: Migration date of 6-Dec possible if all required info is received by 22-Nov. 8-Nov: Still many missing info to prepare for migration. Cisco to propose 26-Nov as migration date. | Complete | Circuit Migrated |  |  | AR-GHU01-0001 | ARGENTINA_GUALEGUAYCHU |  |  |  |  | Parque Industrial, Ruta Nacional 14 acceso sur Gualeguychú | Gualeguaychu | 2820 |  |  |  |  | Ricardo Caldes | Ricardo.caldes@unilever.com | 10Mbps | 30 | -33.0564 | -58.4694 | 2019 | Nov | Internet |  | Geo IT priority | 1 |  |  | ART insurance required | 9AM local time | ART | Yes | Local users to be informed of downtime | /29 |  |  | 181.13.196.8/30 | 181.13.196.9 | 181.13.196.10 | 181.13.196.0/29 | [8 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | 2019-01-23 |  | Standard site type - Hybrid (DMVPN + IEN) | Complete | NO |  | No |  | Yes-Onboarding file created for CMS | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 13:00 PM | 9:00 AM | 19474 20254 (Alarms supression) 20472 (router onboarding to CMS) | CRQ000000627296 | Approved | 40410 | CRQ000000625220 | Completed | Completed | Tested -Pass-First Time | 19474 20254 (Alarms supression) |  | Circuit Migrated - First Time right |  |  |  |  | 2019-12-01
CKT-I-01-MX-CIU03-0001-BT-1 | I013281BT1 | 1 | Yes. Should order /29 + /30 IP | Top | Latin America | Mexico | Bosques |  | un-ula-mexbos1-drt001 | un-ula-mexbqs1-vpn002 | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-01-31 | 2020-01-31 | Out of Scope | 2019-01-31 | 2020-02-08 | Out of Scope | 2019-04-11 | 2020-02-28 | Out of Scope | 2019-04-25 | 2020-10-15 | Out of Scope | 8-May: Pending circuit installation. 19-Mar: Circuit order to be cancelled. New circuit to be ordered as CTL or GTT. 30-Jan: It was agreed with Dave and Zoe that there needs to be a country-wide analysis done in Mexico before migrating hub site Tultitlan_Tepalcapa, and then, once we have a strategy, we will schedule the rest of the other migrations in Mexico. 17-Jan: IPT spoke site. Can't migrate MPLS until IPT strategy is defined. 20-Dec: Requested BT to change the order and provide a /29 with the circuit. 13-Dec: Circuit being delivered by BT. Delivery date before 31-Dec. | Yellow | Circuit not ordered | Unilever SNT |  | MX-CIU03-0001 | MEXICO_BOSQUES_DE_LAS_LOMAS_PASEOS_DE_LOS_TAMARINDOS |  |  |  |  | Bosque de Tamarindos No 150 - Edificio Arcos Norte "D" | Ciudad de Mexico | 05120 |  | Karen.Soto | Karen.Soto@unilever.com | 525513844803 | Karen Soto | Karen.Soto@unilever.com | 200MB | 200 | 19.3226 | -99.125 | 2019 | Nov | MPLS | 2020-11-15 | Geo IT priority | [11 empty] | N/A | 0 | 0 | 0 | [8 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | [6 empty] | Yes |  |  | Assessment Complete | [19 empty] | 2020-01-01
CKT-I-02-MX-TTN01-0009-GTT-1 | I022794GTT1 | 1 | ISR4451-X router will be available once RAVB router is migrated. That should be used. Unable to validate the NAT Pools as NAT takes place on Juniper FW which we don't have access to. There are 3 additional routers with their own circuits, one for Agile, 2 for Regional MPLS. | Top | Latin America | Mexico | Tultitlan_Tepalcapa |  | ULA-MXTTLR2-RAVB | un-ula-mextul1-vpn001 | Juan Simon | WAN Circuit Migration | Circuit + Router + Agile wifi consolidation | GTT | GTT |  | GTT/001821703 | 2020-01-31 | 2020-01-27 | Complete | 2019-01-31 | 2020-02-07 | Complete | 2019-04-11 | 2020-07-30 | Complete | 2019-04-25 | 2020-07-19 | Complete | 19-Jul: Circuit successfully migrated. 6-Jul: Migration scheduled on July 19th along with the peer circuit migration.. 26-Jun: High Level Plan agreed. Pending GeoIT to approve migration date, as well as to get the internal cabling ready before migration. 10-Jun: Discussion with BAU Team (LAN changes) to align activities and avoid conflicts between both team's changes. 25-May: FW rules received. Cisco is analyzing them. 8-May: Pending Unilever to get FW rules from BT, and Cisco to implement LAN changes. 31-Apr: Pending last meeting to finalize planning of the migration (LAN changes before WAN changes? WAN first and then LAN? During same window? Risks for any scenario) 19-Mar: Some changes required for this migration might need to be done by the BAU Team. Will discuss internally. 18-Mar: Migrations in Mexico postponed indefinitely due to coronavirus. 30-Jan: It was agreed with Dave and Zoe that there needs to be a country-wide analysis done in Mexico before migrating hub site Tultitlan_Tepalcapa, and then, once we have a strategy, we will schedule the rest of the other migrations in Mexico. 15-Jan: Migration requires deep analysis since the tasks involved fall outside the scope of the WAN migration. | Complete | Circuit Migrated | Cisco Unilever Geo-IT | Check dates | MX-TTN01-0009 | MEXICO_TULTITLAN_TEPALCAPA |  |  |  |  | Av. Tepalcapa No. 2, Col. Rancho Santo Domingo. Tultitlan, Estado de México. C.P. 54900 | Tultitlan | 54900 |  | Karen.Soto | Karen.Soto@unilever.com | 525513844803 | Karen Soto | Karen.Soto@unilever.com | 150Mb | 260 | 19.612 | -99.1569 | 2019 | Nov | Internet | 2020-11-15 | Geo IT priority | [12 empty] | 98.124.162.17 | 98.124.162.18 | 173.205.101.232-173.205.101.239 | [8 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Complex site type - requires redesign |  |  | No |  |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  |  |  | 102743 | CRQ000000692744 | Approved | 41661 | CRQ000000651600 CRQ000000691306 | Completed | Completed | Tested-Pass | Jul-17: Circuit test successful. Set to Autonegotiate. Jul-16: Tested the circuit for a second time and we are still getting low DL speeds. UL speed is correct. |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-04-01
CKT-I-01-MX-TTN03-0002-BT-1 | I013243BT1 | 1 | Found in network diagram - MEXICO_TULTITLAN_JOSE_LOPEZ_PORTILLO Login via Telnet and TACACS. Yes. Should order /30. | Top | Latin America | Mexico | Jose Lopez Portillo |  | UNI_MX_TUL2_RTR_01 | UNI_MX_TUL2_VPN_01 | Juan Simon | WAN Circuit Migration |  | BT | BT |  | BT OT 94011373 | 2019-01-31 | 2019-01-31 | Complete | 2019-01-31 | 2019-01-31 | Complete | 2019-04-11 | 2020-02-28 | Complete | 2019-04-25 | 2020-08-22 | Complete | 24-Aug: Migration successful. 6-Aug: Migration approved for August 22 at 9AM. 26-Jun: Migration date pushed for a future date since the HW move to the new building has been postponed. Date TBD. 16-Jun: Migration pushed to one week later. Exact time TBD. Need to coordinate with BAU Team for LAN and WAN changes. Circuit testing failed today. To be fixed by provider tomorrow. 12-Jun: Circuit to be migrated on June 21st. Circuit test on June 17th 10AM. 22-May: Site expected to be activated the 1st week of June. Welington will help coordinate activities with BAU Team. 30-Apr: Pending GeoIT to confirm the circuit has been reconnected so we can test it. 18-Mar: Migrations in Mexico postponed indefinitely due to coronavirus. 07-Mar: Circuit un-installed due to changes in the site. GeoIT will inform once circuit is installed again. 30-Jan: It was agreed with Dave and Zoe that there needs to be a country-wide analysis done in Mexico before migrating hub site Tultitlan_Tepalcapa, and then, once we have a strategy, we will schedule the rest of the other migrations in Mexico. 17-Jan: IPT spoke site. Can't migrate MPLS until IPT strategy is defined. 13-Dec: Office move. Circuit already delivered to the new office location and connected to a new router. | Complete | Circuit Migrated | Unilever Geo-IT |  | MX-TTN03-0002 | MEXICO_TULTITLAN_JOSE_LOPEZ_PORTILLO |  |  |  |  | Via Lopez Portillo 2, Colonia Recursos Hidraulicos | Tultitlan | 54913 |  | Karen.Soto | Karen.Soto@unilever.com | 525513844803 | Karen Soto | Karen.Soto@unilever.com | 512kbps | 10 | 19.6212 | -99.1667 | 2019 | Nov | Internet | 2020-11-15 | Geo IT priority | [11 empty] | WAN CL = 168.195.200.229/30 WAN BT= 168.195.200.230/30 LAN = 168.195.201.200/29 | 168.195.200.229/30 | 168.195.200.230/30 | 168.195.201.200/29 | [8 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo | [6 empty] | Yes | [7 empty] | 116433 | CRQ000000702670 | Approved |  | CRQ000000683166 | Completed | Completed | Tested-Pass | June-23: Circuit now successfully tested. Device is not conected to the rack |  | Circuit Migrated - First Time right |  |  |  |  | 2020-01-01
CKT-I-01-DE-HAM99-9999-GTT-1 |  | 1 | Yes. Require to order /29 + /30. Also present on site- un-uen-deuham1-rtr001 | High | Europe | Germany | Hamburg Strandkai - New office |  |  |  |  | BAU Projects |  | GTT | GTT |  | GTT/001792343 | 2019-05-11 | 2019-05-11 | Complete | 2019-05-17 | 2019-05-17 | Green | 2019-07-26 | 2020-04-30 | Red | 2019-08-09 |  | Red |  | Yellow | Circuit Ordered |  |  | DE-HAM99-9999 | [5 empty] | Neue Burg 1 | Hamburg | 20457 | [6 empty] | 140MB | 1000 |  |  | 2020 | [14 empty] | Ground Floor, Patch room (where the current fiber goes up to the 1st floor). | 154.14.8.192/28 Network - 154.14.8.192 First usable - 154.14.8.193 Last usable - 154.14.8.206 Broadcast - 154.14.8.207 Subnet Mask - 255.255.255.240 | [5 empty] | Colt
CKT-I-02-DE-HAM99-9999-CTL-1 |  | 1 | Yes. Require to order /29 + /30. Also present on site- un-uen-deuham1-rtr001 | High | Europe | Germany | Hamburg Strandkai - New office |  |  |  |  | BAU Projects |  | CenturyLink | CL |  | 441770218 335571864 - DIA 335571865 - Access 335571866 - Logical 335571867 - Port | 2019-05-11 | 2019-05-11 | Complete | 2019-05-11 | 2019-05-11 | Complete | 2019-07-20 | 2020-06-15 | Complete | 2019-08-02 |  | Red |  | Yellow | Circuit Delivered |  |  | DE-HAM99-9999 | [5 empty] | Neue Burg 1 | Hamburg | 20457 | [6 empty] | 140MB | 1000 |  |  | 2020 | [15 empty] | LAN: 212.162.54.32/28 WAN: 212.162.18.144/30 CTL: 212.162.18.145 UNI: 212.162.18.146
CKT-I-01-FI-HEL02-0001-UNL-1 |  | 1 | Not found in NP, used old BW given. Not sure of IP address mask required Yes. Existing reported as 10 MB | High | Europe | Finland | Helsinki |  |  |  |  | BAU Projects |  | Unilever | Uni |  |  | 2019-01-11 | 2019-01-11 | Complete | 2019-01-18 | 2019-11-06 | Red | 2019-03-29 | 2020-02-12 | Red | 2019-04-12 |  | Red |  | Yellow | Circuit Ordered |  |  | FI-HEL02-0001 | FINLAND_HELSINKI_VALLILA |  |  |  |  | Roineentie 10, Vallila | Helsinki | FI-00510 | [6 empty] | 0 | 70 | 60.1929 | 24.9544 | 2019 | Nov
CKT-I-02-FI-HEL02-0001-UNL-1 |  | 1 | Not found in BT document or NP | High | Europe | Finland | Helsinki |  |  |  |  | BAU Projects |  | Unilever | Uni |  |  | 2019-01-11 | 2019-01-11 | Complete | 2019-01-18 | 2019-11-06 | Red | 2019-03-29 | 2020-02-12 | Red | 2019-04-12 |  | Red |  | Yellow | Circuit Ordered |  |  | FI-HEL02-0001 | FINLAND_HELSINKI_VALLILA |  |  |  |  | Roineentie 10, Vallila | Helsinki | FI-00510 | [7 empty] | 70 | 60.1929 | 24.9544 | 2019 | Nov
CKT-I-1-NL-TVG02-9999-GTT-1 |  | 1 | Not found in BT document or NP |  | Europe | Netherlands | The Vegetarian Butcher |  |  |  |  | BAU Projects |  | GTT | GTT |  | GTT/001791289 | 2019-12-11 | 2019-12-11 | Complete | 2019-12-18 | 2019-12-18 | Green | 2020-02-26 | 2020-04-22 | Red | 2020-03-11 |  | Red |  | Yellow | Circuit Ordered |  |  | NL-TVG02-9999 | [5 empty] | Markhek 5 |  | 4824AV | [7 empty] | 100 |  |  | 2020 | [15 empty] | 154.14.10.148/30 Network - 154.14.10.148 First usable - 154.14.10.149 Last usable - 154.14.10.150 Broadcast - 154.14.10.151 Subnet Mask - 255.255.255.252 | [5 empty] | Tele2 Netherlands
CKT-I-02-NL-TVG02-9999-CTL-1 |  | 1 | Not found in BT document or NP |  | Europe | Netherlands | The Vegetarian Butcher |  |  |  |  | BAU Projects |  | CenturyLink | CL |  | 441741250 335485013 - DIA 335485014 - Access 335485015 - Logical 335485016 - Port | 2019-12-11 | 2019-12-11 | Complete | 2019-12-11 | 2019-12-11 | Complete | 2020-02-19 | 2020-05-10 | Red | 2020-03-04 |  | Red |  | Yellow | Circuit Order Accepted |  |  | NL-TVG02-9999 | [5 empty] | Markhek 5 |  | 4824AV | [7 empty] | 100 |  |  | 2020
CKT-I-02-RO-BUH01-4244-UNL-1 | I013744UNL1 | 1 | Yes. Confirm if /30 ordered. Could also be device name un-uen-rouebr1-rtr002 which requires only /30 and 10000kbps | High | Europe | ROMANIA | Bucharest HO |  | un-uen-roubuc1-pio001 |  | Agnieszka Pajak | WAN Circuit Migration |  | Unilever | Uni |  |  | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-10-01 | 2019-12-15 | Complete | 28/11 Date for the configuration has been confirmed by local GeoIT 26/11 Awaiting confirmation on date for PIO change into DMVPN from the customer | Complete | Circuit Migrated |  |  | RO-BUH01-4244 | ROMANIA_BUCHAREST_HEAD_OFFICE |  |  |  |  | 42-44 Sos. Bucuresti-Ploiesti, 4th Floor | Bucharest | 13696 |  | Andrei Costache | Andrei.costache@unilever.com | 0040727531060 | Dusan Stefanovic | Dusan.Stefanovic@unilever.com | 200M | 300 | 44.4389 | 26.0975 | 2019 | Nov | Internet |  | Service |  |  | SC2 | Convert existing PIO to DMVPN | 0800 - 1400 UTC | Escort from local contact required | NA | NA | [15 empty] | Adrian Lazar | Adrian Lazar | Adrian Lazar | 2019-12-16 |  | Complex site type - requires redesign | Complete |  | No | Yes | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 0800 - 1400 | 1000 - 1600 | 18735 | CRQ000000624900 | Approved | 40283 | CRQ000000624473 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right |  |  |  |  | 2019-12-01
CKT-I-02-RO-PLT02-0001-UNL-1 | I011404UNL1 | 1 | Yes. Confirm if /30 ordered. Could also be device name un-uen-roubic-rtr002 | High | Europe | ROMANIA | Ploiesti Factory |  | un-uen-rouplo1-pio001 |  | Agnieszka Pajak | WAN Circuit Migration |  | Unilever | Uni |  |  | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-10-01 | 2019-12-15 | Complete | 28/11 Date confirmed. 26/11 Awaiting confirmation on date for PIO change into DMVPN from the customer | Complete | Circuit Migrated |  |  | RO-PLT02-0001 | ROMANIA_PLOESTI_FACTORY_REPUBLICII_291 |  |  |  |  | 291 Bd. Republicii | Ploiesti | 100072 |  | Irinel Matei | Irinel.matei@unilever.com | 0040727736342 | Dusan Stefanovic | Dusan.Stefanovic@unilever.com | 10000Kbps | 100 | 44.9412 | 26.0225 | 2019 | Nov | Internet |  | Service |  |  | SC2 | Convert existing PIO to DMVPN | 0800 - 1400 UTC | Escort from local contact required | NA | NA | [15 empty] | Adrian Lazar | Adrian Lazar | Adrian Lazar | 2019-12-16 |  | Complex site type - requires redesign | Complete |  | No | Yes | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 0800 - 1400 | 1000 - 1600 | 18737 | CRQ000000625514 | Approved | 40284 | CRQ000000624761 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right |  |  |  |  | 2019-12-01
CKT-I-01-MM-MDL01-0001-UNL-1 |  | 1 | Not found in BT document or NP | Medium | SEAA | Myanmar | Unilever Mandalay Office |  |  |  |  | SNT |  | Unilever | Uni |  | NA | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-09-20 | 2019-08-01 | Complete | 2019-10-01 | 2019-10-01 | Complete | Completed by UL/BT | Complete | Circuit Migrated |  |  | MM-MDL01-0001 | MYANMAR_MAHARAUNGMYAE_NO 69 70 CORNER OF 68 43 STR |  |  |  |  | No - 69/70, Corner of 68 & 43 Street, Mahamyaing (11), Qtr (1 ) , MahaAungMyae Township, Mandalay, Myanmar | Mandalay | 5033 | Office | Han Soe Htut | Hansoe.htut@unilever.com | +959 964216348 | Thiha Kyaw | Thiha.Kyaw@unilever.com |  | 20 |  |  | 2019 | Nov | Internet | [17 empty] | 0.925 | Within 4 hours | GTMH | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual DMVPN | Complete
CKT-I-02-MM-MDL01-0001-UNL-1 | I0220129UNL1 | 1 | Yes. Confirm if /30 ordered | Medium | SEAA | Myanmar | Unilever Mandalay Office |  | un-sea-mmrumd-agi001 |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | GT00464:1 | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2020-01-23 | Complete | 2019-10-01 | 2020-02-18 | Complete | 5-Feb: Thiha confirmed during the testing meeting that the bandwidth ordered is 5 MBPS only. Tracker updated to reflect this BW. Migration window was changed to start at 2 pm. NTT engineer to come to site by 11 am to rack the new router. 3-Feb: Testing planned for 5th Feb. Thiha to confirm IP details to confirm no changes by 4th Feb. 27-Jan: Migration date of 18th Feb per discussion with GEO IT. Will configure Agile only for 5 MB on this link and use existing 4321 router. | Complete | Circuit Migrated |  |  | MM-MDL01-0001 | MYANMAR_MAHARAUNGMYAE_NO 69 70 CORNER OF 68 43 STR |  |  |  |  | No - 69/70, Corner of 68 & 43 Street, Mahamyaing (11), Qtr (1 ) , MahaAungMyae Township, Mandalay, Myanmar | Mandalay | 5033 | Office | Han Soe Htut | Hansoe.htut@unilever.com | +959 964216348 | Thiha Kyaw | Thiha.Kyaw@unilever.com | 20MB | 5 |  |  | 2019 | Nov | Internet | [6 empty] | 2:00 PM to 8:00 PM Local Time | "Local contact will escort the Field engineer. Training - None. Safety Gear - Helmet, Wear Boots, safety colour belt." | No | High |  |  |  | """Network : 103.113.87.180/30 Gateway IP : 103.113.87.181 Subnet Mark : 255.255.255.252 DNS Server : 103.213.228.90""" | 103.113.87.181/30 | 103.113.87.182/30 |  | 0.925 | Within 4 hours | GTMH | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual DMVPN | Complete | NO |  | Yes |  | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 04:30 to 13:30 UTC | 14:00 to 00:00 Local time | 37477 | CRQ000000642399 | Approved | 41022 | CRQ000000637282 | Completed | Completed | Tested -Pass-First Time |  | Han Soe | Circuit Migrated - First Time right |  |  |  | 2020-01-01 | 2020-02-01
CKT-I-01-MM-MDY99-9999-UNL-1 |  | 1 | Yes | Medium | SEAA | Myanmar | MDY 1 Plant |  | un-sea-mmruem-vpn001 |  |  | SNT |  | Unilever | Uni |  |  | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-09-20 | 2019-08-01 | Complete | 2019-10-01 | 2019-10-01 | Complete | Completed by UL/BT | Complete | Circuit Migrated |  |  | MM-MDY99-9999 | MYANMAR_PYIGYITAKHAN_PLOT NO 128 133 WARD_MANDALAY |  |  |  |  | Plot No. 130,131,132,133, H Ward, Pyigyitakhun Township, Mandalay, Myanmar | Mandalay | 5051 | Factory | Han Soe Htut | Hansoe.htut@unilever.com | +959 964216348 | Thiha Kyaw | Thiha.Kyaw@unilever.com | 30MB | 30 |  |  | 2019 | Sep | Internet | [17 empty] | 0.925 | Within 4 hours | [6 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual DMVPN | Complete
CKT-I-02-MM-MDY99-9999-UNL-1 |  | 1 | Yes | Medium | SEAA | Myanmar | MDY 1 Plant |  | un-sea-mmruem-vpn002 |  |  | SNT |  | Unilever | Uni |  |  | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-08-01 | Complete | 2019-09-20 | 2019-08-01 | Complete | 2019-10-01 | 2019-10-01 | Complete | Completed by UL/BT | Complete | Circuit Migrated |  |  | MM-MDY99-9999 | MYANMAR_PYIGYITAKHAN_PLOT NO 128 133 WARD_MANDALAY |  |  |  |  | Plot No. 130,131,132,133, H Ward, Pyigyitakhun Township, Mandalay, Myanmar | Mandalay | 5051 | Factory | Han Soe Htut | Hansoe.htut@unilever.com | +959 964216348 | Thiha Kyaw | Thiha.Kyaw@unilever.com | 30MB | 30 |  |  | 2019 | Sep | Internet | [17 empty] | 0.925 | Within 4 hours | [6 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual DMVPN | Complete
CKT-I-01-BD-DAC01-0002-UNL-1 |  | 1 | Yes | High | South Asia | Bangladesh | Dhaka |  | un-sea-bgddha1-rtr001 |  |  | SNT |  | Unilever | Uni |  |  | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-09-01 | Complete | 2019-10-01 |  | Complete |  | Complete | Circuit Migrated |  |  | BD-DAC01-0002 | [5 empty] | ZN Tower , Plot No.2 of Block SW(1) Gulshan Avenue, Road No.8 | Dhaka | [5 empty] | Faisal Rahman | Faisal.Rahman@unilever.com | 2000Kbps2000Kbps6000Kbps2000Kbps25MB | 200 |  |  | 2019 | Oct | Internet
CKT-I-02-BD-DAC01-0002-UNL-1 |  | 1 | Yes | High | South Asia | Bangladesh | Dhaka |  | un-sea-bgddha1-rtr002 |  |  | SNT |  | Unilever | Uni |  |  | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-09-01 | Complete | 2019-10-01 |  | Complete |  | Complete | Circuit Migrated |  |  | BD-DAC01-0002 | [5 empty] | ZN Tower , Plot No.2 of Block SW(1) Gulshan Avenue, Road No.8 | Dhaka | [5 empty] | Faisal Rahman | Faisal.Rahman@unilever.com | 25MB2000Kbps100Kbps25MB2000Kbps6000Kbps25MB2000Kbps | 200 |  |  | 2019 | Oct | Internet
CKT-I-01-LK-CMB05-0001-UNL-1 |  | 1 | Not found in BT document or NP | High | South Asia | Sri Lanka | Colombo |  |  |  |  | SNT |  | Unilever | Uni |  | 099-4606523 | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-09-01 | Complete | 2019-10-01 |  | Complete |  | Complete | Circuit Migrated |  |  | LK-CMB05-0001 | [5 empty] | Lot 3, No. 258, M Vincent Perera Mawatha, Grandpass | Colombo | [5 empty] | Kushan Wijesinghe | Kushan.Wijesinghe@unilever.com |  | 200 |  |  | 2019 | Oct | Internet
CKT-I-02-LK-CMB05-0001-UNL-1 |  | 1 | Hostname Of the Device : un-sea-ikacol1-vpn002 | High | South Asia | Sri Lanka | Colombo |  | un-sea-lkacol1-pio001 |  |  | SNT |  | Unilever | Uni |  | D28099 | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-09-01 | Complete | 2019-09-01 | 2019-09-01 | Complete | 2019-10-01 |  | Complete |  | Complete | Circuit Migrated |  |  | LK-CMB05-0001 | [5 empty] | Lot 3, No. 258, M Vincent Perera Mawatha, Grandpass | Colombo | [5 empty] | Kushan Wijesinghe | Kushan.Wijesinghe@unilever.com | 150MB | 200 |  |  | 2019 | Oct | Internet
CKT-I-01-BD-CGP01-0001-UNL-1 | I019673UNL1 | 2 | Hostname Of the Device : un-sea-bd-kgf-vpn001 | Medium | South Asia | Bangladesh | Chittagong KGF |  | un-sea-bd-kgf-vpn001 | un-sea-bd-kgf-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | ADN Telecom | Kalurghat Internet | 2019-12-13 | 2019-12-13 | Complete | 2019-12-18 | 2019-12-20 | Complete | 2020-02-16 | 2020-02-07 | Complete | 2020-02-28 | 2020-03-20 | Complete | 9-Mar: Migration of new links rolled back due to issue with LAN during MW. Need to investigate and re-plan 10-Feb: Proposed migration date of 6th Mar and will need to be confirmed with GEO IT. 3-Feb: Meeting scheduled with GEO IT for 6th Feb to further discussion on technical queries and finalise plan. 27-Jan: Received partial information from GEO IT and working with them to get rest of the required info 19 Jan: Technical meeting done on 13th. Awaiting technical info 10 Jan: IP received. Network diagram shared by UL is incomplete. Requested revised document. | Complete | Circuit Migrated | [8 empty] | UBL Foods Factory , 51 Kalurghat Heavy Industrial Area | Chittagong |  |  | A.K.M. Saiede | AKM.Saiede@unilever.com | T: +88 031 670500, Ext- 23302 | Faisal Rahman | Faisal.Rahman@unilever.com | 100 | 100 | [10 empty] | Plan migration on friday and between 10 am to 4 pm local time. GEO IT can perform the tasks of NTT and may not need FE | 10 am to 4 pm | ID card, company and person details. Safety induction. Every Monday and Wednesday safety training are arranged and engineer to attend one of these activities. |  |  | /29 |  | Floor 1, KGF Server room | WAN segment IP: IP Address: 103.219.161.234 Subnet MASK: 255.255.255.252 Gateway: 103.219.161.233 LAN segment IP Block: 103.219.161.240/29 LAN SUbnet - 255.255.255.248 | 103.219.161.233 | 103.219.161.234 | 103.219.161.240/29 | 0.99 |  | ADN Telecom Ltd | CTG_GEC_POP | 38203 |  |  |  | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  | Complex site type - requires redesign | Complete |  | No | No | No | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Prep documents uploaded to central storage SSR approved | Window Date agreed - End user Comms sent |  | 4:00 am to 10:00 am UTC | 10am to 4pm local time. | 44623(March 6) 47868(March 20) | CRQ000000647950(6 Mar) CRQ000000652300 (20 Mar) | Approved | 41298 | CRQ000000641867 | Completed | Completed | Tested -Pass-First Time |  | Saiede | Circuit Migrated | Incorrect configuration on the core switch resulted in packet drops leading to window roll back. |  |  | 2020-02-01 | 2020-02-01
CKT-I-02-BD-CGP01-0001-UNL-1 | I029673UNL1 | 2 | Hostname Of the Device : un-sea-bd-kgf-vpn002 | Medium | South Asia | Bangladesh | Chittagong KGF |  | un-sea-bd-kgf-vpn002 | un-sea-bd-kgf-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | ADN Telecom | Kalurghat Internet | 2019-12-13 | 2019-12-13 | Complete | 2019-12-18 | 2019-12-20 | Complete | 2020-02-16 | 2020-02-07 | Complete | 2020-02-28 | 2020-03-20 | Complete | 9-Mar: Migration of new links rolled back due to issue with LAN during MW. Need to investigate and re-plan 10-Feb: Proposed migration date of 6th Mar and will need to be confirmed with GEO IT. 3-Feb: Meeting scheduled with GEO IT for 6th Feb to further discussion on technical queries and finalise plan. 27-Jan: Received partial information from GEO IT and working with them to get rest of the required info 19 Jan: Technical meeting done on 13th. Awaiting technical info | Complete | Circuit Migrated | [8 empty] | UBL Foods Factory , 51 Kalurghat Heavy Industrial Area | Chittagong |  |  | A.K.M. Saiede | AKM.Saiede@unilever.com | T: +88 031 670500, Ext- 23302 | Faisal Rahman | Faisal.Rahman@unilever.com | 100 | 100 | [10 empty] | Plan migration on friday and between 10 am to 4 pm local time. GEO IT can perform the tasks of NTT and may not need FE | 10 am to 4 pm | ID card, company and person details. Safety induction. Every Monday and Wednesday safety training are arranged and engineer to attend one of these activities. |  |  | /29 |  | Floor 1, KGF Server room | WAN segment IP: IP Address: 103.219.161.238 Subnet MASK: 255.255.255.252 Gateway: 103.219.161.237 LAN segment IP Block: 103.219.161.224/29 LAN Subnet Mask - 255.255.255.248 | 103.219.161.237 | 103.219.161.238 | 102.219.161.224/29 | 0.99 |  | ADN Telecom Ltd | CTG-Kalurghat_POP | 38203 |  |  |  | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  | Complex site type - requires redesign | Complete |  | No | No | No | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Prep documents uploaded to central storage SSR approved | Window Date agreed - End user Comms sent |  | 4:00 am to 10:00 am UTC | 10am to 4pm local time. | 44623(March 6) 47868(match 20) | CRQ000000647950(6 Mar) CRQ000000652300 (20 Mar) | Approved | 41301 | CRQ000000642034 | Completed | Completed | Tested -Pass-First Time |  | Saiede | Circuit Migrated | Incorrect configuration on the core switch resulted in packet drops leading to window roll back. |  |  | 2020-02-01 | 2020-03-01
CKT-I-01-NONHRTZA012-UNL-1 | I0110881UNL1 | 2 | Yes |  | Africa | TANZANIA | KABAMBE TEA FACTORY |  | un-amt-tzakab-vpn001 | un-amt-tzakab-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni |  | 862782300 | 2020-01-15 | 2020-01-15 | Complete | 2020-01-20 | 2020-01-20 | Complete | 2020-03-20 | 2020-06-30 | Complete | 2020-04-03 | 2020-07-21 | Complete | Action Item : Geo IT (Musa.Adeka@unilever.com) is coordinating with service provider for delivery of circuit and IP. Need IP details from ISP. 05-May: Forecast circuit delivery date updated to 5th Jun per discussion with Musa. 05- Feb: As requested by UL, suggestion given for IP requirement. UL is working with service provider. 03- Feb : Site assessment and Network architecture verification is in progress. | Complete | Circuit Migrated | Unilever Geo-IT |  | NONHRTZA012 | TANZANIA_KABAMBE TEA FACTORY_LWANGU VILLAGE_NJOMBE |  |  |  |  | Box 40 Mufindi, Iringa, TANZANIA Lwangu Village, Njombe. | [8 empty] | 2Mbps | 8 |  |  | 2020 | Mar | [14 empty] | IP : 41.59.209.85 Subnet : 255.255.255.0 Gateway : 41.59.209.1 DNS : 41.59.226.59 : 41.59.226.90 | 41.59.209.1 | 41.59.209.85 |  |  |  | TTCL | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  |  | Complex site type - requires redesign | In Progress |  | No | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  |  |  | 98765 | CRQ000000692306 | Approved |  | CRQ000000689046 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-UCORPAUT010-BT-1 | I0120381BT1 | 2 |  |  | Europe | AUSTRIA | AUSTRIA_VIENNA_HQ_OFFICE | 2019_13 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-11-16 | Red | 09/07 - Ruth Berghofer explained they have approx 30 users on site and not a production site - Useful site for testing for DACH region as no impact on production operations 26/06 - Confirmed as Direct Delivery Path - Quick Win 11/06: Discussed with David. Pending update regarding ordering/delivery date for BT circuits 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPAUT010 | AUSTRIA_VIENNA_HQ_OFFICE |  |  |  |  | Unilever Austria GmbH, Stella-Klein-Löw-Weg 13, 1020 Wien, Austria | [9 empty] | 40 |  |  | 2020 | Mar | [26 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar
CKT-I-02-UCORPAUT010-GTT-1 |  | 2 |  | High | Europe | AUSTRIA | [5 empty] | SNT |  | GTT | GTT |  | GTT/001817214 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPAUT010 | AUSTRIA_VIENNA_HQ_OFFICE | [14 empty] | 100 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [40 empty] | 97834 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-BE-BRU04-0001-BT-1 | I0120323BT1 | 2 | Yes |  | Europe | BELGIUM | BELGIUM_ELSENE_EUROPEAN_PUBLIC_AFFAIRS |  | un-uen-belels1-rtr001 |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-10 | Amber | 2020-04-05 | 2020-07-24 | Red | 2020-04-17 | 2020-08-28 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Green | Circuit Ordered | Circuit Provider |  | BE-BRU04-0001 | BELGIUM_ELSENE_EUROPEAN_PUBLIC_AFFAIRS |  |  |  |  | Rue d'Idalie 9/13, Part of 2nd Floor | Brussels | 1050 | [6 empty] | 6MB | 40 |  |  | 2020 | Mar | [26 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar | [5 empty] | No |  | No
CKT-I-02-BE-BRU04-0001-GTT-1 | I0220323GTT1 | 2 | Yes |  | Europe | BELGIUM | BELGIUM_ELSENE_EUROPEAN_PUBLIC_AFFAIRS | 2019_33 | un-uen-belels1-vpn001 |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001830192 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-10-30 | Red | 2020-04-17 | 2020-10-13 | Red | 15/07 - still awaiting for permits to carry out civil engineering work 01/07 Pending confirmation if the Vendor's subcontractor submitted the request for permits. 17/06 - email sent saying we will conctact Kaiti and Jan nearer the time if Eurofibre work can be started 17/06 - key user (Kaiti Grivet) and IT availability (Van-Ocken, Jan ) requesting date in September 17/06 - Julian Williamson asked Gergana over email if that is worst case date 17/06 - Gergana GTT -> Eurofiber set delivery date for connection of 14-08-2020 as needs civil installation (new route) June 1st: 27/05: Pending site survey results and FOC date. 10/06: Circuit should be delivered on the 14th August 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Order Accepted | Circuit Provider | Check dates | BE-BRU04-0001 | BELGIUM_ELSENE_EUROPEAN_PUBLIC_AFFAIRS |  |  |  |  | Rue d'Idalie 9/13, Part of 2nd Floor | Brussels | 1050 | [6 empty] | 20Mbps | 40 |  |  | 2020 | Mar | [13 empty] | 2nd floor. computer room | 154.14.57.156/30 Network - 154.14.57.156 First usable - 154.14.57.157 Last usable - 154.14.57.158 Broadcast - 154.14.57.159 Subnet Mask - 255.255.255.252 | [5 empty] | Eurofiber Belgium | [5 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar | [5 empty] | No |  | No
CKT-I-01-UCORPBIH002-GTT-1 | I0110698GTT1 | 2 | Yes |  | Europe | BOSNIA | BOSNIA_AND_HERZEGOVINE | 2019_38 | un-uen-bihsar1-pio001 |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001830187 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-09-30 | Red | 2020-04-17 | 2020-10-24 | Red | 21/08: Vendor visiting site on 24th August 15/07 - waiting for GTT vendor to feedback 13/07 - Deepak checking with GTT and Mihail has asked to confirm how this is done in other sites 09/07 - Dusan requested clarity from Deepak as to who pays the cable cost 08/07 - Dusan sent email to Deepak asking him to confiirm that 175.00 EUR cost is for cable between 2 buildings 08/07 - Dusan confirmed Unilever cost will be covered locally - Dusan will follow up with local team. 07/07 - Currently no delivery date advised by GTT (status is on hold) 02/07- Aldina confirmed expense is handled by local site and she will be raising a PO and advise u when completed and approved – so u can proceed further. 26/06 - Aldina confirmed she can not check and confirm on questions until her LM is back on 1st July 24/06 - Sarajevo - Dusan requested Aldina to help progress 17/06 - Deepak confirmed spoken to Dusan & will clarify the support model as soon as Aldina back in office on Monday 16/06 - Deepak emailed for confirmation of how the internal building cable rental can be funded. 16/06 - email sent to Lipowicz, Adam local GEO-IT to confirm who supports the shared line in building June 3rd - email to Andrew.B.Colley@unilever.com asking how this would be funded but he was not sure June 1st: 19/05: Pending response from Unilever how they are going to proceed with the in-house cabling. Support required for Andrew.04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Order Accepted | Circuit Provider |  | UCORPBIH002 | BOSNIA_AND_HERZEGOVINE |  |  |  |  | FRA ANDJELA ZVIZDOVICA 1 / 19B | [8 empty] | 20Mbps | 10 |  |  | 2020 | Mar | [13 empty] | 19th floor (Object B). Server Room | 154.14.46.12030 Network - 154.14.46.120 First usable - 154.14.46.121 Last usable - 154.14.46.122 Broadcast - 154.14.46.123 Subnet Mask - 255.255.255.252 | [5 empty] | HT-Hrvatske telekom. d.d. | [5 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar | [7 empty] | Yes
CKT-I-02-UCORPBIH002-ORA-1 |  | 2 |  |  | Europe | BOSNIA |  |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  |  | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-10 | Amber | 2020-04-05 | 2020-07-24 | Red | 2020-04-17 | 2021-01-01 | Red | 21/08 Still not in tracker UL 19/07: Not in Unilever's tracker 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPBIH002 | BOSNIA_AND_HERZEGOVINE | [14 empty] | 10 |  |  | 2020 | Mar | [26 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar
CKT-I-01-BG-DEN99-9999-GTT-1 | I0120366GTT1 | 2 | Device needs replacement |  | Europe | BULGARIA | Denny Ice cream Factory |  | un-uen-bgrvel1-rtr001 | un-uen-bgrvel1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | N/A | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-06-30 | Complete | 2020-04-17 | 2020-07-10 | Complete | 10/07 - Migration completed successfully 07/07: Migration date confrimed - techincal discussion taking place today 02/07 - Gergana confirmed missing IP details as required by Cisco for the migration on 10th July 02/07 - Martin confirmed to Eloise that he should be able to confirm SFP have been supplied on Tuesday 07/07 01/07 - Martin Kostadinov confirmed 10:00 am local on 10th July should be possible - Eloise to setup techincal call first 30/06 - LCON mailed to see if possible to migrate on 10th July 30/06 - Circuit testing confirmed successful 29/06 - Gergana confirmed testing for 30/06 at 10:00 local time 26/06 - Martin confirmed have admin account and laptop with installed Team Viewer, iPerf and AnyDesk. We can arrange testing for 30th June, 10:00 local time. 25/06 - email between Maria GTT and Kostadinov, Martin <Martin.Kostadinov@unilever.com> - try to arrange tesitng resources for 30th June 23/06 - email sent by Maria to Kostadinov, Martin <Martin.Kostadinov@unilever.com> to arrange testing 23/06 - GTT Start of Service Email received - Eloise and Aga emailed for awareness 17/06 - Martin.Kostadinov@unilever.com confirmed call by Telnet & should install link Friday, 19th June 17/06 - Eloise to check with Cisco Technical lead to ensure that we are able to support all traffic via DMVPN as we will be ceasing P2P link after Internet is deployed. 11/06 - Circuit ordered 29th April to arrive 29th July - Possible migration August (depending on ice cream season) June 1st: 20/05: The order was placed with the vendor. 10/06: Circuit still not appearing in GTT tracker 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | BG-DEN99-9999 | BULGARIA_DENNY_ICE_CREAM_FACTORY | [13 empty] | 6Mbps | 10 |  |  | 2020 | Mar | [7 empty] | 10:00am to 17:00pm | [6 empty] | 154.14.114.132/30 Network - 154.14.114.132 First usable - 154.14.114.133 Last usable - 154.14.114.134 Broadcast - 154.14.114.135 Subnet Mask - 255.255.255.252 154.14.112.32/29 Network - 154.14.112.32 First usable - 154.14.112.33 Last usable - 154.14.112.38 Broadcast - 154.14.112.39 Subnet Mask - 255.255.255.248 | 154.14.114.133 | 154.14.114.134 | 154.14.112.32/29 | [8 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar | [7 empty] | No |  |  | Window Date agreed - End user Comms sent |  | 07;00 to 13:00pm | 10:00am to 17:00pm | 95729 | CRQ000000688980 | Approved |  | CRQ000000688527 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-UCORPBGR052-VOD-1 | I011434VOD1 | 2 |  |  | Europe | BULGARIA | BULGARIA_SOFIA_BUSINESS_PARK | 2019_69 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Vodafone Global | Vod |  | UNIPX-IPQM-00023 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-09-30 | Red | 2020-07-31 | 2020-11-23 | Red | 16/07 - testing requested for 10 a.m on Monday 20th Experio believe to be handing over the circuit to Vodafone before 25th July 15/07 - Dusan confirmed delivered on 13th July - pending testing which is being planned with LCON for 20th July 10/07 - not in Vodafone tracker - circuit order not confirmed - Vodafone to confirm why not in tracker as order marked complete 09/07 - Circuit expected to be delivered by 14th July - LCON is on leave after that date 11/06 - Circuit not ordered - check with supplier 11/06 - Circuit not ordered - check with supplier 10/06: Circuit still not appearing in Vodafone tracker 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPBGR052 | BULGARIA_SOFIA_BUSINESS_PARK |  |  |  |  | Unilever Bulgaria EOOD Sofia 1766, Mladost 4 district Business Park Sofia, building 4, floor 5 | [9 empty] | 40 |  |  | 2020 | Mar | [26 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar
CKT-I-02-UCORPBGR052-GTT-1 | I021434GTT1 | 2 | Yes |  | Europe | BULGARIA | BULGARIA_SOFIA_BUSINESS_PARK |  | un-uen-bgrsof1-vpn002 | un-uen-bgrsof1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001832551 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-06-08 | Complete | 2020-04-17 | 2020-07-27 | Complete | 27/07: Migration successful 15/07 - migrate on 27th July confirmed - ES requested from Dimitar a start time and offered to setup techical walkthrough on Friday if required 14/07 - waiting for second circuit migraiton at same date 07/07: Ready for circuit to be migrated. Working with local team and Cisco to secure migration date 21/06 - email send confirming circuit acceptance based on test evidence and next stage to plan migration. 09/06: The vendor provided a document stating that an equipment was installed. Pending confirmation if the line can be tested or is in the process of being deployed. 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | UCORPBGR052 | BULGARIA_SOFIA_BUSINESS_PARK |  |  |  |  | Unilever Bulgaria EOOD Sofia 1766, Mladost 4 district Business Park Sofia, building 4, floor 5 | [8 empty] | 30Mbps | 40 |  |  | 2020 | Mar | [7 empty] | 13:00pm to 21:00 | [5 empty] | 5th floor. Server room | 154.14.50.12/30 Network - 154.14.50.12 First usable - 154.14.50.13 Last usable - 154.14.50.14 Broadcast - 154.14.50.15 Subnet Mask - 255.255.255.252 | 154.14.50.13 | 154.14.50.14 |  |  |  | Sofia Communications EAD | [5 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar |  |  | Standard site type - Dual DMVPN |  |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 10:00am to 16:00 | 13:00pm to 21:00pm | 105449 | CRQ000000694194 | Approved |  | CRQ000000686763 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-UCORPHRV066-VOD-1 | I0111216VOD1 | 2 |  |  | Europe | CROATIA | CROATIA_ZAGREB | 2019_119 | un-uen-hrvzag1-rtr001 | un-uen-hrvzag1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | Vodafone Global | Vod |  | UNIPX-IPQM-00025 | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Complete | 2020-07-19 | 2020-07-20 | Complete | 2020-07-31 | 2020-08-17 | Complete | 17/08: Migration successful 10/08: Migration unsuccessful - re-planned for 17th August FE to be confirmed 16/07 - testing requested for 10 a.m on Monday 20th Experio believe to be handing over the circuit to Vodafone before 25th July 15/07 - Dusan confirmed delivered on 13th July - pending testing which is being planned with LCON for 20th July 10/07 - not in Vodafone tracker - circuit order not confirmed - Vodafone to confirm why not in tracker as order marked complete 09/07 - Circuit expected to be delivered by 14th July - LCON is on leave after that date 11/06 - Circuit not ordered - check with supplier 15/06: Not showing in tracker yet 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | UCORPHRV066 | CROATIA_ZAGREB |  |  |  |  | SAVSKA Strojarska cesta 20, 13th floor | [9 empty] | 30 |  |  | 2020 | Mar | [14 empty] | Static 89.201.166.68 255.255.255.252 Network Address Static 89.201.166.69 255.255.255.252 LAN IP / Default gateway Static 89.201.166.70 255.255.255.252 IP free to use Static 89.201.166.71 255.255.255.252 Broadcast Address Static 85.114.52.72 255.255.255.252 Additional /29 Routed to 89.201.166.70 | 89.201.166.69 | 89.201.166.70 | [9 empty] | Fat Nela | Fat Nela | Fat Nela |  |  | Standard site type - Hybrid (MPLS + DMVPN) |  |  | No |  |  | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 08:00:00 to 16:00:00 | 10:00 to 18:00 | 111848 (OLD) 113766 (NEW) | CRQ000000700613 | Approved |  | CRQ000000701026 | Completed | Completed |  |  |  | Circuit Migrated
CKT-I-02-UCORPHRV066-GTT-1 | I0211216GTT1 | 2 | Yes |  | Europe | CROATIA | CROATIA_ZAGREB |  | un-uen-hrvzag1-vpn001 | un-uen-hrvzag1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001821795 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-06 | Complete | 2020-04-17 | 2020-08-10 | Complete | 4-Feb: Action is Transfer + Transform. | Complete | Circuit Migrated | Circuit Provider |  | UCORPHRV066 | CROATIA_ZAGREB | [13 empty] | 2048 (E1)Kbps MPLS1 MPLS | 100 |  |  | 2020 | Mar | [26 empty] | Fat Nela | Fat Nela | Fat Nela |  |  | Standard site type - Hybrid (MPLS + DMVPN) |  |  | No |  | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 09:30:00 to 19:30:00 | 11:30 to 21:30 | 111849 | CRQ000000699119 | Approved | [7 empty] | Circuit Migrated - First Time right |  |  |  | 2020-04-01
CKT-I-01-UCORPCYP067-ORA-1 |  | 2 |  |  | Europe | CYPRUS |  |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  |  | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-10 | Amber | 2020-04-05 | 2020-07-24 | Red | 2020-04-17 | 2021-01-01 | Red | 21/08: Not in Unilever tracker 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPCYP067 | CYPRUS_NICOSIA 195 C OLD ROAD_HEAD_OFFICE | [14 empty] | 40 |  |  | 2020 | Mar | [26 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar
CKT-I-02-UCORPCYP067-ORA-1 |  | 2 |  |  | Europe | CYPRUS |  |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  |  | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-10 | Amber | 2020-04-05 | 2020-07-24 | Red | 2020-04-17 | 2021-01-01 | Red | 21/08: Not in UL tracker 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPCYP067 | CYPRUS_NICOSIA 195 C OLD ROAD_HEAD_OFFICE | [14 empty] | 40 |  |  | 2020 | Mar | [26 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar
CKT-I-01-UCORPCYP068-VOD-1 |  | 2 |  |  | Europe | CYPRUS |  |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | Vodafone Global | Vod |  |  | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-05-07 | Red | 2020-04-17 | 2020-12-31 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPCYP068 | CYPRUS_NICOSIA_2 MARCOU DRACOU STREET_UNILEVER PMT LTD | [14 empty] | 20 |  |  | 2020 | Mar | [26 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar
CKT-I-01-UCORPCZE067-CTL-1 | I0110664CTL1 | 2 | No access on device |  | Europe | CZECH REPUBLIC | CZECH_REPUBLIC_PRAGUE | 2019_124 | un-uen-czepra1-rtr001 | un-uen-czepra1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2007089291UNI - Access FRO2007089292DIR - Service | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Complete | 2020-07-19 | 2020-06-29 | Complete | 2020-07-31 | 2020-07-23 | Complete | 23/07: Migration successful 17/07 - Field engineer needed for migration on 23/07 - 09:00 - 16:00 16/07 - Migration confirmed as 23/07 - LCON Michal.Andrle@unilever.com +420 606 689 449 15/07 - migration pending moved to 23/07 - Vit to confirm 14/07 - Dusan checking with Vit is 22/07 is ok for migrations? 13/07 - Testing successful 09/07 - Testing confirmed for Monday 13th June 11am to 13:00 30/06 - emails sent to GTT and Eloise to follow up response from Novak, Vitezslav <Vitezslav.Novak@unilever.com> 29/06 - Eloise emailed to see if we can arrange testing of both circuits at the same time 29/06 - CenturyLink confirmed circuit delivered 11/06 - Circuit ordered - should arrive 20th July - migration August June 2nd: Queries addressed to Eloise/Cisco related to technical matter June 1st: Provider 14/07 - Dusan checking with Vit is 22/07 is ok for migrationsdelivery date not informed 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | UCORPCZE067 | CZECH_REPUBLIC_PRAGUE |  |  |  |  | ROHANSKE NABREZI UNILEVER ČR, spol. s r. o. Voctářova 2497/18 , Palmovka Open Park IV 180 00 | [9 empty] | 100 |  |  | 2020 | Mar | [7 empty] | 09:00am to 15:00pm | [6 empty] | WAN: 195.122.181.164/30 CTL: 195.122.181.165 UNI: 195.122.181.166 | 195.122.181.165 | 195.122.181.166 | [9 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar | [10 empty] | Window Date agreed - End user Comms sent |  | 07:00am to 13:00pm | 09:00am to 15:00pm | 104553 | CRQ000000693883 | Approved |  | CRQ000000693516 | Completed | Completed
CKT-I-02-UCORPCZE067-GTT-1 | I0210664GTT1 | 2 | No access on device |  | Europe | CZECH REPUBLIC | CZECH_REPUBLIC_PRAGUE | 2019_123 | un-uen-czepra1-vpn001 | un-uen-czepra1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001830183 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-06-29 | Complete | 2020-04-17 | 2020-07-23 | Complete | 23/07: Migration successful 17/07 - Field engineer needed for migration on 23/07 - 09:00 - 16:00 16/07 - Migration confirmed as 23/07 - LCON Michal.Andrle@unilever.com +420 606 689 449 15/07 - migration pending moved to 23/07 - Vit to confirm 14/07 - Dusan checking with Vit is 22/07 is ok for migrations? 13/07 - Tesitng successful 09/07 - Testing confirmed for Monday 13th June 13:00 to 15:00 07/07 - We’re waiting for Deepak to approve those costs for field engineer for that site and two more and once he do that we’ll arrange testing. Maybe 13th July is better as a date 07/07 - Circuit still needs to be tested 02/07 - Gergana confirmed "We’ll request resources and we’ll let you inform you once they are confirmed." 01/07 - requested GTT to provide field engineer to support testing 30/06 - emails sent to GTT and Eloise to follow up response from Novak, Vitezslav <Vitezslav.Novak@unilever.com> 29/06 - Eloise emailed to see if we can arrange testing of both circuits at the same time 15/06 - GTT confirmed circuit delivered - to be tested 05/06 - GTT Confirmed Circuit Delivery scheduled for 11th June - pending GTT confirmation that complete 02/06 - Installation of antenna on the Prague HO rooftop has been approved by the landlord June 1st: 27/05: The Vendor is ready for installation. They are only waiting for the consent of the building owner. Vendor has already urged it several times and they have also solved it with the UNILEVER, but so far they have not been able to obtain approval. 28/04 Vendor needs to make site survey first. The site is closed at the moment. | Complete | Circuit Migrated | Circuit Provider |  | UCORPCZE067 | CZECH_REPUBLIC_PRAGUE |  |  |  |  | ROHANSKE NABREZI UNILEVER ČR, spol. s r. o. Voctářova 2497/18 , Palmovka Open Park IV 180 00 | [9 empty] | 100 |  |  | 2020 | Mar | [7 empty] | 09:00am to 15:00pm | [5 empty] | 3rd floor . Server Room | 154.14.116.120/30 Network - 154.14.116.120 First usable - 154.14.116.121 Last usable - 154.14.116.122 Broadcast - 154.14.116.123 Subnet Mask - 255.255.255.252 154.14.126.96/29 Network - 154.14.126.96 First usable - 154.14.126.97 Last usable - 154.14.126.102 Broadcast - 154.14.126.103 Subnet Mask - 255.255.255.248 | 154.14.116.121 | 154.14.116.122 | 154.14.126.96/29 |  |  | Ceske Radiokomunikace a.s. | [5 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar | [10 empty] | Window Date agreed - End user Comms sent |  | 07:00am to 13:00pm | 09:00am to 15:00pm |  | CRQ000000693883 | Approved |  | CRQ000000693605 | Completed | Completed
CKT-I-02-EE-TLL03-0001-UNL-1 | I0211190UNL1 | 2 | Device needs replacement |  | Europe | ESTONIA | Talinn |  | un-uen-esttal1-vpn002 | un-uen-esttal1-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  |  | 2020-02-07 | 2020-01-20 | Complete | 2020-02-12 | 2020-02-17 | Complete | 2020-04-12 | 2020-02-17 | Complete | 2020-04-24 | 2020-02-26 | Complete | 03/03 additional change window required to Enable cross-over interface on un-uen-esttal1-vpn002 after SFP installation for full site redundancy - scheduled for 30.03. 26/02 Migration completed 20/02 Migration scheduled for 26/02. Pending Algosec to be implemented - this is due on Monday 24 Feb | Complete | Circuit Migrated |  |  | EE-TLL03-0001 | ESTONIA_TALINN |  |  |  |  | Sopruse pst 145 | Tallinn | 145 13417 |  | Mattias Igalaan | mattias.igalaan@greip.ee | +37256257440 | Mykolas Norvaisas | Mykolas.Norvaisas@unilever.com | 8Mbps | 40 | 59.4153 | 24.7108 | 2020 | Feb | [7 empty] | 1100 - 1700 UTC | NA | NA | NA |  |  |  | IP 194.204.29.17 Mask 255.255.255.252 GW 194.204.29.18 DNS 194.204.0.18 DNS 194.204.0.208 | 194.204.29.18 | 194.204.29.17 | 194.204.29.16/30 | [8 empty] | Fat Nela | Fat Nela | Fat Nela | 2020-02-27 |  | Standard site type - Dual DMVPN | Complete | NO | No | Yes | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 1100 - 1700 | 1300 - 1900 | 39202 | CRQ000000643264 | Approved | 41159 | CRQ000000640847 | Completed | Completed | Tested-Pass |  |  | Circuit Migrated - First Time right | NA | NA | NA |  | 2020-02-01
CKT-I-01-UCORPFRA082-ORA-1 | I012698ORA1 | 2 |  |  | Europe | FRANCE | FRANCE_CHEVIGNY_SAINT_SAUVEUR_AMORA_FACTORY | 2019_153 | un-uen-frache1-vpn001 | un-uen-frache1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | GO0AQ9Y652 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-06-05 | Red | 2020-07-19 | 2020-07-15 | Green | 2020-07-31 | 2020-09-15 | Red | 29/08: testing was unsuccessful on 28/08. We need Orange engineer to visit or advise what could be wrong. Site has also asked for us to migrate links one at a time. Re-planned for 7th September 21/08: Migration planned for 31st August./ Link still needs to be tested. 17/07 - Circuit delivery finished on 13/07 - testing pending ACTION - Circuit delivery possibly DONE need to check and follow up if can arrnage testing 15/07 - follow up with Ruth on /30 range - confirmation sought form Matt Barber and David Collins that provided IP ranges are ok 15/07 - email from Ruth confirmed circuit delivery done but need to check IP range 14/07 - RIPE form sent to Dave Collins and Matt Barber (Cisco) for comment 07/07 - IP RIPE Form sent through - passed to Cisco and Deepak for comment 06/07 - Bastien Meyer confirmed 13 of July, at 10 oclock To Orange business services 30/06 - Pascal forwarded to LCON Hildebrand, Luc <Luc.Hildebrand@unilever.com> for reply 30/06 - email from samuel.minchilli.ext@orange.com to MEYER, BASTIEN <BASTIEN.MEYER@unilever.com> forwarded to Pascal Busseau for review and comment 22/06 - Orange Tracker week 25 - 17-Jun-20: Ordering in progress 09/06 - Cisco have circuit delivery as 20-07-20 with migration in mid August June 2nd: 27-May-20: Order in Approval (Customer signature) 01-Jul-20: Carrier has scheduled the installation for 13th July but is still pending confirmation of the date from the LCON (update from Orange tracker) 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPFRA082 | FRANCE_CHEVIGNY_SAINT_SAUVEUR_AMORA_FACTORY |  |  |  |  | Amora Maille Rue des Serruriers 21800 Chevigny Saint Sauveur | [8 empty] | 10Mbps | 40 |  |  | 2020 | Mar | [14 empty] | Réseau LAN : 192.168.1.0/24 IP routeur Orange : 192.168.1.254/24 Adresse IP Publique : 212.234.226.142 DHCP : Non Serveurs DNS Orange : 194.2.0.20 / 194.2.0.50 | N/A | 212.234.226.142 |  |  |  | ORANGE BUSINESS SERVICES | [5 empty] | Arijon Alija | Arijon Alija | Arijon Alija |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  |  |  |  | No | [9 empty] | CRQ000000704480 | Completed | Completed
CKT-I-02-UCORPFRA082-GTT-1 | I022698GTT1 | 2 |  |  | Europe | FRANCE | FRANCE_CHEVIGNY_SAINT_SAUVEUR_AMORA_FACTORY | 2019_152 | un-uen-frache1-rtr001 | un-uen-frache1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001928102 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-07-24 | Complete | 2020-07-17 | 2020-08-31 | Complete | 31/08: Migration successful. 21/08: Circuit tested and ready for migration on 31st August 17/07 - Maria confirmed still no update from vendor and she chased them earlier today 15/07: Vendor informed that the order is in commercial validation. Vendor chased for the handover document. 15/07 - updated requested from GTT - GTT following up with supplier 24/06 - expected delivery date 13th July 09/06 - Cisco have reference CKT-I-02-UCORPFRA082-GTT-1 June 1st: 18/05: The order was palced with the vendor. 04/05 Unilever to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Unilever SNT |  | UCORPFRA082 | FRANCE_CHEVIGNY_SAINT_SAUVEUR_AMORA_FACTORY |  |  |  |  | Amora Maille Rue des Serruriers 21800 Chevigny Saint Sauveur | [8 empty] | 8Mbps | 40 |  |  | 2020 | Apr | [14 empty] | 154.14.104.112/29 Network - 154.14.104.112 First usable - 154.14.104.113 Last usable - 154.14.104.118 Broadcast - 154.14.104.119 Subnet Mask - 255.255.255.248 154.14.104.92/30 Network - 154.14.104.92 First usable - 154.14.104.93 Last usable - 154.14.104.94 Broadcast - 154.14.104.95 Subnet Mask - 255.255.255.252 | 154.14.104.93 | 154.14.104.94 | [9 empty] | Arijon Alija | Arijon Alija | Arijon Alija |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  |  |  |  | No | Assessment Complete MOP created & config created Partner MOP created | Window Date agreed - End user Comms sent |  | 07:00 to 15:00 | 09:00 to 13:00 | 119409 | CRQ000000705022 | Approved |  | CRQ000000704564 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-NONULFRA180-BT-1 | I011680BT1 | 2 |  |  | Europe | FRANCE | FRANCE_DUPPIGHEIM_FACTORY | 2019_155 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-10-17 | Red | 2020-07-31 | 2020-11-16 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | NONULFRA180 | FRANCE_DUPPIGHEIM_FACTORY |  |  |  |  | Besfoods France Industries Usines Knorr 5 Avenue Jean Precheur 67120 DUPPIGHEIM | [9 empty] | 40 |  |  | 2020 | Apr | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-02-NONULFRA180-GTT-1 |  | 2 | Yes |  | Europe | FRANCE |  |  | un-uen-fradup-rtr001 |  | Eloise Shepheard | SNT |  | GTT | GTT |  | GTT/001831581 | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-06-30 | Red | 2020-04-17 | 2020-04-15 | Green | 4-Feb: Action is Transfer + Transform. | Pink | Circuit not ordered |  | Check dates | NONULFRA180 | FRANCE_DUPPIGHEIM_FACTORY | [13 empty] | 6Mbps | 100 |  |  | 2020 | Mar | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija | [14 empty] | 97834
CKT-I-01-NONULFRA171-CTL-1 |  | 2 | Device needs replacement |  | Europe | FRANCE | FRANCE_FAUVERNEY_FM_LOGISTIQUE_3RDPARTY |  | un-uen-frfau1 | un-uen-frfau1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2021-01-01 | Red | 21/08 : Not in UL tracker 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | NONULFRA171 | FRANCE_FAUVERNEY_FM_LOGISTIQUE_3RDPARTY |  |  |  |  | FM Logistic Fauverney-ZONE DACTIVITÉ LA BOULOUZE Industrielle de la Plaine de L`Ain | [8 empty] | 1280Kbps | 10 |  |  | 2020 | Mar | [26 empty] | Eloise Shepheard | Eloise Shepheard | Eloise Shepheard |  |  | Complex site type - requires redesign |  |  | No | No | No | No
CKT-I-02-NONULFRA171-TIS-1 |  | 2 |  |  | Europe | FRANCE | FRANCE_FAUVERNEY_FM_LOGISTIQUE_3RDPARTY | 2019_157 |  |  | Eloise Shepheard | WAN Circuit Migration |  | TI Sparkle | TIS |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-08-31 | Red | 2020-07-31 | 2021-01-01 | Red | 20/08 : Not in UL tracker 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | NONULFRA171 | FRANCE_FAUVERNEY_FM_LOGISTIQUE_3RDPARTY |  |  |  |  | FM Logistic Fauverney-ZONE DACTIVITÉ LA BOULOUZE Industrielle de la Plaine de L`Ain | [9 empty] | 10 |  |  | 2020 | Apr | [26 empty] | Eloise Shepheard | Eloise Shepheard | Eloise Shepheard
CKT-I-01-NONULFRA179-CTL-1 | I0111041CTL1 | 2 | Yes |  | Europe | FRANCE | FRANCE_LA_REUNION_SALES_OFFICE |  | un-uen-fralar-pio001 |  | Eloise Shepheard | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2021-01-01 | Red | No updates in UL tracker 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | NONULFRA179 | FRANCE_LA_REUNION_SALES_OFFICE |  |  |  |  | Distribution Centre/La Reunion UNITRANS,1 RUE PAUL VERLAINE ZONE INDUSTRIELLE N 2 | [8 empty] | 8Mbps | 10 |  |  | 2020 | Mar | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-02-NONULFRA179-TIS-1 | I0211041TIS1 | 2 |  |  | Europe | FRANCE | FRANCE_LA_REUNION_SALES_OFFICE | 2019_159 |  |  | Eloise Shepheard | WAN Circuit Migration |  | TI Sparkle | TIS |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-08-31 | Red | 2020-07-31 | 2021-01-01 | Red | No updates in UL tracker 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | NONULFRA179 | FRANCE_LA_REUNION_SALES_OFFICE |  |  |  |  | Distribution Centre/La Reunion UNITRANS,1 RUE PAUL VERLAINE ZONE INDUSTRIELLE N 2 | [9 empty] | 10 |  |  | 2020 | Apr | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-01-UCORPFRA031-GTT-1 | I011443GTT1 | 2 | Yes |  | Europe | FRANCE | FRANCE_LAGNIEU_SAINT_VULBAS_FACTORY | 2019_161 | un-uen-fralag1-rtr001 | un-uen-fralag1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001834042 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-08-18 | Complete | 2020-04-17 | 2020-08-27 | Complete | 27/08: Migration successful 20/08: Migration planned for 27th August at 2pm start. Field engineer required. Circuit still to be tested. GTT has organised for 26th 15/07 - vendor carrying out work on 21/07 10/07 - No delivery date provided 09/07 - site confirmed last mile provider has arranged visit for 21/07/2020 à 08:00AM to 1:00PM 07/07 - Carlo confirmed we’ll inform our vendor to proceed straight away. 06/07 - Proposed additional €809 construction charge approved June 1st: 12/05: A new site visit date was scheduled for 28th May with the LCON. 02/07: The Vendor sent detailed spreadsheet with the excessive costs. Unilever needs to approve 808,94 €. (From GTT tracker) 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | UCORPFRA031 | FRANCE_LAGNIEU_SAINT_VULBAS_FACTORY |  |  |  |  | Unilever HPC SI, Parc industriel de la plaine de l’Ain 01150 Saint Vulbas | [8 empty] | 4Mbps | 40 |  |  | 2020 | Mar | [13 empty] | Bat. Administrative / Ground floor. Bat computer room. Administrative | 154.14.59.172/30 Network - 154.14.59.172 First usable - 154.14.59.173 Last usable - 154.14.59.174 Broadcast - 154.14.59.175 Subnet Mask - 255.255.255.252 | 154.14.59.173 | 154.14.59.174 |  |  |  | Phibee | [5 empty] | Fat Nela | Fat Nela | Fat Nela |  |  | Standard site type - Hybrid (MPLS + IEN) | Complete |  | No | No | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 07:00:00 to 13:00:00 | 09:00 to 15:00 | 117614 | CRQ000000703998 | Approved |  | CRQ000000703965 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-02-UCORPFRA031-BT-1 | I021443BT1 | 2 |  |  | Europe | FRANCE | FRANCE_LAGNIEU_SAINT_VULBAS_FACTORY | 2019_160 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-10-17 | Red | 2020-07-31 | 2020-11-16 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | UCORPFRA031 | FRANCE_LAGNIEU_SAINT_VULBAS_FACTORY |  |  |  |  | Unilever HPC SI, Parc industriel de la plaine de l’Ain 01150 Saint Vulbas | [9 empty] | 40 |  |  | 2020 | Apr | [26 empty] | Fat Nela | Fat Nela | Fat Nela
CKT-I-01-UCORPFRA047-GTT-1 | I012700GTT1 | 2 | Yes |  | Europe | FRANCE | FRANCE_LE MEUX_RUE DU ROI DU BUISSON_LE MEUX | 2019_162 | un-uen-fracom1-rtr001 | un-uen-fracom1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001834616 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-13 | Complete | 2020-04-17 | 2020-08-26 | Complete | 26/08: Migration successful 14/08: Migration planned for 26th August at 13:30pm start LT - FE required 13/07 - Circuit delivery complete - pending testing 10/07 - Still not delivered - was planned 30/06 - follow up with GTT 02/07 - Pascal confirms appointment has been arranged 02/07 - Pascal Busseau emailed to help arrange site access for engineer to install fibre 24/076 - expected to be handed over 27th June June 1st: 18/05: Vendor chased for updates. 01/07: The Vendor expects to handover the service at the end of week 27. The subcontractor needs a final on site visit to install NTU. LCON is not reachable, a mail has been sent. Waiting for LCON to respond (From GTT Tracker) 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | UCORPFRA047 | FRANCE_LE MEUX_RUE DU ROI DU BUISSON_LE MEUX |  |  |  |  | Unilever France HPC Industries ZI- Rue du Buisson du Roi 60880 LE MEUX | [8 empty] | 15Mbps | 40 |  |  | 2020 | Mar | [13 empty] | Bat. Administrative / 1st floor. Computer room | 154.14.52.20/30 Network - 154.14.52.20 First usable - 154.14.52.21 Last usable - 154.14.52.22 Broadcast - 154.14.52.23 Subnet Mask - 255.255.255.252 | 154.14.52.21 | 154.14.52.22 |  |  |  | Phibee | [5 empty] | Fat Nela | Fat Nela | Fat Nela |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  | No | No |  | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 11:30:00 to 17:30:00 | 13:30 to 19:30 | 117488 | CRQ000000704508 | Approved |  | CRQ000000702849 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-02-UCORPFRA047-BT-1 | I022700BT1 | 2 |  |  | Europe | FRANCE | FRANCE_LE MEUX_RUE DU ROI DU BUISSON_LE MEUX | 2019_163 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-10-17 | Red | 2020-07-31 | 2020-11-16 | Red | CKT-I-02-UCORPFRA047-TIS-1 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | UCORPFRA047 | FRANCE_LE MEUX_RUE DU ROI DU BUISSON_LE MEUX |  |  |  |  | Unilever France HPC Industries ZI- Rue du Buisson du Roi 60880 LE MEUX | [9 empty] | 40 |  |  | 2020 | Apr | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-01-UCORPFRA070-GTT-1 | I011670GTT1 | 2 | Yes |  | Europe | FRANCE | FRANCE_SAINT_DIZIER_FACTORY | 2019_167 | un-uen-fradiz1-rtr001 | un-uen-fradiz1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001834624 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-06-15 | Complete | 2020-04-17 | 2020-07-09 | Complete | 09/07: Migration was successful 28/06: Circuit was successfully tested on 25th June. Migration needs to be planned within July. 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | UCORPFRA070 | FRANCE_SAINT_DIZIER_FACTORY |  |  |  |  | Z.I. des 3 Fontaines Rue Bonnor 52111 SAINT DIZIER Cedex | [8 empty] | 6Mbps | 40 |  |  | 2020 | Mar | [7 empty] | 09:00 to 15:00 local time | [5 empty] | Bat. Administrative / 1st floor. Server room - PAER00 computer rack | 154.14.52.16/30 Network - 154.14.52.16 First usable - 154.14.52.17 Last usable - 154.14.52.18 Broadcast - 154.14.52.19 Subnet Mask - 255.255.255.252 | 154.14.52.17 | 154.14.52.18 |  |  |  | Phibee | [5 empty] | Fat Nela | Fat Nela | Fat Nela |  |  | Standard site type - Hybrid (MPLS + IEN) |  |  | No | No | No | No | Assessment Complete CMSP ticket raised MOP created & config created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms not sent |  | 07:00 to 13:00 | 09:00 to 15:00 | 91317 | CRQ000000688734 | Approved |  | CRQ000000683098 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-02-UCORPFRA070-BT-1 | I021670BT1 | 2 |  |  | Europe | FRANCE | FRANCE_SAINT_DIZIER_FACTORY | 2019_166 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-11-16 | Red | CKT-I-02-UCORPFRA070-TIS-1 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | UCORPFRA070 | FRANCE_SAINT_DIZIER_FACTORY |  |  |  |  | Z.I. des 3 Fontaines Rue Bonnor 52111 SAINT DIZIER Cedex | [9 empty] | 40 |  |  | 2020 | Apr | [26 empty] | Fat Nela | Fat Nela | Fat Nela
CKT-I-01-UCORPDEU022-GTT-1 | I011324GTT1 | 2 | Yes |  | Europe | GERMANY | GERMANY_ HEPPENHEIM | 2019_169 | un-uen-deuhep1-vpn001 | un-uen-deuhep1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001832541 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-21 | Complete | 2020-04-17 | 2020-08-29 | Complete | 29/08: Migration successful 20/08: Migration confirmed for 29th August at 07:30am start. Field engineer required. 15/07 - vendor plannned installation for 21/07 10/07 - On Track 20/05: The order is on track. 13/05: The order is progressing, construction works are still not completed. 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | UCORPDEU022 | GERMANY_ HEPPENHEIM |  |  |  |  | Unilever Deutschland Produktions GmbH & Co. OHG, Langnesestraße 1, D-64646 Heppenheim | [8 empty] | 40Mbps | 100 |  |  | 2020 | Mar | [13 empty] | DTAG: Administration Building, 1. Floor. Computer Room | 154.14.63.60/30 Network - 154.14.63.60 First usable - 154.14.63.61 Last usable - 154.14.63.62 Broadcast - 154.14.63.63 Subnet Mask - 255.255.255.252 | 154.14.63.61 | 154.14.63.62 |  |  |  | 1&1 Versatel Deutschland GmbH | [5 empty] | Lalhmunsanga Fanai | Lalhmunsanga Fanai | Lalhmunsanga Fanai |  |  | Standard site type - Dual DMVPN | Complete |  | No |  | No |  | Assessment Complete CMSP ticket raised MOP created & config created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 05:30 to 11:30 | 08:30 to 14:30 | 118264 | CRQ000000704535 | Approved |  | CRQ000000703288 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-02-UCORPDEU022-CTL-1 | I021324CTL1 | 2 | Yes |  | Europe | GERMANY | GERMANY_ HEPPENHEIM | 2019_168 | un-uen-deuhep1-vpn002 |  | Eloise Shepheard | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2007083028UNI - Access FRO2007083035DIR - Service | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-11-30 | Red | 2020-07-31 | 2020-10-01 | Red | 18/08: Delivery for this circuit was scheduled on 15/08. This is not going to happen. Prior to delivery they realised initially proposed solution (COLT with a DTAG last mile) provided diversity issues with Unilever’s alternate provider, and we were asked to find an alternate solution. Solution will be presented to Deepak end of this week for approval. We are at start of process again (90 days). 16/07 - LCON Hagan Schubert confirmed For next week I got an request for access by Telnet GmbH. But they didn’t send me an exact appointment yet. 15/07 - Thomas Dehmel following up with site to see if DTAG were on site last week to install last mile connection 10/07 - Pending delivery 08/07 - FOC (Firm Order Committment) date of 23/07 01/07 - looking for overall delivery mid July 25/06 - email sent in response to mail from site about delays - confirmed this is being expedited at every opportunity within SNT 24/06 - Colt are not able to set a date for work on site as their supplier DTAG as last mile provider are delayed 18/06 - Graham Yates has confirmed that he has instructed Colt to work on this basis 18/06 - Graham Yates has said he will take it up with Colt and site contact Hagah Schubert has requested 2 weeks notice 17/06 - contacted site who confimred site access is now possible - informed Graham Yates - CenturyLink June 1st: Not presented on Providers tracker 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Ordered | Circuit Provider | Check dates | UCORPDEU022 | GERMANY_ HEPPENHEIM |  |  |  |  | Unilever Deutschland Produktions GmbH & Co. OHG, Langnesestraße 1, D-64646 Heppenheim | [8 empty] | 40Mbps | 100 |  |  | 2020 | Mar | [26 empty] | Damian Dabros | Damian Dabros | Damian Dabros | [7 empty] | No
CKT-I-01-UCORPDEU004-BT-1 | I011271BT1 | 2 |  |  | Europe | GERMANY | GERMANY_BUXTEHUDE_25 ALTER POSTWEG_BUXTEHUDE | 2019_172 | un-uen-deubux1-rtr001 | un-uen-deubux1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-08 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPDEU004 | GERMANY_BUXTEHUDE_25 ALTER POSTWEG_BUXTEHUDE |  |  |  |  | ALTER POSTWEG | [8 empty] | 20Mbps | 100 |  |  | 2020 | Mar | [26 empty] | Damian Dabros | Damian Dabros | Damian Dabros | [7 empty] | No
CKT-I-02-UCORPDEU004-GTT-1 |  | 2 |  | High | Europe | GERMANY | [5 empty] | SNT |  | GTT | GTT |  | GTT/001817213 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPDEU004 | GERMANY_BUXTEHUDE_25 ALTER POSTWEG_BUXTEHUDE | [14 empty] | 100 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Damian Dabros | Damian Dabros | Damian Dabros | [14 empty] | 97834 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-UCORPDEU066-GTT-1 | I0111021GTT1 | 2 | Yes |  | Europe | GERMANY | GERMANY_ESSEN_GREVENBROICH | 2019_174 | un-uen-deuess1-rtr001 |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001833708 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-11-30 | Red | 2020-04-17 | 2020-11-30 | Red | 15/07 - extensive civils - GTT to chasing vendor for update as pushed out to 11th November 10/07 - No Delivey Date - site survey taken place 17/06 Maria Hristova <Maria.Hristova@gtt.net> contacted for new estimated ciruit delivery date 09/06: GTT TRACKER - Appointment for site visit was scheduled for 24th June 2020 at 9.00 h CET. June 1st: 19/05: Pending a new site visit to be scheduled - COVID 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Order Accepted | Circuit Provider | Check dates | UCORPDEU066 | GERMANY_ESSEN_GREVENBROICH |  |  |  |  | Unilever Deutschland GmbH Schürmannstr. 16 | [8 empty] | 2Mbps | 10 |  |  | 2020 | Mar | [13 empty] | 1st Floor . IT Room | 154.14.63.56/30 Network - 154.14.63.56 First usable - 154.14.63.57 Last usable - 154.14.63.58 Broadcast - 154.14.63.59 Subnet Mask - 255.255.255.252 | [5 empty] | 1&1 Versatel Deutschland GmbH | [5 empty] | Damian Dabros | Damian Dabros | Damian Dabros | [7 empty] | No
CKT-I-02-DE-MHG01-0001-CTL-1 | I021360CTL1 | 2 |  |  | Europe | GERMANY | MANNHEIM_RHENANIASTRASSE |  | un-uen-deuman1-rtr001 | un-uen-deuman1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2007066151CA5 - Access FRO2007066154CAP - Port FRO2007066186DIR - Service | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-17 | Red | 2020-04-17 | 2020-09-10 | Red | 21/08: Migration to be planned fro 10th September. We will do both links at same time. CTL to confirm when final test is complete by themselves. Results next week 15/07 - Appears to be a throughput issue - UDP working but TCP/IP not working - need to investigate 10/07 - Circuit testing not successful - Results not good enough. GTT contacted Vendor to try find out what is the problem. 07/07 - Bernd Graf requested GTT testing Friday, 10th of July, from 11h CEST (German Summer time) on. Your site contact is Denis Rogausch (in cc) Please confirm a time slot. 02/07 - Gergana confirmed new upgraded line for MANNHEIM RHENANIASTRASSE to be delivered in the end of this week. After that it will be required to schedule testing. Once speed confirmed we’ll need to work with Cisco to arrange migration. During migration we’ll move the configuration and the IPs from the old circuit to the new one (the same as we did for the Circuit in Barcelona). 02/07 - original 40Mbps circuit moved to SNT Other Deliverables tab - This row will now be used to monitor the 100Mbps circuit 01/07 - post circuit installation it has been required to update from 40Mbps to 100Mbps - soft update not possible so new line being ran in and will require switchover as was carried out for Barcelona 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Order Accepted | Circuit Provider |  | DE-MHG01-0001 | GERMANY_MANNHEIM_RHENANIASTRASSE |  |  |  |  | Rhenaniastrasse 76-102 | [8 empty] | 10Mbps | 100 |  |  | 2020 | Mar | [14 empty] | WAN: 62.67.23.224/30 CTL: 62.67.23.225 UNI: 62.67.23.226 | 62.67.23.225 | 62.67.23.226 | [9 empty] | Lalhmunsanga Fanai | Lalhmunsanga Fanai | Lalhmunsanga Fanai |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | 1000Base-T with GLC-TE on ISR4k | No |  | No |  | Assessment Complete MOP created & config created Received tunnel IP or LAN IP (if required) | [8 empty] | CRQ000000706598 | Completed | Completed
CKT-I-01-UCORPDEU036-GTT-1 | I01471GTT1 | 2 | Yes |  | Europe | GERMANY | GERMANY_STAVENHAGEN_SCHULTETUSSTRASSE | 2019_179 | un-uen-deusta1-rtr001 | un-uen-deusta1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001833709 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-06-18 | Complete | 2020-04-17 | 2020-08-13 | Complete | 13/08: Migration successful 11/08: Migration re-scheduled for 13/08 10/07 - Matthias confrimed migration of 5th August at 10.00 CET and field engineer required 10/07 - proposed migration date of 05/08 when on-site team return from holiday - ES checking with LCONs 06/07 - Eloise chasing Heiden, Matthias <Matthias.Heiden@unilever.com> for migration date 02/07 - Eloise proposed migraiton date of 15/07 - Heiden, Matthias <Matthias.Heiden@unilever.com> to confirm back 25/06 - Maria confirmed testing successful 23/06 - <Matthias.Heiden@unilever.com> confirmed he will be on site to welcome the engineer at 13:00 19/06 - Testing date confirmed as Thursday 25th June - 14:00 local time 18/06 - DC sent email to Matthias.Heiden@unilever.com; Maria.Hristova@gtt.net to get testing arranged with external engineer hopefully for Thursday 25th June. 18/06 - Carlo sent email confirming that awaiging Colt to formally handover circuit to GTT before testing can be arranged 17/06 - Carlo GTT confirmed that Colt now need to formally hand over circuit to GTT who then need to test 17/06 - Colt visitied site again and successfully transmitted packets - Email sent to Carlo asking to confirm next steps 11/06 - Circuit Ordered - arrival 10th August - possibly migration 31/08 09/06 - Confirmed that FE from Colt turned up on site yesterday but had problems - looking to resolve next week. June 1st: 13/05: The circuit delivery is delayed due to no access to customer location untill 30th June 2020 - COVID 28/06: Circuit was successfully tested on 25th June. Migration needs to be planned- eta July 2020 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | UCORPDEU036 | GERMANY_STAVENHAGEN_SCHULTETUSSTRASSE |  |  |  |  | Schultetusstrasse , Mecklenburg Vorpommern STAVENHAGEN Pfanni GmbH & Co Schultetusstrße 37 Stavenhagen | [8 empty] | 4Mbps | 40 |  |  | 2020 | Mar | [13 empty] | Lower Ground floor. EDV Room | 154.14.63.12/30 Network - 154.14.63.12 First usable - 154.14.63.13 Last usable - 154.14.63.14 Broadcast - 154.14.63.15 Subnet Mask - 255.255.255.252 | 154.14.63.13 | 154.14.63.14 |  |  |  | Colt Technology Services GmbH | [5 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN) |  |  |  | No | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 07:30:00 to 16:00:00 | 09:30 to 18:30 | 109159 | CRQ000000696794 | Approved |  | CRQ000000686873 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-02-UCORPDEU065-GTT-1 | I029953GTT1 | 2 | No Visio Diagram |  | Europe | GERMANY | GERMANY_WUNSTORF_18 IM STADTFELDE_WUNSTORF DISTRIBUTION CENTRE | 2019_181 |  |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001830173 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-12-31 | Red | 2020-04-17 | 2021-02-27 | Red | 17/07- GTT pushing vendor for an update 10/07 - EX MILITARY ZONE 29/06 - Gergana confirms documents passed to their supplier 29/06 - Expediation escalation sheet provided back to Maria / Gergana for passing on to their supplier 29/06 - Thomas Dehmel provided response - checking reason for prioritisation and then provide back to Maria 26/06 - Maria reached out to local contacts Stucke, Martin Dehmel, Thomas for help completing an escalation sheet required to expediate delivery before January 2021 June 1st: 18/05: The requested additional information was provided to the vendor in order to confirm if the lead time can be reduced. 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Order Accepted | Circuit Provider |  | UCORPDEU065 | GERMANY_WUNSTORF_18 IM STADTFELDE_WUNSTORF DISTRIBUTION CENTRE |  |  |  |  | IM STADTFELDE | [9 empty] | 10 |  |  | 2020 | Mar | [13 empty] | 1st Floor. Computer Room 2 | 154.14.126.84/30 Network - 154.14.126.84 First usable - 154.14.126.85 Last usable - 154.14.126.86 Broadcast - 154.14.126.87 Subnet Mask - 255.255.255.252 | [5 empty] | 1&1 Versatel Deutschland GmbH | [5 empty] | Damian Dabros | Damian Dabros | Damian Dabros
CKT-I-01-UCORPGRC061-BT-1 | I0110003BT1 | 2 |  |  | Europe | GREECE | GREECE_ATHENS_EVGA_ICE_CREAMS | 2019_182 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGRC061 | GREECE_ATHENS_EVGA_ICE_CREAMS |  |  |  |  | IERA ODOS | [9 empty] | 10 |  |  | 2020 | Mar | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-01-UCORPGRC052-BT-1 | I015125BT1 | 2 |  |  | Europe | GREECE | GREECE_GASTOUNI_FACTORY_FGT | 2019_186 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGRC052 | GREECE_GASTOUNI_FACTORY_FGT |  |  |  |  | GEOR. SISINI , Km Old Nat.Road, Patras Pyrgou | [9 empty] | 40 |  |  | 2020 | Mar | [26 empty] | Fat Nela | Fat Nela | Fat Nela
CKT-I-02-UCORPGRC052-BT-1 | I025125BT1 | 2 |  |  | Europe | GREECE | GREECE_GASTOUNI_FACTORY_FGT | 2019_187 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGRC052 | GREECE_GASTOUNI_FACTORY_FGT |  |  |  |  | GEOR. SISINI , Km Old Nat.Road, Patras Pyrgou | [9 empty] | 40 |  |  | 2020 | Mar | [26 empty] | Fat Nela | Fat Nela | Fat Nela
CKT-I-01-GR-PAT99-9999-BT-1 | I0120295BT1 | 2 |  |  | Europe | GREECE | GREECE_PATRAS_ICF_KAPOTAS | 2019_188 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | GR-PAT99-9999 | GREECE_PATRAS_ICF_KAPOTAS |  |  |  |  | Magoula Riou (Kapota) | [9 empty] | 10 |  |  | 2020 | Mar | [26 empty] | Fat Nela | Fat Nela | Fat Nela
CKT-I-01-UCORPGRC043-VOD-1 | I01498VOD1 | 2 |  |  | Europe | GREECE | GREECE_PIRAEUS_RENTIS_LEGAKI | 2019_190 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Vodafone Global | Vod |  | UNIPX-IPQM-00024 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-09-30 | Red | 2020-07-31 | 2020-11-23 | Red | "16/07 - Order to be placed with carrier 10/07 - not in Vodafone tracker - circuit order not confirmed - Vodafone to confirm why not in tracker as order marked complete 11/06 - Circuit not ordered - check with supplier" 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGRC043 | GREECE_PIRAEUS_RENTIS_LEGAKI |  |  |  |  | LEGAKI | [9 empty] | 60 |  |  | 2020 | Mar | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-02-UCORPGRC043-PCCW-1 |  | 2 |  |  | Europe | GREECE |  |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | PCCW | PCCW |  | N/A | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-04-07 | Amber | 2020-04-17 | 2020-12-07 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGRC043 | GREECE_PIRAEUS_RENTIS_LEGAKI | [14 empty] | 60 |  |  | 2020 | Mar | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-01-UCORPGRC062-BT-1 | I0110004BT1 | 2 |  |  | Europe | GREECE | GREECE_SALONICA_ICF_MAKIOS | 2019_192 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGRC062 | GREECE_SALONICA_ICF_MAKIOS |  |  |  |  | EPAR. OD. THESSALONIKIS - KALOCHORIOU | [9 empty] | 10 |  |  | 2020 | Mar | [26 empty] | Fat Nela | Fat Nela | Fat Nela
CKT-I-01-UCORPGRC064-BT-1 | I019482BT1 | 2 |  |  | Europe | GREECE | GREECE_SCHIMATARI_DC_FSX | 2019_194 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGRC064 | GREECE_SCHIMATARI_DC_FSX |  |  |  |  | 2ND KM SCHIMATARI - HALKIDA | [9 empty] | 60 |  |  | 2020 | Mar | [26 empty] | Fat Nela | Fat Nela | Fat Nela
CKT-I-02-UCORPGRC064-BT-1 | I029482BT1 | 2 |  |  | Europe | GREECE | GREECE_SCHIMATARI_DC_FSX | 2019_195 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGRC064 | GREECE_SCHIMATARI_DC_FSX |  |  |  |  | 2ND KM SCHIMATARI - HALKIDA | [9 empty] | 60 |  |  | 2020 | Mar | [26 empty] | Fat Nela | Fat Nela | Fat Nela
CKT-I-01-UCORPGRC063-BT-1 | I0110005BT1 | 2 |  |  | Europe | GREECE | GREECE_UBF_SALONICA_SALES_OFFICE | 2019_196 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGRC063 | GREECE_UBF_SALONICA_SALES_OFFICE |  |  |  |  | NEOU RYSSIOU - TAGARADON | [9 empty] | 10 |  |  | 2020 | Mar | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-01-UCORPHUN037-GTT-1 | I0120098GTT1 | 2 | Yes |  | Europe | HUNGARY | HUNGARY_BUDAPEST_117-133 VACI GEENS |  | un-uen-hunbud1-rtr001 | un-uen-hunbud1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001828648 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-04-24 | Complete | 2020-04-17 | 2020-06-11 | Complete | 211/06: Migration Successful 9/05 Migration planned for 11/06. 19/05: Eloise suggesting migration to take place w/c 8th June 27/04 Circuit delivered. Cisco to start prep work for the migration. | Complete | Circuit Migrated | Cisco |  | UCORPHUN037 | HUNGARY_BUDAPEST_117-133 VACI GEENS | [13 empty] | 50Mbps | 100 |  |  | 2020 | Mar | [6 empty] | FE needs to bring USB with pre downloaded software. | 09:00-16:00 | NA | NA |  |  |  | 2nd Floor. server room | 154.14.53.92/30 Network - 154.14.53.92 First usable - 154.14.53.93 Last usable - 154.14.53.94 Broadcast - 154.14.53.95 Subnet Mask - 255.255.255.252 | 154.14.53.93 | 154.14.53.94 |  |  |  | Invitech ICT Services Kft | [5 empty] | Adrian Lazar | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN) |  |  | Yes | No | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 07:00-14:00 | 09:00-16:00 | 73030 | CRQ000000679907 | Approved |  | CRQ000000676448 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  |  | 2020-06-01
CKT-I-02-UCORPHUN037-UNL-1 | I0220098UNL1 | 2 | Yes |  | Europe | HUNGARY | HUNGARY_BUDAPEST_117-133 VACI GEENS |  | un-uen-hunbud1-pio001 | un-uen-hunbud1-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit | Unilever | Uni |  |  | 2020-03-01 | 2020-03-01 | Complete | 2020-03-06 | 2020-03-01 | Complete | 2020-05-05 | 2020-03-01 | Complete | 2020-05-19 | 2020-04-17 | Complete | 17/04 Migration completed successfully. Issues at the beginning of the migration window - Algosec implemented on the old FW only, not implemented on new FW by Microland. Microland supported us on the bridge and added missing IP addresses to the new FW. | Complete | Circuit Migrated |  |  | UCORPHUN037 | HUNGARY_BUDAPEST_117-133 VACI GEENS | [13 empty] | 25Mbps | 100 |  |  | 2020 | Mar | [6 empty] | NA - Cisco requested not to provide onsite support for the migration. Unilever local team will provide relevant support. | 0900 - 1500 UTC | NA | NA | NA |  |  |  |  | 37.220.215.53 | 37.220.215.54 | 37.220.215.52/30 | [8 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde | 2020-04-16 |  | Standard site type - Hybrid (MPLS + IEN) |  |  | No | No | No | No | CMSP ticket raised Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms not sent |  | 0900 - 1500 | 1000 - 1600 | 55093 | CRQ000000659262 | Approved | 41923 | CRQ000000656051 | Completed | Completed |  |  | Tamas Varga | Circuit Migrated - First Time right | NA | NA | NA |  | 2020-04-01
CKT-I-01-HU-MKO99-9999-UNL-1 | I013270UNL1 | 2 | Yes |  | Europe | HUNGARY | HUNGARY_MARKO_WAREHOUSE |  | un-uen-hunmar1-rtr001 | un-uen-hunmar1-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit | Unilever | Uni |  |  | 2020-03-01 | 2020-03-01 | Complete | 2020-03-06 | 2020-03-01 | Complete | 2020-05-05 | 2020-03-01 | Complete | 2020-05-19 | 2020-04-15 | Complete | 12/05 NTT quote for SFP module has been sent to Adam. Adam to compare with the local offering and provide feedback to Cisco whether to order with NTT or locally. 15/04 As copper SFP was missing for new wan interface, connected new circuit on cross connect interface between wan routers . Tested failover and its working properly through lan interface hsrp configuration. To keep the design as per unilever standard, Need to send the copper sfp and arrange 30 min maintenance window with no downtime to have cross connectivity between this wan routers. | Complete | Circuit Migrated |  |  | HU-MKO99-9999 | HUNGARY_MARKO_WAREHOUSE |  |  |  |  | IPAROS UTCA | [8 empty] | 1984kbps | 10 |  |  | 2020 | Mar | [6 empty] | NA - Cisco requested not to provide onsite support for the migration. Unilever local team will provide relevant support. | 0900 - 1500 UTC | NA | NA | NA |  |  |  |  | 37.220.215.41 | 37.220.215.42 | 37.220.215.40/30 | [8 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde | 2020-04-09 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  | No |  |  | No | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 0900 - 1500 | 1000 - 1600 | 54549 | CRQ000000659547 | Approved | 41791 | CRQ000000654409 | Completed | Completed |  |  | Tibor Matos | Circuit Migrated - First Time right | NA | NA | NA |  | 2020-04-01
CKT-I-02-HU-MKO99-9999-GTT-1 | I023270GTT1 | 2 | Yes |  | Europe | HUNGARY | HUNGARY_MARKO_WAREHOUSE | 2018_98 | un-uen-hunmar1-vpn001 | un-uen-hunmar1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001835306 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-06-25 | Complete | 2020-04-17 | 2020-07-31 | Complete | 31/07: Migration complete 22/07: Migration planned for 31st July - field engineer required 17/07 - Maria confirmed testing successful - migration to be planned next 16/07 - Maria confirmed FE András Fenzel +36 30 438 7566 on Friday 17th July 14/07 - ES mailed for either 21st July at 10am local start if 17th not available - Maria Hristova to reply 13/07 - ES mailed Maria Hristova <Maria.Hristova@gtt.net> to check 17th July at 10am local ? 09/07 - testing un-successful - needs GTT to attend site 08/07 - Eloise has session scheduled with Tibor and Cisco engineer to test circuit on 09/07 at 9am UK time. If unsucessful in this attempt we will need FE from GTT to come to site 08/07 - Maria requested new date form Tibor when they can test the line 07/07 - Tibor test not successful - ES checking with Tibor when he is next on site to see if we can support with FE 06/07: Eloise reached out to Tibor - Tibor is going to see if he can get internet connection on 07/07 at 11am CET. IF succesful we will arrange a GTT testing call. If un-successful we will need to get a FE from GTT to come to site. ACTION: Check in on Tibor tomorrow. 01/07 - Tibor Macz emailed to see if he can support a re-test as recommended by vendor 24/06 - Maria GTT confirmed field engineer already left site when trying to troubleshoot so vendor not able to troubleshoot - new testing to be arranged so equipment can be connected 22/06 - Maria GTT confirmed ran the test 22/06,but ran into issues and working on resolving them with our vendor 18/06 - Testing booked for 22/06 17/06 - Due to clash of test dates - moved to Monday 22nd June at 10 AM CET? 16/06 - Tibor Matos confirmed he will be avilable for circuit testing on 19.06 11/06 - GTT confirm circuit handed over to them from supplier 11/06 - circuit ordered - possibly arriving 25th June - - Migration possbily end of July June 1st: 18/05: The FOC provided by the vendor is 17th August. 11/05: Vendor confirmed copper was ordered as a last mile solution. | Complete | Circuit Migrated | Circuit Provider |  | HU-MKO99-9999 | HUNGARY_MARKO_WAREHOUSE |  |  |  |  | IPAROS UTCA | [8 empty] | 10Mbps | 10 |  |  | 2020 | Mar | [7 empty] | 10:00am to 16:00pm | [5 empty] | Ground Floor. Middle section of the warehouse, behind the office cubicle. Network rack | 154.14.59.64/30 Network - 154.14.59.64 First usable - 154.14.59.65 Last usable - 154.14.59.66 Broadcast - 154.14.59.67 Subnet Mask - 255.255.255.252 | 154.14.59.65 | 154.14.59.66 |  |  |  | Turk Telekom International | [5 empty] | Arijon Alija | Arijon Alija | Arijon Alija |  |  | Standard site type - Dual DMVPN | [6 empty] | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression | Window Date agreed - End user Comms not sent |  | 08:00am to 14:00pm | 10:00am to 16:00pm | 106282 |  |  |  | CRQ000000694921 | Completed | Completed
CKT-I-02-UCORPHUN040-UNL-1 | I021380UNL1 | 2 | Yes | Top | Europe | HUNGARY | HUNGARY_NYIRBATOR_FACTORY |  | un-uen-hunnyi1-rtr001 | un-uen-hunnyi1-vpn002 | Agnieszka Pajak | WAN Circuit Migration |  | Unilever | Uni |  |  | 2019-12-01 | 2019-12-01 | Complete | 2019-12-06 | 2020-01-20 | Complete | 2020-02-04 | 2020-02-17 | Complete | 2020-02-18 | 2020-02-24 | Complete |  | Complete | Circuit Migrated |  |  | UCORPHUN040 | HUNGARY_NYIRBATOR_FACTORY |  |  |  |  | TANCSICS MIHALY U | [8 empty] | 10Mbps | 50 |  |  | 2020 | Feb |  |  | Service |  |  |  | NA | 0800 - 1400 UTC | NA | NA | NA |  |  |  | IP address(es) 37.220.211.130 Subnet Mask 255.255.255.252 Gateway address 37.220.211.129 DNS1 80.244.97.30 DNS2 80.244.98.166 Interface on CPE Gi0/10 | 37.220.211.129 | 37.220.211.130 | 37.220.211.128/30 | [8 empty] | Arijon Alija | Arijon Alija | Arijon Alija | 2020-02-25 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete | NO | No | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 0800 - 1400 | 0900 - 1500 | 36635 | CRQ000000643640 | Approved | 41032 | CRQ000000638628 | Completed | Completed | Tested-Pass |  |  | Circuit Migrated - First Time right | NA | NA | NA
CKT-I-01-UCORPHUN040-GTT-1 |  | 2 |  | High | Europe | HUNGARY | HUNGARY_NYIRBATOR_FACTORY |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817220 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPHUN040 | HUNGARY_NYIRBATOR_FACTORY |  |  |  |  | TANCSICS MIHALY U | [9 empty] | 100 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Fat Nela | Fat Nela | Fat Nela | [14 empty] | 97834 | [9 empty] | Circuit Migrated - First Time right
CKT-I-02-UCORPHUN051-UNL-1 | I021419UNL1 | 2 | Yes | High | Europe | HUNGARY | HUNGARY_ROSZKE_FACTORY |  | un-uen-hunros1-rtr001 | un-uen-hunros1-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit | Unilever | Uni |  |  | 2020-01-15 | 2020-01-15 | Complete | 2020-01-20 | 2020-01-20 | Complete | 2020-03-20 | 2020-03-01 | Complete | 2020-04-03 | 2020-04-14 | Complete | 17/05 Testing successfully concluded - speed test showed good results/browsing was fast. Cisco configured the DMVPN link to be Primary for both Corporate and Internet traffic with the 10Mbps IEN link acting as backup only. 15/05 The issue continues - local end users have issues with accessing different corporate applications. A couple of tests have been performed already but no rootcause found. Additional test planned for 17 May to troubleshoot (participants: local UL, Zscaler team, Cisco team). 21/04 Zscaler issue resolved. Swap of the traffic required. An additional change window to swap the traffic has been agreed for 28 Apr. 14/04 Migration completed successfully. Problem with unilever.sharepoint.com probably related to Zscaler when on DMVPN link, but currently on IEN, so no any issue and all other services was tested and working on DMVPN. | Complete | Circuit Migrated |  |  | UCORPHUN051 | HUNGARY_ROSZKE_FACTORY |  |  |  |  | FELSZABADULAS U. 110. | [8 empty] | 8Mbps | 50 |  |  | 2020 | Mar |  |  | Service |  |  |  | NA - Cisco requested not to provide onsite support for the migration. Unilever local team will provide relevant support. | 0700 - 1300 UTC | NA | NA | NA |  |  |  |  | 37.220.211.133 | 37.220.211.134 | 37.220.211.132/30 | [8 empty] | Damian Dabros | Damian Dabros | Damian Dabros | 2020-04-15 |  | Standard site type - Hybrid (MPLS + IEN) | Complete |  | Yes | No | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms not sent |  | 0700 - 1300 | 0800 - 1400 | 55057 | CRQ000000659338 | Approved | 41848 | CRQ000000654750 | Completed | Completed | Tested -Pass-First Time |  | Bence Asztalos | Circuit Migrated - First Time right | NA | NA | NA |  | 2020-04-01
CKT-I-01-UCORPHUN051-GTT-1 | I011419GTT1 | 2 | Agile to be incorporated |  | Europe | HUNGARY | HUNGARY_ROSZKE_FACTORY | 2019_209 | un-uen-hunros1-pio001 | un-uen-hunros1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001828629 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-04 | Complete | 2020-04-17 | 2020-08-06 | Complete | 06/08: Migration successful 16/07 - work with Tibor to establish migration date and if Field Engineer required 14/07 - Testing confirmed successful - Migration date to be planned 08/07: GTT secured engineer for testing on 14th July - invitation has been sent out 07/07 - GTT trying to secure engineer for 14th July at 12:30 PM CET 06/07: Circuit has been delivered - Eloise has sent mail about organising testing 06/07 - circuit has been delivered and cease is already initiated. Current service cease date 10th Sep 2020. – need to arrange testing and migration before then June 1st: 15/05: A new FOC was provided by the vendor: 2nd July | Complete | Circuit Migrated | Circuit Provider |  | UCORPHUN051 | HUNGARY_ROSZKE_FACTORY |  |  |  |  | FELSZABADULAS U. 110. | [8 empty] | 10Mbps | 50 |  |  | 2020 | Mar | [13 empty] | 2nd floor. Knorr building IT room (C304) IT room / network rack | 154.14.53.112/30 Network - 154.14.53.112 First usable - 154.14.53.113 Last usable - 154.14.53.114 Broadcast - 154.14.53.115 Subnet Mask - 255.255.255.252 | 154.14.53.113 | 154.14.53.114 |  |  |  | Turk Telekom International | [5 empty] | Adrian Lazar | Adrian Lazar | Adrian Lazar |  |  | Standard site type - Hybrid (MPLS + IEN) |  |  | No | No | Yes | No | Partner MOP created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 06:00 to 12:00 | 08:00 to 14:00 | 109535 | CRQ000000697310 | Approved |  | CRQ000000691307 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-UCORPHUN045-GTT-1 |  | 2 |  | High | Europe | HUNGARY | HUNGARY_VESZPREM_FACTORY |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817219 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPHUN045 | HUNGARY_VESZPREM_FACTORY | [14 empty] | 50 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Arijon Alija | Arijon Alija | Arijon Alija | [14 empty] | 97834 | [9 empty] | Circuit Migrated - First Time right
CKT-I-02-UCORPHUN045-UNL-1 | I021467UNL1 | 2 | Yes |  | Europe | HUNGARY | HUNGARY_VESZPREM_FACTORY |  | un-uen-hunves1-rtr001 | un-uen-hunves1-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit | Unilever | Uni |  |  | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-02-03 | Complete | 2020-03-18 | 2020-03-01 | Complete | 2020-04-01 | 2020-03-29 | Complete |  | Complete | Circuit Migrated |  |  | UCORPHUN045 | HUNGARY_VESZPREM_FACTORY |  |  |  |  | KISTO U. 5 | [8 empty] | 10Mbps | 50 |  |  | 2020 | Mar | [6 empty] | Cisco not required to provide onsite support during the migration. UL local team to support. | 0900 - 1500 UTC | Induction training required; this shouldn’t take more than 1 hr | NA | NA |  |  |  |  | 37.220.215.45 | 37.220.215.46 | 37.220.215.44/30 | [8 empty] | Arijon Alija | Arijon Alija | Arijon Alija | 2020-03-30 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  | No |  | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms not sent |  | 0900 - 1500 | 1000 - 1600 | 50648 | CRQ000000654754 | Approved | 41792 | CRQ000000654184 | Completed | Completed |  |  | Tibor Matos | Circuit Migrated - First Time right | NA | NA | NA
CKT-I-01-UCORPIRL009-ORA-1 | I011285ORA1 | 2 |  |  | Europe | IRELAND | IRELAND_CORK_CARRIGALINE | 2019_415 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | LO005KAC43 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-06-16 | Red | 2020-07-19 | 2020-08-24 | Red | 2020-07-31 | 2020-10-01 | Red | 15/07 - follow up with Ruth on /30 range 14/07 - RIPE form sent to Dave Collins and Matt Barber (Cisco) for comment 08/07 - email sent to Sandra at BT with comms room details to see if this order can now be progressed 07/07 - BTI RIPE form partly filled in and emailed back need update from Geo-IT and Cisco 02/07 - hussein.soogali@orange.com confirmed site survey has been requested and BT Ireland will contact Holly Maiden as LCON 30/06 - email from Josh to Orange (Hussein Soogali) in follow up to the mail on 10th - asking whether a site survey will be carried out 17/06 - email sent to Josh updating him on the point below and asking Ruth if site survey is planned. 17/06 - Orange Weekly Tracker : Order validated by LCON on 16th, order to be placed with the carrier 11/06 - Circuit not ordered - check with supplier 10/06 - Orange stated issues contacting local contact - no response on phone number June 2nd: 27-May-20: Order in Approval (Customer signature) 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPIRL009 | IRELAND_CORK_CARRIGALINE |  |  |  |  | KILNAGLEARY | [9 empty] | 20 |  |  | 2020 | Mar | [20 empty] | BT IRELAND | [5 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-02-UCORPIRL009-GTT-1 | I021285GTT1 | 2 | Yes |  | Europe | IRELAND | IRELAND_CORK_CARRIGALINE | 2019_416 | un-uen-irlcar1-rtr001 | un-uen-irlcar1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001833710 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-04-17 | Complete | 2020-04-17 | 2020-08-19 | Complete | 19/08: Migration successful 06/08: Testing successful. Migration date suggested is 19th August 14/07 - Field engineer confirmed as Ciaran Kelly +447474465464 for 23rd July at 9am local time 10/07 - Gergana confirmed requested resources (field engineer and network provisioning engineer) for 23rd July, 09:00 local time. 09/07 - requested for FE visit for testing on 23rd July when Jim Broderick is back from leave 08/07 - new circuit found - FE required - trying to arrange testing date for w/c 13th July once UL sign off on additional cost. 08/07 - new circuit found - FE required - trying to arrange testing date for w/c 13th July once UL sign off on additional cost. 06/07: Testing circuit still needs to be scheduled 30/06: Circuit was handed over to us by our Vendor on 17.04.2020. We have contacted vendor to ask for more information. (From GTT tracker) 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | UCORPIRL009 | IRELAND_CORK_CARRIGALINE |  |  |  |  | KILNAGLEARY | [8 empty] | 1984Kbps | 20 |  |  | 2020 | Mar | [13 empty] | Ground Floor. Server room | 154.14.59.168/30 Network - 154.14.59.168 First usable - 154.14.59.169 Last usable - 154.14.59.170 Broadcast - 154.14.59.171 Subnet Mask - 255.255.255.252 | 154.14.59.169 | 154.14.59.170 |  |  |  | open eir fka_Eircom | [5 empty] | Fat Nela |  |  |  |  | Standard site type - Hybrid (MPLS + DMVPN) |  |  | No |  |  | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 09:00 to 15:00 | 10:00 to 16:00 | 114934 | CRQ000000701596 | Approved |  | CRQ000000691127 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-UCORPIRL006-ORA-1 | I011283ORA1 | 2 |  |  | Europe | IRELAND | IRELAND_DUBLIN_CITY_WEST | 2019_417 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | LO005KMB42 | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-08-12 | Red | 2020-07-31 | 2020-10-01 | Red | 15/07 - Order validation complete 08/07 - Josh and Ruth Swinnerton emailed for Order Validation questions 01/07 - Ruth confirmed what LCON confirmation entails - passed to Josh for his response 22/06 - Orange Tracker - Order validation pending with the LCON - Josh and Ruth emailed for support 11/06 - Circuit ordered - should arrive 20th August - migration September June 3rd: Inform Geo IT about the project June 2nd: 29-May-20: Validation email to be send to the LCON 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Ordered | Circuit Provider |  | UCORPIRL006 | IRELAND_DUBLIN_CITY_WEST |  |  |  |  | NATIONAL DIGITAL PARK | [9 empty] | 40 |  |  | 2020 | Mar | [20 empty] | BT IRELAND | [5 empty] | Fat Nela | Fat Nela | Fat Nela
CKT-I-02-UCORPIRL006-GTT-1 |  | 2 |  | High | Europe | IRELAND | [5 empty] | SNT |  | GTT | GTT |  | GTT/001817209 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPIRL006 | IRELAND_DUBLIN_CITY_WEST | [14 empty] | 100 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Fat Nela | Fat Nela | Fat Nela | [14 empty] | 97834 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-IE-LIS99-9999-GTT-1 | I0120075GTT1 | 2 | Yes |  | Europe | IRELAND | IRELAND_LISBURN_DISTRIBUTION_CENTRE | 2019_419 | un-uen-irlisb1-rtr001 |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001828612 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-10-31 | Red | 2020-04-17 | 2020-11-14 | Red | 13/07 - emailed Mike Blackwell / Darren Carr to see if they can help. 09/07 - PC in cabinet is possibly some sort of DHCP server for site - need clarity on how to address 09/07 - Checking if local IT support in Dublin who can help remediate the issue in Lisburn 07/07 - Josh sent a follow up email regards monitor replacement 07/07 - Excess construction costs for review/approval re-submitted to Deepak 29/06 - Photos provided by GTT & Dermot - problem appears to be PC tower and old CRT monitor taking up 3/4 space in cabinet. Josh asked if can replace CRT with flat screen to free up space? 25/06 - follow up email sent to Dermot Johnson asking him to send through photographs at his next opportunity 25/06 - Email from Deepak to GTT confirming Child PON to cover the ECC costs issued for signature. 22/06 - email sent to site owner Dermot Johnson asking if they can support by supplying photographs of the comms cabinet in question for reivew by GTT and Unilever 19/06 - email sent to team plus Josh Mackinnon to see if this can be completed as requested. 18/06 - Gergana confirmed the their Vendor is targeting 17.07.2020 for delivery and their engineer has completed fibre splicing but advises that you need to free up space in comms cabinet so engineers can complete installation. 15/06 - Payment agreed and in progress - Our vendor is prepared to absorb £2,800 of the total costs of £3,381. Is Unilever ok to pay the remaining £581.84 June 1st: 27/05: Unilever informed us that Openreach called to arrange visit on Friday lunchtime (29.05.2020) to survey for an order to put in a fibre line. Pending confirmation for that appointment. 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Order Accepted | Circuit Provider |  | IE-LIS99-9999 | IRELAND_LISBURN_DISTRIBUTION_CENTRE |  |  |  |  | c/o Johnson Brothers, HILLSBOROUGH OLD ROAD | [8 empty] | 2Mbps | 10 |  |  | 2020 | Mar | [13 empty] | First Floor. room in Johnson Brothers office | 154.14.59.132/30 Network - 154.14.59.132 First usable - 154.14.59.133 Last usable - 154.14.59.134 Broadcast - 154.14.59.135 Subnet Mask - 255.255.255.252 | [5 empty] | TalkTalk | [5 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-01-UCORPITA125-ORA-1 | I011273ORA1 | 2 |  |  | Europe | ITALY | ITALY_CAIVANO_FACTORY | 2019_445 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | ORA |  | LO005MN939 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-11-16 | Red | "15/07 - chase up email sent to LCON and Mauro for a response 09/07 - Order validation pending with LCON - no delivery date on Orange tracker 11/06 - Check with Supplier on order June 2nd: No details in the providers list" 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | UCORPITA125 | ITALY_CAIVANO_FACTORY |  |  |  |  | VIA BELLINI LOC. PASCAROLA Consorzio Csa-Asi , Napoli | [8 empty] | 15MB | 100 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + DMVPN)
CKT-I-02-UCORPITA125-GTT-1 |  | 2 |  | High | Europe | ITALY | ITALY_CAIVANO_FACTORY |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817217 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPITA125 | ITALY_CAIVANO_FACTORY | [14 empty] | 100 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde | [14 empty] | 97834 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-UCORPITA174-GTT-1 | I019634GTT1 | 2 |  |  | Europe | ITALY | ITALY_CAMPOLUNGO_DEPOT | 2019_447 | un-uen-itacam1-rtr002 | un-uen-itacam1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001832524 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-23 | Red | 2020-04-17 | 2020-09-16 | Red | 31/08: Migration rescheduled for September - SFP required 21/08: Still awaiting GTT handover. Migration planned for 31st August "15/07 - Miriam confirmed Last Monday a technician installed the support that I am attaching, I don't know if there are other communications with telecom.- Gergana asked to check with Telecom Italia what they need from site 15/07 - email forwarded to Mauro asking him if he can check with local contacts if Telecom Italia have been in touch 09/07 - Fibre Laying in Progress - once complete install at site - expected update next week June 1st: 27/05: Pending FOC date." 04/05 Circuit provider to advise on the status of circuit order & delivery process | Green | Circuit Order Accepted | Circuit Provider |  | UCORPITA174 | ITALY_CAMPOLUNGO_DEPOT |  |  |  |  | Marconi Freddeuropa S.r.l. VIA DEI MUTILATI DEL LAVORO - Zona Industriale, | [8 empty] | 2MB | 10 |  |  | 2020 | Mar | [13 empty] | Ground floor . server room | 154.14.48.156/30 Network - 154.14.48.156 First usable - 154.14.48.157 Last usable - 154.14.48.158 Broadcast - 154.14.48.159 Subnet Mask - 255.255.255.252 | 154.14.48.157 | 154.14.48.158 |  |  |  | Retelit | [5 empty] | Fat Nela | Fat Nela | Fat Nela |  |  | Standard site type - Dual MPLS | Complete |  | No | No | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved |  |  |  |  | CHG000000000042239 CHG000000000041428 (OLD) |  |  |  | CRQ000000709652 | In Progress | Completed
CKT-I-02-UCORPITA174-BT-1 | I029634BT1 | 2 |  |  | Europe | ITALY | ITALY_CAMPOLUNGO_DEPOT | 2019_448 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | UCORPITA174 | ITALY_CAMPOLUNGO_DEPOT |  |  |  |  | Marconi Freddeuropa S.r.l. VIA DEI MUTILATI DEL LAVORO - Zona Industriale, | [8 empty] | 512KB | 10 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Dual MPLS
CKT-I-01-NONULITA208-BT-1 | I0110920BT1 | 2 |  |  | Europe | ITALY | ITALY_CARINI_PALERMO_DEPOT | 2019_450 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-06-30 | Green | 2020-07-31 | 2020-12-07 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | NONULITA208 | ITALY_CARINI_PALERMO_DEPOT |  |  |  |  | VIA DON MILANI | [8 empty] | 128KB | 10 |  |  | 2020 | Mar | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Dual MPLS
CKT-I-02-NONULITA208-ORA-1 | I0210920ORA1 | 2 |  |  | Europe | ITALY | ITALY_CARINI_PALERMO_DEPOT | 2019_449 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | GO0AU31368 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-06-11 | Red | 2020-07-19 | 2020-10-15 | Red | 2020-07-31 | 2020-11-18 | Red | "15/07 - Telecom Italia advised GTT that they are still pending information from Unilever in order to schedule the final activities to deliver that circuit - Gergana reached out to site and Geo-IT contacts 09/07 - Order placed with carrier 11/06 - Check with Supplier on order June 2nd: No details in the providers list" 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | NONULITA208 | ITALY_CARINI_PALERMO_DEPOT |  |  |  |  | VIA DON MILANI | [8 empty] | 7MB | 10 |  |  | 2020 | Mar | [20 empty] | FASTWEB | [5 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Dual MPLS
CKT-I-02-IT-CAS99-9999-GTT-1 | I021278GTT1 | 2 | The visio is not correct |  | Europe | ITALY | ITALY_CASALPUSTERLENGO_FACTORY | 2019_451 |  |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001830147 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-25 | Red | 2020-04-17 | 2020-10-20 | Red | "15/07 - possibly a rack space issue on site - ask Alberto over email 09/07 - Vendor to complete digging and fibre splicing works 16/06 - Meeting held with Alberto, Eloise and Gergana to discuss local requirements. GTT Internet circuit does not require a new router - GTT believe Retelit stating circcuit may not be delivered until September as external works needed but Alberto does not believe this is correct based on his discussions with Telecom Italia and thinks it is just neccessary to connect wires. GTT to check with Retelit 15/06 - Meeting set for 15/06 with LCON, GTT, Cisco to clarify requirements 08/06 - GTT requesting local resource ""Our Vendor are asking is to check with you the current infrastructure from rack to the end of the private property. Is the current infrastucture suitable to proceed with the cable-laying or it could be necessary a new infrastructure if the current one is full?"" June 1st: 29/05: Digging and fiber splicing works are required on the route from CASALPUSTERLENGO (CSLPITAL) to CODOGNO (CODOITAE). These activities require more time than expected (85 days) for our Vendor and the expedite is not possible for them. The expected delivery date is September 20th. Unilever confimer to proceed with that order." 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Order Accepted | Circuit Provider |  | IT-CAS99-9999 | ITALY_CASALPUSTERLENGO_FACTORY |  |  |  |  | via Lever Gibbs, 3 | [8 empty] | 15MB | 100 |  |  | 2020 | Mar | [13 empty] | Ground Floor. Primary server room | 154.14.116.112/30 Network - 154.14.116.112 First usable - 154.14.116.113 Last usable - 154.14.116.114 Broadcast - 154.14.116.115 Subnet Mask - 255.255.255.252 154.14.126.176/29 Network - 154.14.126.176 First usable - 154.14.126.177 Last usable - 154.14.126.182 Broadcast - 154.14.126.183 Subnet Mask - 255.255.255.248 | [5 empty] | Retelit | [5 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + DMVPN)
CKT-I-01-IT-OPM99-9999-ORA-1 | I019697ORA1 | 2 |  |  | Europe | ITALY | ITALY_CASORATE_PRIMO_DEPOT | 2019_454 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | GO0AWDUF2C | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-10-05 | Red | 2020-07-31 | 2020-12-02 | Red | "09/07 - no dates in Orange Tracker 30/06 - Deepak cleared the order to progress 30/06 - follow up email sent as no response from Andrew Colley / Marco Parise 23/06 - Orange completed feasibility & advised can only deliver 8Mbps Internet fibre instead of 20Mbps requested. Site appears to have 4Mbps capacity today through 3 links not clear why 20Mbps was requested by Geo IT when we gathered SNT requirements. Andrew Colley to review and advise if 8Mbps would be adequate. 11/06 - Check with Supplier on order June 2nd: No details in the providers list" 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | IT-OPM99-9999 | ITALY_CASORATE_PRIMO_DEPOT |  |  |  |  | VIA ENRICO MATTEI Via Enrico Mattei, snc (c/o Kuehne+Nagel), Pavia [‎13-‎02-‎2020 21:20] Consorte, Fabio: Casorate, province of Pavia | [8 empty] | 1MB | 20 |  |  | 2020 | Mar | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-02-IT-OPM99-9999-BT-1 | I029697BT1 | 2 |  |  | Europe | ITALY | ITALY_CASORATE_PRIMO_DEPOT | 2019_453 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-30 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | IT-OPM99-9999 | ITALY_CASORATE_PRIMO_DEPOT |  |  |  |  | VIA ENRICO MATTEI Via Enrico Mattei, snc (c/o Kuehne+Nagel), Pavia [‎13-‎02-‎2020 21:20] Consorte, Fabio: Casorate, province of Pavia | [8 empty] | 2MB | 20 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-01-UCORPITA214-ORA-1 | I0111207ORA1 | 2 |  |  | Europe | ITALY | ITALY_CATANIA_DEPOT | 2019_455 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | LO005MN838 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-06-11 | Red | 2020-07-19 | 2020-10-07 | Red | 2020-07-31 | 2020-11-01 | Red | 09/07 - Order placed with carrier 11/06 - Check with Supplier on order June 2nd: No details in the providers list 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPITA214 | ITALY_CATANIA_DEPOT |  |  |  |  | Via Pantano D’arci BLOCCO PALMA PRIMO Industriale | [8 empty] | 2MB | 10 |  |  | 2020 | Mar | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-02-UCORPITA214-BT-1 | I0211207BT1 | 2 |  |  | Europe | ITALY | ITALY_CATANIA_DEPOT | 2019_456 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | UCORPITA214 | ITALY_CATANIA_DEPOT |  |  |  |  | Via Pantano D’arci BLOCCO PALMA PRIMO Industriale | [8 empty] | 20MB | 10 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN) |  |  |  |  | Yes
CKT-I-01-NONULITA213-ORA-1 | I0111040ORA1 | 2 |  |  | Europe | ITALY | ITALY_CISTERNA_DI_LATINA_GROTTE_DI_NOTTOLA | 2019_457 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | LO005MNS53 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-06-11 | Red | 2020-07-19 | 2020-10-01 | Red | 2020-07-31 | 2020-10-31 | Red | "09/07 - Order placed with carrier 11/06 - Check with Supplier on order June 2nd: No details in the providers list" 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | NONULITA213 | ITALY_CISTERNA_DI_LATINA_GROTTE_DI_NOTTOLA |  |  |  |  | V. GROTTE DI NOTTOLA | [8 empty] | 1024KB | 10 |  |  | 2020 | Mar | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-02-NONULITA213-CTL-1 | I0211040CTL1 | 2 |  |  | Europe | ITALY | ITALY_CISTERNA_DI_LATINA_GROTTE_DI_NOTTOLA | 2019_458 |  |  | Eloise Shepheard | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-21 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit Ordered | Unilever SNT |  | NONULITA213 | ITALY_CISTERNA_DI_LATINA_GROTTE_DI_NOTTOLA |  |  |  |  | V. GROTTE DI NOTTOLA | [8 empty] | 2MB | 10 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-01-UCORPITA118-ORA-1 | I012768ORA1 | 2 |  |  | Europe | ITALY | ITALY_LATINA_SCALO | 2019_461 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | GO0AQ9XZ3E | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-06-25 | Red | 2020-07-19 | 2020-09-11 | Red | 2020-07-31 | 2020-10-25 | Red | "09/07 - Order in progress with carrier 11/06 - Circuit not ordered - check with supplier June 2nd: No details in the providers list" 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPITA118 | ITALY_LATINA_SCALO |  |  |  |  | VIALE DELL INDUSTRIA 4013 | [8 empty] | 2MB | 10 |  |  | 2020 | Mar | [20 empty] | FASTWEB | [5 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-02-UCORPITA118-BT-1 | I022768BT1 | 2 |  |  | Europe | ITALY | ITALY_LATINA_SCALO | 2019_462 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | UCORPITA118 | ITALY_LATINA_SCALO |  |  |  |  | VIALE DELL INDUSTRIA 4013 | [8 empty] | 7MB | 10 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-01-IT-CTA99-999-ORA-1 | I0111038ORA1 | 2 |  |  | Europe | ITALY | ITALY_MARCELLINARA | 2019_463 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | GO0AU31962 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-09-06 | Red | 2020-07-31 | 2020-10-06 | Red | "09/07 - Order placed with carrier 26/06 - Deepak confirmed to proceed with wireless connection for 10Mb service as other carriers can only provide 8Mb by fibre 11/06 - Check with Supplier on order June 2nd: No details in the providers list" 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | IT-CTA99-999 | ITALY_MARCELLINARA |  |  |  |  | CONTR. GRANORISO ZONA INDUSTRIALE (Igea Calabra) | [8 empty] | 1024KB | 10 |  |  | 2020 | Mar | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-02-IT-CTA99-999-BT-1 | I0211038BT1 | 2 |  |  | Europe | ITALY | ITALY_MARCELLINARA | 2019_464 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | IT-CTA99-999 | ITALY_MARCELLINARA |  |  |  |  | CONTR. GRANORISO ZONA INDUSTRIALE (Igea Calabra) | [8 empty] | 7MB | 10 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-01-UCORPITA175-BT-1 | I019696BT1 | 2 |  |  | Europe | ITALY | ITALY_MODUGNO_SALES_DEPOT | 2019_465 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPITA175 | ITALY_MODUGNO_SALES_DEPOT |  |  |  |  | Adriatica Tecno Logistica srl in VIA DEL LILIUM | [8 empty] | 2048K | 10 |  |  | 2020 | Mar | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-02-UCORPITA175-GTT-1 | I029696GTT1 | 2 |  |  | Europe | ITALY | ITALY_MODUGNO_SALES_DEPOT | 2019_466 | un-uen-itamod1-ien001 | un-uen-itamod1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001832518 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-04 | Complete | 2020-04-17 | 2020-08-04 | Complete | 04/08: Migration successful "16/07 - testing confirmed for 21st July - 10am local time - FE confirmed as Andrea Fontana Cell: +39 3929810400 / Andrea Fotia - back up Cell: +39 348 4381427 15/07 - ES sent email for GTT to confirm FE for 21st July 09/07 - Gergana confirmed they will request FE for 21st 10:00 local time. I’ll inform you once the resources are confirmed. 09/07 - Gergana confirmed field engineer requested for Monday 21st 10:00 local time. 08/07 - Mauro confirmed FE would be required and Francesco.Curci@unilever.com (SPOC of Modugno) is proposing Monday 21st. 08/07 - Mauro Biso contacted to see if testing can be arrnaged for 21st July 06/07 - Circuit delivered and to be tested – and to mark in the tracker testing pending 24/06 - should be delived 8th July 04/06 - Modugno Sales Depot site address details confirmed to Gergana.Atanasova2@gtt.net June 1st: 21/05: Pending FOC date." 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | UCORPITA175 | ITALY_MODUGNO_SALES_DEPOT |  |  |  |  | Adriatica Tecno Logistica srl in VIA DEL LILIUM | [8 empty] | 20M | 10 |  |  | 2020 | Mar | [13 empty] | Ground Floor. Server Room | 154.14.50.136/29 Network - 154.14.50.136 First usable - 154.14.50.137 Last usable - 154.14.50.142 Broadcast - 154.14.50.143 Subnet Mask - 255.255.255.248 154.14.50.128/30 Network - 154.14.50.128 First usable - 154.14.50.129 Last usable - 154.14.50.130 Broadcast - 154.14.50.131 Subnet Mask - 255.255.255.252 | 154.14.50.129 | 154.14.50.130 | 154.14.50.136/29 |  |  | FASTWEB SpA | [5 empty] | Fat Nela | Fat Nela | Fat Nela |  |  | Standard site type - Hybrid (MPLS + IEN) | Complete |  | No | No | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 07:00 to 13:00 | 09:00 to 14:00 | 109091 | CRQ000000697061 | Approved |  | CRQ000000696385 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-NONULITA207-ORA-1 | I0110918ORA1 | 2 |  |  | Europe | ITALY | ITALY_OLBIA_SALES&DEPOT | 2019_467 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | LO005L3A41 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-06-11 | Red | 2020-07-19 | 2020-10-15 | Red | 2020-07-31 | 2020-11-03 | Red | "09/07 - Order in progress with carrier 11/06 - Check with Supplier on order June 2nd: No details in the providers list" 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | NONULITA207 | ITALY_OLBIA_SALES&DEPOT |  |  |  |  | VIALE MANZONI | [8 empty] | 1024KB | 10 |  |  | 2020 | Mar | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-02-NONULITA207-BT-1 | I0210918BT1 | 2 |  |  | Europe | ITALY | ITALY_OLBIA_SALES&DEPOT | 2019_468 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-30 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | NONULITA207 | ITALY_OLBIA_SALES&DEPOT |  |  |  |  | VIALE MANZONI | [8 empty] | 7MB | 10 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-01-NONULITA202-ORA-1 | I0110899ORA1 | 2 |  |  | Europe | ITALY | ITALY_ORISTANO_12 VIA GINEVRA_ORISTANO WAREHOUSE | 2019_469 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | GO0AVE725E | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-10-13 | Red | 2020-07-31 | 2020-12-04 | Red | "09/07 - No dates in Orange tracker 11/06 - Check with Supplier on order June 2nd: No details in the providers list" 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | NONULITA202 | ITALY_ORISTANO_12 VIA GINEVRA_ORISTANO WAREHOUSE |  |  |  |  | VIA GINEVRA | [8 empty] | 1024KB | 10 |  |  | 2020 | Mar | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-02-NONULITA202-BT-1 | I0210899BT1 | 2 |  |  | Europe | ITALY | ITALY_ORISTANO_12 VIA GINEVRA_ORISTANO WAREHOUSE | 2019_470 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-30 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | NONULITA202 | ITALY_ORISTANO_12 VIA GINEVRA_ORISTANO WAREHOUSE |  |  |  |  | VIA GINEVRA | [8 empty] | 2MB | 10 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-01-UCORPITA172-BT-1 | I019632BT1 | 2 |  |  | Europe | ITALY | ITALY_PARMA_3 VIA STOCCOLMA_DEPOSITO PARMA | 2019_471 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-30 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | UCORPITA172 | ITALY_PARMA_3 VIA STOCCOLMA_DEPOSITO PARMA |  |  |  |  | VIA STOCCOLMA | [8 empty] | 2048KB | 20 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-02-UCORPITA172-ORA-1 | I029632ORA1 | 2 |  |  | Europe | ITALY | ITALY_PARMA_3 VIA STOCCOLMA_DEPOSITO PARMA | 2019_472 | un-uen-itapar1-pio001 | un-uen-itapar1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | LO005M7Z5A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-07-01 | Red | 2020-07-19 | 2020-10-13 | Red | 2020-07-31 | 2020-11-30 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPITA172 | ITALY_PARMA_3 VIA STOCCOLMA_DEPOSITO PARMA |  |  |  |  | VIA STOCCOLMA | [8 empty] | 7MB | 10 |  |  | 2020 | Mar | [20 empty] | Fastweb | [5 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-01-NONULITA205-ORA-1 | I0110900ORA1 | 2 |  |  | Europe | ITALY | ITALY_PASTORANO_193 VIA STRADA STATALE APPIA_PASTORANO WAREHOUSE | 2019_473 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | LO005L3U55 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-06-11 | Red | 2020-07-19 | 2020-10-20 | Red | 2020-07-31 | 2020-11-19 | Red | "09/07 - Order validation pending with local contact 11/06 - Check with Supplier on order June 2nd: No details in the providers list" 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | NONULITA205 | ITALY_PASTORANO_193 VIA STRADA STATALE APPIA_PASTORANO WAREHOUSE | [13 empty] | 1024KB | 10 |  |  | 2020 | Mar | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Dual MPLS
CKT-I-02-NONULITA205-BT-1 | I0210900BT1 | 2 |  |  | Europe | ITALY | ITALY_PASTORANO_193 VIA STRADA STATALE APPIA_PASTORANO WAREHOUSE | 2019_474 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-30 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | NONULITA205 | ITALY_PASTORANO_193 VIA STRADA STATALE APPIA_PASTORANO WAREHOUSE | [14 empty] | 10 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Dual MPLS
CKT-I-01-UCORPITA130-GTT-1 | I011411GTT1 | 2 |  |  | Europe | ITALY | ITALY_POZZILLI_FACTORY | 2019_475 |  |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | N/A | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Amber | 2020-07-04 | 2020-06-30 | Green | 2020-07-17 | 2020-10-27 | Red | "17/07 - GTT to chase vendor for an updated date 09/07 - Pending new updates 11/06 - Circuit Ordered - migration possibly end of July 08/06 - Vendor confirmed they are going to use Via Cerqueto Pozzili IS address because the coordinates provided by you corresponds to it and the Vendor confirmed that it is the same place June 1st: 27/05: The Vendor has to make feasibility checks so they can be sure what is the correct address. This will take 30 days. " 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Ordered | Circuit Provider |  | UCORPITA130 | ITALY_POZZILLI_FACTORY |  |  |  |  | Unilever Italia Manufacturing, STRADA COMUNALE CERQUETO , S. Maria Oliveto | [8 empty] | 8MB | 40 |  |  | 2020 | Mar | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-02-UCORPITA130-BT-1 | I021411BT1 | 2 |  |  | Europe | ITALY | ITALY_POZZILLI_FACTORY | 2019_476 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | UCORPITA130 | ITALY_POZZILLI_FACTORY |  |  |  |  | Unilever Italia Manufacturing, STRADA COMUNALE CERQUETO , S. Maria Oliveto | [8 empty] | 10MB | 40 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-01-IT-POM01-0001-GTT-1 | I011405GTT1 | 2 |  |  | Europe | ITALY | ITALY_ROMA_4 VIA DELLA CASTAGNETTA_FILIALE POMEZIA | 2019_477 | un-uen-itapom1-rtr001 | un-uen-itapom1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001832515 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-08-01 | Complete | 2020-04-17 | 2020-08-02 | Red | 01/08: Marked as out of scope - site to close in September "16/07 - confirmed for 20/07@ 9am - FE Andrea Fontana to attend site 15/07 - Gergana emailed to check if they were able to arrange a FE fo tesitng on 20th July 13/07 - GTT trying to arrange testing for July 20th at 9am local. 10/07 - GTT propose FE for testing on Thursday 16th July, at 13:00 local time. - Corrected to 14:00 local time 09/07 - ES contacted Gergana for FE availability next week 07/07 - Gergana confirmed 'We’re waiting for Deepak to approve thе costs for that visit so we can book field engineer. I’m afraid we won’t be able to schedule that visit for 9th July.' 06/07 - Circuit confirmed delivered and looking to test on 9th July if GTT field engineer available June 1st: 27/05: The Vendor might be ready to release the service into the end of June." 28/04 GTT waiting for Unilever to provide signed declaration for the delivery point so they could place that order with the Vendor. | On Hold | Circuit Delivered | Unilever SNT | Check dates | IT-POM01-0001 | ITALY_ROMA_4 VIA DELLA CASTAGNETTA_FILIALE POMEZIA |  |  |  |  | VIA DELLA CASTAGNETTA | [8 empty] | 1024Kbps | 20 |  |  | 2020 | Mar | [13 empty] | Ground Floor. Server room | "154.14.126.88/29 Network - 154.14.126.88 First usable - 154.14.126.89 Last usable - 154.14.126.94 Broadcast - 154.14.126.95 Subnet Mask - 255.255.255.248 154.14.115.76/30 Network - 154.14.115.76 First usable - 154.14.115.77 Last usable - 154.14.115.78 Broadcast - 154.14.115.79 Subnet Mask - 255.255.255.252" | 154.14.115.77 | 154.14.115.78 | 154.14.126.88/29 |  |  | FASTWEB SpA | [5 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN) | Complete | [10 empty] | 108421 |  |  |  | CRQ000000696550 | Completed | Completed
CKT-I-02-IT-POM01-0001-BT-1 | I021405BT1 | 2 |  |  | Europe | ITALY | ITALY_ROMA_4 VIA DELLA CASTAGNETTA_FILIALE POMEZIA | 2019_478 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | IT-POM01-0001 | ITALY_ROMA_4 VIA DELLA CASTAGNETTA_FILIALE POMEZIA |  |  |  |  | VIA DELLA CASTAGNETTA | [9 empty] | 20 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde
CKT-I-01-IT-ZVR01-0001-ORA-1 | I0111036ORA1 | 2 |  |  | Europe | ITALY | ITALY_TAVAZZANO_DEPOT | 2019_485 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | GO0AU3206B | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-06-25 | Red | 2020-07-19 | 2020-09-30 | Red | 2020-07-31 | 2020-10-30 | Red | "09/07 - Order in progress with carrier 11/06 - Check with Supplier on order June 2nd: No details in the providers list" 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | IT-ZVR01-0001 | ITALY_TAVAZZANO_DEPOT |  |  |  |  | VIA ETTORE MAJORANA | [8 empty] | 2MB | 10 |  |  | 2020 | Mar | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-02-IT-ZVR01-0001-BT-1 | I0211036BT1 | 2 |  |  | Europe | ITALY | ITALY_TAVAZZANO_DEPOT | 2019_486 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | IT-ZVR01-0001 | ITALY_TAVAZZANO_DEPOT |  |  |  |  | VIA ETTORE MAJORANA | [8 empty] | 1MB | 10 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Standard site type - Hybrid (MPLS + IEN)
CKT-I-01-NONHRITA215-ORA-1 | I0111218ORA1 | 2 |  |  | Europe | ITALY | ITALY_VENICE_1 VIA DRIZZAGNO SNC_SCORZE - COLD STORE | 2019_487 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | GO0AVE7F2A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-10-05 | Red | 2020-07-31 | 2020-10-28 | Red | "09/07 - Order under processing - No delivery date provided in Orange tracker 11/06 - Check with Supplier on order June 2nd: No details in the providers list" 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | NONHRITA215 | ITALY_VENICE_1 VIA DRIZZAGNO SNC_SCORZE - COLD STORE |  |  |  |  | VIA DRIZZAGNO SNC | [8 empty] | 1984Kbps | 10 |  |  | 2020 | Mar | [20 empty] | Fastweb | [5 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde
CKT-I-02-NONHRITA215-BT-1 | I0211218BT1 | 2 |  |  | Europe | ITALY | ITALY_VENICE_1 VIA DRIZZAGNO SNC_SCORZE - COLD STORE | 2019_488 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | NONHRITA215 | ITALY_VENICE_1 VIA DRIZZAGNO SNC_SCORZE - COLD STORE |  |  |  |  | VIA DRIZZAGNO SNC | [8 empty] | 2 Mbps | 10 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde
CKT-I-01-IT-SNU01-0023-CTL-1 | I011425CTL1 | 2 | Yes |  | Europe | ITALY | ITALY_VERONA_23 VIA ROMA_SANGUINETTO |  | un-uen-itasang1-rtr001 |  | Eloise Shepheard | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-31 | Red | Not in Unilever tracker - 20th July 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | IT-SNU01-0023 | ITALY_VERONA_23 VIA ROMA_SANGUINETTO |  |  |  |  | Via Roma 23 | Sanguinetto | 37058 | [6 empty] | 10Mbps | 40 | 45.1863 | 11.1507 | 2020 | Mar | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde
CKT-I-02-IT-SNU01-0023-BT-1 | I021425BT1 | 2 |  |  | Europe | ITALY | ITALY_VERONA_23 VIA ROMA_SANGUINETTO | 2019_489 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-30 | Red | Not in Unilever tracker - 20th July 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | IT-SNU01-0023 | ITALY_VERONA_23 VIA ROMA_SANGUINETTO |  |  |  |  | Via Roma 23 | Sanguinetto | 37058 | [7 empty] | 40 | 45.1863 | 11.1507 | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde
CKT-I-01-UCORPITA159-ORA-1 | I011470ORA1 | 2 |  |  | Europe | ITALY | ITALY_VITULAZIO_DEPOT | 2019_491 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | LO005KGN4E | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-06-17 | Red | 2020-07-19 | 2020-09-26 | Red | 2020-07-31 | 2020-10-26 | Red | "11/06 - Circuit not ordered - check with supplier June 2nd: No details in the providers list" 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPITA159 | ITALY_VITULAZIO_DEPOT |  |  |  |  | STRADA STATALE APPIA LOC MAROTTA | [8 empty] | 2MB | 20 |  |  | 2020 | Mar | [20 empty] | FASTWEB | [5 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Complex site type - requires redesign
CKT-I-02-UCORPITA159-BT-1 | I021470BT1 | 2 |  |  | Europe | ITALY | ITALY_VITULAZIO_DEPOT | 2019_492 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-30 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | UCORPITA159 | ITALY_VITULAZIO_DEPOT |  |  |  |  | STRADA STATALE APPIA LOC MAROTTA | [8 empty] | 2MB | 20 |  |  | 2020 | Apr | [26 empty] | Rajesh Dagde | Rajesh Dagde | Rajesh Dagde |  |  | Complex site type - requires redesign
CKT-I-01-NL-WAG01-0001-GTT-1 |  | 2 |  |  | Europe | NETHERLANDS | FIC Wageningen (Food Innovation Centre Wageningen) |  |  |  | Eloise Shepheard | SNT |  | GTT | GTT |  | GTT/001837533 | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-06-30 | Red | 2020-04-17 | 2020-07-14 | Red | 4-Feb: Action is Transfer + Transform. | Pink | Circuit not ordered |  |  | NL-WAG01-0001 | NETHERLANDS_WAGENINGEN - circuit 1 |  |  |  |  | Bronland 14 | Wageningen | 6807WH | [7 empty] | 1000 |  |  | 2020 | Mar | [26 empty] | Damian Dabros | Damian Dabros | Damian Dabros | [14 empty] | 97834
CKT-I-02-NL-WAG01-0001-BT-1 | I0220359BT1 | 2 |  |  | Europe | NETHERLANDS | FIC Wageningen (Food Innovation Centre Wageningen) | 2018_160 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-05-30 | Red | 2020-04-17 | 2020-12-31 | Red | Not in Unilever's tracker - 20th July 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Ordered | Circuit Provider |  | NL-WAG01-0001 | NETHERLANDS_WAGENINGEN - circuit 2 |  |  |  |  | Bronland 14 | Wageningen | 6807WH | [7 empty] | 1000 |  |  | 2020 | Mar | [26 empty] | Damian Dabros | Damian Dabros | Damian Dabros
CKT-I-01-UCORPNLD060-GTT-1 |  | 2 |  | High | Europe | NETHERLANDS | [5 empty] | SNT |  | GTT | GTT |  | GTT/001817224 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Green | 2020-03-18 | 2020-06-30 | Red | 2020-04-01 | 2020-03-31 | Green |  | Pink | Circuit Ordered |  | Check dates | UCORPNLD060 | NETHERLANDS_WEENA_Circuit_1 | [14 empty] | 1000 |  |  | 2020 | Mar |  | 2020-04-15 | Cost Reduction | [40 empty] | 102214
CKT-I-02-UCORPNLD060-GTT-1 |  | 2 |  | High | Europe | NETHERLANDS | [5 empty] | SNT |  | GTT | GTT |  | GTT/001817225 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Green | 2020-03-18 | 2020-06-30 | Red | 2020-04-01 | 2020-03-31 | Green |  | Pink | Circuit Ordered |  | Check dates | UCORPNLD060 | NETHERLANDS_WEENA_Circuit_2 | [14 empty] | 1000 |  |  | 2020 | Mar |  | 2020-04-15 | Cost Reduction
CKT-I-01-UCORPPOL015-BT-1 | I012495BT1 | 2 |  |  | Europe | POLAND | POLAND_BANINO | 2019_606 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-31 | Red | Not in Unilever's tracker - 20th July 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPPOL015 | POLAND_BANINO |  |  |  |  | UNILEVER POLSKA SA. ODDZIA LODW I PRODUKTW MRO | [9 empty] | 30 |  |  | 2020 | Mar | [26 empty] | Damian Dabros | Damian Dabros | Damian Dabros
CKT-I-02-UCORPPOL015-GTT-1 |  | 2 |  | High | Europe | POLAND | [5 empty] | SNT |  | GTT | GTT |  | GTT/001817212 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPPOL015 | POLAND_BANINO | [14 empty] | 100 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Damian Dabros | Damian Dabros | Damian Dabros | [14 empty] | 97834 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-UCORPPOL013-BT-1 | I011272BT1 | 2 |  |  | Europe | POLAND | POLAND_BYDGOSZCZ | 2019_607 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-16 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPPOL013 | POLAND_BYDGOSZCZ |  |  |  |  | Józefa Ignacego Kraszewskiego, 85-240 | [8 empty] | 15 | 70 |  |  | 2020 | Mar | [26 empty] | Damian Dabros | Damian Dabros | Damian Dabros | [7 empty] | No
CKT-I-02-UCORPPOL013-GTT-1 |  | 2 |  | High | Europe | POLAND | [5 empty] | SNT |  | GTT | GTT |  | GTT/001817199 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPPOL013 | POLAND_BYDGOSZCZ | [14 empty] | 70 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Damian Dabros | Damian Dabros | Damian Dabros | [14 empty] | 97834 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-PL-GRA99-9999-GTT-1 | I0120138GTT1 | 2 |  |  | Europe | POLAND | POLAND_GRABICA_31 WOLA BYKOWSKA | 2019_608 | un-uen-polgra1-pio001 | un-uen-polgra1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001833713 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-06-05 | Red | 2020-04-17 | 2020-09-25 | Red | 01/09: Migration planned for 8th September 21/08: Still waiting for feedback from GTT that issue has been resolved. 16/07 - Follow up with GTT who are still waiting for update from vendor 15/07 - GTT vendor is performing tests and hope to have an update tonight 14/07 - testing failed on Monday 13th - escalated to vendor 10/07 - Gergana confirmed testing resource for Monday 13th July 08/07 - Working towards 13th July and costs being signed off 07/07 - checking with Gergana if this testing was carried as per date and time below 26/06 - Gergana confirmed trying to schedule testing for Friday, 3rd July at 14:00 local time 23/06 - Gergana to propose time that is good 06/07: Circuit still needs to be tested by GTT. 19/05: Eloise suggesting migration takes place w/c 22nd June 04/05 Circuit provider to advise on the status of circuit order & delivery process | Green | Circuit Order Accepted | Circuit Provider |  | PL-GRA99-9999 | POLAND_GRABICA_31 WOLA BYKOWSKA |  |  |  |  | UNILEVER POLAND SERVICES SP. Z O.O. DC1 AGNIESZKA MALINOWSKA(601 316 073) Wola Bykowska 34 | [9 empty] | 20 |  |  | 2020 | Mar | [13 empty] | First Floor. Server Room | 154.14.44.4/30 Network - 154.14.44.4 First usable - 154.14.44.5 Last usable - 154.14.44.6 Broadcast - 154.14.44.7 Subnet Mask - 255.255.255.252 | 154.14.44.5 | 154.14.44.6 |  |  |  | Telnap Telecom Sp. z o.o. | [5 empty] | Fat Nela | Fat Nela | Fat Nela | [18 empty] | CRQ000000708339 | Completed | Completed
CKT-I-01-UCORPPOL014-GTT-1 | I011334GTT1 | 2 |  |  | Europe | POLAND | Kolodziejska Katowice |  | un-uen-polkat1-rtr001 | un-uen-polkat1-vpn002 | Eloise Shepheard | WAN Circuit Migration | Circuit | GTT | GTT |  | GTT/001828583 | 2020-01-31 | 2020-01-31 | complete | 2020-02-05 | 2020-02-07 | complete | 2020-04-05 | 2020-04-17 | complete | 2020-04-17 | 2020-06-16 | complete | 23/06: Migration was successful today 27/05: 2nd of June no longer feasible - looking to reschedule on 16th June 19/05: Eloise suggesting migration takes place w/c 1st June 27/04 Circuit delivered. GTT to schedule a test. | Complete | Circuit Migrated | Cisco |  | UCORPPOL014 | POLAND_KATOWICE | [13 empty] | 50 | 50 |  |  | 2020 | Mar | [8 empty] | FE to arrive 15 minutes prior to migration start time |  |  |  |  | Production building, first floor. Server room | 154.14.53.48/29 Network - 154.14.53.48 First usable - 154.14.53.49 Last usable - 154.14.53.54 Broadcast - 154.14.53.55 Subnet Mask - 255.255.255.248 154.14.50.76/30 Network - 154.14.50.76 First usable - 154.14.50.77 Last usable - 154.14.50.78 Broadcast - 154.14.50.79 Subnet Mask - 255.255.255.252 | 154.14.50.77 | 154.14.50.78 |  |  |  | 3S Spolka Akcyjna | [5 empty] | Damian Dabros | Damian Dabros | Damian Dabros |  |  | Standard site type - Hybrid (MPLS + DMVPN) |  |  |  |  | No |  | Assessment Complete MOP created & config created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 07:00 to 13:00 | 09:00 to 15:00 | 82290 | CRQ000000684193 | Approved |  | CRQ000000674891 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  |  | 2020-05-01
CKT-I-02-UCORPPOL014-UNL-1 | I021334UNL1 | 2 |  |  | Europe | POLAND | POLAND_KATOWICE | 2019_609 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Unilever | Uni |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-11-11 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | UCORPPOL014 | POLAND_KATOWICE |  |  |  |  | UL.KOLODZIEJSKA 2 KATOWICE | [8 empty] | 20 | 50 |  |  | 2020 | Mar | [26 empty] | Damian Dabros | Damian Dabros | Damian Dabros | [7 empty] | No
CKT-I-01-UCORPPOL055-GTT-1 | I029903GTT1 | 2 |  |  | Europe | POLAND | POLAND_KATOWICE_KIE_CENTRUM_BIZNESU_BUILDING | 2019_611 |  |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001963789 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-10-31 | Red | 2020-07-31 | 2020-10-01 | Red | 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT | Check dates | UCORPPOL055 | POLAND_KATOWICE_KIE_CENTRUM_BIZNESU_BUILDING |  |  |  |  | Katowice Business Centre ul. Chorzowska 6, Unilever Poland Services Sp. z o.o. | [9 empty] | 350 |  |  | 2020 | Mar | [14 empty] | 154.14.118.12/30 Network - 154.14.118.12 First usable - 154.14.118.13 Last usable - 154.14.118.14 Broadcast - 154.14.118.15 Subnet Mask - 255.255.255.252 154.14.118.16/29 Network - 154.14.118.16 First usable - 154.14.118.17 Last usable - 154.14.118.22 Broadcast - 154.14.118.23 Subnet Mask - 255.255.255.248 | [11 empty] | Damian Dabros | Damian Dabros | Damian Dabros
CKT-I-01-UCORPPOL016-BT-1 | I011410BT1 | 2 |  |  | Europe | POLAND | POLAND_POZNAN_BALTYCKA | 2019_612 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-16 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPPOL016 | POLAND_POZNAN_BALTYCKA |  |  |  |  | UL. BALTYCKA | [8 empty] | 20Mbps | 100 |  |  | 2020 | Mar | [26 empty] | Damian Dabros | Damian Dabros | Damian Dabros | [7 empty] | No
CKT-I-02-UCORPPOL016-GTT-1 |  | 2 |  | High | Europe | POLAND | [5 empty] | SNT |  | GTT | GTT |  | GTT/001817204 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPPOL016 | POLAND_POZNAN_BALTYCKA | [14 empty] | 100 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [40 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-UCORPROM002-BT-1 | I015083BT1 | 2 |  |  | Europe | ROMANIA | ROMANIA_PLOIESTI_DEPOT | 2019_623 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  | GTT/001838259 | 2020-05-15 | 2020-05-15 | Red | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-25 | Red | 2020-07-31 | 2020-12-16 | Red | 04/05 Unilever requested to put the order on hold. This order to be cancelled. | On Hold | Circuit not ordered | Circuit Provider |  | UCORPROM002 | ROMANIA_PLOIESTI_DEPOT |  |  |  |  | Ploiesti Depot (Aricesti Warehouse) ,COMMUNE ARICEST RAHTIVANI | [9 empty] | 20 |  |  | 2020 | Mar | [13 empty] | Ground Floor . PBX Room | [12 empty] | Adrian Lazar | Adrian Lazar | Adrian Lazar
CKT-I-02-UCORPROM002-UNL-1 | I025083UNL1 | 2 |  |  | Europe | ROMANIA | ROMANIA_PLOIESTI_DEPOT | 2019_624 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Unilever | Uni |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-12 | Red | 14/07 - Due to new outbreak of Covid 19, Ploiesti depo – Aricesti is closed again so delivery/migration is on hold again. 14/07 - Dusan confirms order for Aricesti Romania (Ploiesti depo) with GTS complete. Deepalk requested Dusan to confirm circuit delivery forecast so can follow up with delivery/migration planning. 07/07 - Circuit Order delayed due to Coronavirus in Warehouse - George.Dulgheru@unilever.com confirmed "We will reschedule the implementation when things are okay…" 18/06 - Dusan confirmed contract with GTS RO will be signed next week from Unilever side and then I will send scan to GTS for signing. After the contract signing GTS will need max 20 days to deliver new link in Aricesti. 11/06 - check with local team 04/05 Unilever to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Unilever SNT |  | UCORPROM002 | ROMANIA_PLOIESTI_DEPOT |  |  |  |  | Ploiesti Depot (Aricesti Warehouse) ,COMMUNE ARICEST RAHTIVANI | [9 empty] | 20 |  |  | 2020 | Mar | [26 empty] | Adrian Lazar | Adrian Lazar | Adrian Lazar
CKT-I-01-UCORPSRB001-BT-1 | I011254BT1 | 2 |  |  | Europe | SERBIA | SERBIA_BELGRADE | 2019_641 | un-uen-serbel1-pio001 | un-uen-serbel1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-09-18 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Green | Circuit not ordered | Circuit Provider |  | UCORPSRB001 | SERBIA_BELGRADE |  |  |  |  | OMLADINSKIH BRIGADA | [8 empty] | 8M | 20 |  |  | 2020 | Mar | [15 empty] | 78.24.111.237 | 78.24.111.238 | 78.24.111.236/30 | [8 empty] | Fat Nela | Fat Nela | Fat Nela |  |  | Standard site type - Hybrid (MPLS + IEN) | Complete |  | No |  | No | No | Assessment Complete MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required) | [8 empty] | CRQ000000710349 | Submitted | Submitted
CKT-I-02-UCORPSRB001-UNL-1 | I021254UNL1 | 2 | MPLS and IEN set up |  | Europe | SERBIA | SERBIA_BELGRADE | 2019_642 | un-uen-serbel1-rtr001 | un-uen-serbel1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | Unilever | Uni |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Complete | 2020-07-19 | 2020-07-20 | Complete | 2020-07-31 | 2020-09-18 | Red | 28/08: Migration re-arranged for following Friday - 4th September 21/08: Migration planned for 28th August 16/07 - waiting for contract to be reviewed and signed on Unilever and local side 09/07 - expected soft upgrade 07/07 - Once signed will need to ask Cisco to update service description and shaper configuration in the router to reflect revised capacity. 07/07 - Contract for Belgrade office is signed from IT011 side and now I’m organizing signing from UL side. When link speed is changed I will let you know. 11/06 - no visibility to CISCO check with local team 04/05 Unilever to advise on the status of circuit order & delivery process | Green | Circuit not ordered | Unilever SNT |  | UCORPSRB001 | SERBIA_BELGRADE |  |  |  |  | OMLADINSKIH BRIGADA | [8 empty] | 4M | 20 |  |  | 2020 | Feb | [15 empty] | 78.24.111.137 | 78.24.111.138 | 78.24.111.136/30 | [8 empty] | Fat Nela | Fat Nela | Fat Nela |  |  | Standard site type - Hybrid (MPLS + IEN) | Complete |  | No |  | Yes | No | Assessment Complete MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required) |  |  |  |  | CHG000000000041653 (OLD) |  |  |  | CRQ000000706346 | Completed | Completed
CKT-I-01-UCORPSVK093-BT-1 | I0110751BT1 | 2 | MPLS - DMVPN Setup |  | Europe | SLOVAKIA | SLOVAKIA_BRATISLAVA_HEAD_OFFICE | 2018_215 | un-uen-svkbra1-rtr001 |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-12-07 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPSVK093 | SLOVAKIA_BRATISLAVA_HEAD_OFFICE |  |  |  |  | Unilever Slovensko, spol. s r.o. Karadžičova 10, | [8 empty] | 10M | 100 |  |  | 2020 | Mar | [26 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar | [7 empty] | No
CKT-I-02-UCORPSVK093-ORA-1 | I0210751ORA1 | 2 |  |  | Europe | SLOVAKIA | SLOVAKIA_BRATISLAVA_HEAD_OFFICE | 2019_643 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  | GO0AVE7N22 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-07-01 | Red | 2020-07-19 | 2020-08-26 | Red | 2020-07-31 | 2020-09-25 | Red | 13/06 - email confirmed back to Orange with LCON details 10/06 - email sent to Dusan and Vitezslav for site contact details to be emailed to Mohammed 10/06 - The LDM has advised that the LCON is not correct. Requested that he contact David and Welington to assist - no delivery date from Orange 11/06 - Check with Supplier on order June 2nd: No details in the providers list 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPSVK093 | SLOVAKIA_BRATISLAVA_HEAD_OFFICE |  |  |  |  | Unilever Slovensko, spol. s r.o. Karadžičova 10, | [9 empty] | 100 |  |  | 2020 | Mar
CKT-I-02-ES-BCN04-0001-GTT-1 | I029610GTT1 | 2 |  |  | Europe | SPAIN | BCN-Viladecans HO |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001827261 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-06-26 | Complete | 26/06: Migration successful on 26th June 05/06: Migration had to be postpone due to issue with the line | Complete | Circuit Migrated |  |  | ES-BCN04-0001 | SPAIN_BARCELONA_VILADECANS_HEAD_OFFICE | [14 empty] | 200 |  |  | 2020 | Feb | [7 empty] | 15:00 | [31 empty] | Window Date agreed - End user Comms sent |  | 13:00 to 19:00 | 15:00 to 21:00 | 71414 | CRQ000000677850 | Approved | [7 empty] | Circuit Migrated
CKT-I-01-UCORPS028-GTT-1 | I011259GTT1 | 2 | MPLP - DMVPM Setup |  | Europe | SPAIN | SPAIN_BILBAO_LEIOA_FACTORY | 2019_645 | un-uen-espbil1-rtr001 |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001831084 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Amber | 2020-07-04 | 2020-09-30 | Red | 2020-07-17 | 2020-10-01 | Red | 15/07 - highlighted to GTT possible incorrect address but they believe site survey was completed 13/07 - Raul messaged again to check on next suitable date for factory and to confrim what documentation is reqiured 10/07 - No delivery date provided in provider tracker - ES sent follow up email 23/06 - Borja Lopez Arnaiz <borja.lopez@eltec.es> emailed again for details of site access 23/06 - Raul Burgos confirmed site visit to be arranged through Borja Lopez Arnaiz <borja.lopez@eltec.es> 22/06 - email to site and geo-it contacts to find if possible to arrange TRADIA engineer site access to configure radio links 11/06 - Circuit ordered - should arrive 30th June 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Ordered | Circuit Provider | Check dates | UCORPS028 | SPAIN_BILBAO_LEIOA_FACTORY |  |  |  |  | SLOVAKIA | [8 empty] | 6M | 20 |  |  | 2020 | Mar | [14 empty] | 154.14.127.8/29 Network - 154.14.127.8 First usable - 154.14.127.9 Last usable - 154.14.127.14 Broadcast - 154.14.127.15 Subnet Mask - 255.255.255.248 | [5 empty] | TRADIA | [5 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar | [7 empty] | No
CKT-I-02-UCORPS028-VOD-1 | I021259VOD1 | 2 |  |  | Europe | SPAIN | SPAIN_BILBAO_LEIOA_FACTORY | 2019_645 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Vodafone Global | Vod |  | UNIPX-IPQM-00026 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-09-30 | Red | 2020-07-31 | 2020-11-23 | Red | 16/07 - ACTION follow up on address - loop in Hisham 15/07 - Address supplied was incorrect - Correct address supplied 10/07 - not in Vodafone tracker - circuit order not confirmed - Vodafone to confirm why not in tracker as order marked complete 11/06 - Circuit not ordered - check with supplier 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPS028 | SPAIN_BILBAO_LEIOA_FACTORY |  |  |  |  | SLOVAKIA | [9 empty] | 20 |  |  | 2020 | Mar | [26 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar
CKT-I-02-CH-SCH01-0005-GTT-1 |  | 2 | Dual DMVPN set up. |  | Europe | SWITZERLAND | SWITZERLAND_SCHAFFHAUSEN_LANDHAUS | 2019_649 | un-uen-chesch1-vpn002 |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001821750 | 2020-01-31 | 2019-08-13 | Complete | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-06-30 | Red | 2020-04-17 | 2020-12-24 | Red | 4-Feb: Action is Transfer + Transform. | Pink | Circuit Ordered | Circuit Provider |  | CH-SCH01-0005 | SWITZERLAND_SCHAFFHAUSEN_LANDHAUS |  |  |  |  | Spitalstrasse 5 | [8 empty] | 100 | 100 |  |  | 2020 | Mar | [43 empty] | 102214 | [13 empty] | 2020-04-01
CKT-I-02-CH-HHM01-0030-GTT-1 |  | 2 |  | High | Europe | SWITZERLAND | FS6 Steinhausen |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817215 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | CH-HHM01-0030 | SWITZERLAND_STEINHAUSEN |  |  |  |  | Hinterbergstrasse 30 CH-6312 Steinhausen Switzerland (HB50 is a location office with production as HB30 is office) | [9 empty] | 100 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [40 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-UCORPCHE054-BT-1 | I01674BT1 | 2 | MPLS-DMVPN setup |  | Europe | SWITZERLAND | SWITZERLAND_THAYNGEN_BAHNHOFSTRASSE | 2019_651 | un-uen-chetha1-rtr001 |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-11-16 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPCHE054 | SWITZERLAND_THAYNGEN_BAHNHOFSTRASSE |  |  |  |  | BAHNHOFSTRASSE | [8 empty] | 70M | 100 |  |  | 2020 | Mar | [26 empty] | Damian Dabros | Damian Dabros | Damian Dabros | [7 empty] | No
CKT-I-02-UCORPCHE054-GTT-1 | I01674GTT1 | 2 | MPLS-DMVPN setup |  | Europe | SWITZERLAND | SWITZERLAND_THAYNGEN_BAHNHOFSTRASSE |  | un-uen-chetha1-vpn001 |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001831143 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-04-22 | Complete | 2020-04-17 | 2020-05-13 | Complete | 4-Feb: Action is Transfer + Transform. | Complete | Circuit Migrated | Circuit Provider |  | UCORPCHE054 | SWITZERLAND_THAYNGEN_BAHNHOFSTRASSE | [13 empty] | 100 | 100 |  |  | 2020 | Mar | [26 empty] | Damian Dabros | Damian Dabros | Damian Dabros | [7 empty] | No |  |  | Window Date agreed - End user Comms sent |  | 09:30am to 13:30pm | 11:30am to 15:30pm | 64989 | CRQ000000671017 | Approved | [7 empty] | Circuit Migrated - First Time right |  |  |  | 2020-04-01
CKT-I-01-UA-IEV04-0004-UNL-1 | I0112000UNL1 | 2 | Needs to be validated |  | RUB/ TUI&I | UKRAINE | Gostomel - Tea & Soy & Fruit Beverages | 2019_699 | un-uen-ukrhos-vpn001 | un-uen-ukrhos-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | Unilever | Uni |  | ID: 1130849 | 2020-01-31 | 2020-02-07 | Complete | 2020-02-05 | 2020-02-10 | Complete | 2020-04-05 | 2020-04-27 | Complete | 2020-04-17 | 2020-06-10 | Complete | 10/05: Migration was successful 29/05 Migration date confirmed for 10/06. 19/05: Eloise suggesting migration w/c 15th June 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Cisco |  | UA-IEV04-0004 | UKRAINE_HOSTOMEL_141S SVYATO-POKROVSKAYA STREET_TEA FACTORY |  |  |  |  | 141c, Sviato-Pokrovska street | Kiev | 08290 | [7 empty] | 30 |  |  | 2020 | Mar | [7 empty] | 10:00-23:00 | NA | NA | [5 empty] | 83.170.247.173 | 83.170.247.174 | [9 empty] | Rahul Durugkar | Damian Dabros | Damian Dabros | [10 empty] | Window Date agreed - End user Comms not sent |  | 05:00-20:00 | 10:00-23:00 | 76924 | CRQ000000680809 | Approved |  | CRQ000000679128 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  |  | 2020-06-01
CKT-I-02-UA-IEV04-0004-BT-1 | I0212000BT1 | 2 |  |  | RUB/ TUI&I | UKRAINE | UKRAINE_HOSTOMEL_141S SVYATO-POKROVSKAYA STREET_TEA FACTORY | 2019_698 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-07-23 | Red | 2020-07-19 | 2020-11-06 | Red | 2020-07-31 | 2020-12-07 | Red | 20/08: Order placed on 23rd July - expected delivery late October to early November CKT-I-02-UA-IEV04-0004-CTL-1 <-- davids input 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UA-IEV04-0004 | UKRAINE_HOSTOMEL_141S SVYATO-POKROVSKAYA STREET_TEA FACTORY |  |  |  |  | 141c, Sviato-Pokrovska street | Kiev | 08290 | [7 empty] | 30 |  |  | 2020 | Mar | [26 empty] | Rahul Durugkar | Rahul Durugkar | Rahul Durugkar
CKT-I-01-UCORPUKR211-UNL-1 | I012545UNL1 | 2 | Needs to be validated |  | RUB/ TUI&I | UKRAINE | UKRAINE_KIEV_DEGTYAREVSKAYA |  | un-uen-uakiev1-vpn001 | un-uen-uakiev1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | Unilever | Uni |  | ID: 1144084 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-10 | Complete | 2020-04-05 | 2020-04-27 | Complete | 2020-04-17 | 2020-06-10 | Complete | 10/05: Migration was successful 29/05 Migration confirmed for 10/06. 19/05: Eloise suggesting migration week w/c 8th June 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Cisco |  | UCORPUKR211 | UKRAINE_KIEV_DEGTYAREVSKAYA |  |  |  |  | DEGTYAREVSKAYA STR | [9 empty] | 50 |  |  | 2020 | Mar | [7 empty] | 10:00-23:00 | NA | NA | [5 empty] | 94.153.218.17/29 | 94.153.218.18/29 | [9 empty] | Rahul Durugkar | Damian Dabros | Damian Dabros | [10 empty] | Window Date agreed - End user Comms not sent |  | 05:00-20:00 | 10:00-23:00 | 76909 | CRQ000000680654 | Approved |  | CRQ000000679036 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  |  | 2020-06-01
CKT-I-02-UCORPUKR211-BT-1 | I022545BT1 | 2 | No access to the device. |  | RUB/ TUI&I | UKRAINE | UKRAINE_KIEV_DEGTYAREVSKAYA | 2019_700 | un-uen-uakier1 |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-09-30 | Red | 20/08: Order placed on 23rd July - expected delivery late October to early November 06/08: Artem sending email - last mile provided has started work at this site CKT-I-02-UCORPUKR211-CTL-1 <-- davids input 04/05 Circuit provider to advise on the status of circuit order & delivery process | Green | Circuit not ordered | Circuit Provider |  | UCORPUKR211 | UKRAINE_KIEV_DEGTYAREVSKAYA |  |  |  |  | DEGTYAREVSKAYA STR | [9 empty] | 50 |  |  | 2020 | Mar | [26 empty] | Fat Nela
CKT-I-02-GB-BHK01-0002-CTL-1 | I029987CTL1 | 2 | Detailed discussion needed, Aga to set it up alongwith Adrian |  | Europe | UNITED KINGDOM | Bromborough Data Centre |  | un-uen-isp-gbbmb1 | un-uen-isp-gbbmb1 | Eloise Shepheard | WAN Circuit Migration |  | CenturyLink | CL |  | 442116925 336618122 - DIA 336618123 - Access 336618124 - Logical 336618125 - Port | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-15 | Complete | 2020-04-17 | 2020-08-20 | Complete | 21/08: Migration successful 16/07 - Graham Yates confirmed circut completion note handed over today and circuit now ready for testing / migration 10/07 - IP config has a dependency on queries relating to BGP that have been put to Cisco/Unilever - once answers are provided and config completed connection will be ready for activation. 08/07 - Zyad to confirm outcome of meeting on Monday 6th and CTL provisioning engineer has/is setting up the config. 02/07 - on-going discussion around BGP routing and configuration between Graham Yates (CenturyLink) and Matt Barber (Cisco) 01/07 - still outstanding information for IP config - and BGP routing protocol 29/06 - Matt Barber responded to Graham Yates - Graham checking with his team that it is what is required. 26/06 - Graham Yates requesting additional information for the IP requirements and specifically around BGP set up. Passed to Cisco for review and comment - pending feedback 25/06 - email from Graham that CenturyLink received formal handover from BT Openreach this morning and they can now proceed to complete end to end circuit build and they will inform of circuit activation hopefully early July 24/06 - Local loop work complete and BT having issues handing over to CenturyLink - only IP configs pending on CenturyLink side 16/06 - Confirmation now received that BT OR completed the fit and test activity on 11/06 and are pending resolution of system issues to be able to hand the connection over - once this is received Centurylink will work to have the connection ready for activation ASAP 15/06 - Graham Yates @ CenturyLInk confirmed BT OR fibre work completed as planned but they didn’t complete “fit and test” before handover to Centurylink, this will be scheduled for later date and involve an OR engineer on site to connect their termination equipment to the fibres and test back through the circuit. Will let you know when we expect this activity to proceed. 11/06 - should be getting delivered today 08/06 - working to get circuit delivery completed on Thursday 11/06 June 1st: Required RAMS analysis from Local Site Contact to proceed 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | GB-BHK01-0002 | UK_BROMBOROUGH_DATACENTRE |  |  |  |  | Unit 2 Georgia Avenue, Wirral International Business Park Bromborough, CH62 3RG | Bromborough | CH62 3RG |  | Kim Newton | Kim.Newton@unilever.com | +44 (0) 7557 986245 |  |  |  | 1000 | 53.3383 | -2.9745 | 2020 | Mar | [14 empty] | WAN: 212.187.136.108/30 CTL: 212.187.136.109 UNI: 212.187.136.110 | 212.187.136.109 | 212.187.136.110 | [9 empty] | Arijon Alija | Arijon Alija | Arijon Alija |  |  | Complex site type - requires redesign | [6 empty] | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 22:00 to 02:00 | 23:00 to 03:00am | 114752 | CRQ000000701846 / CRQ000000698012 | Approved |  | CRQ000000702151 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-UCORPGBR314-BT-1 | I011270BT1 | 2 |  |  | Europe | UNITED KINGDOM | UK_BURTON_ON_TRENT_FACTORY | 2019_676 | un-uen-gbrbur1-rtr001 | un-uen-gbrbur1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-09-18 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGBR314 | UK_BURTON_ON_TRENT_FACTORY |  |  |  |  | WELLINGTON ROAD | [9 empty] | 40 |  |  | 2020 | Mar | [15 empty] | 195.99.26.152 | 195.99.26.153 | 195.171.209.40/29 | [9 empty] | Fat Nela | Fat Nela | [18 empty] | CRQ000000709669 | In Progress | Completed
CKT-I-02-UCORPGBR314-GTT-1 |  | 2 |  | High | Europe | UNITED KINGDOM | UK_BURTON_ON_TRENT_FACTORY |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817226 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPGBR314 | UK_BURTON_ON_TRENT_FACTORY |  |  |  |  | WELLINGTON ROAD | [9 empty] | 40 |  |  | 2020 | Apr |  | 2020-05-14 | Cost Reduction | [23 empty] | Fat Nela | Fat Nela | Fat Nela | [14 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-02-GB-SRK01-0102-VOD-1 | I02689VOD1 | 2 |  |  | Europe | UNITED KINGDOM | UK_COLWORTH_RESEARCH_LABORATORY | 2018_279 | un-uen-gbrcol1-rtr001 | un-uen-gbrcol1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | Vodafone Local | Vod |  | 3C04084369 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-22 | Amber | 2020-07-31 | 2020-09-04 | Red | 21/08; Migration agreed for 4th September 17/07 - Covid form returned and confirmed for 9am slot on 22nd July 16/07 - Engineer details confirmed as Name: Allan Page / E-Mail: allan.page@vodafone.com / Mobile Number: +447714837930 - Covid form still to be filled in 16/07 - email sent to Mohammed Hisham to check that delivery will be on 22nd July and not 20th July 16/07 - installation pushed to 22nd July 09/07 - Jacob Masih R&D site 22/06 - email sent to Cisco to find out if there is resilience on site now that GTT circuit is active 11/06 - check with supplier on circuit order status 04/05 Circuit provider to advise on the status of circuit order & delivery process | Green | Circuit not ordered | Circuit Provider |  | GB-SRK01-0102 | UK_COLWORTH_RESEARCH_LABORATORY |  |  |  |  | Colworth Science Park, Sharnbrook, Bedfordshire, MK44 1LQ | Colworth | MK44 1LQ |  | Jacob Masih | Jacob.Masih@unilever.com | +44 (0) 7824 538699 |  |  | 50M | 200 | 52.2299 | -0.55971 | 2020 | Mar | [14 empty] | Cust WAN IP and subnet Customer IP: 217.161.92.166 VF WAN IP and subnet 217.161.92.164/30 Cust Lan range and subnet Vodafone IP: 217.161.92.165 | 217.161.92.165 | 217.161.92.166 | [9 empty] | Lalhmunsanga Fanai | Fat Nela | Fat Nela |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  | No |  |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved |  |  |  |  | CHG000000000041642 |  |  |  | CRQ000000701822 | Completed | Completed
CKT-I-01-UCORPGBR316-GTT-1 |  | 2 |  | High | Europe | UNITED KINGDOM | UK_CRUMLIN_FACTORY_CROESPENMAEN_INDUSTRIAL_ESTATE |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817207 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPGBR316 | UK_CRUMLIN_FACTORY_CROESPENMAEN_INDUSTRIAL_ESTATE |  |  |  |  | CROESPENMAEN INDUSTRIAL ESTATE | [9 empty] | 20 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Arijon Alija | Arijon Alija | Arijon Alija | [14 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-02-UCORPGBR316-BT-1 | I021287BT1 | 2 |  |  | Europe | UNITED KINGDOM | UK_CRUMLIN_FACTORY_CROESPENMAEN_INDUSTRIAL_ESTATE | 2019_679 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-11-16 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGBR316 | UK_CRUMLIN_FACTORY_CROESPENMAEN_INDUSTRIAL_ESTATE |  |  |  |  | CROESPENMAEN INDUSTRIAL ESTATE | [9 empty] | 20 |  |  | 2020 | Mar | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-01-UCORPGBR060-GTT-1 | I011304GTT1 | 2 |  |  | Europe | UNITED KINGDOM | UK_FOUR_ACRES_MANAGEMENT_CENTRE | 2018_281 |  |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001828570 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-12-31 | Red | 2020-04-17 | 2020-09-24 | Red | "10/07 - still pending on-site resources from Unilever - no supplier delivery date 07/07 - Confirmed to Gergana that this is on-hold until Unilever travel restrictions eased 29/06 - Escalated through Thyago for arranging on-site support 24/06 - Paul confirmed wont be possible to access site until Unilever's restrictions on using Public Transport are relaxed. Gergana is cc'd on this email 23/06 - email Gergana to Patrick Major / Paul Bentley - confirming better for someone to be on site to host GTT engineer. Gergana requested Paul to provide a list of possible dates for Circuit Delivery 22/06 - email sent to Partick and Paul Bentley to find out if there are photos and if they can provide dates to support and engineer visit to site so they can setup their ADVA and test? 22/06 - Major, Patrick <Patrick.Major@unilever.com> confirmed he believes there is space 17/06 - Gergana confirmed that have no info on whether there is spare fibre. As it is “quick win” fibre is already in place. Normally 1U rack space is needed to install their ADVA unit with power available and at least one other power socket for engineer test device 16/06 - Emails sent to Paul Bentley as Geo-IT Contact for Four Acres to check on engineer access to site and comms room" 04/05 Circuit provider to advise on the status of circuit order & delivery process | On Hold | Circuit Ordered | Circuit Provider | Check dates | UCORPGBR060 | UK_KINGSTON UPON THAMES_GEORGE ROAD_FOUR ACRES LONDON | [14 empty] | 20 |  |  | 2020 | Mar | [13 empty] | Ground Floor. MER | 154.14.45.200/30 Network - 154.14.45.200 First usable - 154.14.45.201 Last usable - 154.14.45.202 Broadcast - 154.14.45.203 Subnet Mask - 255.255.255.252 | [5 empty] | TalkTalk | [5 empty] | Ragu Bangaru | Fat Nela | Fat Nela
CKT-I-02-UCORPGBR060-VOD-1 | I021304VOD1 | 2 |  |  | Europe | UNITED KINGDOM | UK_FOUR_ACRES_MANAGEMENT_CENTRE | 2019_682 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Vodafone Local | Vod |  | 3C04084611 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-09-30 | Red | 2020-07-31 | 2020-11-23 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGBR060 | UK_KINGSTON UPON THAMES_GEORGE ROAD_FOUR ACRES LONDON | [14 empty] | 20 |  |  | 2020 | Mar | [26 empty] | Ragu Bangaru | Fat Nela | Fat Nela
CKT-I-01-UCORPGBR142-BT-1 | I011313BT1 | 2 |  |  | Europe | UNITED KINGDOM | UK_GLOUCESTER_FACTORY | 2019_680 | un-uen-gbrglo1-rtr001 | un-uen-gbrglo1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  | FTIP005670826 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-08-10 | Red | 2020-07-31 | 2020-09-11 | Red | 21/08: Circuit delivery. Testing needs to be scheduled. 04/05 Circuit provider to advise on the status of circuit order & delivery process | Green | Circuit not ordered | Circuit Provider |  | UCORPGBR142 | UK_GLOUCESTER_FACTORY |  |  |  |  | Walls House,CORINIUM AVENUE, Barnwwood, Gloucester, GL4 3BW | [8 empty] | 15MB | 40 |  |  | 2020 | Mar | [14 empty] | CE WAN INTERFACE IPV4 ADDRESS: 194.75.219.247/31 PE WAN INTERFACE IPV4 ADDRESS: 194.75.219.246/31 LAN IP - 194.73.106.152/ 29 | 194.75.219.247/31 | 194.75.219.246/31 | 194.73.106.152/29 | [8 empty] | Arijon Alija | Arijon Alija | Arijon Alija |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress |  | No |  |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) |  |  |  |  | CHG000000000042117 |  |  |  | CRQ000000708509 | Completed | Completed
CKT-I-02-UCORPGBR142-GTT-1 |  | 2 |  | High | Europe | UNITED KINGDOM | UK_GLOUCESTER_FACTORY |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817206 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPGBR142 | UK_GLOUCESTER_FACTORY | [14 empty] | 40 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Arijon Alija | Arijon Alija | Arijon Alija | [14 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-UCORPGBR078-PCCW-1 | I01706PCCW1 | 2 |  |  | Europe | UNITED KINGDOM | UK_KINGSTON_HEAD_OFFICE_ST_JAMES_ROAD | 2019_683 | un-uen-gbrkin1-rtr001 | un-uen-gbrkin1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | PCCW | PCCW |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-09-22 | Red | 10/07 - pending site access through Unilever - ON HOLD 29/06 - Escalated through Thyago for arranging on-site support 24/06 - Candy confirmed she will put the order on hold until hears back from Unilever 24/06 - Candy sent email update on the point below 24/06 - Paul confirmed wont be possible to access site until Unilever's restrictions on using Public Transport are relaxed. 23/06 - Candy is checking with local supplier to confirm details 23/06 - Paul Bentley cofirmed he may not be allowed to travel to site as has to use Public Transport 23/06 - Candy confirmed local supplier (BT) has requested access to the site on Monday June 29th 11/06 - possibly migration late August 05/06 - telephone call off Candy confirming she had contacted local suppliers with details provided 04/06 - email to Paul.Bentley@unilever.com; Peter.Laird@unilever.com for details requested by Candy Chabanel PCCW 04/06 - email from Chabanel, Candy <cchabanel@pccwglobal.com> confirming receipt of order June 2nd: Not found on providers list 04/05 Circuit provider to advise on the status of circuit order & delivery process | Green | Circuit not ordered | Circuit Provider |  | UCORPGBR078 | UK_KINGSTON_HEAD_OFFICE_ST_JAMES_ROAD |  |  |  |  | Unilever House, 3 St James Road | [9 empty] | 200 |  |  | 2020 | Apr | [14 empty] | 63.218.55.25/29 PCCW 63.218.55.26/29 customer | 63.218.55.25/29 | 63.218.55.26/29 | [9 empty] | Fat Nela | Fat Nela | Fat Nela |  |  | Complex site type - requires redesign | [15 empty] | CRQ000000708845 | Completed | Completed
CKT-I-02-UCORPGBR078-GTT-1 |  | 2 |  | High | Europe | UNITED KINGDOM | UK_KINGSTON_HEAD_OFFICE_ST_JAMES_ROAD |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817218 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPGBR078 | UK_KINGSTON_HEAD_OFFICE_ST_JAMES_ROAD |  |  |  |  | Unilever House, 3 St James Road | [9 empty] | 200 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Fat Nela | Fat Nela | Fat Nela | [14 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-02-GB-LEH01-0001-PCCW-1 | I023745PCCW1 | 2 |  |  | Europe | UNITED KINGDOM | UK_LEATHERHEAD | 2019_685 | un-uen-gbrlea1-rtr001 | un-uen-gbrlea1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | PCCW | PCCW |  | N/A | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Complete | 2020-07-19 | 2020-07-20 | Complete | 2020-07-31 | 2020-08-28 | Complete | 28/08: Migration is successful 21/08: Migration on track for 28th August 16/07 - SFP confirmed delivered at exchange so PCCW expecing handover 17/06 or 20/06 09/07 - installation of fibre last week so going back to install new SFP w/c 13th July 02/07 - circuit delivery still in progress as of 15:45 - Candy waiting for update on 03/07 01/07 - Josh confrimed that BT Openreach can be support on site tomorrow 29/06 - Candy confirmed to Josh that BT Openreach want to come to site on July 2nd to complete fibre works 25/06 - Candy confirmed will re-arrange 24/06 - email from Candy - supplier requesting site access Friday 26th June to complete the fibre works - Josh is on leave so email sent to Candy asking her to request date with supplier on site during next week. 11/06 - possibly migration late August? 05/06 - telephone call off Candy confirming she had contacted local suppliers with details provided 04/06 - email to Josh.Mackinnon@unilever.com for details requested by Candy Chabanel PCCW 04/06 - email from Chabanel, Candy <cchabanel@pccwglobal.com> confirming receipt of order June 2nd: Not found on providers list 04/05 Circuit provider to advise on the status of circuit order & delivery process | Complete | Circuit Migrated | Circuit Provider |  | GB-LEH01-0001 | UK_LEATHERHEAD |  |  |  |  | Unilever House, Springfield Drive, Leatherhead, KT22 7GR | Leatherhead | KT22 7GR |  | Josh Mackinnon | Josh.Mackinnon@unilever.com | +44 (0) 7342 063818 |  |  | 70M | 400 | 51.2964 | -0.32942 | 2020 | Apr | [15 empty] | 63.218.55.201/30 | 63.218.55.202/30 | 207.226.50.0/29 | [8 empty] | Arijon Alija | Arijon Alija | Arijon Alija |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  | Yes |  |  | No | Assessment Complete CMSP ticket raised MOP created & config created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 09:00am to 17:00 | 10:00 to 18:00 | 118256 | CRQ000000704621 | Approved |  | CRQ000000703821 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-UCORPGBR327-GTT-1 | I012897GTT1 | 2 | MPLS -Dual PIO site |  | Europe | UNITED KINGDOM | UK_LONDON_100VE | 2018_285 | un-uen-gbrlon1-pio001 | un-uen-gbrlon1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001828523 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-07-06 | Red | 2020-04-17 | 2020-09-14 | Red | 6/07 - Planned for 22nd July 09:00 local time - Greg Fowler confirmed he will arrange site access - Engineer to confirm they are Covid safe 15/07 - ES sent mail to Greg Fowler regarding testing on 22nd July - Greg to reply 08/07 - Possibly last site for Unilever to open - Greg not allowed to travel so FE required 06/07 - Circuit Handed Over - Cease alarm raised for 4th Oct 2020 so needs to be tested and migrated before then 01/07 - vendor handed over to GTT and GTT now need couple of days to complete internal works 17/06 - Greg Fowler has arranged site access for BT Openreach on 29th June for Circuit Delivery 16/06 - Gergana confirmed BT OR have scheduled fibre install for 29th June - Greg.Fowler@unilever.com emailed to see if we can work to that date. 16/06 - Paul Bentley and Josh MacKinnon emailed to confirm if it is possible to get site access post Covid 06/07: Circuit has been delivered. Email sent regarding testing. 04/05 Order on-hold due to covid-19 | Green | Circuit Ordered | Circuit Provider |  | UCORPGBR327 | UK_LONDON_100VE |  |  |  |  | VICTORIA EMBANKMENT | [8 empty] | 1000M | 1000 |  |  | 2020 | Mar | [13 empty] | Level -3. MER -3 Cabinet E2 | "154.14.53.24/30 Network - 154.14.53.24 First usable - 154.14.53.25 Last usable - 154.14.53.26 Broadcast - 154.14.53.27 Subnet Mask - 255.255.255.252 154.14.53.32/29 Network - 154.14.53.32 First usable - 154.14.53.33 Last usable - 154.14.53.38 Broadcast - 154.14.53.39 Subnet Mask - 255.255.255.248" | 154.14.53.25 | 154.14.53.26 | 154.14.53.32/29 |  |  | Openreach | [6 empty] | Fat Nela | Fat Nela |  |  | Complex site type - requires redesign | In Progress | [14 empty] | CRQ000000709478 | In Progress | Completed
CKT-I-02-UCORPGBR327-CTL-1 | I022897CTL1 | 2 | MPLS -Dual PIO site |  | Europe | UNITED KINGDOM | UK_LONDON_100VE | 2018_286 | un-uen-gbrlon1-pio002 | un-uen-gbrlon1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | CenturyLink | CL |  | 442235155 336973569 - DIA 336973570 - Access 336973571 - IP Logical 336973572 - IP Port | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-01 | Red | 10/07 - Pending feedback from site survey - Follow up with CTL 01/07 - survey completed yesterday - waiting for feedback 26/06 - Graham confirmed new FE details and Covid cleared 26/06 - Greg Fowler confrimed back to Graham Yates that Monday is ok and he will let security know 25/06 - Graham Yates confirmed he has booked FE for Monday 29th June for fibre survey 24/06 - Graham Yates confirmed that Vodafone had tried to contact Paul to arrange site survey visit and left Paul a voice mail - requested Paul gets back in touch with Vodafone or lets him know if he needs support getting back to them. 23/06 - Graham Yates checked with Paul Bentley regards date in June to for Vodafone to attend site - Paul confirmed to pencil in 24th August overall delivery mid-sept maybe 17/06 - Graham Yates has confired to Vodafone that they could have site access on 29th June - pending if they can meet the date 11/06 - Circuit ordered - should arrive 20th July - migration August June 1st: Design phase due new capacity required - no ETA for circuit delivery 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Ordered | Circuit Provider |  | UCORPGBR327 | UK_LONDON_100VE |  |  |  |  | VICTORIA EMBANKMENT | [8 empty] | 1000M | 1000 |  |  | 2020 | Mar | [27 empty] | Fat Nela | Fat Nela |  |  | Complex site type - requires redesign | In Progress
CKT-I-01-UCORPGBR332-BT-1 | I015068BT1 | 2 |  |  | Europe | UNITED KINGDOM | UK_LONDON_16 CHARLES II STREET_UNILEVER VENTURES | 2018_289 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-11-16 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGBR332 | UK_LONDON_16 CHARLES II STREET_UNILEVER VENTURES |  |  |  |  | CHARLES II STREET | [9 empty] | 20 |  |  | 2020 | Mar | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-02-UCORPGBR332-GTT-1 |  | 2 |  | High | Europe | UNITED KINGDOM | UK_LONDON_16 CHARLES II STREET_UNILEVER VENTURES |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817210 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPGBR332 | UK_LONDON_16 CHARLES II STREET_UNILEVER VENTURES |  |  |  |  | CHARLES II STREET | [9 empty] | 20 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Arijon Alija | Arijon Alija | Arijon Alija | [14 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-UCORPGBR367-GTT-1 | I0110636GTT1 | 2 | Dual Pio Site |  | Europe | UNITED KINGDOM | UK_LONDON_BUCKLEY_BUILDING |  | un-uen-gbrbuc1-pio001 | un-uen-gbrbuc1-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001828517 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-06-27 | Complete | 2020-04-17 | 2020-07-20 | Complete | 20/7: Migration successful 15/07 - ES sent email to DM requesting if End User Comms required 07/07 - David Moore confirmed ok for FE to attend site on 20th July for migration 06/07 - Cisco engineer able to support migration on 20th July – David Moore to advise if you require a field engineer. 02/07 - David Moore and Eloise working towards Monday 13th July or Monday 20th July 02/07 - Gergana confirmed circuit testing successful - David Moore / Eloise emailed to propose migraiton dates 29/06 - GTT Confirmed 2nd July, 09:00 and access needed for Paul Wade, phone number 07976 291891 25/06 - Gergana confirmed she has requested resources for 2nd July, 09:00 am local time but awaiting confirmation 24/06 - David Moore confirmed over email to Gergana that next available date to attend site Thursday 2nd July between 08.00-12.00 24/06 - Gergana contacted local site contacts Moore, David <David.Moore@unilever.com>; David.Szladek@unilever.com directly to see if they can provide site access for engineer to test line. 23/06 - Greg confirmed Field Engineer would be required to support testing - Greg has been asked to confirm if he is allowed to attend site and then provide a list of possible dates so GTT can work to secure field engineer 23/06 - GTT confirmed circuit is delivered and needs testing - DC sent email to Greg Fowler to confirm dates and if engineer needed to support 22/06 - email sent to GTT to confirm status of circuit and next steps 22/06 - need to follow up with GTT to confirm this circuit has been delivered and needs testing 10/06 - Greg.Fowler@unilever.com - spoke to facilities manage at Pitch who was contacted on 29th April for site access. Came on 4th May but he was told it was only for site survey. Not sure if line was delivered at the same time. 04/05 Order on hold due to covid-19 | Complete | Circuit Migrated | Circuit Provider |  | UCORPGBR367 | UK_LONDON_BUCKLEY_BUILDING | [13 empty] | 100M | 100 |  |  | 2020 | Mar | [7 empty] | 09:00am to 15:00pm | [5 empty] | Lower Ground. MER Lower Ground | 154.14.53.40/29 Network - 154.14.53.40 First usable - 154.14.53.41 Last usable - 154.14.53.46 Broadcast - 154.14.53.47 Subnet Mask - 255.255.255.248 154.14.53.28/30 Network - 154.14.53.28 First usable - 154.14.53.29 Last usable - 154.14.53.30 Broadcast - 154.14.53.31 Subnet Mask - 255.255.255.252 | 154.14.53.29 | 154.14.53.30 | 154.14.53.40/29 |  |  | Openreach | [5 empty] | Arijon Alija | Arijon Alija | Arijon Alija | [10 empty] | Window Date agreed - End user Comms sent |  | 08:00 to 14:00 | 09:00am to 15:00pm | 102018 | CRQ000000692519 | Approved |  | CRQ000000691448 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
I0210636BT1 | I0210636BT1 | 2 |  |  | Europe | UNITED KINGDOM | UK_LONDON_BUCKLEY_BUILDING | 2018_288 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-06-19 | 2020-06-19 | Complete | 2020-06-24 | 2020-06-24 | Green | 2020-08-23 | 2020-10-17 | Red | 2020-09-04 | 2021-01-01 | Red | Not in Unilever's tracker - 20th July 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit Ordered | Circuit Provider |  | UCORPGBR367 | UK_LONDON_BUCKLEY_BUILDING |  |  |  |  | The Buckley Building, 49 Clerkenwell Green | [9 empty] | 100 |  |  | 2020 | Mar | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-01-UCORPGBR334-BT-1 | I012363BT1 | 2 |  |  | Europe | UNITED KINGDOM | UK_SLOUGH_RIDING COURT ROAD_WINDSOR BEN AND JERRYS | 2019_693 | un-uen-gbrwin1-rtr001 | un-uen-gbrwin1-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-09-18 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGBR334 | UK_SLOUGH_RIDING COURT ROAD_WINDSOR BEN AND JERRYS |  |  |  |  | The Barn,RIDING COURT ROAD | [8 empty] | 4 | 40 |  |  | 2020 | Mar | [14 empty] | PE WAN IP: 195.99.26.142/31 CE WAN IP: 195.99.26.143 IP Address: 62.172.79.120/29 | 195.99.26.142/31 | 195.99.26.143 | 62.172.79.120/29 | [8 empty] | Adam Taracha | Fat Nela | Fat Nela |  |  | Standard site type - Hybrid (MPLS + DMVPN) |  |  |  | Yes |  |  | Assessment Complete | [8 empty] | CRQ000000709725 | In Progress | Completed
CKT-I-02-UCORPGBR334-GTT-1 |  | 2 |  | High | Europe | UNITED KINGDOM | UK_SLOUGH_RIDING COURT ROAD_WINDSOR BEN AND JERRYS |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817203 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPGBR334 | UK_SLOUGH_RIDING COURT ROAD_WINDSOR BEN AND JERRYS |  |  |  |  | The Barn,RIDING COURT ROAD | [9 empty] | 40 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Fat Nela | Fat Nela | Fat Nela | [14 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-UCORPGBR157-BT-1 | I01733BT1 | 2 |  |  | Europe | UNITED KINGDOM | UK_TRAFFORD_PARK_FACTORY | 2019_694 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-09-21 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGBR157 | UK_TRAFFORD_PARK_FACTORY |  |  |  |  | TRAFFORD PARK ROAD | [9 empty] | 40 |  |  | 2020 | Mar | [26 empty] | Arijon Alija | Arijon Alija | Arijon Alija
CKT-I-02-UCORPGBR157-GTT-1 |  | 2 |  | High | Europe | UNITED KINGDOM | UK_TRAFFORD_PARK_FACTORY |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817202 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPGBR157 | UK_TRAFFORD_PARK_FACTORY |  |  |  |  | TRAFFORD PARK ROAD | [9 empty] | 40 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Arijon Alija | Arijon Alija | Arijon Alija | [14 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-UCORPGBR111-BT-1 | I011473BT1 | 2 |  |  | Europe | UNITED KINGDOM | UK_WARRINGTON_LIVERPOOL_ROAD_FACTORY | 2019_697 |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-11-16 | Red | 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPGBR111 | UK_WARRINGTON_LIVERPOOL_ROAD_FACTORY |  |  |  |  | LIVERPOOL ROAD | [9 empty] | 40 |  |  | 2020 | Mar | [26 empty] | Fat Nela | Fat Nela | Fat Nela
CKT-I-02-UCORPGBR111-GTT-1 |  | 2 |  | High | Europe | UNITED KINGDOM | UK_WARRINGTON_LIVERPOOL_ROAD_FACTORY |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817201 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPGBR111 | UK_WARRINGTON_LIVERPOOL_ROAD_FACTORY |  |  |  |  | LIVERPOOL ROAD | [9 empty] | 40 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Fat Nela | Fat Nela | Fat Nela | [14 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-UCORPARG059-BT-1 | I019699BT1 | 2 |  |  | Latin America | Argentina | Fatima Monumental | 2019_1 | un-ula-argfat1-drt001 | un-ula-argfat1-vpn002 | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-15 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPARG059 | ARGENTINA_BUENOS_AIRES_FATIMA_MONUMENTAL |  |  |  |  | COLECTORA RUTA NACIONAL 8 | [8 empty] | 20Mb | 20 |  |  | 2020 | Apr | [26 empty] | Rene Gonzalez Iniguez | [8 empty] | Yes
CKT-I-02-UCORPARG059-CTL-1 | I029699CTL1 | 2 |  |  | Latin America | Argentina | Fatima Monumental | 2019_1 | un-ula-argfat1-vpn001 | un-ula-argfat1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2007081273CA5 - Access FRO2007081274CAP - Port FRO2007081260DIR - Service | 2020-01-31 | 2020-03-09 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-05-22 | Complete | 2020-04-17 | 2020-08-14 | Complete | 15-Aug: Migration successful. 31-Jul: To keep diversity, this new CTL circuit will replace the existing CTL circuit. Migration approved for August 14th at 10AM. 27-Jul: Deepak looking to change last mile provider, since previous BT circuit also uses CTL. 26-Jun: Circuit testing successful. Pending approval on migration date. There might be an issue with circuit installation (same ADVA for old and new circuit). 12-Jun: Circuit to be tested on June 19th at 2PM. 28-May: Circuit delivered. Pending circuit testing. 30-Apr: Pending circuit delivery. | Complete | Circuit Migrated | Unilever Geo-IT |  | UCORPARG059 | ARGENTINA_BUENOS_AIRES_FATIMA_MONUMENTAL |  |  |  |  | COLECTORA RUTA NACIONAL 8 | [8 empty] | 20Mb | 20 |  |  | 2020 | Mar | [14 empty] | WAN: 64.210.69.248/30 CTL: 64.210.69.249 UNI: 64.210.69.250 | 64.210.69.249 | 64.210.69.250 | 146.82.228.112/29 | [8 empty] | Rene Gonzalez Iniguez | [11 empty] | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  |  |  | 111528 | CRQ000000699397 | Approved |  | CRQ000000701027 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right
CKT-I-02-5098-CTL-1 | I025098CTL1 | 2 |  |  | Latin America | Argentina | Bouchard - Argentina Head Office | 2019_2 | un-ula-argmar1-rtr001 | un-ula-argmar1-vpn002 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-01-31 | 2020-03-09 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-15 | Complete | 2020-04-17 | 2020-08-10 | Complete | 10-Aug: Migration successful. 27-Jul: Migration approved for August 10th at 9AM. 27-Jul: Site also called Martinez and Munro. 30-Apr: Pending circuit delivery. 23-Mar; Renamed the circuit and site name | Complete | Circuit Migrated | Circuit Provider |  | AR-BUE04-0001 | ARGENTINA_BUENOS_AIRES_HEAD_OFFICE | [13 empty] | 90Mb | 230 |  |  | 2020 | Mar | [14 empty] | WAN: 8.243.7.224/30 CTL: 8.243.7.225 UNI: 8.243.7.226 | 8.243.7.225 | 8.243.7.226 | [9 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress |  | Yes |  | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) |  |  |  |  | 111152 | CRQ000000698460 | Approved |  | CRQ000000696509 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-UCORPARG025-CTL-1 | I015093CTL1 | 2 |  |  | Latin America | Argentina | Pilar | 2019_3 | un-ula-argpil1-vpn001 | un-ula-argpil1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-04-01 | 2020-04-01 | Complete | 2020-04-06 | 2020-04-08 | Complete | 2020-06-05 | 2020-06-24 | Complete | 2020-06-19 | 2020-08-21 | Complete | 24-Aug: Migration successful. 10-Aug: Migration pushed to Aug 21 at 9AM. Pending confirmation. 31-Jul: Migration pushed to August 16th at 9AM. 27-Jul: Migration approved for August 9th. 27-Jul: Circuit test failed. 30-Apr: Pending circuit delivery. | Complete | Circuit Migrated | Circuit Provider |  | UCORPARG025 | ARGENTINA_BUENOS_AIRES_PILAR |  |  |  |  | RUTA 8 - CALLE 8 ENTRE 5 Y 9 - PARQUE INDUSTRIAL PILAR | [8 empty] | 80Mb | 80 |  |  | 2020 | Mar | [14 empty] | WAN: 64.211.1.168/30 CTL: 64.211.1.169/30 UNI: 64.211.1.170/30 64.211.69.224/29 | 64.211.1.169 | 64.211.1.170 | 64.211.69.224/29 | [8 empty] | Rene Gonzalez Iniguez | [11 empty] | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved |  |  |  |  | 111543 | CRQ000000700117 | Approved |  | CRQ000000701047 | Completed | Completed | Tested-Pass | Aug-12: Circuit test results delievered by CTL accepted by Welington. 24-Jul: Test failed. A lot of fluctuations in the speed test. |  | Circuit Migrated - First Time right
CKT-I-02-UCORPARG025-BT-1 | I025093BT1 | 2 |  |  | Latin America | Argentina | Pilar | 2019_3 | un-ula-argpil1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPARG025 | ARGENTINA_BUENOS_AIRES_PILAR |  |  |  |  | RUTA 8 - CALLE 8 ENTRE 5 Y 9 - PARQUE INDUSTRIAL PILAR | [8 empty] | 20Mb | 80 |  |  | 2020 | Apr | [26 empty] | Rene Gonzalez Iniguez | [8 empty] | Yes
CKT-I-01-AR-BUE04-0001-CTL-1 | I015095CTL1 | 2 |  |  | Latin America | Argentina | Planta Tortuguitas | 2019_4 | un-ula-argtort1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2007081495 | 2020-04-01 | 2020-04-01 | Complete | 2020-04-06 | 2020-04-08 | Amber | 2020-06-05 | 2020-07-08 | Red | 2020-06-19 | 2020-10-06 | Red | 28-Aug: Migration scheduled to September 8th. 30-Apr: Pending circuit delivery. | Green | Circuit Ordered | Circuit Provider |  | AR-BUE04-0001 | ARGENTINA_BUENOS_AIRES_TORTUGUITAS |  |  |  |  | DESCARTES 4020 - PARQUE INDUSTRIAL TORTUGUITAS | [8 empty] | 90Mb | 90 |  |  | 2020 | Mar | [14 empty] | LAN: 8.243.7.136/29 WAN: 8.243.7.108/30 CTL: 8.243.7.109 UNI: 8.243.7.110 | 8.243.7.109 | 8.243.7.110 | 8.243.7.136/29 | [8 empty] | Dulce Basilio Gonzalez | Dulce Basilio Gonzalez | Dulce Basilio Gonzalez | [18 empty] | CRQ000000706962 | Completed | Completed
CKT-I-02-AR-BUE04-0001-GTT-1 | I025095GTT1 | 2 |  |  | Latin America | Argentina | Planta Tortuguitas | 2019_4 | un-ula-argtort1-drt001 |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001928480 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Amber | 2020-07-04 | 2020-09-30 | Red | 2020-07-17 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit Ordered | Unilever SNT |  | AR-BUE04-0001 | ARGENTINA_BUENOS_AIRES_TORTUGUITAS |  |  |  |  | DESCARTES 4020 - PARQUE INDUSTRIAL TORTUGUITAS | [8 empty] | 36Mb | 90 |  |  | 2020 | Apr | [26 empty] | Dulce Basilio Gonzalez | Dulce Basilio Gonzalez | Dulce Basilio Gonzalez | [6 empty] | Yes
CKT-I-02-AR-GHU01-0001-CTL-1 | I021846CTL1 | 2 | There is a 3rd Router on the site with a circuit connected to it, UNI_AR_GUAL1_POWDER |  | Latin America | Argentina | Gualeguaychú | 2019_5 | un-ula-arggua1-drt001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit Ordered | Unilever SNT |  | AR-GHU01-0001 | ARGENTINA_GUALEGUAYCHU |  |  |  |  | Parque Industrial, Ruta Nacional 14 acceso sur Gualeguychú | Gualeguaychu | 2820 |  |  |  |  | Ricardo Caldes | Ricardo.caldes@unilever.com | 8Mb | 30 | -33.0564 | -58.4694 | 2020 | Apr | [26 empty] | Rene Gonzalez Iniguez | [8 empty] | Yes
CKT-I-02-AR-MDZ01-1015-CTL-1 | I021848CTL1 | 2 |  |  | Latin America | Argentina | Plante Mendoza | 2019_8 | un-ula-argmen1-pio001 | un-ula-argmen1-vpn002 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-04-01 | 2020-04-01 | Complete | 2020-04-06 | 2020-04-08 | Complete | 2020-06-05 | 2020-06-17 | Complete | 2020-06-19 | 2020-07-24 | Complete | 27-Jul: Migration successful. 13-Jul: Migration approved on July 24th. 8-Jul: Circuit tested successfully. 26-Jun: Pending circuit testing. 30-Apr: Circuit ordered. Pending circuit delivery. Jan-24: Wave-2 circuit. Still not ordered. | Complete | Circuit Migrated | Unilever SNT |  | AR-MDZ01-1015 | ARGENTINA_Mendoza |  |  |  |  | Godoy Cruz 10155, Dpto. Guaymallén | Mendoza | 5525 | [6 empty] | 12Mb | 30 |  |  | 2020 | Mar | [7 empty] | 9AM | [6 empty] | WAN: 204.199.1.0/30 CTL: 204.199.1.1 UNI: 204.199.1.2 | 204.199.1.1 | 204.199.1.2 | [9 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Standard site type - Hybrid (MPLS + IEN) | In Progress | NO | Yes |  | Yes |  | Assessment Complete Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 12hrs UTC | 9AM | 103531 | CRQ000000693124 | Approved |  | CRQ000000693435 | Completed | Completed | Tested -Pass-First Time | 8-Jul: Circuit tested successfully. |  | Circuit Migrated - First Time right
CKT-I-01-UCORPARG022-CTL-1 | I015088CTL1 | 2 |  |  | Latin America | Argentina | Tortuguitas PLN: Centro Distribucion | 2019_10 | un-ula-argpln1-vpn001 | un-ula-argpln1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-04-01 | 2020-04-01 | Complete | 2020-04-06 | 2020-04-08 | Complete | 2020-06-05 | 2020-07-08 | Complete | 2020-06-19 | 2020-09-04 | Complete | 04-Sep: Migration successful. 25-Aug: Sep-04 tentative migration date. 24-Aug: Circuit test successful, but IPs had to be changed. Need to request new Algosec & Zscaler. New migration date to be confirmed for Aug 31st. 13-Aug: Migration pushed to Aug 24th at 11AM. 31-Jul: Migration approved for August 15th 9AM. 15-Jul: Circuit test failed. Pending new test. 30-Apr: Pending circuit delivery. | Complete | Circuit Migrated | Circuit Provider |  | UCORPARG022 | ARGENTINA_TORTUGUITAS_3520 DESCARTES_P.L.N. CTRO. DISTRIBUCION |  |  |  |  | Descartes 3520 , Tortuguitas town, Buenos Aires argentina, CP B1667AYD DESCARTES 3520 - PARQUE INDUSTRIAL TORTUGUITAS | [8 empty] | 90Mb | 50 |  |  | 2020 | Mar | [14 empty] | Customer side: 8.243.137.18/30 CTL side: 8.243.137.17/30 IP LAN: 8.243.4.192/29 | 8.243.137.17 | 8.243.137.18 | 8.243.4.192/29 | [8 empty] | Dulce Basilio Gonzalez | Dulce Basilio Gonzalez | Dulce Basilio Gonzalez | [7 empty] | Yes |  |  | Window Date agreed - End user Comms sent |  | 14hrs UTC | 11AM | CHG000000000041952 (New) 111535 (Old) | CRQ000000708111 (new) CRQ000000700144 (old) | Approved |  | CRQ000000701120/CRQ000000705410 | Completed | Completed | Tested-Pass | Aug-24: Test successful. New IPs were provided. Aug-14: Tested failed for third time. Need CenturyLink to review. |  | Circuit Migrated - First Time right
CKT-I-02-UCORPARG022-BT-1 | I025088BT1 | 2 |  |  | Latin America | Argentina | Tortuguitas PLN: Centro Distribucion | 2019_11 | un-ula-argtort1-drt001 |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPARG022 | ARGENTINA_TORTUGUITAS_3520 DESCARTES_P.L.N. CTRO. DISTRIBUCION |  |  |  |  | Descartes 3520 , Tortuguitas town, Buenos Aires argentina, CP B1667AYD DESCARTES 3520 - PARQUE INDUSTRIAL TORTUGUITAS | [8 empty] | 36Mb | 50 |  |  | 2020 | Apr | [26 empty] | Dulce Basilio Gonzalez | Dulce Basilio Gonzalez | Dulce Basilio Gonzalez | [6 empty] | Yes | Yes
CKT-I-01-UCORPARG004-CTL-1 | I011852CTL1 | 2 |  |  | Latin America | Argentina | Planta Galvez | 2019_12 | un-ula-argpla1-vpn001 | un-ula-argpla1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-04-01 | 2020-04-01 | Complete | 2020-04-06 | 2020-04-08 | Complete | 2020-06-05 | 2020-07-08 | Complete | 2020-06-19 | 2020-08-28 | Complete | 28-Aug: Migration successful. 24-Aug: Migration had to be cancelled due to CenturyLink not being ready with their changes. To be rescheduled at a later date. 13-Aug: Migration changed for August 21st at 11AM. 31-Jul: Pending successful circuit test. Migration approved for August 22nd at 9AM. 27-Jul: Site has history of circuit failover failing. 26-Jul: Circuit Test failed. 30-Apr: Pending circuit delivery. | Complete | Circuit Migrated | Circuit Provider |  | UCORPARG004 | ARGENTINA_V_G_GALVEZ_PLANTA_GALVEZ |  |  |  |  | CAMINO DEL INMIGRANTE 864 | [8 empty] | 30Mb | 30 |  |  | 2020 | Mar | [14 empty] | WAN: 204.199.1.4/30 CTL: 204.199.1.5/30 UNI: 204.199.1.6/30 | 204.199.1.5 | 204.199.1.6 | 204.199.1.32/29 | [8 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos | [6 empty] | Yes | [7 empty] | 114757 | CRQ000000701997 | Approved |  | CRQ000000701212 | Completed | Completed | Test with migration | Jul:23: |  | Circuit Migrated - First Time right
CKT-I-02-UCORPARG004-TIS-1 |  | 2 |  |  | Latin America | Argentina | Planta Galvez | 2019_12 | un-ula-argpla1-vpn002 |  | Juan Simon | WAN Circuit Migration |  | TI Sparkle | TIS |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-08-31 | Red | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPARG004 | ARGENTINA_V_G_GALVEZ_PLANTA_GALVEZ |  |  |  |  | CAMINO DEL INMIGRANTE 864 | [8 empty] | 16Mb | 30 |  |  | 2020 | Apr | [26 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos
CKT-I-02-BO-CBB01-0001-ORA-1 | I021859ORA1 | 2 | Separate Agile router on site. Should this be collapsed into secondary of site ? |  | Latin America | Bolivia | Head Office Cochabamba | 2019_35 | ULA-BOCBBR2-RAVB | ula-bocbbr1-vpn002 | Juan Simon | WAN Circuit Migration |  | Orange | Ora |  | GO0AQ9XX3C | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-06-11 | Red | 2020-07-19 | 2020-08-10 | Red | 2020-07-31 | 2020-10-10 | Red | 01-Sep: Circuit test successful. Migration scheduled for September 9th at 9AM local time. 01-Jul-20: Carrier advised that they are still preparing the project and expect to schedule the site survey over the next few days(from orange tracker) 29-Apr: Pending circuit order to provider. | Green | Circuit Ordered | Unilever SNT |  | BO-CBB01-0001 | BOLIVIA_COCHABAMBA |  |  |  |  | Av. Blanco Galindo Km. 10.4, S/N Zona Irquicollo | [8 empty] | 6Mb | 60 |  |  | 2020 | Mar | [7 empty] | 9AM local | [5 empty] | Technical details: Demarcation point: Mikrotik RB760IGS S/N AE37BC72IE9/941 Port Eth 2 a 4 | Subnet: 200.12.252.240/29 Range: 200.12.252.242 - .246 Mask: 255.255.255.248 DefGW: 200.12.252.241 | 200.12.252.241/29 | 200.12.252.242/29 | 206.221.91.208/29 |  |  | INTELLIGLOBE | [5 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos |  |  | Complex site type - requires redesign | Complete | [8 empty] | 13hrs | 9AM
CKT-I-02-BO-SRZ04-0001-CTL-1 | I0220357CTL1 | 2 |  |  | Latin America | Bolivia | Centro de Distribución Paititi | 2019_36 | un-ula-bolpai1-pio001 | un-ula-bolpai1-vpn002 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2007100457 | 2020-01-31 | 2020-03-09 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-30 | Complete | 2020-04-17 | 2020-09-09 | Red | 9-Sep: Migration successful 8-Sep: Migration re-scheduled to Sep-9. 7-Sep: Migration pushed to September 15th by GeoIT. 28-Aug: Circuit test failed. Pending CTL to troubleshoot. Migration scheduled to Sep-07. 14-Aug: MIgration approved on Aug 26th, pending successful circuit test. 30-Apr: Circuit ordered. Pending circuit delivery. Jan-24: Wave-2 circuit. Still not ordered. | Complete | Circuit Delivered | Circuit Provider |  | BO-SRZ04-0001 | BOLIVIA_PAITITI_CD |  |  |  |  | Complejo Industrial del Norte - Carretera Norte Km. 23 | [8 empty] | 10M | 10 |  |  | 2020 | Mar | [14 empty] | LAN: 8.242.201.216/29 WAN: 8.242.201.212/30 CTL: 8.242.201.213 UNI: 8.242.201.214 | 8.242.201.213 | 8.242.201.214 | 8.242.201.216/29 | [8 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Standard site type - Hybrid (MPLS + IEN) | In Progress |  | Yes |  | No |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved |  |  |  |  | CHG000000000041893 | CRQ000000707535 | Approved |  | CRQ000000707051 | Completed | Completed | Tested-Pass | Sep-7: Test successful |  | Circuit Migrated - First Time right
CKT-I-01-UCORPB101-CTL-1 | I013142CTL1 | 2 |  |  | Latin America | Brazil | BRAZIL_ARACAJU | 2019_40 | un-ula-braara1-pio001 | un-ula-braara1-VPN001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-09-21 | Red | 10-Sep: Migration tentatively approved for Sep-21. 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPB101 | BRAZIL_ARACAJU |  |  |  |  | Rua Paulo Henrique Machado Pimentel, 160 Inacio Barbosa | [8 empty] | 1Mb | 10 |  |  | 2020 | Mar | [26 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo
CKT-I-01-UCORPBRA125-CTL-1 | I0110943CTL1 | 2 | Access granted. |  | Latin America | Brazil | BRAZIL_BRASILIA | 2018_34 | un-ula-brabra2-rtr001 | un-ula-brabra2-vpn002 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | CID: 500181771 | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-09-17 | Red | 29-Apr: Pending circuit order to provider. | Pink | Circuit not ordered | Unilever SNT |  | UCORPBRA125 | BRAZIL_BRASILIA |  |  |  |  | Pólo de Desenvolvimento Econômico Juscelino Kubitscheck, trecho 1 - Conj. 10 - Sala 7 - Santa Maria | [8 empty] | 6Mb | 10 |  |  | 2020 | Mar | [14 empty] | LAN: 204.199.32.208/29 WAN: 204.199.32.196/30 CTL: 204.199.32.197 UNI: 204.199.32.198 | 204.199.32.197 | 204.199.32.198 | 204.199.32.208/29 | [8 empty] | Rene Gonzalez Iniguez | [5 empty] | Complete |  | No |  |  |  | Assessment Complete | [8 empty] | CRQ000000708056 | Completed | Completed
CKT-I-01-NONULBRA120-CTL-1 | I0110884CTL1 | 2 |  |  | Latin America | Brazil | BRAZIL_CABODESANTOAGOSTINHO_SCHIO | 2019_43 | un-ula-braago1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | NONULBRA120 | BRAZIL_CABODESANTOAGOSTINHO_SCHIO |  |  |  |  | Rod BR 101 SUL, KM 96,4 BL D, Distrito Industrial Santo Estevão – Cabo de Santo Agostinho CEP 54503-010 - PE | [8 empty] | 6Mb | 10 |  |  | 2020 | Mar
CKT-I-02-BR-IGA01-0001-BT-1 | I011899BT1 | 2 |  |  | Latin America | Brazil | IGARASSU | 2019_49 | un-ula-braiga1-rtr001 | un-ula-braiga1-vpn002 | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | BR-IGA01-0001 | BRAZIL_IGARASSU |  |  |  |  | ROD BR 101 NORTE, S/N, KM 43,6, CENTRO | Igarassu | 53.610-000 |  | Paulo Dionizio | Paulo.Dionizio@unilever.com | 55 81 9 9149 0160 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 20Mb | 40 | -783354 | -34918985 | 2020 | Apr | [26 empty] | Sedat Citaku |  |  |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress |  | No |  |  | No
CKT-I-02-BR-IDU01-0001-TIS-1 |  | 2 |  |  | Latin America | Brazil | INDAIATUBA | 2018_38 | Un-ula-braind1-vpn001 | Un-ula-braind1-vpn001 | Juan Simon | WAN Circuit Migration |  | TI Sparkle | TIS |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-08-31 | Red | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | BR-IDU01-0001 | BRAZIL_INDAIATUBA |  |  |  |  | ROD ENGENHEIRO ERMENIO DE OLIVEIRA PENTEADO, S/N, KM 52,7 ITAICI | Indaiatuba | 13.340-600 |  | viviane Paula | viviane.paula@unilever.com | 55 019 3935 6989 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 70Mb | 70 | -23117122 | -472172 | 2020 | Apr | [26 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Dual DMVPN | Complete | [5 empty] | Assessment Complete MOP created & config created Partner MOP created
CKT-I-02-BR-IPO01-0001-BT-1 | I014887BT1 | 2 |  |  | Latin America | Brazil | IPOJUCA | 2019_51 | un-ula-braipo1-rtr001 | un-ula-braipo1-vpn001 | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | BR-IPO01-0001 | BRAZIL_IPOJUCA |  |  |  |  | Complexo Industrial De Suape, ROD PE 60, KM 12, S/N, ENGENHO DO MEIO | Ipojuca | 55.590-000 |  | Andrezza Sales | Andrezza.Sales@unilever.com | 55 81 9 9929 5494 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 15Mb | 40 | -805625 | -34941919 | 2020 | Apr | [26 empty] | Rene Gonzalez Iniguez |  |  |  |  | Standard site type - Hybrid (MPLS + DMVPN)
CKT-I-02-BR-LOZ01-0450-CTL-1 | I022649CTL1 | 2 |  |  | Latin America | Brazil | Louveira | 2019_52 | un-ula-bralou1-rtr001 | un-ula-bralou1-vpn002 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | CID 500182000 - Service | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Complete | 2020-07-19 | 2020-07-20 | Complete | 2020-07-31 | 2020-09-04 | Complete | 04-Sep: Migration successful. 10-Aug: Migration pushed to Sep-04 per GeoIT request. 31-Jul: Circuit test successful. Migration approved for August 14th at 9AM. 29-Apr: Pending circuit order to provider. | Complete | Circuit Migrated | Unilever SNT |  | BR-LOZ01-0450 | BRAZIL_LOUVEIRA |  |  |  |  | AV JOSE LUIZ MAZZALI, Nº 450, SANTO ANTONIO | Louveira | 13.290-000 |  | Jose Pereira Silva | Jose.P.Silva@unilever.com | 55 11 9 9754 1302 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 10Mb | 40 | -3005371 | -512015 | 2020 | Mar | [14 empty] | LAN: 8.243.42.24/29 WAN: 8.243.42.20/30 CTL: 8.243.42.21 UNI: Wan: 8.243.42.22 | 8.243.42.21/30 | 8.243.42.22/30 | 8.243.42.24/29 | [8 empty] | Hugo Trejo |  |  |  |  | Standard site type - Hybrid (MPLS + DMVPN) | [7 empty] | Window Date agreed - End user Comms sent |  | 12hrs UTC | 9AM | 119908 | CRQ000000705406 | Approved |  | CRQ000000705510 | Completed | Submitted | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right
CKT-I-02-BR-PPY02-0001-CTL-1 | I0210669CTL1 | 2 |  |  | Latin America | Brazil | BRAZIL_POUSOALEGRE_DC | 2018_41 | un-ula-brapou2-pio001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | BR-PPY02-0001 | BRAZIL_POUSOALEGRE_DC |  |  |  |  | RODOVIA BR 381 FERNÃO DIAS, S/N, KM 864 - PARTE A, BAIRRO ALGODÃO | [8 empty] | 7Mb | 40 |  |  | 2020 | Mar | [26 empty] | Rene Gonzalez Iniguez | [8 empty] | Yes
CKT-I-02-BR-PPY01-3701-TIS-1 |  | 2 |  |  | Latin America | Brazil | POUSOALEGRE_PLANT | 2018_42 | un-ula-brapou1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | TI Sparkle | TIS |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-08-31 | Red | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | BR-PPY01-3701 | BRAZIL_POUSOALEGRE_PLANT |  |  |  |  | Av. Prefeito Olavo Gomes, 3701, Jardim Mariosa | [8 empty] | 70Mb | 70 |  |  | 2020 | Apr | [26 empty] | Rene Gonzalez Iniguez
CKT-I-01-UCORPB022-CTL-1 | I012648CTL1 | 2 | No access to device |  | Latin America | Brazil | BRAZIL_RECIFE_IC | 2019_58 | un-ula-brajab1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPB022 | BRAZIL_RECIFE_IC |  |  |  |  | Unilever Brasil Gelados do Nordeste S A Rodovia BR 232, Km 13, s/n - Curado Jaboatão dos Guararapes-PE / 54.220-520 | [8 empty] | 12Mb | 40 |  |  | 2020 | Mar | [26 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos
CKT-I-02-UCORPB022-BT-1 | I022648BT1 | 2 |  |  | Latin America | Brazil | BRAZIL_RECIFE_IC | 2019_58 | un-ula-brajab1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPB022 | BRAZIL_RECIFE_IC |  |  |  |  | Unilever Brasil Gelados do Nordeste S A Rodovia BR 232, Km 13, s/n - Curado Jaboatão dos Guararapes-PE / 54.220-520 | [8 empty] | 40Mb | 40 |  |  | 2020 | Apr | [26 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos
CKT-I-01-UCORPBRA103-CTL-1 | I013742CTL1 | 2 |  |  | Latin America | BRAZIL | BRAZIL_RIODEJANEIRO_IC | 2018_45 | un-ula-brario2-vpn001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPBRA103 | BRAZIL_RIODEJANEIRO_IC |  |  |  |  | R HERCULANO PINHEIRO, nº 333, ARMAZEM 01 PARTE A | [8 empty] | 10Mb | 40 |  |  | 2020 | Mar
CKT-I-02-BR-AGU01-0001-CTL-1 | I0210692CTL1 | 2 |  |  | Latin America | Brazil | BRAZIL_SAOPAULO_AGUAI | 2018_46 | un-ula-braagu1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | BR-AGU01-0001 | BRAZIL_SAOPAULO_AGUAI |  |  |  |  | Estrada Aguaí - Pirassunu S/N, | Aguai | 13860-000 |  | Vagner Barcaro | Vagner.Barcaro@unilever.com | 55 19 9 8320 5922 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 10.240Mb | 40 | 0 | 0 | 2020 | Mar | [26 empty] | Hugo Trejo
CKT-I-01-BR-SAO18-0001-CTL-1 | I0120226CTL1 | 2 | NAT done in FW. No information available |  | Latin America | Brazil | W Torre Morumbi | 2019_61 | un-ula-brasao1-rtr001 | un-ula-brasao1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Complete | 2020-07-19 | 2020-07-20 | Complete | 2020-07-31 | 2020-09-01 | Complete | 1-Sep: Migration from MPLS to DMVPN with new circuit successful. Old Internet circuit migration to DMVPN also successful. 29-Aug: LAN changes successful. Pending WAN changes on Sep-1. 27-Aug: LAN changes will be done on Aug-29, and dual-migration on Sep-01. 24-Aug: Migration will include converting the peer IEN circuit to DMVPN (using the current/old circuit), removing the FW, and if ready, comvert to DMVPN the MPLS link with new CTL circuit.. 12-Aug: Migration moved to Aug-25. 6-Aug: Test failed. Pending CTL to confirm working correctly. Migration approved on Aug 19th 9AM. 29-Apr: Pending circuit order to provider. | Complete | Circuit Migrated | Unilever SNT |  | BR-SAO18-0001 | BRAZIL_SAOPAULO_Wtorre |  |  |  |  | Av. das Nações Unidas, 14261 | Sao Paulo | 04533-085 | [6 empty] | 150Mb | 600 |  |  | 2020 | Mar | [14 empty] | LAN: 8.243.36.224/29 WAN: 8.243.36.216/30 8.243.36.217 8.243.36.218 | 8.243.36.217 | 8.243.36.218 | 8.243.36.224/29 | [8 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Hybrid (MPLS + IEN) | In Progress | NIM-2GE-CU-SFP | Yes | Yes |  | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression SSR approved | Window Date agreed - End user Comms sent |  | 11AM UTC | 8AM | 117037 | CRQ000000703831 | Approved |  | CRQ000000702167 | Completed | Completed | Tested-Pass | Aug-7: Circuit test results delievered by CTL accepted by Welington. |  | Circuit Migrated - First Time right
CKT-I-02-BR-SAO18-0001-BT-1 | I0220226BT1 | 2 | NAT done in FW. No information available |  | Latin America | Brazil | W Torre Morumbi | 2019_62 | un-ula-brasao1-rav001 |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | BR-SAO18-0001 | BRAZIL_SAOPAULO_Wtorre |  |  |  |  | Av. das Nações Unidas, 14261 | Sao Paulo | 04533-085 | [6 empty] | 400Mb | 600 |  |  | 2020 | Apr | [26 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku | [6 empty] | Yes |  |  | Assessment Complete MOP created & config created Partner MOP created
CKT-I-01-UCORPBRA124-CTL-1 | I011964CTL1 | 2 |  |  | Latin America | Brazil | BRAZIL_VALINHOS | 2019_65 | un-ula-braval1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPBRA124 | BRAZIL_VALINHOS |  |  |  |  | Avenida Gessy Lever, 99 | [8 empty] | 60Mb | 300 |  |  | 2020 | Mar
CKT-I-02-UCORPBRA124-BT-1 | I021964BT1 | 2 |  |  | Latin America | Brazil | BRAZIL_VALINHOS | 2019_66 | un-ula-braval1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPBRA124 | BRAZIL_VALINHOS |  |  |  |  | Avenida Gessy Lever, 99 | [8 empty] | 300Mb | 300 |  |  | 2020 | Apr
CKT-I-02-BR-VIN01-0001-TIS-1 |  | 2 |  |  | Latin America | Brazil | VINHEDO | 2019_67 | un-ula-bravin1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | TI Sparkle | TIS |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-08-31 | Red | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | BR-VIN01-0001 | BRAZIL_VINHEDO |  |  |  |  | AV. DAS INDUSTRIAS, 315, DISTRITO INDUSTRIAL | Vinhedo | 13.280-000 |  | Cassio Benvenuto | cassio.benvenuto@unilever.com | 55 19 9 8136 8097 | Roberto Sabbag, William Martins and Valdir Goncalves | Roberto.Sabbag@unilever.com; William.Martins@unilever.com; Valdir.Goncalves@unilever.com | 20Mb | 70 | -7179447 | -34903763 | 2020 | Apr | [26 empty] | Rene Gonzalez Iniguez
CKT-I-01-UCORPCHL037-CTL-1 | I013158CTL1 | 2 | No WAN routers, exist a LAN connection to Carrascal via fiber New Site is called KeepCold |  | Latin America | Chile | San Bernardo | 2019_79 | un-ula-chlkee-ien001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-04-01 | 2020-04-01 | Complete | 2020-04-06 | 2020-04-08 | Out of Scope | 2020-06-05 | 2020-07-08 | Out of Scope | 2020-06-19 | 2020-08-20 | Out of Scope | Feb-07: Deepak confirmed to CenturyLink cancellation of the order | Out of Scope | Circuit Ordered | Circuit Provider |  | UCORPCHL037 | CHILE_SAN BERNARDO_1184 CAMINO SANTA MARGARITA | [13 empty] | 2048MB | 10 |  |  | 2020 | Mar | [26 empty] | Fernando Ramos
CKT-I-02-UCORPCHL037-BT-1 | I023158BT1 | 2 | No WAN routers, exist a LAN connection to Carrascal via fiber New Site is called KeepCold |  | Latin America | Chile | San Bernardo | 2019_80 | un-ula-chlkee-ien002 |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPCHL037 | CHILE_SAN BERNARDO_1184 CAMINO SANTA MARGARITA | [13 empty] | 2048MB | 10 |  |  | 2020 | Apr | [26 empty] | Fernando Ramos
CKT-I-02-CL-SCL05-0550-TIS-1 |  | 2 | WAN pool order /30 irrespective |  | Latin America | Chile | Site Lampa | 2019_81 | un-ula-chllam1-pio001 |  | Juan Simon | WAN Circuit Migration |  | TI Sparkle | TIS |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-08-31 | Red | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | CL-SCL05-0550 | CHILE_SANTIAGO_LAMPA |  |  |  |  | La Estera No 550, Parque Industrial Valle Grande, Lampa | [8 empty] | 30Mb | 30 |  |  | 2020 | Apr | [26 empty] | Fernando Ramos |  |  |  |  | Standard site type - Hybrid (DMVPN + IEN) | [6 empty] | Assessment Complete MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required)
CKT-I-02-CL-SCL06-0001-TIS-1 |  | 2 | WAN pool order /30 irrespective |  | Latin America | Chile | Site Panamericana | 2019_82 | un-ula-chlpan1-pio001 |  | Juan Simon | WAN Circuit Migration |  | TI Sparkle | TIS |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-08-31 | Red | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | CL-SCL06-0001 | CHILE_SANTIAGO_PANAMERICANA |  |  |  |  | Panamericana Norte 5981, Conchalí | [8 empty] | 35Mb | 80 |  |  | 2020 | Apr | [26 empty] | Fernando Ramos |  |  |  |  | Standard site type - Hybrid (DMVPN + IEN) | [6 empty] | Assessment Complete MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required)
CKT-I-01-UCORPCHL080-CTL-1 | I014954CTL1 | 2 | WAN pool order /30 irrespective |  | Latin America | CHILE | Temuco | 2018_52 | un-ula-chltem1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-15 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit Ordered | Unilever SNT |  | UCORPCHL080 | CHILE_TEMUCO |  |  |  |  | Road to Chol Chol S / N (Km 2.5), Pedro de Valdivia sector, Temuco, IX Region | [8 empty] | 10Mb | 10 |  |  | 2020 | Mar | [26 empty] | Fernando Ramos
CKT-I-02-UCORPCHL080-TIS-1 |  | 2 | WAN pool order /30 irrespective |  | Latin America | CHILE | Temuco | 2018_52 | un-ula-chltem1-vpn002 |  | Juan Simon | WAN Circuit Migration |  | TI Sparkle | TIS |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-08-31 | Red | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPCHL080 | CHILE_TEMUCO |  |  |  |  | Road to Chol Chol S / N (Km 2.5), Pedro de Valdivia sector, Temuco, IX Region | [8 empty] | 10Mb | 10 |  |  | 2020 | Apr | [26 empty] | Fernando Ramos
CKT-I-02-CO-CLO01-0001-CTL-1 | I021986CTL1 | 2 |  |  | Latin America | Colombia | CALI Planta Foods | 2019_111 | un-ula-colcalf-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-03-09 | Complete | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-07-15 | Red | 2020-04-17 | 2020-10-30 | Red | 30-Apr: Pending circuit delivery. | Yellow | Circuit Ordered | Circuit Provider |  | CO-CLO01-0001 | COLOMBIA_CALI_FOODS |  |  |  |  | Carrera 5 # 52-310 Salomia | [8 empty] | 15Mb | 30 |  |  | 2020 | Mar | [26 empty] | Hugo Trejo
CKT-I-01-CO-QPI01-0002-CTL-1 | I019638CTL1 | 2 |  |  | Latin America | COLOMBIA | CALI HPC Plant | 2018_54 | un-ula-colcal1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-03-09 | Complete | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-08-05 | Red | 2020-04-17 | 2020-10-15 | Red | 30-Apr: Pending circuit delivery. | Yellow | Circuit Ordered | Circuit Provider |  | CO-QPI01-0002 | COLOMBIA_CALI_VARELLA_HPC |  |  |  |  | Km. 13 Vía Yumbo - Aeropuerto Portería 2 | [8 empty] | 20Mb | 50 |  |  | 2020 | Mar | [26 empty] | Hugo Trejo
CKT-I-01-CO-MAC01-0001-PCCW-1 |  | 2 |  |  | Latin America | Colombia | Centro Logistico Madrid Bodegas San Francisco | 2019_114 | un-una-colbod1-pio001 |  | Juan Simon | WAN Circuit Migration |  | PCCW | PCCW |  | N/A | 2020-05-15 | 2020-05-15 | Out of Scope | 2020-05-20 | 2020-05-20 | Out of Scope | 2020-07-19 | 2020-07-20 | Out of Scope | 2020-07-31 | 2020-10-30 | Out of Scope | 27-Apr: Site to be decomissioned on May 31. | Yellow | Circuit not ordered | Unilever SNT |  | CO-MAC01-0001 | COLOMBIA_MADRID_BODEGA |  |  |  |  | Centro Logistico Madrid Bodegas San Francisco, 8C and 10C | Madrid (Colombia) | [7 empty] | 20Mb | 20 |  |  | 2020 | Apr | [26 empty] | Hugo Trejo
CKT-I-01-UCORPCOL087-CTL-1 | I013193CTL1 | 2 |  |  | Latin America | Colombia | Colombia_Pereira | 2019_115 | un-ula-colper1-pio001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | UCORPCOL087 | Colombia_Pereira |  |  |  |  | Carrera 17 # 6-113 Pinares San Martín | [8 empty] | 4Mb | 10 |  |  | 2020 | Apr
CKT-I-02-CR-HER01-0002-CTL-1 | I023197CTL1 | 2 |  |  | Latin America | Costa Rica | Valencia Distribution Center | 2019_116 | un-ula-crival1-drt001 | un-ula-crival1-vpn002 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2007091167 | 2020-04-30 | 2020-04-24 | Complete | 2020-05-05 | 2020-05-07 | Amber | 2020-07-04 | 2020-08-08 | Red | 2020-07-17 | 2020-09-28 | Red | 30-Apr: Circuit ordered. Pending circuit delivery. Jan-24: Wave-2 circuit. Still not ordered. | Yellow | Circuit Ordered | Circuit Provider |  | CR-HER01-0002 | COSTA_RICA_HEREDIA_VALENCIA |  |  |  |  | 1kilometro al este del cruce la valencia, calle a mano derecha frente a Extralum, ultimo almacen , Heredia | [8 empty] | 4Mb | 10 |  |  | 2020 | Mar | [13 empty] | Ciena 3903 puerto 1 - bodega #2, Cuarto de TI, Rack solo hay uno. | WAN: 204.199.210.16/30 CTL: 204.199.210.17 UNI: 204.199.210.18 | 204.199.210.17/30 | 204.199.210.18/30 | [9 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete
CKT-I-02-CR-SJO03-0001-CTL-1 | I022089CTL1 | 2 |  |  | Latin America | Costa Rica | Heredia HeadOffice | 2019_117 | un-ula-cribel1-vpn001 | un-ula-cribel1-vpn002 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-04-30 | 2020-04-24 | Complete | 2020-05-05 | 2020-05-07 | Amber | 2020-07-04 | 2020-08-08 | Red | 2020-07-17 | 2020-09-24 | Red | 10-Sep: Migration tentatively scheduled for Sep-24 30-Apr: Circuit ordered. Pending circuit delivery. Jan-24: Wave-2 circuit. Still not ordered. | Pink | Circuit Ordered | Circuit Provider |  | CR-SJO03-0001 | COSTA_RICA_SAN_JOSE_BELEN |  |  |  |  | Unilever, Heredia, Belén, Costa Rica 9°59'14.0"N 84°10'07.7"W 400m al Oeste y 800m al Norte Del Cruce Sobre El Puente Real Cariari,Fte A La Sede Testigos De Jehova / Heredia | [8 empty] | 40Mb | 40 |  |  | 2020 | Mar | [26 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress | NO | No |  | No | No | Assessment Complete
CKT-I-02-DO-SDQ04-0001-CTL-1 | I028533CTL1 | 2 |  |  | Latin America | Dominican Republic | Acropolis - Corporate | 2019_129 | un-ula-domacr1-pio001 | un-ula-domacr1-vpn002 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-04-23 | 2020-04-23 | Complete | 2020-04-28 | 2020-05-07 | Complete | 2020-06-27 | 2020-08-08 | Complete | 2020-07-10 | 2020-08-21 | Complete | 24-Aug: Migration successful. 14-Aug: Migration confirmed 21-Aug 10:00 AM 6-Aug: To be confirmed by GeoIT if approved on Aug-21. 31-Jul: Migration approved for August 21 at 10AM. 2-Jul: From CMS: To fix failover: For the VPN001 we need to advertise neighbor MGMT ip address. And for the PIO001 need to make sure it is redistributing routes from WAN to LAN 30-Apr: Pending circuit delivery. | Complete | Circuit Migrated | Circuit Provider |  | DO-SDQ04-0001 | DOMINICAN_REPUBLIC_SANTO_DOMINGO_WINSTON_CHURCHILL |  |  |  |  | ZIP CODE 1099 WINSTON CHURCHILL AVE 17TH FLOOR SANTO DOMINGO | [8 empty] | 15Mb | 30 |  |  | 2020 | Mar | [14 empty] | IP 190.122.102.121(29) DNS1 200.26.170.15 DNS2 200.26.170.67 | 190.122.102.121 | 190.122.102.126 | [9 empty] | Hugo Trejo | [16 empty] | 116401 | CRQ000000702624 | Approved |  | CRQ000000698791 | Completed | Completed | Tested-Fail | Jul-23: Circuit test failed. |  | Circuit Migrated
CKT-I-02-EC-GYQ01-0001-ORA-1 | I021992ORA1 | 2 | IP took from int Loopback |  | Latin America | ECUADOR | Guayaquil Matriz (OASIS) | 2018_62 | un-ula-ecugua1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | Orange | Ora |  | GO0AQ9W85C | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-06-04 | Red | 2020-07-19 | 2020-07-11 | Green | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit Ordered | Unilever SNT |  | EC-GYQ01-0001 | ECUADOR_GUAYAQUIL_OASIS |  |  |  |  | Km. 25 Vía A Daule | [8 empty] | 24Mb | 100 |  |  | 2020 | Mar | [20 empty] | UFINET LATAM | [5 empty] | Fernando Ramos |  |  |  |  | Standard site type - Hybrid (MPLS + DMVPN)
CKT-I-02-SV-SAL10-0001-ORA-1 |  | 2 |  |  | Latin America | El Salvador | El Salvador - Head Office |  | un-ula-slvsal-rtr001 |  | Juan Simon | WAN Circuit Migration |  | Orange | Ora |  |  | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-10 | Amber | 2020-04-05 | 2020-07-24 | Red | 2020-04-17 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | SV-SAL10-0001 | EL_SALVADOR_SAN_SALVADOR_NEW_HOME | [13 empty] | 35Mb | 100 |  |  | 2020 | Mar | [20 empty] | UFINET LATAM | [5 empty] | Rene Gonzalez Iniguez
CKT-I-01-UCORPGTM050-CTL-1 | I019897CTL1 | 2 |  |  | Latin America | Guatemala | GUATEMALA_UNILEVER | 2019_198 | un-ula-guagua1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-04-23 | 2020-04-23 | Complete | 2020-04-28 | 2020-05-07 | Red | 2020-06-27 | 2020-08-08 | Red | 2020-07-10 | 2020-10-15 | Red | 30-Apr: Pending circuit delivery. | Yellow | Circuit Ordered | Circuit Provider |  | UCORPGTM050 | GUATEMALA_UNILEVER |  |  |  |  | EDIFICIO INTERAMERICAS WORLD CENTE | [8 empty] | 23Mb | 40 |  |  | 2020 | Mar | [26 empty] | Hugo Trejo
CKT-I-02-UCORPGTM050-ORA-1 | I029897ORA1 | 2 |  |  | Latin America | Guatemala | GUATEMALA_UNILEVER | 2019_199 | un-ula-guagua1-pio001 |  | Juan Simon | WAN Circuit Migration |  | Orange | Ora |  | GO0AQ9XC27 | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-31 | Red | 2020-07-31 | 2020-10-30 | Red | 01-Jul-20: Pending Deepak to provide approval for the costs for the additional IP addresses (from orange tracker) 29-Apr: Pending circuit order to provider. | Yellow | Circuit Ordered | Unilever SNT |  | UCORPGTM050 | GUATEMALA_UNILEVER |  |  |  |  | EDIFICIO INTERAMERICAS WORLD CENTE | [8 empty] | 30Mb | 40 |  |  | 2020 | Mar | [20 empty] | UFINET LATAM | [5 empty] | Hugo Trejo
CKT-I-02-HN-TGU01-0001-CTL-1 | I022175CTL1 | 2 |  |  | Latin America | Honduras | Tegucigalpa CORP & CD | 2018_95 | un-ula-honteg1-vpn001 | un-ula-honteg1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2007082187 | 2020-04-23 | 2020-04-23 | Complete | 2020-04-28 | 2020-05-07 | Complete | 2020-06-27 | 2020-06-19 | Complete | 2020-07-10 | 2020-07-17 | Complete | 17-Jul: Migration successful. 7-Jul: Migration approved for July 17th at 9AM local time. 26-Jun: Pending circuit testing. 30-Apr: Pending circuit delivery. | Complete | Circuit Migrated | Unilever SNT |  | HN-TGU01-0001 | HONDURAS_TEGUCIGALPA |  |  |  |  | Anillo periférico, Km 16. 1 Km adelante de puente las uvas. | Tegucigalpa | NA |  | Luis.Rubio | Luis.Rubio@unilever.com | +57 1 4239727 | Luis.Rubio | Luis.Rubio@unilever.com | 30m | 30 | 14.0467 | -87.2444 | 2020 | Mar | [7 empty] | 9AM | [6 empty] | WAN: 64.209.13.16/30 CTL: 64.209.13.17 UNI: 64.209.13.18 | 64.209.13.17 | 64.209.13.18 | [9 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress |  | Yes |  | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 15hrs | 9AM | 99249 | CRQ000000690700 | Approved |  | CRQ000000691034 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right
CKT-I-01-UCORPHND006-GTT-1 | I012145GTT1 | 2 | /29 between corporate and guest |  | Latin America | Honduras | HONDURAS-COMAYAGUA | 2019_200 | un-ula-hndcom1-dtr001 |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001829222 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-12-31 | On Hold | 2020-04-17 | 2020-07-15 | On Hold | 5-May: Circuit Order on hold per Deepak's request. 30-Apr: Pending circuit delivery. | On Hold | Circuit Ordered | Unilever SNT | Check dates | UCORPHND006 | HONDURAS-COMAYAGUA |  |  |  |  | Complejo Industrial Comayagua Carretera Panamericana, Km 7 (frente a Base Aérea Soto Cano), Palmerola | [8 empty] | 4Mb | 30 |  |  | 2020 | Mar | [13 empty] | 2nd Floor. Gabinete 1 | 209.120.227.48/30 Network - 209.120.227.48 First usable - 209.120.227.49 Last usable - 209.120.227.50 Broadcast - 209.120.227.51 Subnet Mask - 255.255.255.252 | [5 empty] | Tigo | [14 empty] | Yes
CKT-I-02-UCORPHND006-CTL-1 | I022145CTL1 | 2 |  |  | Latin America | Honduras | HONDURAS-COMAYAGUA | 2018_94 | un-ula-hndcom1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-03-09 | Complete | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-07-15 | Red | 2020-04-17 | 2020-10-30 | Red | 30-Apr: Pending circuit delivery. | Yellow | Circuit Ordered | Circuit Provider |  | UCORPHND006 | HONDURAS-COMAYAGUA |  |  |  |  | Complejo Industrial Comayagua Carretera Panamericana, Km 7 (frente a Base Aérea Soto Cano), Palmerola | [8 empty] | 30Mb | 30 |  |  | 2020 | Mar | [26 empty] | Fernando Ramos
CKT-I-02-3281-GTT-1 |  | 2 |  |  | Latin America | Mexico | TALISMÁN |  |  |  | Juan Simon Molina | SNT |  | GTT | GTT |  | GTT/001835494 | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-07-30 | Red | 2020-04-17 | 2020-05-15 | Red | 4-Feb: Action is Transfer + Transform. | Pink | Circuit not ordered |  | Check dates | MX-CIU03-0001 | MEXICO_BOSQUES_DE_LAS_LOMAS_PASEOS_DE_LOS_TAMARINDOS | [14 empty] | 100 |  |  | 2020 | Mar
CKT-I-01-MX-GDL01-3569-GTT-1 |  | 2 |  | High | Latin America | Mexico | MEXICO_GUADALAJARA_CHIMALHUACAN |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817216 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-07-30 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | MX-GDL01-3569 | MEXICO_GUADALAJARA_CHIMALHUACAN |  |  |  |  | 3569 CHIMALHUACAN PISO 9 GUADALAJARA JALISCO MEXICO 44940. | [9 empty] | 10 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [40 empty] | 97834 | [9 empty] | Circuit Migrated - First Time right
CKT-I-02-NI-MGA01-0001-ORA-1 | I0210666ORA1 | 2 |  |  | Latin America | Nicaragua | Head Office & CNd, Managua Nic | 2019_564 | un-ula-nicman1-pio001 | un-ula-nicman1-vpn002 | Juan Simon | WAN Circuit Migration |  | Orange | Ora |  | GO0AQ9WA25 | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Complete | 2020-07-19 | 2020-07-08 | Complete | 2020-07-31 | 2020-09-07 | Complete | 7-Sep: Migration successful. 13-Aug: Migration tentatively scheduled for September 7th. Pending confirmation from site. 7-Aug: Migration called off during maintenance window. Too many delays to start, so we had to call it off and postpone the migration for a future date. 29-Jul: Migration approved for August 7th. 27-Jul: Orange shared their circuit test results. Per Allan Morais' instruction, we will proceed with migration accepting these results. 27-Jul: Migration tentatively scheduled on August 7th. 01-Jul-20: Carrier is scheduling a date for the site survey (from orange tracker) 29-Apr: Pending circuit order to provider. | Complete | Circuit Migrated | Unilever SNT |  | NI-MGA01-0001 | NICARAGUA_MANAGUA_NEWHOME |  |  |  |  | Km 10.5 Carretera Nueva A León | Sandino | NA |  | Luis.Rubio | Luis.Rubio@unilever.com | +57 1 4239727 | Luis.Rubio | Luis.Rubio@unilever.com | 7Mb | 20 | 12.1505 | -86.3359 | 2020 | Mar | [14 empty] | 10.242.101.8/29 (LAN) 190.61.81.100/30 (WAN) 190.61.81.101 gateway 190.61.81.102 customer IP 167.250.220.220 DNS1 | 190.61.81.101/30 | 190.61.81.102/30 |  |  |  | UFINET LATAM | [5 empty] | Hugo Trejo | Hugo Trejo | Hugo Trejo | [14 empty] | CHG000000000041907 | CRQ000000707690 (New) CRQ000000697843 (Old) | Approved |  | CRQ000000697536 | Completed | Completed | Tested-Pass | 26-Jul: Orange shared their circuit test results. Per Allan Morais' instruction, we will proceed with migration accepting these results. 22-Feb: Test failed. |  | Circuit Migrated | Too many delays to start the first migration attempt, so we had to cancel it.
CKT-I-02-PA-PTY04-0001-CTL-1 | I0210116CTL1 | 2 |  |  | Latin America | Panama | Panamá Ofcs Order Factory TDLA | 2019_566 | un-ula-panpan1-vpn001 | un-ula-panpan1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-04-23 | 2020-04-23 | Complete | 2020-04-28 | 2020-05-07 | Red | 2020-06-27 | 2020-08-08 | Red | 2020-07-10 | 2020-09-21 | Red | 10-Sep: Migration tentatively scheduled for Sep-21. 30-Apr: Pending circuit delivery. | Pink | Circuit Ordered | Circuit Provider |  | PA-PTY04-0001 | PANAMA_CIUDAD_DE_PANAMA_ORDER_FACTORY |  |  |  |  | Torres de las Américas / Torre C /Piso 32 /Ave. Punta Darien / Punta Pacífica | Ciudad De Panama | NA |  | Luis.Rubio | Luis.Rubio@unilever.com | +57 1 4239727 | Luis.Rubio | Luis.Rubio@unilever.com | 50Mb | 50 | 8.9829 | -79.5092 | 2020 | Mar | [14 empty] | WAN: 64.208.157.36/30 CTL: 64.208.157.37 UNI: 64.208.157.38 | [11 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Standard site type - Dual DMVPN | Complete |  | No |  |  |  | Assessment Complete Partner MOP created
CKT-I-02-PY-ASU01-0001-GTT-1 | I0212023GTT1 | 2 |  |  | Latin America | Paraguay | Asunción Head Office | 2019_568 | un-ula-pryasu1-pio001 | un-ula-pryasu1-vpn002 | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001829211 | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Complete | 2020-07-19 | 2020-07-01 | Complete | 2020-07-31 | 2020-08-31 | Complete | 31-Aug: Migration successful. 24-Aug: Migration pushed to Aug 31st at 10AM. 14-Aug: Migration pushed to Aug-24 10AM due to COVID cases detected at the site, so it needs to be closed while being sanitized. 10-Aug: Migration rescheduled for August 17th at 9AM. 4-Aug: Migration rolled back. GTT had incorrect IPs in their tracker (first usable and GW IPs inverted), so Algosec & Zscaler were implemented with these wrong IPs. 7-Jul: Circuit testing successful. Migration approved August 4th 9AM. 29-Apr: Pending circuit order to provider. | Complete | Circuit Migrated | Unilever SNT |  | PY-ASU01-0001 | PARAGUAY_ASUNCION_H.O. |  |  |  |  | Calle Roque Centurion Miranda C/ San Martin | Asunción | 1749 | [6 empty] | 23Mb | 40 |  |  | 2020 | Mar | [13 empty] | Rack: Customer Rack – No label Equipment: RAX 701 | 170.83.242.32/29 Network - 170.83.242.32 Gateway - 170.83.242.34 First usable - 170.83.242.33 Last usable - 170.83.242.38 Broadcast - 170.83.242.39 Subnet Mask - 255.255.255.248 10.70.0.95/30 Network - 10.70.0.92 First usable - 10.70.0.93 Last usable - 10.70.0.94 Broadcast - 10.70.0.95 Subnet Mask - 255.255.255.252 | 170.83.242.34/29 | 170.83.242.33/29 |  |  |  | UFINET Panama | [5 empty] | Fernando Ramos |  |  |  | Copper - RJ45 | [11 empty] | 10AM | 112468 (new) 108006 (old) | CRQ000000700446 (new) CRQ000000696260 | Approved |  | CRQ000000696289/CRQ000000698869 | Completed | Completed | Tested -Pass-First Time | 16-Jul: Circuit testing successful. Had to try different IP configurations to get a connection. |  | Circuit Migrated | Algosec & Zscaler were requested incorrectly beacuse of incorrect IPs from GTT.
CKT-I-02-PY-VLL02-0001-ORA-1 | I0220189ORA1 | 2 |  |  | Latin America | Paraguay | CD Villeta | 2019_570 | un-ula-pryvil1-vpn002 | un-ula-pryvil1-vpn002 | Juan Simon | WAN Circuit Migration |  | Orange | Ora |  | GO0ATHUU17 | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Complete | 2020-07-19 | 2020-08-03 | Complete | 2020-07-31 | 2020-09-05 | Complete | Sep-05: Migration successful. Aug-24: Migration pushed to Sep 5th at 8AM. Aug-11: Migration approved on Aug 22th at 9hrs local time. 29-Apr: Pending circuit order to provider. | Complete | Circuit Migrated | Unilever SNT |  | PY-VLL02-0001 | PARAGUAY_VILLETA |  |  |  |  | Ruta Ypane-Villeta Km 3,5., Abay | [8 empty] | 25Mb | 30 |  |  | 2020 | Mar | [7 empty] | 8AM | [6 empty] | WAN 190.128.172.122 Network 190.128.172.120 Gateway 190.128.172.121 | 190.128.172.121 | 190.128.172.122 |  |  |  | TIGO | [5 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Standard site type - Dual DMVPN | Complete |  | No |  | No |  | Assessment Complete Received tunnel IP or LAN IP (if required) |  |  | 12UTC | 8AM | 115206 | CRQ000000702555 | Approved |  | CRQ000000701208 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right
CKT-I-01-UCORPPER022-GTT-1 | I013246GTT1 | 2 | WAN pool order /30 irrespective |  | Latin America | Peru | Peru_Dinet | 2019_571 | un-ula-perdin1-drt001 |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001835594 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-03 | Green | 2020-04-05 | 2020-10-31 | Red | 2020-04-17 | 2020-10-30 | Red | 24/06: Request vendor to reuse the existing fibre for the solution. Vendor to survey. (From GTT tracker) 30-Apr: Pending circuit delivery. | Yellow | Circuit Ordered | Circuit Provider | Check dates | UCORPPER022 | Peru_Dinet |  |  |  |  | Fundo Pedreros Lote 1,2,3 y 4A – Lurigancho | [8 empty] | 2Mb | 15 |  |  | 2020 | Mar | [13 empty] | 2nd floor. Rack: Customer Rack – No label Equipment: RAX 701 | [6 empty] | UFINET Panama | [5 empty] | Fernando Ramos | [8 empty] | Yes
CKT-I-02-UCORPPER022-CTL-1 | I023246CTL1 | 2 |  |  | Latin America | Peru | Peru_Dinet | 2019_572 | un-ula-perdin1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-03-09 | Complete | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-07-15 | Red | 2020-04-17 | 2020-10-30 | Red | 30-Apr: Pending circuit delivery. | Yellow | Circuit Ordered | Circuit Provider |  | UCORPPER022 | Peru_Dinet |  |  |  |  | Fundo Pedreros Lote 1,2,3 y 4A – Lurigancho | [8 empty] | 10Mb | 15 |  |  | 2020 | Mar | [26 empty] | Fernando Ramos
CKT-I-02-TT-CHF01-0001-ORA-1 | I022027ORA1 | 2 |  |  | Latin America | Trinidad and Tobago | Champs Fleurs - Corporate | 2019_653 | un-ula-ttopos1-rtr001 | un-ula-ttopos1-vpn001 | Juan Simon | WAN Circuit Migration |  | Orange | Ora |  | LO005LPE45 | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Complete | 2020-07-19 | 2020-08-03 | Complete | 2020-07-31 | 2020-09-09 | Red | 09-Sep: Migration successful. 02-Sep: Migation rolled back. Algosec & Zscaler requested with incorrect IPs. Rescheduled to Sep-9 11-Aug: Migration approved for Sep-02 at 9AM local time. 29-Apr: Pending circuit order to provider. | Complete | Circuit Delivered | Unilever SNT |  | TT-CHF01-0001 | TRINIDAD_AND_TOBAGO_PORT_OF_SPAIN_EASTERN_MAIN_ROAD |  |  |  |  | Eastern Main Road P.O. Box 295 | [8 empty] | 14Mb | 40 |  |  | 2020 | Mar | [14 empty] | Network Address - 186.96.218.24 / 255.255.255.248 Default Gateway for Customer - 186.96.218.25 / 255.255.255.248 Management IP Expereo Device - 186.96.218.30 / 255.255.255.248 | 186.96.218.25/29 | 186.96.218.26/29 |  |  |  | GLOBAL TELECOM SERVICES B.V | [5 empty] | Hugo Trejo | [16 empty] | CHG000000000041961 (New) 119460 (Old) | CRQ000000705462 | Approved |  | CRQ000000705178/CRQ000000708592 | Completed | Completed | Tested -Pass-First Time | 11-Aug: Circuit test successful. |  | Circuit Migrated | Algosec & Zscaler requested with incorrect IPs. IP assignment format in Orange Tracker was confusing.
CKT-I-02-UY-MVD01-0001-PCCW-1 | I02943PCCW1 | 2 | There is a 3rd Agile Router with its own circuit. |  | Latin America | Uruguay | Montevideo HO | 2019_757 | ULA-URMONR2-RAVB | un-ula-urymon1-vpn002 | Juan Simon | WAN Circuit Migration |  | PCCW | PCCW |  | N/A | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-05-20 | Complete | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-09-22 | Red | 10-Sep: Migration tentatively accepted for Sep-22. 7-Jul: Circuit Order accepted. 29-Apr: Pending circuit order to provider. | Pink | Circuit Order Accepted | Unilever SNT |  | UY-MVD01-0001 | URUGUAY_MONTEVIDEO |  |  |  |  | Camino Carrasco 5975 |  | 12100 | [6 empty] | 15Mb | 30 |  |  | 2020 | Apr | [14 empty] | Network – 190.0.135.192 Mask – 255.255.255.224 Gateway - 190.0.135.193 IP Range for Customer – from 190.0.135.194 | [11 empty] | Rene Gonzalez Iniguez | [8 empty] | Yes
CKT-I-02-UY-MVD01-0001-ORA-1 | I0220069ORA1 | 2 |  |  | Latin America | Uruguay | Montevideo DC | 2019_760 | un-ula-urycam1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | Orange | Ora |  | GO0AQ9W652 | 2020-05-15 | 2020-05-15 | Complete | 2020-05-20 | 2020-07-11 | Red | 2020-07-19 | 2020-08-15 | Red | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit Ordered | Unilever SNT |  | UY-MVD01-0001 | URUGUAY_MONTEVIDEO_DC |  |  |  |  | Camino Bajo de la Petisa 5205 12800 |  | 12800 | [6 empty] | 25Mb | 25 |  |  | 2020 | Mar | [20 empty] | Antel | [5 empty] | Rene Gonzalez Iniguez
CKT-I-01-UCORPDZA004-PCCW-1 |  | 2 |  |  | NAME | ALGERIA |  |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | PCCW | PCCW |  | N/A | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-04-07 | Amber | 2020-04-17 | 2021-01-01 | Red | 20/08 : Not in UL Tracker 11/06: Circuit still not ordered. 04/05 Circuit provider to advise on the status of circuit order & delivery process | On Hold | Circuit not ordered | Circuit Provider |  | UCORPDZA004 | ALGERIA_ORAN | [14 empty] | 20 |  |  | 2020 | Apr
CKT-I-02-UCORPDZA004-BT-1 | I022167BT1 | 2 |  |  | NAME | ALGERIA | Algeria_Oran |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-07-23 | Red | 2020-04-05 | 2020-11-30 | Red | 2020-04-17 | 2020-12-31 | Red | 20/08: Order placed on 23rd July. Expected delivery is Mid to Late November "07/07 - Deepak confirmed we opted to retain existing BT circuit and asked BT to deliver second resilient circuit for this site 12/06: Still pending update regarding status of this order. Spoke with David C today 04/05 Circuit provider to advise on the status of circuit order & delivery process | Yellow | Circuit not ordered | Circuit Provider |  | UCORPDZA004 | ALGERIA_ORAN | [14 empty] | 20 |  |  | 2020 | Mar
CKT-I-01-UCORPTUN001-ORA-1 |  | 2 |  |  | NAME | TUNISIA | TUNISIA_TUNIS_MEGRINE_ERRIADH | 2018_271 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2021-01-01 | Red | 20/08: Not in UL Tracker 04/05 Circuit provider to advise on the status of circuit order & delivery process | On Hold | Circuit not ordered | Circuit Provider |  | UCORPTUN001 | TUNISIA_TUNIS_MEGRINE_ERRIADH |  |  |  |  | Unilever Tunisia SA Voie Z4 Megrine Riadh, 2014 Tunis, Tunisie | [9 empty] | 40 |  |  | 2020 | Mar
CKT-I-02-UCORPTUN001-ORA-1 |  | 2 |  |  | NAME | TUNISIA | TUNISIA_TUNIS_MEGRINE_ERRIADH | 2018_272 |  |  | Eloise Shepheard | WAN Circuit Migration |  | Orange | Ora |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2021-01-01 | Red | 20/08: Not in UL Tracker 04/05 Circuit provider to advise on the status of circuit order & delivery process | On Hold | Circuit not ordered | Circuit Provider |  | UCORPTUN001 | TUNISIA_TUNIS_MEGRINE_ERRIADH |  |  |  |  | Unilever Tunisia SA Voie Z4 Megrine Riadh, 2014 Tunis, Tunisie | [9 empty] | 40 |  |  | 2020 | Mar
CKT-I-01-CA-AJU01-9600-GTT-1 | I012085GTT1 | 2 | /30 + /30 for corporate and guest |  | North America | CANADA | Anjou/ Montreal | 2018_49 | un-una-cananj1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001828477 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Amber | 2020-07-04 | 2020-10-31 | Red | 2020-07-17 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit Ordered | Unilever SNT | Check dates | CA-AJU01-9600 | CANADA_ANJOU_BOULEVARD_DU_GOLF |  |  |  |  | 9305, rue du Parcours, QC | Anjou | H1J 3A8 | [6 empty] | 6Mb | 30 |  |  | 2020 | Mar | [14 empty] | 209.120.233.56/29 Network - 209.120.233.56 First usable - 209.120.233.57 Last usable - 209.120.233.62 Broadcast - 209.120.233.63 Subnet Mask - 255.255.255.248 209.120.235.140/30 Network - 209.120.235.140 First usable - 209.120.235.141 Last usable - 209.120.235.142 Broadcast - 209.120.235.143 Subnet Mask - 255.255.255.252 | [11 empty] | Rene Gonzalez Iniguez | [8 empty] | Yes
CKT-I-02-CA-AJU01-9600-CTL-1 | I022085CTL1 | 2 | /30 + /30 for corporate and guest |  | North America | Canada | Anjou/ Montreal |  | un-una-cananj1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-08-15 | Red | 2020-04-17 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 30-Apr: Pending circuit delivery. | Yellow | Circuit Order Accepted | Circuit Provider |  | CA-AJU01-9600 | CANADA_ANJOU_BOULEVARD_DU_GOLF |  |  |  |  | 9305, rue du Parcours, QC | Anjou | H1J 3A8 | [6 empty] | 30Mb | 30 |  |  | 2020 | Mar | [14 empty] | LAN: 4.59.178.72/29 WAN: 4.59.178.108/30 CTL: 4.59.178.109 UNI: 4.59.178.110 | [11 empty] | Rene Gonzalez Iniguez
CKT-I-01-CA-REX99-9999-GTT-1 | I01WC050GTT1 | 2 | WAN pool order /30 irrespective |  | North America | Canada | Rexdale Iron St | 2019_71 | una-cathomr1-ien |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001831053 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-07-30 | Complete | 2020-07-17 | 2020-10-02 | Red | 9-Sep: Migration pre-approved for Oct 2. 31-Aug: Migration approved for September 9th at 9AM. Pending successful circuit testing. 24-Aug. Migration tentatively scheduled for Sep 4th. Need to test circuit before (Aug 28). 29-Apr: Pending circuit order to provider. | Green | Circuit Delivered | Unilever SNT |  | CA-REX99-9999 | CANADA_REXDALE_100_IRON_ST |  |  |  |  | Thomson Terminals Limited 100 Iron Street | [8 empty] | 10Mb | 10 |  |  | 2020 | Mar | [14 empty] | 209.120.190.136/29 Network - 209.120.190.136 First usable - 209.120.190.137 Last usable - 209.120.190.142 Broadcast - 209.120.190.143 Subnet Mask - 255.255.255.248 209.120.190.100/30 Network - 209.120.190.100 First usable - 209.120.190.101 Last usable - 209.120.190.102 Broadcast - 209.120.190.103 Subnet Mask - 255.255.255.252 | 209.120.190.101 | 209.120.190.102 | 209.120.190.100/30 |  |  | Tetus | [5 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Complex site type - requires redesign | [6 empty] | Assessment Complete MOP created & config created Partner MOP created Received tunnel IP or LAN IP (if required) | [8 empty] | CRQ000000702327 | Completed | Completed
CKT-I-02-CA-REX99-9999-BT-1 | I02WC050BT1 | 2 | WAN pool order /30 irrespective |  | North America | Canada | Rexdale Iron St | 2019_72 | una-cathomr2-ien |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | CA-REX99-9999 | CANADA_REXDALE_100_IRON_ST |  |  |  |  | Thomson Terminals Limited 100 Iron Street | [8 empty] | 1.5Mb | 10 |  |  | 2020 | Mar
CKT-I-02-CAN00ON004-GTT-1 | I022169GTT1 | 2 |  |  | North America | Canada | Rexdale Belfield Rd | 2019_73 | un-una-canrex1-ien001 | un-una-canrex1-vpn001 | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001831050 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-30 | Complete | 2020-04-17 | 2020-09-13 | Red | 1-Sep: Migration pushed to September 13th at 8:30AM Eastern time. 31-Aug: Mgration approved for September 12th at 8:30AM. Pending successful circuit testing. 24-Aug: Circuit test failed. Need new migration date. 30-Apr: Pending circuit delivery. | Green | Circuit Delivered | Circuit Provider |  | CAN00ON004 | CANADA_REXDALE_BELFIELD_RD |  |  |  |  | 195 Belfield Road | [8 empty] | 10Mb | 40 |  |  | 2020 | Mar | [13 empty] | Office, Main Floor. Same as IT room | 209.120.178.48/30 Network - 209.120.178.48 First usable - 209.120.178.49 Last usable - 209.120.178.50 Broadcast - 209.120.178.51 Subnet Mask - 255.255.255.252 | 209.120.178.49 | 209.120.178.50 |  |  |  | Bell Canada | [5 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | [9 empty] | Assessment Complete MOP created & config created |  |  |  |  | CHG000000000042354 (IEN) CHG000000000041600 (MPLS) | CRQ000000710146 (IEN) CRQ000000706371 (MPLS) |  |  | CRQ000000705514 | Completed | Completed
CKT-I-01-CAN00ON014-BT-1 | I012086BT1 | 2 |  |  | North America | Canada | Simcoe | 2019_75 | un-una-cansim1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-30 | 2020-05-30 | Green | 2020-06-04 | 2020-06-08 | Amber | 2020-08-03 | 2020-08-10 | Red | 2020-08-17 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | CAN00ON014 | CANADA_SIMCOE_UNION_STREET |  |  |  |  | 175 Union St, Simcoe, ON N3Y 2B1 | [8 empty] | 8Mb | 50 |  |  | 2020 | Mar
CKT-I-02-CAN00ON014-GTT-1 | I022086GTT1 | 2 | Less BW ordered |  | North America | Canada | Simcoe | 2019_74 | un-una-cansim1-pio001 | un-una-cansim1-vpn001 | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001830982 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-08-01 | Complete | 2020-04-17 | 2020-08-09 | Complete | 9-Aug: Migration successful. 27-Jul: Rescheduled to Aug 9th. 23-Jul: Migraton approved on August 6th at 9.30AM EST 21-Jul: Circuit migration successful. 30-Apr: Pending circuit delivery. | Complete | Circuit Migrated | Circuit Provider |  | CAN00ON014 | CANADA_SIMCOE_UNION_STREET |  |  |  |  | 175 Union St, Simcoe, ON N3Y 2B1 | [8 empty] | 70Mb | 50 |  |  | 2020 | Mar | [7 empty] | 9:30 AM | [5 empty] | Admin Trailer, ground level. Admin Trailer, ground level | 209.120.178.44/30 Network - 209.120.178.44 First usable - 209.120.178.45 Last usable - 209.120.178.46 Broadcast - 209.120.178.47 Subnet Mask - 255.255.255.252 | 209.120.178.45/30 | 209.120.178.46/30 |  |  |  | Bell Canada | [5 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos | [7 empty] | Yes |  |  | Window Date agreed - End user Comms sent |  | 12:30 AM | 9:30 AM | 109227 | CRQ000000697633 | Approved |  | CRQ000000697626 | Completed | Completed | Tested -Pass-First Time | 21-Jul: Circuit test successful. |  | Circuit Migrated - First Time right
CKT-I-01-CAN00ON001-BT-1 | I01975BT1 | 2 |  |  | North America | Canada | Toronto | 2019_77 | un-una-cantor1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | CAN00ON001 | CANADA_TORONTO_BLOOR_STREET |  |  |  |  | BLOOR STREET EAST | [8 empty] | 50Mb | 120 |  |  | 2020 | Mar
CKT-I-02-CAN00ON001-GTT-1 |  | 2 |  | High | North America | Canada | Toronto |  | un-una-cantor1-vpn001 |  |  | SNT |  | GTT | GTT |  | GTT/001817200 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-07-30 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | CAN00ON001 | CANADA_TORONTO_BLOOR_STREET |  |  |  |  | BLOOR STREET EAST | [8 empty] | 100Mb | 120 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [40 empty] | 97834 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-USA00PR005-CTL-1 | I01WC017CTL1 | 2 |  |  | Latin America | Puerto Rico | San Juan | 2019_618 | un-una-priprs1-pio001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | USA00PR005 | USA_SAN_JUAN_PR |  |  |  |  | Unilever de Puerto Rico, Inc. San Juan, PR 00936-8357 Professional Offices Park II, S.E. 1001 San Roberto St., Suite 301, | [8 empty] | 5Mb | 10 |  |  | 2020 | Mar
CKT-I-02-USA00PR005-BT-1 | I02WC017BT1 | 2 | No access to device |  | Latin America | Puerto Rico | San Juan | 2019_619 | un-una-priprs1-ien001 |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | USA00PR005 | USA_SAN_JUAN_PR |  |  |  |  | Unilever de Puerto Rico, Inc. San Juan, PR 00936-8357 Professional Offices Park II, S.E. 1001 San Roberto St., Suite 301, | [9 empty] | 10 |  |  | 2020 | Apr
CKT-I-01-USA00AR603-CTL-1 | I0110244CTL1 | 2 | Is using serial interface with loopback |  | North America | United States | Bentonville | 2019_702 | un-una-usaben1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-08-15 | Red | 2020-04-17 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 30-Apr: Pending circuit delivery. | Yellow | Circuit Order Accepted | Circuit Provider |  | USA00AR603 | USA_BENTONVILLE_609 SOUTHWEST 8TH STREET_BENTONVILLE PLAZA |  |  |  |  | SOUTHWEST 8TH STREET | [8 empty] | 10Mb | 20 |  |  | 2020 | Mar | [14 empty] | LAN: 4.4.16.184/29 WAN: 4.4.16.128/30 CTL: 4.4.16.129 UNI: 4.4.16.130 | [20 empty] | Yes
CKT-I-02-USA00AR603-GTT-1 |  | 2 |  | High | North America | UNITED STATES |  |  | un-una-usaben1-vpn001 |  |  | SNT |  | GTT | GTT |  | GTT/001817197 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-07-30 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | USA00AR603 | USA_BENTONVILLE_609 SOUTHWEST 8TH STREET_BENTONVILLE PLAZA | [13 empty] | 10Mb | 20 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [40 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-02-USA00VT907-GTT-1 | I0210246GTT1 | 2 |  |  | North America | United States | Burlington Founder's | 2019_705 | un-una-usabur1-pio001 |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001828474 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-12-31 | Red | 2020-04-17 | 2020-10-30 | Red | 30-Apr: Pending circuit delivery. | Yellow | Circuit Order Accepted | Circuit Provider | Check dates | USA00VT907 | USA_BURLINGTON_191 BANK STREET_BURLINGTON - 191 BANK STREET |  |  |  |  | Bank Street Burlington | [8 empty] | 5Mb | 10 |  |  | 2020 | Mar | [13 empty] | 3rd floor. supply closet | 209.120.191.80/29 Network - 209.120.191.80 First usable - 209.120.191.81 Last usable - 209.120.191.86 Broadcast - 209.120.191.87 Subnet Mask - 255.255.255.248 209.120.191.88/30 Network - 209.120.191.88 First usable - 209.120.191.89 Last usable - 209.120.191.90 Broadcast - 209.120.191.91 Subnet Mask - 255.255.255.252 | [5 empty] | Consolidated Communications
CKT-I-01-USA00NC603-CTL-1 | I0110269CTL1 | 2 |  |  | North America | United States | Charlotte | 2019_706 | un-una-usacha1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-09-15 | Red | 2020-04-17 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 30-Apr: Pending circuit delivery. | Yellow | Circuit Ordered | Circuit Provider |  | USA00NC603 | USA_CHARLOTTE_ARCO_CORP_DRIVE |  |  |  |  | 3600 Arco Corporate Drive, Suite 210 | [8 empty] | 10Mb | 20 |  |  | 2020 | Mar
CKT-I-02-USA00NC603-GTT-1 |  | 2 | BW ordered is low than actuall |  | North America | United States | Charlotte |  | un-una-usacha1-pio001 |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | N/A | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-07-30 | Red | 2020-04-17 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | USA00NC603 | USA_CHARLOTTE_ARCO_CORP_DRIVE | [13 empty] | 50Mb | 20 |  |  | 2020 | Mar | [36 empty] | Yes
CKT-I-01-USA00IL612-CTL-1 | I012129CTL1 | 2 | BW ordered is low than actuall |  | North America | United States | Kilbourn | 2019_709 | un-una-usachi1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-01 | Red | 2020-04-17 | 2020-10-30 | Red | 26-Jun: Access restricted to the site. Circuit delivery on hold. 30-Apr: Pending circuit delivery. | Yellow | Circuit Order Accepted | Circuit Provider |  | USA00IL612 | USA_CHICAGO_SOUTH_KILBOURN_AVE |  |  |  |  | SOUTH KILBOURNE AVE | [8 empty] | 30Mb | 30 |  |  | 2020 | Mar | [36 empty] | Yes
CKT-I-02-USA00IL612-GTT-1 | I022129GTT1 | 2 | BW ordered is low than actuall |  | North America | United States | Kilbourn | 2019_708 | un-ula-chikil1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001828465 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-12-31 | Red | 2020-04-17 | 2020-10-30 | Red | 30-Apr: Pending circuit delivery. | Yellow | Circuit Order Accepted | Circuit Provider | Check dates | USA00IL612 | USA_CHICAGO_SOUTH_KILBOURN_AVE |  |  |  |  | SOUTH KILBOURNE AVE | [8 empty] | 25Mb | 20 |  |  | 2020 | Mar | [13 empty] | 1st floor. server room | 209.120.176.76/30 Network - 209.120.176.76 First usable - 209.120.176.77 Last usable - 209.120.176.78 Broadcast - 209.120.176.79 Subnet Mask - 255.255.255.252 | [5 empty] | Comcast | [15 empty] | Yes
CKT-I-02-USA00TN603-GTT-1 |  | 2 |  | High | North America | UNITED STATES |  |  | un-una-usacov1-rtr001 |  |  | SNT |  | GTT | GTT |  | GTT/001817205 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-07-30 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | USA00TN603 | USA_COVINGTON_HIGHWAY_51_NORTH | [13 empty] | 50Mb | 50 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [32 empty] | Yes | [7 empty] | 102214 | [9 empty] | Circuit Migrated - First Time right
CKT-I-02-USA00NJ004-GTT-1 |  | 2 |  |  | North America | UNITED STATES |  |  | un-una-usaec700-rtr001 |  | Juan Simon | SNT |  | GTT | GTT |  | GTT/001821620 | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-07-30 | Red | 2020-04-17 | 2020-05-15 | Red | 4-Feb: Action is Transfer + Transform. | Pink | Circuit not ordered |  | Check dates | USA00NJ004 | USA_ENGLEWOOD_CLIFFS_700_SYLVAN_AVENUE | [13 empty] | 250Mb | 1000 |  |  | 2020 | Mar | [43 empty] | 97836
CKT-I-01-USA00NV600-GTT-1 | I01WC054GTT1 | 2 | There is just 1 circuit in this site, /25 needed, no nat pool |  | North America | United States | Henderson East Horizon |  | un-una-usahen3-tpn001 | un-una-usahen3-vpn001 | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001828457 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-23 | Complete | 2020-04-17 | 2020-09-17 | Red | 9-Sep: Migration still on track for Sep-17. Pending demarc extension. 24-Aug: Migration date still to be confirmed. 29-Apr: Pending circuit order to provider. | Pink | Circuit Delivered | Unilever SNT |  | USA00NV600 | USA_HENDERSON_830 EAST HORIZON DRIVE | [13 empty] | 3Mb | 10 |  |  | 2020 | Mar | [13 empty] | main floor. no specific room | 209.120.176.88/30 Network - 209.120.176.88 First usable - 209.120.176.89 Last usable - 209.120.176.90 Broadcast - 209.120.176.91 Subnet Mask - 255.255.255.252 | 209.120.176.89/30 | 209.120.176.90/30 |  |  |  | Cox | [5 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos | [18 empty] | CRQ000000702338 | Completed | Completed
CKT-I-02-US-HNZ99-9999-CTL-1 | I02WC054CTL1 | 2 | There is just 1 circuit in this site |  | North America | United States | Henderson East Horizon | 2019_716 |  |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-29 | Red | 2020-04-17 |  | Red | 4-Aug: Deepak confirmed this order should be taken out of scope and cancelled 30-Apr: Pending circuit delivery. | Out of Scope | Circuit Order Accepted | Circuit Provider |  | US-HNZ99-9999 | USA_HENDERSON_830 EAST HORIZON DRIVE |  |  |  |  | EAST HORIZON DRIVE | [9 empty] | 10 |  |  | 2020 | Mar
CKT-I-01-USA00MO604-GTT-1 | I012047GTT1 | 2 | No access to device |  | North America | United States | Independence | 2019_721 | uam-usnler2-ien |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | "GTT/001828451 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Amber | 2020-07-04 | 2020-09-30 | Red | 2020-07-17 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit Ordered | Unilever SNT |  | USA00MO604 | USA_INDEPENDENCE_EAST_35TH_STREET_SOUTH |  |  |  |  | E 35TH ST | [9 empty] | 30 |  |  | 2020 | Mar | [14 empty] | 209.120.190.208/29 Network - 209.120.190.208 First usable - 209.120.190.209 Last usable - 209.120.190.214 Broadcast - 209.120.190.215 Subnet Mask - 255.255.255.248 209.120.190.216/30 Network - 209.120.190.216 First usable - 209.120.190.217 Last usable - 209.120.190.218 Broadcast - 209.120.190.219 Subnet Mask - 255.255.255.252
CKT-I-02-USA00MO604-CTL-1 | I022047CTL1 | 2 | /28 needed? no nat pool |  | North America | United States | Independence | 2019_722 | un-una-usaind1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-08-15 | Red | 2020-04-17 | 2020-10-30 | Red | 30-Apr: Pending circuit delivery. | Yellow | Circuit Order Accepted | Circuit Provider |  | USA00MO604 | USA_INDEPENDENCE_EAST_35TH_STREET_SOUTH |  |  |  |  | E 35TH ST | [8 empty] | 20Mb | 30 |  |  | 2020 | Mar | [35 empty] | Yes
CKT-I-01-USA00WA415-GTT-1 | I0110255GTT1 | 2 | Is using serial interface with loopback |  | North America | United States | Issaquah | 2019_723 | un-una-usaissa-rtr001 |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001828445 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-07-30 | Red | 2020-04-17 | 2020-07-15 | Red | 23-Jul: Site to be closed. Circuit order cancelled. 30-Apr: Pending circuit delivery. | Out of Scope | Circuit Ordered | Circuit Provider | Check dates | USA00WA415 | USA_ISSAQUAH_64TH_PLACE |  |  |  |  | SE 64TH PLACE, Suite 140 | [8 empty] | 1.536Mb | 10 |  |  | 2020 | Mar | [13 empty] | main floor. first floor building G at Meadow Creek
CKT-I-02-USA00WA415-CTL-1 | I0210255CTL1 | 2 | BW ordered is low than actuall |  | North America | United States | Issaquah | 2019_724 | un-una-usaissa-ien001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-08-15 | Red | 2020-04-17 | 2020-09-15 | Red | 23-Jul: Site to be closed. Circuit order cancelled. 1-Jun: Sales site closed until September. 30-Apr: Pending circuit delivery. | Out of Scope | Circuit Order Accepted | Circuit Provider |  | USA00WA415 | USA_ISSAQUAH_64TH_PLACE |  |  |  |  | SE 64TH PLACE, Suite 140 | [8 empty] | 50Mb | 50 |  |  | 2020 | Mar | [36 empty] | Yes
CKT-I-01-USA00AR602-BT-1 | I019475BT1 | 2 | 2 additional circuits, one for voice and one for video conference, unsure if these should be migrated as well. |  | North America | United States | Jonesboro | 2019_729 | un-una-usajon1-drt001 |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  | N/A | 2020-05-30 | 2020-05-30 | Green | 2020-06-04 | 2020-06-08 | Amber | 2020-08-03 | 2020-08-10 | Red | 2020-08-17 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | USA00AR602 | USA_JONESBORO_QUALITY_WAY |  |  |  |  | 2407 Quality Way, Jonesboro, AR 72401, United States | [8 empty] | 30Mb | 40 |  |  | 2020 | Mar
CKT-I-02-USA00AR602-GTT-1 |  | 2 | 2 additional circuits, one for voice and one for video conference, unsure if these should be migrated as well. |  | North America | United States | Jonesboro | 2019_728 | un-una-usajon1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001821840 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-30 | Red | 2020-04-17 | 2020-10-30 | Red | 4-Feb: Action is Transfer + Transform. | Pink | Circuit Order Accepted | Circuit Provider |  | USA00AR602 | USA_JONESBORO_QUALITY_WAY |  |  |  |  | 2407 Quality Way, Jonesboro, AR 72401, United States | [8 empty] | 30Mb | 40 |  |  | 2020 | Mar | [43 empty] | 97836 | [13 empty] | 2020-04-01
CKT-I-01-USA00MN603-CTL-1 | I019615CTL1 | 2 | Additional router with own circuit una-usminr3-cme. |  | North America | United States | Minneapolis | 2019_730 | un-una-usamin1-rtr001 | un-una-usamin1-vpn002 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-05-15 | Complete | 2020-04-17 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 15-May: Circuit delivered. Pending testing. 30-Apr: Pending circuit delivery. | Pink | Circuit Delivered | Unilever Geo-IT |  | USA00MN603 | USA_MINNEAPOLIS_NICOLLETT_MALL |  |  |  |  | 801 NICOLLET MALL | [8 empty] | 30Mb | 50 |  |  | 2020 | Mar | [14 empty] | LAN: 4.34.146.192/29 WAN: 4.14.209.228/30 CTL: 4.14.209.229 UNI: 4.14.209.230 | 4.14.209.229/30 | 4.14.209.230/30 | 4.34.146.192/29 | [8 empty] | Fernando Ramos | [8 empty] | Yes
CKT-I-02-USA00MN603-GTT-1 |  | 2 | Additional router with own circuit una-usminr3-cme. | High | North America | UNITED STATES | Minneapolis |  | un-una-usamin1-vpn001 |  |  | SNT |  | GTT | GTT |  | GTT/001827066 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-07-30 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | USA00MN603 | USA_MINNEAPOLIS_NICOLLETT_MALL | [13 empty] | 50Mb | 50 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [32 empty] | Yes | Yes | [6 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-USA00NY603-CTL-1 | I0110865CTL1 | 2 | Cannot find diagram for New York Hudson Street |  | North America | UNITED STATES | New York Hudson St | 2018_304 | un-una-usanyc2-vpn001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-08-15 | Red | 2020-04-17 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 30-Apr: Pending circuit delivery. | Yellow | Circuit Order Accepted | Circuit Provider |  | USA00NY603 | USA_NEW YORK_99HUDSON_STREET |  |  |  |  | 99 HUDSON ST | [8 empty] | 100Mb | 100 |  |  | 2020 | Mar | [14 empty] | LAN: 4.34.119.128/29 WAN: 4.14.156.216/30 CTL: 4.14.156.217 UNI: 4.14.156.218 | [20 empty] | Yes
CKT-I-02-USA00NY603-GTT-1 |  | 2 | Cannot find diagram for New York Hudson Street |  | North America | UNITED STATES | New York Hudson St |  | un-una-usanyc2-vpn002 |  | Juan Simon | SNT |  | GTT | GTT |  | GTT/001832685 | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-07-30 | Red | 2020-04-17 | 2020-05-15 | Red | 4-Feb: Action is Transfer + Transform. | Pink | Circuit not ordered |  | Check dates | USA00NY603 | USA_NEW YORK_99HUDSON_STREET | [13 empty] | 100Mb | 100 |  |  | 2020 | Mar | [35 empty] | Yes | [7 empty] | 97836
CKT-I-01-USA00IL907-CTL-1 | I0110696CTL1 | 2 | Maximum bandwidth for 4331 is 40Mb There is an additional router un-una-usnbrr2-cube with 2 circuits connected to it. |  | North America | United States | Northbrook | 2019_732 | un-una-usanbr1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-08-15 | Red | 2020-04-17 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 30-Apr: Pending circuit delivery. | Yellow | Circuit Order Accepted | Circuit Provider |  | USA00IL907 | USA_NORTHBROOK_4080 COMMERCIAL AVENUE_NORTHBROOK SALES OFFICE |  |  |  |  | COMMERCIAL AVE | [8 empty] | 10Mb | 10 |  |  | 2020 | Mar | [14 empty] | WAN: 4.14.9.80/30 CTL: 4.14.9.81 UNI: 4.14.9.82 | [21 empty] | Yes
CKT-I-02-USA00IL907-GTT-1 | I0210696GTT1 | 2 | Maximum bandwidth for 4331 is 40Mb There is an additional router un-una-usnbrr2-cube with 2 circuits connected to it. |  | North America | United States | Northbrook | 2019_732 | un-una-usanbr1-pio001 |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001828439 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Amber | 2020-07-04 | 2020-12-31 | Red | 2020-07-17 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit Ordered | Unilever SNT | Check dates | USA00IL907 | USA_NORTHBROOK_4080 COMMERCIAL AVENUE_NORTHBROOK SALES OFFICE |  |  |  |  | COMMERCIAL AVE | [8 empty] | 50Mb | 10 |  |  | 2020 | Mar | [14 empty] | 209.120.232.232/29 Network - 209.120.232.232 First usable - 209.120.232.233 Last usable - 209.120.232.238 Broadcast - 209.120.232.239 Subnet Mask - 255.255.255.248 209.120.146.180/30 Network - 209.120.146.180 First usable - 209.120.146.181 Last usable - 209.120.146.182 Broadcast - 209.120.146.183 Subnet Mask - 255.255.255.252 | [20 empty] | Yes
CKT-I-01-USA00CA203-CTL-1 | I012067CTL1 | 2 |  |  | North America | United States | Pleasanton | 2019_733 | un-una-usaple-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-08-15 | Red | 2020-04-17 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 30-Apr: Pending circuit delivery. | Yellow | Circuit Order Accepted | Circuit Provider |  | USA00CA203 | USA_PLEASANTON_HACIENDA_DRIVE | [13 empty] | 10Mb | 20 |  |  | 2020 | Mar | [14 empty] | WAN: 4.28.13.200/30 CTL: 4.28.13.201 UNI: 4.28.13.202
CKT-I-02-USA00CA203-GTT-1 | I022067GTT1 | 2 | Ordered BW lower than current |  | North America | United States | Pleasanton | 2019_734 | un-una-usaple1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001828423 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-12-31 | Red | 2020-04-17 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 30-Apr: Pending circuit delivery. | Yellow | Circuit Ordered | Circuit Provider | Check dates | USA00CA203 | USA_PLEASANTON_HACIENDA_DRIVE |  |  |  |  | 4305 HACIENDA DRIVE | [8 empty] | 50Mb | 20 |  |  | 2020 | Mar | [13 empty] | 4th floor, suite 450. server room | [22 empty] | Yes
CKT-I-02-US-RFN01-0001-GTT-1 |  | 2 | Maximum bandwidth for 4331 is 70Mb | High | North America | United States | Raeford |  | un-una-usarae1-vpn001 |  |  | SNT |  | GTT | GTT |  | GTT/001827137 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-07-30 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | US-RFN01-0001 | USA_RAEFORD_FABERGE_BLVD | [13 empty] | 60Mb | 100 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Rene Gonzalez Iniguez | [16 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-USA00AR604-CTL-1 | I0110701CTL1 | 2 |  |  | North America | United States | Rogers | 2019_736 | un-una-usarog1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-08-15 | Red | 2020-04-17 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 30-Apr: Pending circuit delivery. | Yellow | Circuit Order Accepted | Circuit Provider |  | USA00AR604 | USA_ROGERS_5078_NORTHGATE_ROAD |  |  |  |  | 5078 NORTHGATE RD | [8 empty] | 45Mb | 50 |  |  | 2020 | Mar | [14 empty] | WAN: 4.4.16.12/30 CTL: 4.4.16.13 UNI: 4.4.16.14
CKT-I-02-USA00AR604-GTT-1 |  | 2 | Additional router uni-us-rog-cme with voice circuit. |  | North America | United States | Rogers |  | un-una-usarog1-rtr001 |  | Juan Simon | SNT |  | GTT | GTT |  | GTT/001821831 | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-07-30 | Red | 2020-04-17 | 2020-05-15 | Red | 4-Feb: Action is Transfer + Transform. | Pink | Circuit not ordered |  | Check dates | USA00AR604 | USA_ROGERS_5078_NORTHGATE_ROAD | [13 empty] | 45Mb | 50 |  |  | 2020 | Mar | [35 empty] | Yes | [7 empty] | 102214
CKT-I-01-USA00MO607-GTT-1 | I0110264GTT1 | 2 |  |  | North America | United States | Sikeston 2400 | 2019_740 | un-una-usasik1-pio001 | un-una-usasik1-vpn002 | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001828417 | 2020-01-31 | 2020-01-27 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-06-15 | Complete | 2020-04-17 | 2020-08-18 | Complete | 24-Aug: Migration successful. 4-Aug: Migration pushed to August 18th at 1PM central time. 20-Jul: Migration approved for August 6th at 1PM. 13-Jul: Tested again with GTT and had issues. They will follow up with AT&T. 1-Jul: We tested the circuit but could not get a connection. Will need to test with GTT. 26-Jun: Pending circuit testing: 30-Apr: Pending circuit delivery. | Complete | Circuit Migrated | Unilever SNT |  | USA00MO607 | USA_SIKESTON_2400_ROSE_PARKWAY |  |  |  |  | 2400 Rose Parkway | Sikeston |  |  | Scott Russell | Scott.Russell@unilever.com | 573 472 8489 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 15Mb | 100 |  |  | 2020 | Mar | [13 empty] | 2nd floor. Same as IT room | 209.120.176.180/30 Network - 209.120.176.180 First usable - 209.120.176.181 Last usable - 209.120.176.182 Broadcast - 209.120.176.183 Subnet Mask - 255.255.255.252 | 209.120.176.181/30 | 209.120.176.182/30 |  |  |  | AT&T Wholesale | [5 empty] | Fernando Ramos | [16 empty] | 109199 | CRQ000000696891 | Approved |  | CRQ000000696504 | Completed | Completed | Tested-Pass | 13-Jul: Tested again with GTT and iPerf. Issues with TCP transfers. GTT will look into it. 1-Jul: Could not get a connection. |  | Circuit Migrated
CKT-I-02-USA00MO607-CTL-1 | I0210264CTL1 | 2 |  |  | North America | United States | Sikeston 2400 | 2019_739 | un-una-usasik1-rtr001 | un-una-usasik1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-06-16 | Complete | 2020-04-17 | 2020-07-23 | Complete | 13-Jul: Tested again with CTL and got successful results. To be migrated on July 23rd at 1PM local time. 1-Jul: We tested the circuit and got OK download speeds, but low upload speeds. Will need to test again with CTL in an activation call. 26-Jun: Pending circuit testing: 30-Apr: Pending circuit delivery. | Complete | Circuit Migrated | Unilever SNT |  | USA00MO607 | USA_SIKESTON_2400_ROSE_PARKWAY |  |  |  |  | 2400 Rose Parkway | Sikeston |  |  | Scott Russell | Scott.Russell@unilever.com | 573 472 8489 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 50Mb | 70 |  |  | 2020 | Mar | [7 empty] | 1PM | [6 empty] | WAN: 4.28.94.52/30 CTL: 4.28.94.53 UNI: 4.28.94.54 | 4.28.94.53/30 | 4.28.94.54/30 | [9 empty] | Fernando Ramos | [12 empty] | Window Date agreed - End user Comms sent |  | 6PM UTC | 1PM | 102768 | CRQ000000692770 | Approved |  | CRQ000000692182 | Completed | Completed | Tested-Pass | 13-Jul: Tested again with CTL remotely and test was successful. 1-Jul: Download speed OK, Upload speed very slow. |  | Circuit Migrated
CKT-I-01-US-SIK99-2500-ORA-1 | I01WC056ORA1 | 2 | IP took from int Loopback |  | North America | United States | Sikeston 2500 | 2019_741 | un-una-usasik1-tpi001 |  | Juan Simon | WAN Circuit Migration |  | Orange | Ora |  |  | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-20 | Amber | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | US-SIK99-2500 | USA_SIKESTON_2500_ROSE_PARKWAY |  |  |  |  | 2500 Rose Parkway | Sikeston |  |  | Scott Russell | Scott.Russell@unilever.com | 573 472 8489 | Debbie Clarke | Debbie.G.Clarke@unilever.com | .5Mb | 10 |  |  | 2020 | Mar | [26 empty] | Fernando Ramos
CKT-I-02-US-SIK99-2500-CTL-1 | I01WC056CTL1 | 2 |  |  | North America | United States | Sikeston 2500 | 2019_742 | un-una-usasik2-pio001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | 442310507 | 2020-05-30 | 2020-05-30 | Green | 2020-06-04 | 2020-06-08 | Amber | 2020-08-03 | 2020-06-30 | Green | 2020-08-17 | 2020-09-26 | Red | 29-Apr: Pending circuit order to provider. | Pink | Circuit not ordered | Unilever SNT |  | US-SIK99-2500 | USA_SIKESTON_2500_ROSE_PARKWAY |  |  |  |  | 2500 Rose Parkway | Sikeston |  |  | Scott Russell | Scott.Russell@unilever.com | 573 472 8489 | Debbie Clarke | Debbie.G.Clarke@unilever.com | 3Mb | 10 |  |  | 2020 | Mar | [13 empty] | 1st Mechanical Wall Mounted | LAN: 4.79.252.216/29 WAN: 4.79.253.100/30 CTL: 4.79.253.101 UNI: 4.79.253.102 | 4.79.253.101/30 | 4.79.253.102/30 | 4.79.252.216/29 | [8 empty] | Fernando Ramos
CKT-I-01-NONULMO608-CTL-1 | I0110910CTL1 | 2 | Only one router on site, should both circuits be connected to this single router? WAN pool order /30 irrespective |  | North America | United States | Sikeston Noles Rd | 2019_743 | un-una-usasik2-pio001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-05-15 | 2020-05-15 | Green | 2020-05-20 | 2020-05-20 | Green | 2020-07-19 | 2020-07-15 | Green | 2020-07-31 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit not ordered | Unilever SNT |  | NONULMO608 | USA_SIKESTON_515 NOLES ROAD |  |  |  |  | NOLES ROAD, Noles Dr | [8 empty] | 3Mb | 10 |  |  | 2020 | Mar | [26 empty] | Fernando Ramos
CKT-I-02-NONULMO608-ORA-1 | I0210910ORA1 | 2 | Only one router on site, should both circuits be connected to this single router? WAN pool order /30 irrespective |  | North America | United States | Sikeston Noles Rd | 2019_744 | un-una-usasik2-pio001 |  | Juan Simon | WAN Circuit Migration |  | Orange | Ora |  |  | 2020-05-30 | 2020-05-30 | Complete | 2020-06-04 | 2020-06-11 | Red | 2020-08-03 | 2020-08-10 | Red | 2020-08-17 | 2020-10-30 | Red | 29-Apr: Pending circuit order to provider. | Yellow | Circuit Ordered | Unilever SNT |  | NONULMO608 | USA_SIKESTON_515 NOLES ROAD |  |  |  |  | NOLES ROAD, Noles Dr | [8 empty] | 3Mb | 10 |  |  | 2020 | Mar | [26 empty] | Fernando Ramos
CKT-I-01-USA00VT001-CTL-1 | I012853CTL1 | 2 | /30 + /30 for corporate and guest |  | North America | United States | South Burlington | 2019_746 | un-una-usabur1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-03-10 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-05-01 | Complete | 2020-04-17 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 1-May: Circuit delivered. Pending testing. 30-Apr: Pending circuit delivery. | Pink | Circuit Delivered | Unilever Geo-IT |  | USA00VT001 | USA_SOUTH_BURLINGTON_COMMUNITY_DRIVE |  |  |  |  | 30 COMMUNITY DR. | [8 empty] | 25Mb | 100 |  |  | 2020 | Mar | [14 empty] | WAN: 4.53.50.168/29 CTL: 4.53.50.169 UNI: 4.53.50.170 | [11 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | [6 empty] | Yes
CKT-I-02-USA00VT001-GTT-1 |  | 2 | already GTT with 100Mb | High | North America | UNITED STATES | South Burlington |  | un-una-usabur1-vpn001 |  |  | SNT |  | GTT | GTT |  | GTT/001817227 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-07-30 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | USA00VT001 | USA_SOUTH_BURLINGTON_COMMUNITY_DRIVE | [13 empty] | 100Mb | 100 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [40 empty] | 102214 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-USA00VA603-CTL-1 | I012054CTL1 | 2 |  |  | North America | United States | Suffolk | 2019_748 | un-una-usasuf1-rtr001 | un-una-usasuf1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | 441620966 | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-01 | Complete | 2020-04-17 | 2020-07-04 | Complete | 4-Jul: Migration successful. Circuit upload speed still lower than expected. Will need an activations call with CenturyLink. 2-Jul: We tested the circuit and got OK download speed, but very slow upload speed. Welington approved to continue with the migration anyway since current circuit speed is similar to the UL results we got. Will ask CTL to analyze and fix circuit after migration. 1-Jul: Circuit delivered. 26-Jun: Risk of circuit not being ready on time. 17-Jun: Migration approved for July 4th 7AM EST. 8-Jun: Circuit not to be installed before late-June. Migration will most likely be in July. 3-Jun: Circuit test requested for June 9th, and migration on June 16th at 1PM CDT. 30-Apr: Pending circuit delivery. | Complete | Circuit Migrated | Circuit Provider | Check dates | USA00VA603 | USA_SUFFOLK_WEST_WASHINGTON_STREET |  |  |  |  | W WASHINGTON ST | [8 empty] | 8Mb | 50 |  |  | 2020 | Mar | [14 empty] | WAN: 4.16.72.232/29 CTL: 4.16.72.233 UNI: 4.16.72.234 | 4.16.72.233/29 | 4.16.72.234/29 | [9 empty] | Sandor Jardon Vera |  |  |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress |  | No | Yes |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 11AM UTC | 7AM EST | 88058 | CRQ000000686973 | Approved |  | CRQ000000685559 | Completed | Completed | Tested-Fail | 2-Jul: We got OK DL speed, but very slow UL speed. Will do migration anyway since current circuit speed is similar to tthe UL results we got. |  | Circuit Migrated - First Time right
CKT-I-02-USA00VA603-GTT-1 |  | 2 |  |  | North America | United States | Suffolk |  | un-una-usasuf1-vpn001 |  | Juan Simon | SNT |  | GTT | GTT |  | GTT/001845462 | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-07-30 | Red | 2020-04-17 | 2020-05-15 | Red | 4-Feb: Action is Transfer + Transform. | Pink | Circuit not ordered |  | Check dates | USA00VA603 | USA_SUFFOLK_WEST_WASHINGTON_STREET | [13 empty] | 40Mb | 50 |  |  | 2020 | Mar | [43 empty] | 102214
Out of Scope |  | 2 | Out of scope - No Device Access |  | North America | United States | Washington DC | 2019_54 | un-ula-branat1-rtr001 |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | #NO MATCH | 2020-01-31 | 2020-01-31 | Out of Scope | 2020-02-05 | #NO MATCH | Out of Scope | 2020-04-05 | #NO MATCH | Out of Scope | 2020-04-17 |  | Out of Scope | Out of Scope | Out of Scope | Circuit not ordered |  |  | USA00DC900 | USA_WASHINGTON DC_816 CONNECTICUT AVENUE NORTHWEST_WASHINGTON -816 CONNECTICUT | [13 empty] | 2Mbps | 50 |  |  | 2020 | Mar | [13 empty] | #NO MATCH | #NO MATCH |  |  |  | #NO MATCH | #NO MATCH | #NO MATCH | [9 empty] | #NO MATCH
CKT-I-02-USA00DC900-GTT-1 |  | 2 | Only one router on site, should both circuits be connected to this single router? No access by Telnet and SSH to the router. Regarding Vision diagram router needs to be replaced, current one is Cisco 2911. | High | North America | United States | Washington DC |  | un-uni-us-wdc1-ien1 |  |  | SNT |  | GTT | GTT |  | GTT/001820124 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-07-30 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | USA00DC900 | USA_WASHINGTON DC_816 CONNECTICUT AVENUE NORTHWEST_WASHINGTON -816 CONNECTICUT |  |  |  |  | CONNECTICUT AVENUE NORTHWEST NORTHWEST WASHINGTON | [8 empty] | 50Mb | 10 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [50 empty] | Circuit Migrated - First Time right
CKT-I-01-USA00VT600-CTL-1 | I012855CTL1 | 2 |  |  | North America | United States | Waterbury | 2019_753 | un-una-usawat1-rtr001 | un-una-usawat1-vpn002 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | N/A | 2020-01-31 | 2020-01-29 | Complete | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-06-08 | Complete | 2020-04-17 | 2020-07-06 | Complete | 6-Jul: Migration successful. Circuit found with slow upload speed. Will have to get CenturyLink to investigate. 3-Jul: CenturyLink found a port misconfiguration in their router. They fixed it and we will have to test again at the beginning of the migration window. 1-Jul: We tested the circuit but could not get a connection. Will try again to test at the beginning of migration window with FE, and only continue if the test is successful. 26-Jun: Migration pushed to July 6th at 8:30AM EST. 17-Jun: Migration approved for July 3rd 11AM EST. 8-Jun: Circuit delivered 30-Apr: Pending circuit delivery. | Complete | Circuit Migrated | Cisco |  | USA00VT600 | USA_WATERBURY_WATERBURY_STOWE_ROAD |  |  |  |  | 1281 Waterbury Stowe Rd , Waterbury, VT 05676 , USA | [8 empty] | 8Mb | 30 |  |  | 2020 | Mar | [7 empty] | 11AM EST | [6 empty] | WAN: 4.15.70.208/29 CTL: 4.15.70.209 UNI: 4.15.70.210 | 4.15.70.209/30 | 4.15.70.210/30 | [9 empty] | Fernando Ramos | [8 empty] | Yes |  |  |  | Window Date agreed - End user Comms sent |  | 12:30PM UTC | 8:30 AM local | 88335 | CRQ000000687177 | Approved |  | CRQ000000686348 | Completed | Completed | Tested-Fail | 3-Jul: CTL reviewed their circuit configuration on their end and found a misconfiguration in Port 3. Will have to test again at the beginning of the migration window. 1-Jul: Circuit testing failed. Could not get a connection. |  | Circuit Migrated - First Time right
CKT-I-02-USA00VT600-GTT-1 |  | 2 | Static NAT confiugred (seems to be internal connection and not to internet) |  | North America | United States | Waterbury |  | un-una-usawat1-vpn001 |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001821835 | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Complete | 2020-04-05 | 2020-07-30 | Red | 2020-04-17 | 2020-10-30 | Red | 4-Feb: Action is Transfer + Transform. | Pink | Circuit not ordered | Unilever SNT |  | USA00VT600 | USA_WATERBURY_WATERBURY_STOWE_ROAD | [13 empty] | 20Mb | 30 |  |  | 2020 | Mar | [26 empty] | Fernando Ramos | [16 empty] | 102214 | [13 empty] | 2020-04-01
CKT-I-01-UCORPHKG004-GTT-1 |  | 2 |  | High | North Asia | HONG KONG | HONG_KONG_TAIPO_GIOHONG_KONG |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817198 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Green | 2020-03-18 | 2020-06-30 | Red | 2020-04-01 | 2020-05-06 | Red |  | Pink | Circuit Ordered |  | Check dates | UCORPHKG004 | HONG_KONG_TAIPO_GIOHONG_KONG |  |  |  |  | Unilever Hongkong Ltd. 6 DAI FU ST., TAI PO IND. ESTATE, TAI PO NT | [9 empty] | 50 |  |  | 2020 | May |  | 2020-05-21 | Cost Reduction | [40 empty] | 97834
CKT-I-02-UCORPHKG004-BT-1 | I023776BT1 | 2 |  |  | North Asia | HONG KONG |  |  |  |  | Vishal Joshi | Soft Delete | Circuit | BT | BT |  | N/A | 2020-01-31 | 2020-01-31 | Green | 2020-02-05 | 2020-02-07 | Amber | 2020-04-05 | 2020-04-07 | Amber | 2020-04-17 | 2020-05-29 | Red |  | Out of Scope | Circuit not ordered |  |  | UCORPHKG004 | HONG_KONG_TAIPO_GIOHONG_KONG | [14 empty] | 50 |  |  | 2020 | Mar
CKT-I-01-PH-TAU02-0001-GTT-1 |  | 2 |  | High | SEAA | PHILIPPINES | Bonifacio Stopover Corporate Center |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817221 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | PH-TAU02-0001 | PHILIPPINES_BGC_HQ |  |  |  |  | 31st Street corner 2nd Avenue, Bonifacio Global City | Taguig | 1486 | [7 empty] | 300 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [40 empty] | 97834 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-SG-SIN98-9999-GTT-1 |  | 2 |  | High | SEAA | SINGAPORE | 1 Net DC |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817222 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | SG-SIN98-9999 | SINGAPORE_750E CHAI CHEE_1-NET DC | [5 empty] | SINGAPORE | [8 empty] | 1000 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [50 empty] | Circuit Migrated - First Time right
CKT-I-01-US-CXP01-NY5-GTT-1 |  | 2 |  | High | North America | United States | NY5 |  | un-una-usasec1-rtr001 |  |  | SNT |  | GTT | GTT |  | GTT/001820848 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Green | 2020-03-18 | 2020-07-30 | Red | 2020-04-01 | 2020-03-17 | Green |  | Pink | Circuit Ordered |  | Check dates | US-CXP01-NY5 | USA_SECAUCUS_800 SECAUCUS ROAD |  |  |  |  | 800 Secaucus Rd, Secaucus, NJ, 7094 | New Jersey | 7094 | [10 empty] | 2020 | Mar |  | 2020-04-01 | Cost Reduction | [40 empty] | 107850
CKT-I-01-US-CXP02-DC6-GTT-1 |  | 2 |  | High | North America | United States | DC6 |  | un-una-usawdc2-rtr001 |  |  | SNT |  | GTT | GTT |  | GTT/001820802 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Green | 2020-03-18 | 2020-07-30 | Red | 2020-04-01 | 2020-03-17 | Green |  | Pink | Circuit Ordered |  | Check dates | US-CXP02-DC6 | USA_ASHBURN_21715 FILIGREE COURT_BUILDING F |  |  |  |  | 21721 Filigree Ct., VA | Ashburn | 20147 | [10 empty] | 2020 | Mar |  | 2020-04-01 | Cost Reduction | [40 empty] | 107850
CKT-I-01-UK-CXP01-LD6-GTT-1 |  | 2 |  | High | Europe | UNITED KINGDOM | LD6 |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001820742 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | UK-CXP01-LD6 | CxP Equinix LD6 | [17 empty] | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [23 empty] | Arijon Alija | Arijon Alija | [25 empty] | Circuit Migrated - First Time right
CKT-I-01-KR-SEL02-0001-GTT-1 |  | 2 |  | High | SEAA | South Korea | Apple Tree Tower |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001827145 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | KR-SEL02-0001 | KOREA_SEOUL_HEAD_OFFICE | [17 empty] | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [40 empty] | 102214 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-KR-TJN02-0001-GTT-1 |  | 2 |  | High | SEAA | South Korea | Unilever SC Office, R&D Office and Laboratory |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001817211 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | KR-TJN02-0001 | SOUTH KOREA_DAEJEON_40 - 66 DEHWA-DONG_DAEJEON-FACTORY | [17 empty] | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [40 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-SG-SIN07-0001-GTT-1 |  | 2 |  | High | SEAA | SINGAPORE | Four Acres |  |  |  |  | SNT |  | GTT | GTT |  | GTT/001827055 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Green | 2020-03-18 | 2020-06-30 | Red | 2020-04-01 | 2020-06-03 | Red |  | Pink | Circuit Ordered |  | Check dates | SG-SIN07-0001 | SINGAPORE_SINGAPORE_18 PORTSDOWN ROAD_FOUR ACRES SINGAPORE |  |  |  |  | 18 Nepal Park | SINGAPORE | 139407 | [7 empty] | 100 | 1.2938 | 103.8533 | 2020 | Jun |  | 2020-06-18 | Cost Reduction | [40 empty] | 97836
CKT-I-01-SG-SIN90-9999-GTT-1 |  | 2 |  | High | SEAA | SINGAPORE | [5 empty] | SNT |  | GTT | GTT |  | GTT/001817208 | 2020-01-13 | 2020-01-13 | Complete | 2020-01-18 | 2020-01-18 | Complete | 2020-03-18 | 2020-02-29 | Complete | 2020-04-01 | 2020-02-29 | Complete |  | Complete | Circuit Migrated |  | Check dates | SG-SIN90-9999 | SINGAPORE_TOLL_ASIA_TANJONG_PENJURU | [5 empty] | SINGAPORE | [8 empty] | 10 |  |  | 2020 | Feb |  | 2020-03-15 | Cost Reduction | [40 empty] | 97836 | [9 empty] | Circuit Migrated - First Time right
CKT-I-01-UCORPLKA041-UNL-1 | I018531UNL1 | 2 | dont have existing WAN router configs in site. Need them for validation | High | South Asia | Sri Lanka | Horana - Factory |  | un-sea-lkahor-vpn001 |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | 099-4606075 | 2020-01-10 | 2020-01-10 | Complete | 2019-11-01 | 2020-01-17 | Complete | 2020-02-29 | 2020-02-29 | Complete | 2020-03-13 | 2020-03-09 | Complete |  | Complete | Circuit Migrated |  |  | UCORPLKA041 | [5 empty] | UNILEVER SRI LANKA HORANA MANUFACTURING FACILITY, HORANA, EXPORT PROCESSING ZONE, BORALUGODA, PORUWADANDA, HORANA | Horana |  | Factory |  |  |  | Kushan Wijesinghe | Kushan.Wijesinghe@unilever.com |  | 50 |  |  | 2020 | Feb | Internet |  |  |  |  | SC2 |  |  | No training required, 15 mins briefing on safety to be done on the day of activity. |  |  | /29 |  |  | WAN Block (first IP will be used in PE side) 122.255.35.248/30 LAN Block: 122.255.32.64/29 | 122.255.35.249/30 | 122.255.35.250/30 | 122.255.32.64/29 | 0.995 | 4 hrs | Dialog | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual MPLS | Complete |  | No | Yes | Yes | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Prep documents uploaded to central storage Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 2:30 am to 12:30 pm UTC | 8am to 5 pm local time | 44655 | CRQ000000647571 | Approved | 41412 | CRQ000000644247 | Completed | Completed | Tested -Pass-First Time |  | Prasanna | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-03-01
CKT-I-02-UCORPLKA041-UNL-1 | I028531UNL1 | 2 | dont have existing WAN router configs in site. Need them for validation | High | South Asia | Sri Lanka | Horana - Factory |  | un-sea-lkahor-vpn002 |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | D87885 | 2020-01-10 | 2020-01-10 | Complete | 2019-11-01 | 2020-01-17 | Complete | 2020-02-15 | 2020-02-22 | Complete | 2020-02-28 | 2020-03-09 | Complete |  | Complete | Circuit Migrated |  |  | UCORPLKA041 | [5 empty] | UNILEVER SRI LANKA HORANA MANUFACTURING FACILITY, HORANA, EXPORT PROCESSING ZONE, BORALUGODA, PORUWADANDA, HORANA | Horana |  | Factory |  |  |  | Kushan Wijesinghe | Kushan.Wijesinghe@unilever.com |  | 30 |  |  | 2020 | Feb | Internet |  |  |  |  | SC2 |  |  | No training required, 15 mins briefing on safety to be done on the day of activity. | [5 empty] | WAN IP (Customer End): 203.94.91.178 Subnet Mask - 255.255.255.252 LAN IP Block - 220.247.249.24 Subnet Mask - 255.255.255.248 | 203.94.91.177/30 | 203.94.91.178/30 | 220.247.249.24/29 |  |  | SLT | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual MPLS | Complete |  | No | Yes | Yes | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Prep documents uploaded to central storage Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 2:30 am to 12:30 pm UTC | 8am to 5 pm local time | 44655 | CRQ000000647571 | Approved | 41327 | CRQ000000642592 | Completed | Completed | Tested -Pass-First Time |  | Prasanna | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-03-01
CKT-I-01-UCORPLKA034-UNL-1 | I012322UNL1 | 2 | dont have existing WAN router configs in site. Need them for validation | High | South Asia | Sri Lanka | Agarapathana |  | un-sea-lkaagp-vpn001 |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | 099-4606004 | 2020-01-10 | 2020-01-10 | Complete | 2019-11-01 | 2020-01-17 | Complete | 2020-02-29 | 2020-02-29 | Complete | 2020-03-13 | 2020-05-17 | Complete |  | Complete | Circuit Migrated |  |  | UCORPLKA034 | [5 empty] | UNILEVER PREMIUM EXPORTS LTD, CEYTEA, HOLBROOKE, DIYAGAMA ROAD, LINDULA, AGARAPATHANA | Agarapathana | [5 empty] | Kushan Wijesinghe | Kushan.Wijesinghe@unilever.com |  | 30 |  |  | 2020 | Feb | Internet |  |  |  |  | SC2 |  |  | No training required, 15 mins briefing on safety to be done on the day of activity. |  |  | /29 |  |  | WAN Block (first IP will be used in PE side) 122.255.36.8/30 LAN Block: 122.255.32.112/29 | 122.255.36.9/30 | 122.255.36.10/30 | 122.255.32.112/29 | 0.995 | 4 hrs | Dialog | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual MPLS | Complete |  | No | Yes | Yes | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 3:30 am to 3:30 pm UTC | 9 am to 9 pm local time | 61068 | CRQ000000669233 | Approved | 41413 | CRQ000000644539 | Completed | Completed | Tested-Pass | 1st link testing was successful in 2nd attempt. Issue was ISP had tagged the link on their end and hence next hop provider IP was not pinging. Sorted after the ISP removed the tagged config on their end | Razeen, Mohamed <Mohamed.Razeen@unilever.com> | Circuit Migrated - First Time right |  | INC000107386112 | P3 site users unable to access internet | 2020-02-01 | 2020-03-01
CKT-I-02-UCORPLKA034-UNL-1 | I022322UNL1 | 2 | dont have existing WAN router configs in site. Need them for validation | High | South Asia | Sri Lanka | Agarapathana |  | un-sea-lkaagp-vpn002 |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | D87888 | 2020-01-10 | 2020-01-10 | Complete | 2019-11-01 | 2020-01-17 | Complete | 2020-02-15 | 2020-02-22 | Complete | 2020-02-28 | 2020-05-17 | Complete |  | Complete | Circuit Migrated |  |  | UCORPLKA034 | [5 empty] | UNILEVER PREMIUM EXPORTS LTD, CEYTEA, HOLBROOKE, DIYAGAMA ROAD, LINDULA, AGARAPATHANA | Agarapathana | [5 empty] | Kushan Wijesinghe | Kushan.Wijesinghe@unilever.com |  | 20 |  |  | 2020 | Feb | Internet |  |  |  |  | SC2 |  |  | No training required, 15 mins briefing on safety to be done on the day of activity. | [5 empty] | WAN IP (Customer End): 203.94.91.174 Subnet Mask - 255.255.255.252 LAN IP Block - 220.247.229.16 Subnet Mask - 255.255.255.248 | 203.94.91.173/30 | 203.94.91.174/30 | 220.247.229.16/29 |  |  | SLT | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual MPLS | Complete |  | No | Yes | Yes | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 3:30 am to 3:30 pm UTC | 9 am to 9 pm local time | 61068 | CRQ000000669233 | Approved | 41326 | CRQ000000642299 | Completed | Completed | Tested -Pass-First Time | This was successfully tested in the 1st attempt | Razeen, Mohamed <Mohamed.Razeen@unilever.com> | Circuit Migrated - First Time right |  | INC000107386112 | P3 site users unable to access internet | 2020-02-01 | 2020-03-01
CKT-I-01-UCORPLKA035-UNL-1 | I012323UNL1 | 2 | dont have existing WAN router configs in site. Need them for validation | High | South Asia | Sri Lanka | Lindel |  | un-sea-lkalin-vpn001 |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | 099-4606057 | 2020-01-10 | 2020-01-10 | Complete | 2019-11-01 | 2020-01-17 | Complete | 2020-02-29 | 2020-02-29 | Complete | 2020-03-13 | 2020-03-15 | Complete |  | Complete | Circuit Migrated |  |  | UCORPLKA035 | [5 empty] | LINDEL INDUSTRIAL LABORATORIES LIMITED (LILL), LANKA INDUSTRIAL ESTATES, PATTIWILA ROAD, MAKOLA 11640 | Sapugaskanda | [5 empty] | Kushan Wijesinghe | Kushan.Wijesinghe@unilever.com |  | 30 |  |  | 2020 | Feb | Internet |  |  |  |  | SC2 |  |  | No training required, 15 mins briefing on safety to be done on the day of activity. |  |  | /29 |  |  | WAN Block (first IP will be used in PE side) 122.255.35.252/30 LAN Block: 122.255.32.80/29 | 122.255.35.253/30 | 122.255.35.254/30 | 122.255.32.80/29 | 0.995 | 4 hrs | Dialog | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual MPLS | Complete |  | No | Yes | Yes | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 2:30 am to 12:30 pm UTC | 8am to 5 pm local time | 46372 | CRQ000000650757 | Approved | 41414 | CRQ000000644275 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-03-01
CKT-I-02-UCORPLKA035-UNL-1 | I022323UNL1 | 2 | dont have existing WAN router configs in site. Need them for validation, 4321 router provided by GeoIT which cannot be used, 4331 router ordered from vendor as per Deepak. | High | South Asia | Sri Lanka | Lindel |  | un-sea-lkalin-vpn002 |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | D87875 | 2020-01-10 | 2020-01-10 | Complete | 2019-11-01 | 2020-01-17 | Complete | 2020-02-15 | 2020-02-22 | Complete | 2020-02-28 | 2020-03-15 | Complete |  | Complete | Circuit Migrated |  |  | UCORPLKA035 | [5 empty] | LINDEL INDUSTRIAL LABORATORIES LIMITED (LILL), LANKA INDUSTRIAL ESTATES, PATTIWILA ROAD, MAKOLA 11640 | Sapugaskanda | [5 empty] | Kushan Wijesinghe | Kushan.Wijesinghe@unilever.com |  | 20 |  |  | 2020 | Feb | Internet |  |  |  |  | SC2 |  |  | No training required, 15 mins briefing on safety to be done on the day of activity. | [5 empty] | WAN IP (Customer End): 203.94.91.118 Subnet Mask - 255.255.255.252 LAN IP Block - 220.247.221.144 Subnet Mask - 255.255.255.248 | 203.94.91.117/30 | 203.94.91.118/30 | 220.247.221.144/29 |  |  | SLT | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual MPLS | Complete |  | No | Yes | Yes | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 2:30 am to 12:30 pm UTC | 8am to 5 pm local time | 46372 | CRQ000000650757 | Approved | 41325 | CRQ000000642478 | Completed | Completed | Tested -Pass-First Time |  |  | Circuit Migrated - First Time right |  |  |  | 2020-02-01 | 2020-03-01
CKT-I-01-UCORPRUS003-UNL-1 | I012393UNL1 | 2 | Yes | Top | RUB/ TUI&I | Russia | Moscow |  | N/A | un-uen-rumosc1-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | ID:IP-902053-2.RU.MSK.SMK | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-11 | Complete | 2020-04-05 | 2020-02-10 | Complete | 2020-04-17 | 2020-02-12 | Complete |  | Complete | Circuit Migrated |  | Check dates | UCORPRUS003 | [5 empty] | Sergeya Makeeva st. 13, 123022 | Moscow | 123022 |  |  |  | +7 495 745-75-00 | Artem Hamatdinov | Artem.Hamatdinov@unilever.com | 60Mbps | 250 |  |  | 2020 | Feb | Fibre | [5 empty] | Last minute request from Unilever to support Teams Rollout in Moscow HO. | 1500 - 2100 UTC | No training required, contact details to be shared with local team in advance. | NA | NA | /31 |  |  |  | 46.46.161.233 | 46.46.161.234 | 46.46.161.232/30 |  |  |  | Moscow | AS9002 RETN |  |  |  | Fat Nela | Fat Nela | Fat Nela | 2020-02-13 |  | Complex site type - requires redesign | Complete | NO | Yes | Yes | Yes | Yes-Onboarding completed by CMS | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 1500 - 2100 | 1800 - 2400 | 39810 | CRQ000000642845 | Approved | 41286 | CRQ000000641609 | Completed | Completed | Tested-Pass | Tested by Local team. | Artem Hamatdinov | Circuit Migrated - First Time right
CKT-I-02-UCORPRUS003-UNL-1 | I022393UNL1 | 2 |  | Top | RUB/ TUI&I | Russia | Moscow |  | un-uen-rumosc1-rtr001 | un-uen-rumosc1-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit | Unilever | Uni |  | ID:2315277 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-11 | Complete | 2020-04-05 | 2020-02-03 | Complete | 2020-04-17 | 2020-04-30 | Complete |  | Complete | Circuit Migrated | Cisco |  | UCORPRUS003 | [5 empty] | Sergeya Makeeva st. 13, 123022 | Moscow | 123022 |  |  |  | +7 495 745-75-00 | Artem Hamatdinov | Artem.Hamatdinov@unilever.com | 50Mbps | 200 |  |  | 2020 | Feb | Fibre | [5 empty] | UL local team requested not to arrange Cisco FE to support the migration onsite. UL local team will support all the migration activities, instead. | 1500 - 2300 UTC | NA | NA | NA | /30 |  |  |  | 79.104.19.77 | 79.104.19.78 | 79.104.19.76/30 |  |  |  | Moscow | AS3216 |  |  |  | Astrit Kadriu | Astrit Kadriu | Astrit Kadriu | 2020-05-01 |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  | No | No | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 1500 - 2300 UTC | 1800 - 0200 | Second attempt: 60161 First attempt: 55046 | CRQ000000664377 CRQ000000659415 | Approved | 41765 | CRQ000000653300 | Completed | NA |  | As it is old circuit Zscaler was not raised as per Adrian Lazar's instructions | Artem Hamatdinov | Circuit Migrated |  |  |  |  | 2020-04-01
CKT-I-01-UCORPRUS005-UNL-1 | I011440UNL1 | 2 |  | High | RUB/ TUI&I | Russia | St. Petesburg | 2019_633 |  | un-uen-ruprog2-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | ID:517383 | 2020-08-15 | 2019-08-15 | Complete | 2020-08-20 | 2020-02-17 | Complete | 2020-10-19 | 2020-05-30 | Complete | 2020-11-02 | 2020-04-30 | Complete |  | Complete | Circuit Migrated | Circuit Provider | Check dates | UCORPRUS005 | [5 empty] | Progonnaya st 1, 192102 | St. Petesburg | 192102 |  |  |  | +7 812 718-43-00 | Artem Hamatdinov | Artem.Hamatdinov@unilever.com | 100 | 100 |  |  | 2019 | Aug | Fibre | [5 empty] | UL local team requested not to arrange Cisco FE to support the migration onsite. UL local team will support all the migration activities, instead. | 1500 - 2300 UTC | NA | NA | NA | /31 |  |  | IP: 139.45.234.14 MASK: 255.255.255.252 GW: 139.45.234.13 | 139.45.234.13 | 139.45.234.14 |  |  |  |  | St. Petersburg, Bucharest street, 9 | AS2854 |  |  |  | Adrian Lazar | Adrian Lazar | Adrian Lazar | 2020-05-01 |  | Complex site type - requires redesign | Complete |  | No |  |  |  |  | Window Date agreed - End user Comms sent |  | 1500 - 2300 UTC | 1800 - 0200 | 61059 | CRQ000000665521 | Approved | 41763 | CRQ000000653476 | Completed | NA |  | As it is old circuit Zscaler was not raised as per Adrian Lazar's instructions | Artem Hamatdinov | Circuit Migrated - First Time right | NA | NA | NA | 2020-05-01
CKT-I-02-UCORPRUS005-UNL-1 | I021440UNL1 | 2 | Yes | High | RUB/ TUI&I | Russia | St. Petesburg |  | un-uen-ruprog1 | un-uen-ruprog2-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | Unilever | Uni |  | ID:IP-902053-3.RU.SPB.OV | 2020-02-07 | 2020-02-07 | Complete | 2020-02-12 | 2020-02-11 | Complete | 2020-04-12 | 2020-05-12 | Complete | 2020-04-24 | 2020-07-29 | Complete |  | Complete | Circuit Migrated | Unilever SNT |  | UCORPRUS005 | [5 empty] | Progonnaya st 1, 192102 | St. Petesburg | 192102 |  |  |  | +7 812 718-43-00 | Artem Hamatdinov | Artem.Hamatdinov@unilever.com | 100Mbps | 100 |  |  | 2020 | Feb | Fibre | [6 empty] | 17:30pm to 23:30pm |  |  |  | /31 |  |  | 212.176.195.5 | 212.176.195.2 | 212.176.195.1 |  |  |  |  | St. Petesburg | AS9002 RETN |  |  |  | Rajesh Dagde | [12 empty] | Window Date agreed - End user Comms sent |  | 14:30pm to 20:30pm | 17:30pm to 23:30pm |  |  |  | 41615 | CRQ000000694953/ CRQ000000651060 | Completed | Completed
CKT-I-01-UCORPRUS171-UNL-1 | I0110642UNL1 | 2 | Device needs replacement | High | RUB/ TUI&I | Russia | Tula |  | un-uen-rutula3 | un-uen-rutula3-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | ID:1261 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-11 | Complete | 2020-04-05 | 2020-03-01 | Complete | 2020-04-17 | 2020-03-26 | Complete |  | Complete | Circuit Migrated |  |  | UCORPRUS171 | [5 empty] | Varvarovsky proezd 15, Varvaravka, Leninsky, 300911 | Tula | 300911 |  |  |  | +7 4872 300-700 | Artem Hamatdinov | Artem.Hamatdinov@unilever.com | 15Mbps | 100 |  |  | 2020 | Feb | Fibre | [5 empty] | UL local team requested not to arrange Cisco FE to support the migration onsite. UL local team will support all the migration activities, instead. | 1500 - 2100 UTC | NA | NA | NA | 91.201.252.152/30 91.201.253.32/29 |  |  |  | 83.217.21.141 | 83.217.21.142 |  |  |  |  | ZIP 300026, 415, Lenina avenue 108, Tula, Russia | AS42916 |  |  |  | Adrian Lazar | Adrian Lazar | Adrian Lazar | 2020-03-27 |  | Standard site type - Hybrid (MPLS + IEN) | Complete |  | Yes | No |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 1500 - 2100 | 1800 - 2400 | 49089 | CRQ000000653297 | Approved | 41612 | CRQ000000650967 | Completed | Completed |  |  | Artem Hamadtinov | Circuit Migrated - First Time right | NA | NA | NA
CKT-I-02-UCORPRUS171-UNL-1 | I0210642UNL1 | 2 | Device needs replacement | High | RUB/ TUI&I | Russia | Tula |  | un-uen-rutula4 | un-uen-rutula4-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | ID:CMS 19-210247 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-11 | Complete | 2020-04-05 | 2020-03-01 | Complete | 2020-04-17 | 2020-03-26 | Complete |  | Complete | Circuit Migrated |  |  | UCORPRUS171 | [5 empty] | Varvarovsky proezd 15, Varvaravka, Leninsky, 300911 | Tula | 300911 |  |  |  | +7 4872 300-700 | Artem Hamatdinov | Artem.Hamatdinov@unilever.com | 30Mbps | 100 |  |  | 2020 | Feb | Fibre | [5 empty] | UL local team requested not to arrange Cisco FE to support the migration onsite. UL local team will support all the migration activities, instead. | 1500 - 2100 UTC | NA | NA | NA | /30 |  |  |  | 91.201.253.38 | 91.201.253.37 |  |  |  |  | Tula | AS12389 |  |  |  | Adrian Lazar | Adrian Lazar | Adrian Lazar | 2020-03-27 |  | Standard site type - Hybrid (MPLS + IEN) | Complete |  | Yes | No |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 1500 - 2100 | 1800 - 2400 | 49089 | CRQ000000653297 | Approved | 41660 | CRQ000000651661 | Completed | NA |  | As it is old circuit Zscaler was not raised as per Adrian Lazar's instructions | Artem Hamadtinov | Circuit Migrated - First Time right | NA | NA | NA
CKT-I-01-UCORPRUS129-UNL-1 | I019479UNL1 | 2 | Device needs replacement | High | RUB/ TUI&I | Russia | Omsk |  | un-uen-ruomsk3 | un-uen-ruomsk-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | ID:CMS 19-210252 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-11 | Complete | 2020-04-05 | 2020-03-01 | Complete | 2020-04-17 | 2020-03-19 | Complete |  | Complete | Circuit Migrated |  |  | UCORPRUS129 | [5 empty] | 10 let Oktyabrya st 205, 644031 | Omsk | 644031 |  |  |  | +7 381 245-35-53 | Artem Hamatdinov | Artem.Hamatdinov@unilever.com | 20Mbps | 100 |  |  | 2020 | Feb | Fibre | [5 empty] | UL local team requested not to arrange Cisco FE to support the migration onsite. UL local team will support all the migration activities, instead. | 1200 - 1800 UTC | NA | NA | NA | /30 |  |  |  | 176.210.102.213 | 176.210.102.214 |  |  |  |  | Omsk | AS12389 |  |  |  | Astrit Kadriu | Astrit Kadriu | Astrit Kadriu | 2020-03-20 |  | Standard site type - Dual MPLS | Complete |  | Yes | No | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 1200 - 1800 | 1800 - 2400 | 47693 | CRQ000000652283 | Approved | 41614 | CRQ000000650977 | Completed | Completed | Tested -Pass-First Time |  | Artem Hamadtinov | Circuit Migrated - First Time right | NA | NA | NA
CKT-I-02-UCORPRUS129-UNL-1 | I029479UNL1 | 2 | Device will be replaced | High | RUB/ TUI&I | Russia | Omsk |  | un-uen-ruomsk2 | un-uen-ruomsk-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | ID:4647569 | 2019-08-15 | 2019-08-15 | Complete | 2019-08-20 | 2020-02-11 | Complete | 2019-10-19 | 2020-03-01 | Complete | 2019-11-01 | 2020-03-19 | Complete |  | Complete | Circuit Migrated |  |  | UCORPRUS129 | [5 empty] | 10 let Oktyabrya st 205, 644031 | Omsk | 644031 |  |  |  | +7 381 245-35-53 | Artem Hamatdinov | Artem.Hamatdinov@unilever.com | 100 | 100 |  |  | 2019 | Aug | Fibre | [5 empty] | UL local team requested not to arrange Cisco FE to support the migration onsite. UL local team will support all the migration activities, instead. | 1200 - 1800 UTC | NA | NA | NA | /30 |  |  |  | 77.41.151.73 | 77.41.151.74 |  |  |  |  | Omsk | AS3216 |  |  |  | Astrit Kadriu | Astrit Kadriu | Astrit Kadriu | 2020-03-20 |  | Standard site type - Dual MPLS | Complete |  | Yes | No | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 1200 - 1800 | 1800 - 2400 | 47693 | CRQ000000652284 | Approved | 41658 | CRQ000000651746 | Completed | NA |  | As it is old circuit Zscaler was not raised as per Adrian Lazar's instructions | Artem Hamadtinov | Circuit Migrated - First Time right | NA | NA | NA
CKT-I-01-UCORPRUS166-UNL-1 | I019636UNL1 | 2 | Device will be replaced | High | RUB/ TUI&I | Russia | Ekaterinburg |  | un-uen-ruekah3 | un-uen-ruekah3-vpn001 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | ID: 555462 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-11 | Complete | 2020-04-05 | 2020-03-01 | Complete | 2020-04-17 | 2020-03-24 | Complete |  | Complete | Circuit Migrated |  |  | UCORPRUS166 | [5 empty] | Komsomolskaya st 80-125, 620138 | Ekaterinburg | 620138 |  |  |  | +7 343 365-83-00 | Artem Hamatdinov | Artem.Hamatdinov@unilever.com | 30Mbps | 100 |  |  | 2020 | Feb | Fibre | [5 empty] | UL local team requested not to arrange Cisco FE to support the migration onsite. UL local team will support all the migration activities, instead. | 1300 - 1900 | NA | NA | NA | /30 |  |  |  | 195.151.218.254 | 195.151.218.253 |  |  |  |  | Ekaterinburg, Gagarina, 8 | AS2854 |  |  |  | Adrian Lazar | Adrian Lazar | Adrian Lazar | 2020-03-25 |  | Standard site type - Hybrid (MPLS + IEN) | Complete |  | Yes | No |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 1300 - 1900 | 1800 - 2400 | 49032 | CRQ000000653469 | Approved | 41613 | CRQ000000651301 | Completed | Completed |  |  | Artem Hamadtinov | Circuit Migrated - First Time right | NA | NA | NA
CKT-I-02-UCORPRUS166-UNL-1 | I029636UNL1 | 2 | Device will be replaced | High | RUB/ TUI&I | Russia | Ekaterinburg |  | un-uen-ruekah4 | un-uen-ruekah4-vpn002 | Agnieszka Pajak | WAN Circuit Migration | Circuit + Router | Unilever | Uni |  | ID:4647566 | 2019-08-15 | 2019-08-15 | Complete | 2019-08-20 | 2020-02-11 | Complete | 2019-10-19 | 2020-03-01 | Complete | 2019-11-01 | 2020-03-24 | Complete |  | Complete | Circuit Migrated |  |  | UCORPRUS166 | [5 empty] | Komsomolskaya st 80-125, 620138 | Ekaterinburg | 620138 |  |  |  | +7 343 365-83-00 | Artem Hamatdinov | Artem.Hamatdinov@unilever.com | 30Mbps | 100 |  |  | 2019 | Aug | Fibre | [5 empty] | UL local team requested not to arrange Cisco FE to support the migration onsite. UL local team will support all the migration activities, instead. | 1300 - 1900 | NA | NA | NA | /30 |  |  |  | 82.195.17.114 | 82.195.17.113 |  |  |  |  | Ekaterinburg, Gagarina, 8 | AS3216 |  |  |  | Adrian Lazar | Adrian Lazar | Adrian Lazar | 2020-03-25 |  | Standard site type - Hybrid (MPLS + IEN) | Complete |  | Yes | No |  |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 1300 - 1900 | 1800 - 2400 | 49032 | CRQ000000653470 | Approved | 41659 | CRQ000000651655 | Completed | NA |  | As it is old circuit Zscaler was not raised as per Adrian Lazar's instructions | Artem Hamadtinov | Circuit Migrated - First Time right | NA | NA | NA
CKT-I-01-UCORPRUS127-UNL-1 | I019484UNL1 | 2 | Device needs replacement | High | RUB/ TUI&I | Russia | Novosibirsk |  | un-uen-runove2 | un-uen-runove2-vpn001 | Eloise Shepheard | WAN Circuit Migration |  | Unilever | Uni |  | ID 794976 | 2020-01-31 | 2020-01-31 | Complete | 2020-02-05 | 2020-02-11 | Complete | 2020-04-05 | 2020-05-12 | Complete | 2020-04-17 | 2020-07-14 | Complete |  | Complete | Circuit Migrated | Unilever SNT |  | UCORPRUS127 | [5 empty] | poselok Elitnyi, Basa OAO "Sibirskoe", 630500 | Novosibirsk | 630500 |  |  |  | +7 383 363-37-77 | Artem Hamatdinov | Artem.Hamatdinov@unilever.com | 10Mbps | 50 |  |  | 2020 | Feb | Fibre | [5 empty] | At same time as other link at this site | 10:00 – 18:00 |  |  |  | 1. /30 subnet |  |  | IP: 46.111.1.9 MASK: 255.255.255.252 GW: 46.111.1.10 | 46.111.1.10 | 46.111.1.9 |  |  |  |  | Russia, Novosibirsk, Dmitriya Donskogo st. 51 | AS25549 |  |  |  | Rajesh Dagde |  |  |  |  | Standard site type - Hybrid (MPLS + IEN) | [6 empty] | Assessment Complete CMSP ticket raised MOP created & config created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 03:00 - 09:00am | 10:00 – 18:00 | 86792 | CRQ000000686783 | Approved |  | CRQ000000684118 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-02-UCORPRUS127-UNL-1 | I029484UNL1 | 2 | Device needs replacement | High | RUB/ TUI&I | Russia | Novosibirsk |  | un-uen-runove3 | un-uen-runove3-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | Unilever | Uni |  | ID 387-07Y#4 | 2020-02-07 | 2020-02-07 | Complete | 2020-02-12 | 2020-02-17 | Complete | 2020-04-12 | 2020-05-01 | Complete | 2020-04-24 | 2020-07-14 | Complete |  | Complete | Circuit Migrated | Unilever SNT |  | UCORPRUS127 | [5 empty] | poselok Elitnyi, Basa OAO "Sibirskoe", 630500 | Novosibirsk | 630500 |  |  |  | +7 383 363-37-77 | Artem Hamatdinov | Artem.Hamatdinov@unilever.com | 20Mbps | 50 |  |  | 2020 | Feb | Fibre | [6 empty] | 10:00 – 18:00 |  |  |  | /30 |  |  | IP:109.202.21.88 Mask:255.255.255.128 GW:109.202.21.1 | 109.202.21.1 | 109.202.21.88 |  |  |  |  | Novosibirsk, Ordzhonikidze 18 | AS2854 |  |  |  | Rajesh Dagde |  |  |  |  | Standard site type - Hybrid (MPLS + IEN) | [6 empty] | Assessment Complete CMSP ticket raised MOP created & config created Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 03:00 - 09:00am | 10:00 – 18:00 | 86792 | CRQ000000686783 | Approved |  | CRQ000000684184 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
CKT-I-01-9609-UNL-1 | I019609UNL1 | 2 |  | High | South Asia | India | ETSC Bangalore |  |  | un-sea-ind-bgletsc-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | BHARTI AIRTEL | 13475020 | 2019-12-15 | 2019-12-15 | Complete | 2019-12-20 | 2020-02-06 | Complete | 2020-02-18 | 2020-02-18 | Complete | 2020-03-03 | 2020-08-01 | Complete |  | Complete | Circuit Migrated | NTT | [7 empty] | Prestige Shantiniketan,Tower A Whitefield, Opp. ITPL Big Bazar,Bangalore Bangalore 560048 Karnataka | Bangalore | 560048 | Office | [6 empty] | 1000 | [15 empty] | /29 |  |  | WAN IP: PE WAN IP-182.71.86.65 CE WAN IP-182.71.86.66 Subnet-255.255.255.252 LAN IP: 182.75.179.216/29 | 182.71.86.65 | 182.71.86.66 | 182.75.179.216/29 |  |  | BHARTI AIRTEL | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  | Complex site type - requires redesign | Complete | 1000Base-T with GLC-TE on ISR4k | Yes | No |  |  |  | Window Date agreed - End user Comms not sent |  |  |  | 68530 | CRQ000000676521 | Approved | 42051 | CRQ000000658114 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  |  | 2020-05-01
CKT-I-02-9609-UNL-1 | I029609UNL1 | 2 |  | High | South Asia | India | ETSC Bangalore |  |  | un-sea-ind-bgletsc-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Tata | 091BANG030034796789 | 2019-12-15 | 2019-12-15 | Complete | 2019-12-20 | 2020-02-06 | Complete | 2020-02-18 | 2020-03-15 | Complete | 2020-03-03 | 2020-08-01 | Complete |  | Complete | Circuit Migrated | NTT | [7 empty] | Prestige Shantiniketan,Tower A Whitefield, Opp. ITPL Big Bazar,Bangalore Bangalore 560048 Karnataka | Bangalore | 560048 | Office | [6 empty] | 1000 | [15 empty] | /29 |  |  | WAN IP POOL :- 121.242.140.68/30 WAN IP TCL (GATEWAY) :- 121.242.140.69 WAN IP HUL :- 121.242.140.70 LAN - 121.242.141.24/29 | 121.242.140.68 | 121.242.140.69 | 121.242.141.24/29 |  |  | Tata | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  | Complex site type - requires redesign | Complete | 1000Base-T with GLC-TE on ISR4k | Yes | No |  |  |  | Window Date agreed - End user Comms not sent |  |  |  | 68530 | CRQ000000676521 | Approved | 42053 | CRQ000000658210/CRQ000000678831 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  |  | 2020-05-01
CKT-I-01-2274-UNL-1 | I012274UNL1 | 2 |  | High | South Asia | India | Mumbai HO |  |  | un-sea-ind-mumho-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | BHARTI AIRTEL | 13474962 | 2019-12-15 | 2019-12-15 | Complete | 2019-12-20 | 2020-02-06 | Complete | 2020-02-18 | 2020-02-18 | Complete | 2020-03-03 | 2020-08-29 | Complete |  | Complete | Circuit Migrated | Unilever SNT | [7 empty] | (E),Mumbai Mumbai 400099 Mumbai1 Gig Enterprise Internet Bandwidth at Unilever House B. D. Sawant Marg Chakala, Andheri | Mumbai | 400099 | Office | [6 empty] | 1000 | [15 empty] | /29 |  |  | WAN IP: PE WAN IP-125.21.122.69 CE WAN IP-125.21.122.70 Subnet-255.255.255.252 LAN IP-182.76.249.88/29 | 125.21.122.69 | 125.21.122.70 | 182.76.249.88/29 |  |  | BHARTI AIRTEL | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  | Complex site type - requires redesign | Complete | 1000Base-T with GLC-TE on ISR4k | Yes | No | [5 empty] | 3:30am to 3:30 pm UTC | 9 am to 9 pm local time | 117665 | CRQ000000704125 | Approved | 42054 | CRQ000000658211 | Completed | Completed |  |  |  | Circuit Migrated |  |  |  |  | 2020-05-01
CKT-I-02-2274-UNL-1 | I022274UNL1 | 2 |  | High | South Asia | India | Mumbai HO |  |  | un-sea-ind-mumho-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Tata | 091MUMB030034796752 | 2019-12-15 | 2019-12-15 | Complete | 2019-12-20 | 2020-02-06 | Complete | 2020-02-18 | 2020-03-15 | Complete | 2020-03-03 | 2020-08-29 | Complete |  | Complete | Circuit Migrated | Unilever SNT | [7 empty] | (E),Mumbai Mumbai 400099 Mumbai1 Gig Enterprise Internet Bandwidth at Unilever House B. D. Sawant Marg Chakala, Andheri | Mumbai | 400099 | Office | [6 empty] | 1000 | [15 empty] | /29 |  |  | WAN IP POOL :- 1115.114.89.20/30 WAN IP TCL (GATEWAY) :- 115.114.89.21 WAN IP HUL :- 115.114.89.22 LAN - 115.114.56.8/29 | 115.114.89.20 | 115.114.89.21 | 115.114.56.8/29 |  |  | Tata | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  | Complex site type - requires redesign | Complete | 1000Base-T with GLC-TE on ISR4k | Yes | No | [5 empty] | 3:30am to 3:30 pm UTC | 9 am to 9 pm local time | 117665 | CRQ000000704125 | Approved | 42055 | CRQ000000657975/CRQ000000701550 | Completed | Completed |  |  |  | Circuit Migrated |  |  |  |  | 2020-05-01
I022800UNL1 | I022800UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_FACTORY_CAVITE |  | un-sea-phlcvt-vpn002 | un-sea-phlcvt-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Agile wifi consolidation | Unilever | Uni | Globe | IC-ASZ-2824 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-05-30 | Complete | 2020-07-17 | 2020-06-07 | Complete |  | Complete | Circuit Migrated | Circuit Provider | [7 empty] | Gateway Business Park Brangay Javalera, General Trias, Cavite |  |  | Factory | Andro Samonte | Andro.samonte@unilever.com | M +639174528070 | Martin Gurion | martin.gurion@unilever.com | 15 | 80 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | Wan IP: 124.6.137.4/30 PE IP: 124.6.137.5/30 CE IP: 124.6.137.6/30 LAN IP: 203.177.67.80/29 GW IP: 203.177.67.81/29 Usable IP: 203.177.67.82/29 - 203.177.67.86/29 Primary DNS: 202.126.40.5?Secondary DNS: 222.127.143.5 | 124.6.137.5 | 124.6.137.6 | 203.177.67.80/29 |  |  | Globe | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | 2020-06-08 |  | Standard site type - Dual DMVPN | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 72585 | CRQ000000679301 | Approved |  | CRQ000000677648 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  | INC000107524082 | Cotopaxie application is not working post migration, Static routes need to be added on the WAN router to fix the issue. 18-Jun: This issue was fixed by CRQ81463. |  | 2020-06-01
I012800UNL1 | I012800UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_FACTORY_CAVITE |  | un-sea-phlcvt-vpn001 | un-sea-phlcvt-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit + Agile wifi consolidation | Unilever | Uni | PLDT | UP1I01-052020-37912 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-09-30 | Red | 2020-07-17 | 2020-09-29 | Red |  | Pink | Circuit Order Accepted | Circuit Provider | Check dates | [6 empty] | Gateway Business Park Brangay Javalera, General Trias, Cavite |  |  | Factory | Andro Samonte | Andro.samonte@unilever.com | M +639174528070 | Martin Gurion | martin.gurion@unilever.com | 30 | 80 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | "LAN IPv4 = 124.106.102.152/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 210.1.65.202 " | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | 2020-07-20 |  | Standard site type - Dual DMVPN | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms not sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 75474 | CRQ000000680583 |  |  | CRQ000000679442 | Completed | Completed | [7 empty] | 2020-06-01 | 2020-06-01
I02179UNL1 | I02179UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_FACTORY_PACO |  | un-sea-phlpco-vpn002 | un-sea-phlpco-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Agile wifi consolidation | Unilever | Uni | Globe | IC-ASZ-2929 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-05-30 | Complete | 2020-07-17 | 2020-06-10 | Complete |  | Complete | Circuit Migrated | Circuit Provider | [7 empty] | 1351 U.N. Ave., Paco, Manila |  |  | Factory | Ariel Ordonez | Ariel.Ordonez@unilever.com | M +639461905365 | Martin Gurion | martin.gurion@unilever.com | 40 | 70 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | Wan IP: 222.127.29.0/30 PE IP: 222.127.29.1/30 CE IP: 222.127.29.2/30 LAN IP: 203.177.56.232/29 GW IP: 203.177.56.233/29 Usable IP: 203.177.56.234/29 - 203.177.56.238/29 Primary DNS: 202.126.40.5?Secondary DNS: 222.127.143.5 | [5 empty] | Globe | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | 2020-06-15 |  | Standard site type - Dual DMVPN | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms not sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 72927 | CRQ000000679081 | Approved |  | CRQ000000677551 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  |  | 2020-06-01
I01179UNL1 | I01179UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_FACTORY_PACO |  | un-sea-phlpco-vpn001 | un-sea-phlpco-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit + Agile wifi consolidation | Unilever | Uni | PLDT | UP1I01-052020-37997 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-06-10 | Complete | 2020-07-17 | 2020-06-17 | Complete |  | Complete | Circuit Migrated | Cisco | [7 empty] | 1352 U.N. Ave., Paco, Manila |  |  | Factory | Ariel Ordonez | Ariel.Ordonez@unilever.com | M +639461905365 | Martin Gurion | martin.gurion@unilever.com | 50 | 70 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | LAN IPv4 = 58.69.42.96/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 58.69.47.162 | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | 2020-06-18 |  | Standard site type - Dual DMVPN | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 75478 | CRQ000000680355 | Approved |  | CRQ000000678639 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-06-01 | 2020-06-01
I019711UNL1 | I019711UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_FACTORY_PASIG |  | un-sea-phlpsg-vpn001 | un-sea-phlpsg-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit + Agile wifi consolidation | Unilever | Uni | Globe | IC-ASZ-2844 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-06-01 | Complete | 2020-07-17 | 2020-06-15 | Complete |  | Complete | Circuit Migrated | Circuit Provider | [7 empty] | Manggahan Light Industrial Park, A. Rodriguez Ave., Mangahan, Pasig City |  |  | Factory | Filmore Corales | Filmore.Corales@unilever.com | M +639774591291 | Boy Raymundo | boy.raymundo@unilever.com | 300 | 200 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | Wan IP: 203.177.146.188/30 PE IP: 203.177.146.189/30 CE IP: 203.177.146.190/30 LAN IP: 222.127.23.112/29 GW IP: 222.127.23.113/29 Usable IP: 222.127.23.113/29 - 222.127.23.117/29 Primary DNS: 202.126.40.5?Secondary DNS: 222.127.143.5 | [5 empty] | Globe | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | 2020-06-16 |  | Standard site type - Dual DMVPN | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 76554 | CRQ000000681452 | Approved |  | CRQ000000677652 | Completed | Completed |  |  |  | Circuit Migrated - First Time right | There were issues with DMVPN tunnel not coming up which was resolved after router was rebooted. |  |  | 2020-06-01 | 2020-06-01
I029711UNL1 | I029711UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_FACTORY_PASIG |  | un-sea-phlpsg-vpn002 | un-sea-phlpsg-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Agile wifi consolidation | Unilever | Uni | PLDT | SW02-052020-02959 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-06-24 | Complete | 2020-07-17 | 2020-07-12 | Complete |  | Complete | Circuit Migrated | Cisco | [7 empty] | Manggahan Light Industrial Park, A. Rodriguez Ave., Mangahan, Pasig City |  |  | Factory | Filmore Corales | Filmore.Corales@unilever.com | M +639774591291 | Boy Raymundo | boy.raymundo@unilever.com | 200 | 200 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | "LAN IPv4 = 58.71.75.152/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 58.71.50.246" | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | 2020-07-13 |  | Standard site type - Dual DMVPN | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 77850 | CRQ000000681146 | Approved |  | CRQ000000679644 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-06-01 | 2020-06-01
I0220123UNL1 | I0220123UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_MEGA_DC |  | un-sea-phlcab-vpn002 | un-sea-phlcab-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router + Agile wifi consolidation | Unilever | Uni | Globe | IC-ASZ-2826 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-06-01 | Complete | 2020-07-17 | 2020-06-28 | Complete |  | Complete | Circuit Migrated | Cisco | [7 empty] | Fast Services Cabuyao Property, PuloDiezmo Road, Cabuyao, Laguna |  |  | Warehouse | PHIT - Helpdesk | PHLITSHelpdesk@Lifung.com | M +639175209485 | Martin Gurion | martin.gurion@unilever.com | 20 | 50 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | Wan IP: 222.127.102.60/30 PE IP: 222.127.102.61/30 CE IP: 222.127.102.62/30 LAN IP: 222.127.133.16/29 GW IP: 222.127.133.17/29 Usable IP: 222.127.133.18/29 - 222.127.133.22/29 Primary DNS: 202.126.40.5?Secondary DNS: 222.127.143.5 | [5 empty] | Globe | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | 2020-06-22 |  | Standard site type - Dual DMVPN | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 79927 | CRQ000000682933 | Approved |  | CRQ000000677720 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-06-01 | 2020-06-01
I0120123UNL1 | I0120123UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_MEGA_DC |  | un-sea-phlcab-vpn001 | un-sea-phlcab-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit + Agile wifi consolidation | Unilever | Uni | PLDT | UP1I01-092018-20149 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-06-12 | Complete | 2020-07-17 | 2020-06-28 | Complete |  | Complete | Circuit Migrated | Cisco | [7 empty] | Fast Services Cabuyao Property, PuloDiezmo Road, Cabuyao, Laguna |  |  | Warehouse | PHIT - Helpdesk | PHLITSHelpdesk@Lifung.com | M +639175209485 | Martin Gurion | martin.gurion@unilever.com | C:20 B:40 | 50 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | "LAN IP = 58.71.88.88/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IP = 58.69.193.214 " | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | 2020-06-25 |  | Standard site type - Dual DMVPN | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs |  | CRQ000000682933 | Approved |  | CRQ000000679445 | In Progress | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  | 2020-06-01 | 2020-06-01
I023312UNL1 | I023312UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_BUTUAN |  | un-sea-phlbxu-vpn002 | un-sea-phlbxu-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Globe | IC-ASZ-7323 | 2020-05-30 | 2020-05-30 | Complete | 2020-06-04 | 2020-06-08 | Complete | 2020-08-03 | 2020-09-18 | Red | 2020-08-17 | 2020-10-28 | Red |  | Pink | Circuit Order Accepted | Unilever SNT | [7 empty] | Prime Glee Building, Purok 7, Camella St. Brgy. Villa Kananga, Butuan City |  |  | Warehouse | Jonna Mae Ocio | Jonna.Ocio@unilever.com | M +639088805752 | Boy Raymundo | boy.raymundo@unilever.com | 1 | 10 | [15 empty] | /29 |  |  | WAN IP: 120.28.50.104/30 LAN IP: 120.28.47.104/29 | [5 empty] | Globe | [5 empty] | Sunil Manjunath | [5 empty] | Complete |  |  |  | No | [10 empty] | CRQ000000707414 | Completed | Completed
I013312UNL1 | I013312UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_BUTUAN |  | un-sea-phlbxu-vpn001 | un-sea-phlbxu-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | PLDT | SW02-052020-43685 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-06-10 | Complete | 2020-07-17 | 2020-07-22 | Complete |  | Complete | Circuit Migrated | Cisco | [7 empty] | Prime Glee Building, Purok 7, Camella St. Brgy. Villa Kananga, Butuan City |  |  | Warehouse | Jonna Mae Ocio | Jonna.Ocio@unilever.com | M +639088805752 | Boy Raymundo | boy.raymundo@unilever.com | 0 | 10 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | "LAN IPv4 = 119.92.224.184/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 119.92.219.198 " | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  |  | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 87398, 101741 | CRQ000000686979 (7th July) CRQ000000692641 (22 Jul) | Approved |  | CRQ000000683475 | Completed | Completed |  |  |  | Circuit Migrated | ISP link issue and rolled back on 7th July
I0220301UNL1 | I0220301UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_CALBAYOG |  | un-sea-phlcal-vpn002 | un-sea-phlcal-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Globe |  | 2020-05-30 | 2020-05-30 | Complete | 2020-06-04 | 2020-06-08 | Complete | 2020-08-03 | 2020-10-31 | Red | 2020-08-17 | 2020-10-30 | Red |  | Pink | Circuit Order Accepted | Unilever SNT | Check dates | [6 empty] | Brgy. Dagum Matobato diversion road, Calbayog City |  |  | Warehouse | Michael Falcon, | Michael.Falcon@unilever.com | M +639088805850 | Boy Raymundo | boy.raymundo@unilever.com | 4 | 10 | [15 empty] | /29 | [8 empty] | Globe | [5 empty] | Sunil Manjunath | [5 empty] | Complete |  |  |  | No
I0120301UNL1 | I0120301UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_CALBAYOG |  | un-sea-phlcal-vpn001 | un-sea-phlcal-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | PLDT | SW02-052020-06918 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-09-30 | Red | 2020-07-17 | 2020-10-30 | Red |  | Pink | Circuit Order Accepted | Circuit Provider | [7 empty] | Brgy. Dagum Matobato diversion road, Calbayog City |  |  | Warehouse | Michael Falcon, | Michael.Falcon@unilever.com | M +639088805850 | Boy Raymundo | boy.raymundo@unilever.com | 0 | 10 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | PID1-1AO0EEV_UNILEVER RFM ICE CREAM, INC._I-GATE PREMIUM_10M IGATE TYPE = PREMIUM LAN IPv4 = 210.5.93.136/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 210.5.92.190 | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  |  | Complete |  |  |  | No |  |  |  |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs
I0220105UNL1 | I0220105UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_DUMAGUETE |  | un-sea-phldgt-vpn002 | un-sea-phldgt-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Globe | IC-ASZ-7325 | 2020-05-30 | 2020-05-30 | Complete | 2020-06-04 | 2020-06-08 | Complete | 2020-08-03 | 2020-09-17 | Red | 2020-08-17 | 2020-10-10 | Red |  | Pink | Circuit Order Accepted | Unilever SNT | [7 empty] | Palinpinon Rd, Barangay Candau-ay, Dumaguete City |  |  | Warehouse | Randy Latonero | Randy.Latonero@unilever.com | M +639088805838 | Boy Raymundo | boy.raymundo@unilever.com | 1 | 10 | [15 empty] | /29 |  |  | WAN IP: 203.177.127.204/30 LAN IP: 203.177.91.88/29 | [5 empty] | Globe | [5 empty] | Sunil Manjunath | [5 empty] | Complete |  |  |  | No |  |  |  |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs |  |  |  |  | CRQ000000707419 | Completed | Completed
I0120105UNL1 | I0120105UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_DUMAGUETE |  | un-sea-phldgt-vpn001 | un-sea-phldgt-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | PLDT | SW02-052020-06803 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-06-27 | Complete | 2020-07-17 | 2020-07-16 | Complete |  | Complete | Circuit Migrated | Circuit Provider | [7 empty] | Palinpinon Rd, Barangay Candau-ay, Dumaguete City |  |  | Warehouse | Randy Latonero | Randy.Latonero@unilever.com | M +639088805838 | Boy Raymundo | boy.raymundo@unilever.com | 0 | 10 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | "LAN IPv4 = 58.69.42.152/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 122.55.5.74 " | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  |  | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms not sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 96322 | CRQ000000690738 | Approved |  | CRQ000000689129 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
I0211160UNL1 | I0211160UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_GENSAN |  | un-sea-phlges-vpn002 | un-sea-phlges-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Globe | IC-ASZ-7330 | 2020-05-30 | 2020-05-30 | Complete | 2020-06-04 | 2020-06-08 | Complete | 2020-08-03 | 2020-10-31 | Red | 2020-08-17 | 2020-10-25 | Red |  | Pink | Circuit Order Accepted | Unilever SNT | Check dates | [6 empty] | Purok Malinawon Brg., Conel , General Santos City |  |  | Warehouse | Rhea Donasco | Rhea.Donasco@unilever.com | M +639088805736 | Boy Raymundo | boy.raymundo@unilever.com | 1 | 10 | [15 empty] | /29 |  |  | Wan IP: 203.177.48.168/30 LAN IP: 203.177.58.48/29 | [5 empty] | Globe | [5 empty] | Sunil Manjunath | [5 empty] | Complete |  |  |  | No |  |  |  |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs |  |  |  |  | CRQ000000707322 | Completed | Completed
I0111160UNL1 | I0111160UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_GENSAN |  | un-sea-phlges-vpn001 | un-sea-phlges-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | PLDT | SW02-052020-06778 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-07-20 | Complete | 2020-07-17 | 2020-07-28 | Complete |  | Complete | Circuit Migrated | Circuit Provider | [7 empty] | Purok Malinawon Brg., Conel , General Santos City |  |  | Warehouse | Rhea Donasco | Rhea.Donasco@unilever.com | M +639088805736 | Boy Raymundo | boy.raymundo@unilever.com | 0 | 10 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | PID1-1AO0XW1_UNILEVER RFM ICE CREAM, INC._I-GATE PREMIUM_10M IGATE TYPE = PREMIUM LAN IPv4 = 58.69.41.24/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 124.107.238.110 | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  |  | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms not sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 99195 | CRQ000000692165 | Approved |  | CRQ000000690433 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
I0211162UNL1 | I0211162UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_ISABELA |  | un-sea-phlisa-vpn002 | un-sea-phlisa-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Globe | IC-ASZ-7327 | 2020-05-30 | 2020-05-30 | Complete | 2020-06-04 | 2020-06-08 | Complete | 2020-08-03 | 2020-09-07 | Red | 2020-08-17 | 2020-09-17 | Red |  | Green | Circuit Order Accepted | Unilever SNT | [7 empty] | Cindys Commissary Maharlika Highway, Brgy Quezon, San Isidro , Isabela |  |  | Warehouse | Armand Lopez | Armando.Lopez@unilever.com | M +639088805766 | Boy Raymundo | boy.raymundo@unilever.com | 1 | 10 | [15 empty] | /29 |  |  | Wan IP: 124.6.150.16/30 LAN IP:124.6.157.144/29 | [5 empty] | Globe | [5 empty] | Sunil Manjunath | [5 empty] | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms not sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | CHG000000000042324 |  |  |  | CRQ000000707504 | Completed | Completed
I0111162UNL1 | I0111162UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_ISABELA |  | un-sea-phlisa-vpn001 | un-sea-phlisa-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | PLDT | SW02-052020-09949 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-05-28 | Complete | 2020-07-17 | 2020-07-02 | Complete |  | Complete | Circuit Migrated | Cisco | [7 empty] | Cindys Commissary Maharlika Highway, Brgy Quezon, San Isidro , Isabela |  |  | Warehouse | Armand Lopez | Armando.Lopez@unilever.com | M +639088805766 | Boy Raymundo | boy.raymundo@unilever.com | 0 | 10 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | "LAN IPv4 = 27.110.228.144/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 122.53.112.26" | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  |  | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 79932 | CRQ000000685588 | Approved |  | CRQ000000678634 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
I023253UNL1 | I023253UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_PALAWAN |  | un-sea-phlpps-vpn002 | un-sea-phlpps-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Globe |  | 2020-05-30 | 2020-05-30 | Complete | 2020-06-04 | 2020-06-08 | Complete | 2020-08-03 | 2020-09-10 | Red | 2020-08-17 | 2020-10-16 | Red |  | Pink | Circuit Order Accepted | Unilever SNT | [7 empty] | Jentec Cold Storage, Lomboy Street, Brgy. San Jose, Purok Masunurin, Puerto Princesa City, Palawan |  |  | Warehouse | jastoni maru | jastoni.maru@unilever.com | M +639985669839 | Boy Raymundo | boy.raymundo@unilever.com | 1 | 10 | [15 empty] | /29 |  |  | WAN 203.177.160.204 /30 LAN 203.177.91.232 /29 | [5 empty] | Globe | [5 empty] | Sunil Manjunath | [5 empty] | Complete |  |  |  | No |  |  |  |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | CHG000000000042148 |  |  |  | CRQ000000707192 | Completed | Completed
I013253UNL1 | I013253UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_PALAWAN |  | un-sea-phlpps-vpn001 | un-sea-phlpps-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | PLDT | SW02-052020-57318 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-05-26 | Complete | 2020-07-17 | 2020-07-01 | Complete |  | Complete | Circuit Migrated | Cisco | [7 empty] | Jentec Cold Storage, Lomboy Street, Brgy. San Jose, Purok Masunurin, Puerto Princesa City, Palawan |  |  | Warehouse | jastoni maru | jastoni.maru@unilever.com | M +639985669839 | Boy Raymundo | boy.raymundo@unilever.com | 0 | 10 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | LAN IPv4 = 58.69.46.224/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 58.69.47.146 | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | 2020-06-30 |  |  | Complete |  |  |  | No |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms not sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 79930 | CRQ000000683418 | Approved |  | CRQ000000678642 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  |  | 2020-06-01
I0220101UNL1 | I0220101UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_PAMPANGA |  | un-sea-phlpam-vpn002 | un-sea-phlpam-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Globe | IC-ASZ-5682 | 2020-05-30 | 2020-05-30 | Complete | 2020-06-04 | 2020-06-08 | Complete | 2020-08-03 | 2020-09-11 | Red | 2020-08-17 | 2020-09-15 | Red |  | Green | Circuit Order Accepted | Unilever SNT | [7 empty] | Panipuan Mexico Pampanga, Mexico, Pampanga |  |  | Warehouse | Angel Galvez | Angel.Galvez@unilever.com | M +639088805743 | Boy Raymundo | boy.raymundo@unilever.com | 1 | 20 | [15 empty] | /29 |  |  | 112.198.18.240/30-WAN 203.177.103.216/29-LAN | [5 empty] | Globe | [5 empty] | Sunil Manjunath | [5 empty] | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs |  | CRQ000000709050 | Approved |  | CRQ000000707333 | Completed | Completed
I0120101UNL1 | I0120101UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_PAMPANGA |  | un-sea-phlpam-vpn001 | un-sea-phlpam-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | PLDT | SW02-052020-08370 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-08-28 | Complete | 2020-07-17 | 2020-09-15 | Red |  | Green | Circuit Delivered | Circuit Provider | [7 empty] | Panipuan Mexico Pampanga, Mexico, Pampanga |  |  | Warehouse | Angel Galvez | Angel.Galvez@unilever.com | M +639088805743 | Boy Raymundo | boy.raymundo@unilever.com | 0 | 20 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | " PID1-1AO04P0_UNILEVER RFM ICE CREAM, INC._I-GATE PREMIUM_20M IGATE TYPE = PREMIUM LAN IPv4 = 124.105.158.192/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 124.105.151.62 " | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  |  | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | CHG000000000041839 | CRQ000000709050 | Approved |  | CRQ000000695701 | Completed | Completed
I0220142UNL1 | I0220142UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_SOUTH_NCR |  | un-sea-phlpqe-vpn002 | un-sea-phlpqe-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Globe | IC-ASZ-7329 | 2020-05-30 | 2020-05-30 | Complete | 2020-06-04 | 2020-06-08 | Complete | 2020-08-03 | 2020-09-19 | Red | 2020-08-17 | 2020-09-23 | Red |  | Green | Circuit Order Accepted | Unilever SNT | [7 empty] | Omni Solid Services, Dr. Arcadio Santos Ave., Brgy San Antonio , Sucat |  |  | Warehouse | Carlito Pasiola | Carlito.Pasiola@unilever.com | M +639998844064 | Boy Raymundo | boy.raymundo@unilever.com | 1 | 10 | [15 empty] | /29 |  |  | WAN IP: 203.177.9.236/30 LAN IP: 203.177.0.208/29 | [5 empty] | Globe | [5 empty] | Sunil Manjunath | [5 empty] | Complete |  |  |  | No |  |  |  |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs |  |  |  |  | CRQ000000707441 | Completed | Completed
I0120142UNL1 | I0120142UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_SOUTH_NCR |  | un-sea-phlpqe-vpn001 | un-sea-phlpqe-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | PLDT | SW02-052020-43417 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-07-14 | Complete | 2020-07-17 | 2020-07-23 | Complete |  | Complete | Circuit Migrated | Circuit Provider | [7 empty] | Omni Solid Services, Dr. Arcadio Santos Ave., Brgy San Antonio , Sucat |  |  | Warehouse | Carlito Pasiola | Carlito.Pasiola@unilever.com | M +639998844064 | Boy Raymundo | boy.raymundo@unilever.com | 0 | 10 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | "LAN IPv4 = 58.69.41.168/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 58.69.47.202" | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath |  |  |  | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 99196 | CRQ000000691792 | Approved |  | CRQ000000683477 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
I022808UNL1 | I022808UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_TACLOBAN |  | un-sea-phltac-vpn002 | un-sea-phltac-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Globe | IC-ASZ-4640 | 2020-05-30 | 2020-05-30 | Complete | 2020-06-04 | 2020-06-08 | Complete | 2020-08-03 | 2020-09-16 | Red | 2020-08-17 | 2020-10-18 | Red |  | Pink | Circuit Order Accepted | Unilever SNT | [7 empty] | Jentec cold storage. National road, Brgy Diit Tacloban City. |  |  | Warehouse | Cybele Janolino | Cybele.Janolino@unilever.com | M +63 9089867807 | Boy Raymundo | boy.raymundo@unilever.com | 1 | 10 | [15 empty] | /29 |  |  | WAN IP: 124.6.136.236/30 LAN IP: 203.177.2.168/29 | 124.6.136.237 | 124.6.136.238 |  |  |  | Globe | [5 empty] | Sunil Manjunath | [5 empty] | Complete |  |  |  | No |  |  |  |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs |  |  |  |  | CRQ000000707522 | Completed | Completed
I012808UNL1 | I012808UNL1 | 2 |  | High | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_TACLOBAN |  | un-sea-phltac-vpn001 | un-sea-phltac-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | PLDT | SW02-052020-09067 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-05-26 | Complete | 2020-07-17 | 2020-06-26 | Complete |  | Complete | Circuit Migrated | Cisco | [7 empty] | Jentec cold storage. National road, Brgy Diit Tacloban City. |  |  | Warehouse | Cybele Janolino | Cybele.Janolino@unilever.com | M +63 9089867807 | Boy Raymundo | boy.raymundo@unilever.com | 0 | 10 | [11 empty] | 8 am to 5 pm local time |  |  |  | /29 |  |  | LAN IPv4 = 124.105.158.96/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 119.92.191.150 | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | 2020-06-29 |  |  | Complete |  |  |  | No |  |  | Window Date agreed - End user Comms not sent |  | 0000 hrs too 0900 hrs | 0800 hrs to1700 hrs | 79928 | CRQ000000684618 | Approved |  | CRQ000000678919 | Completed | Completed |  |  |  | Circuit Migrated - First Time right |  |  |  |  | 2020-06-01
I0220075BT1 | I0220075BT1 |  |  |  | Europe | IRELAND | IRELAND_LISBURN_DISTRIBUTION_CENTRE |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-20 | Amber | 2020-05-20 | 2020-05-22 | Amber | 2020-07-19 | 2020-08-21 | Red | 2020-07-31 | 2020-12-07 | Red |  | Yellow | Circuit not ordered | [18 empty] | 10
I0110626BT1 | I0110626BT1 |  |  |  | Europe | ITALY | ITALY_CALVIGNASCO_DEPOT |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-06-15 | 2020-06-15 | Green | 2020-06-20 | 2020-06-22 | Amber | 2020-08-19 | 2020-09-21 | Red | 2020-09-02 | 2020-10-21 | Red |  | Yellow | Circuit not ordered | [18 empty] | 10
I0220138BT1 | I0220138BT1 |  |  |  | Europe | POLAND | POLAND_GRABICA_31 WOLA BYKOWSKA |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-20 | Amber | 2020-05-20 | 2020-05-22 | Amber | 2020-07-19 | 2020-08-21 | Red | 2020-07-31 | 2020-12-16 | Red |  | Yellow | Circuit not ordered | [18 empty] | 20
I02608VOD1 | I02608VOD1 |  |  | Medium | Europe | PORTUGAL | PORTUGAL_LISBON_JERONIMO_MARTINS_LDA |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | Vodafone Global | VOD |  | UNIPX-IPTD-00004 | 2020-05-15 | 2020-06-15 | Red | 2020-05-20 | 2020-06-22 | Red | 2020-07-19 | 2020-09-25 | Red | 2020-07-31 | 2020-11-23 | Red |  | Yellow | Circuit not ordered | [18 empty] | 100 | [24 empty] | Vodafone Portugal
I0111068BT1 | I0111068BT1 |  |  | Low | Europe | ROMANIA | ROMANIA_CLUJ_NAPOCA |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-20 | Amber | 2020-05-20 | 2020-05-22 | Amber | 2020-07-19 | 2020-08-21 | Red | 2020-07-31 | 2020-12-16 | Red |  | Yellow | Circuit not ordered | [18 empty] | 30
I01WC011GTT1 | I01WC011GTT1 |  |  |  | Latin America | Dominican Republic | SANTO_DOMINGO_AUTOPISTA |  |  | un-ula-domaut1-vpn001 | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001962658 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-07 | Complete | 2020-09-03 | 2020-07-20 | Complete | 2020-09-17 | 2020-09-25 | Red | 20-Aug: GTT delivered circuit with fiber and not copper. GTT to send SFP. 14-Aug: Migration confirmed and approved for September 8th at 10AM. 31-Jul: Migration approved for August 18th at 10AM. | Green | Circuit Delivered | [17 empty] | 9Mbps | 10 | [18 empty] | 209.120.190.16/29 Network - 209.120.190.16 First usable - 209.120.190.17 Last usable - 209.120.190.22 Broadcast - 209.120.190.23 Subnet Mask - 255.255.255.248 209.120.190.24/30 Network - 209.120.190.24 First usable - 209.120.190.25 Last usable - 209.120.190.26 Broadcast - 209.120.190.27 Subnet Mask - 255.255.255.252 | 209.120.190.25 | 209.120.190.26 | 209.120.190.16/29 | [8 empty] | Dulce Basilio Gonzalez |  |  |  |  | Standard site type - Hybrid (MPLS + DMVPN) | In Progress |  | No | No | No | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) |  |  |  |  | 113963 | CRQ000000701336 |  |  | CRQ000000700955 | Completed | Completed
I012004CTL1 | I012004CTL1 |  |  |  | Latin America | Mexico | MEXICO_CUERNAVACA_CALLE_21_ESTE |  |  | un-ula-mexciv1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2007083050 | 2020-04-29 | 2020-04-29 | Complete | 2020-05-04 | 2020-05-07 | Amber | 2020-07-03 | 2020-07-30 | Red | 2020-07-17 | 2020-09-15 | Red | 19-Jun: "Old" current circuit converted to DMVPN to bypass failing firewall. | Yellow | Circuit Ordered | Circuit Provider | [16 empty] | 40Mb | 60 | [18 empty] | LAN: 64.208.239.72/29 WAN: 64.208.205.4/30 CTL: 64.208.205.5 UNI: 64.208.205.6 | 64.208.205.5 | 64.208.205.6 | 64.208.239.72/29 | [8 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Complex site type - requires redesign | Complete |  | No |  | No |  | Assessment Complete MOP created & config created Received tunnel IP or LAN IP (if required) | [8 empty] | CRQ000000706963 | Completed | Completed
I022004GTT1 | I022004GTT1 |  |  |  | Latin America | Mexico | MEXICO_CUERNAVACA_CALLE_21_ESTE |  |  |  | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001929023 | 2020-04-29 | 2020-04-29 | Complete | 2020-05-04 | 2020-05-07 | Amber | 2020-07-03 | 2020-09-30 | Red | 2020-07-17 | 2020-10-30 | Red | 19-Jun: "Old" current circuit converted to DMVPN to bypass failing firewall. | Yellow | Circuit Ordered | Circuit Provider | [17 empty] | 60 | [18 empty] | 209.120.238.232/30 Network - 209.120.238.232 First usable - 209.120.238.233 Last usable - 209.120.238.234 Broadcast - 209.120.238.235 Subnet Mask - 255.255.255.252 209.120.238.224/29 Network - 209.120.238.224 First usable - 209.120.238.225 Last usable - 209.120.238.230 Broadcast - 209.120.238.231 Subnet Mask - 255.255.255.248 | [5 empty] | Axtel a/k/a Alestra | [5 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez
I012143CTL1 | I012143CTL1 |  |  |  | Latin America | Mexico | MEXICO_GUADALAJARA_CHIMALHUACAN |  |  |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-05-15 | 2020-05-20 | Amber | 2020-05-20 | 2020-05-22 | Amber | 2020-07-19 | 2020-08-14 | Red | 2020-07-31 | 2020-10-30 | Red |  | Yellow | Circuit not ordered | [18 empty] | 10 | [18 empty] | WAN: 64.208.169.96/30 CTL: 64.208.169.97 UNI: 64.208.169.98
I01WC015CTL1 | I01WC015CTL1 |  |  |  | Latin America | Mexico | MEXICO_LERMA_ODONNELL |  |  | un-ula-mexodo1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2007089079 | 2020-05-15 | 2020-05-20 | Complete | 2020-05-20 | 2020-05-22 | Complete | 2020-07-19 | 2020-08-14 | Complete | 2020-07-31 | 2020-09-30 | Red |  | Yellow | Circuit Delivered | [17 empty] | 2 Mb | 10 | [17 empty] | Rax711 port: 1/1 | LAN: 64.208.239.104/29 WAN: 64.209.88.88/30 CTL: 64.209.88.89 UNI: 64.209.88.90 | 64.209.88.89 | 64.209.88.90 | 64.208.239.104/29 | [8 empty] | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez | Rene Gonzalez Iniguez |  |  | Complex site type - requires redesign | Complete |  | No |  | No | [10 empty] | CRQ000000707057 | Completed | Submitted
I0220225CTL1 | I0220225CTL1 |  |  |  | Latin America | Mexico | MEXICO_MEXICO CITY_331 CALLE DE LERDO_TLALTELOLCO(now Ceylan) |  |  |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-05-15 | 2020-05-20 | Amber | 2020-05-20 | 2020-05-22 | Amber | 2020-07-19 | 2020-08-14 | Red | 2020-07-31 | 2020-10-30 | Red |  | Yellow | Circuit not ordered | [18 empty] | 10
I01WC016CTL1 | I01WC016CTL1 |  |  |  | Latin America | Mexico | MEXICO_MONTERREY_4001 FUNDADORES_OF_REG_MONTERREY |  |  |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-05-30 | 2020-05-20 | Complete | 2020-06-04 | 2020-06-07 | Amber | 2020-08-03 | 2020-08-30 | Red | 2020-08-17 | 2020-10-30 | Red | 10-Sep: Site to be closed. Circuit order cancelled. | Out of Scope | Circuit Ordered | [18 empty] | 30 | [30 empty] | Hugo Trejo
I022795CTL1 | I022795CTL1 |  |  |  | Latin America | Mexico | MEXIQUENSE_CDU |  |  |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2007088983 | 2020-05-15 | 2020-05-20 | Complete | 2020-05-20 | 2020-05-22 | Amber | 2020-07-19 | 2020-08-14 | Red | 2020-07-31 | 2020-09-20 | Red | 10-Sep: Migration tentatively scheduled for Sep-20. | Pink | Circuit Ordered | [18 empty] | 30 | [17 empty] | RACK REDIT ATC - CIENA ""3930MEX_BTLATAM_14522"" Port: 3 - RJ45/100 Full Auto | LAN: 204.199.193.32/29 WAN: 204.199.193.24/30 CTL: 204.199.193.25 UNI: 204.199.193.26 | 204.199.193.25/30 | 204.199.193.26/30 | 204.199.193.32/29 | [8 empty] | Fernando Ramos
I013260ORA1 | I013260ORA1 |  |  | Top | Latin America | Venezuela | Puerto de la Cruz |  |  |  | Juan Simon | WAN Circuit Migration |  | Orange | ORA |  | GO0AL1W661 | 2020-05-05 | 2020-05-05 | Complete | 2020-05-10 | 2020-06-01 | Red | 2020-07-09 | 2020-07-28 | Red | 2020-07-23 | 2020-10-30 | Red |  | Yellow | Circuit Ordered | [18 empty] | 5 | [24 empty] | Gold data | [5 empty] | Fernando Ramos
I01WC019ORA1 | I01WC019ORA1 |  |  | Top | Latin America | Venezuela | Caracas Frimaca |  |  | un-ula-venfri1-vpn001 | Juan Simon | WAN Circuit Migration |  | Orange | ORA |  | LO65067396 | 2020-05-05 | 2020-05-05 | Complete | 2020-05-10 | 2020-05-12 | Complete | 2020-07-09 | 2020-08-05 | Complete | 2020-07-23 | 2020-09-08 | Complete | 8-Sep: Migration successful. 1-Sep: Migration pushed to Sep-08 from Sep-05. Need to install new 4331 router. | Complete | Circuit Migrated | [18 empty] | 5 | [17 empty] | DMARC: CIENA 311 Port #1 | IP: 200.125.190.194 Mask: 255.255.255.252 GW: 200.125.190.193 | 200.125.190.193/30 | 200.125.190.194/30 | [9 empty] | Fernando Ramos | [16 empty] | CHG000000000041596 |  |  |  | CRQ000000705443 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
I01WC020ORA1 | I01WC020ORA1 |  |  | Top | Latin America | Venezuela | Maracaibo |  |  |  | Juan Simon | WAN Circuit Migration |  | Orange | ORA |  | GO0AL1UE12 | 2020-05-05 | 2020-05-05 | Complete | 2020-05-10 | 2020-06-01 | Red | 2020-07-09 | 2020-08-03 | Red | 2020-07-23 | 2020-10-30 | Red |  | Yellow | Circuit Ordered | [18 empty] | 5 | [24 empty] | Gold Data | [5 empty] | Rene Gonzalez Iniguez
I01WC018ORA1 | I01WC018ORA1 |  |  | High | Latin America | Venezuela | Caracas Blandin y los Chaguaramos |  |  |  | Juan Simon | WAN Circuit Migration |  | Orange | ORA |  | GO0AL1V96E | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-06-02 | Complete | 2020-09-03 | 2020-07-16 | Complete | 2020-09-17 | 2020-09-20 | Amber | 14-Aug: Tentative migration date September 6th. | Pink | Circuit Delivered | [18 empty] | 5 | [18 empty] | DMARC: CIENA 311 Port #1 Network: 190.52.96.248/30 Network: 186.96.69.152/29 Gateway: 190.52.96.249 IP: 190.52.96.250 Subnet: 255.255.255.252 DNS1: 200.125.184.2 DNS2: 200.125.184.3 | [5 empty] | Gold Data | [5 empty] | Dulce Basilio Gonzalez | Dulce Basilio Gonzalez | Dulce Basilio Gonzalez
I02WC018CTL1 | I02WC018CTL1 |  |  | High | Latin America | Venezuela | Caracas Blandin y los Chaguaramos |  |  |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-03-26 | 2020-03-26 | Complete | 2020-03-31 | 2020-04-02 | Amber | 2020-05-30 | 2020-07-15 | Red | 2020-06-12 | 2020-09-27 | Red |  | Yellow | Circuit Ordered | [18 empty] | 20 | [30 empty] | Dulce Basilio Gonzalez | Dulce Basilio Gonzalez | Dulce Basilio Gonzalez
I0110581ORA1 | I0110581ORA1 |  |  | Top | Latin America | Venezuela | Guacara |  |  |  | Juan Simon | WAN Circuit Migration |  | Orange | ORA |  | GO0AL1UC14 | 2020-04-29 | 2020-04-29 | Complete | 2020-05-04 | 2020-06-02 | Red | 2020-07-03 | 2020-08-03 | Red | 2020-07-17 | 2020-10-30 | Red |  | Yellow | Circuit Ordered | [18 empty] | 50 | [24 empty] | Gold Data | [5 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos
I0210581CTL1 | I0210581CTL1 |  |  | Top | Latin America | Venezuela | Guacara |  |  |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  | FRO2007081810 | 2020-03-26 | 2020-03-26 | Complete | 2020-03-31 | 2020-04-02 | Amber | 2020-05-30 | 2020-07-15 | Red | 2020-06-12 | 2020-09-25 | Red | 10-Sep: Migration has to happen on September before MPLS circuit cease this month. | Yellow | Circuit Ordered | [18 empty] | 50 | [18 empty] | LAN: 200.32.64.248/29 WAN: 200.32.64.228/30 CTL: 200.32.64.229 UNI: 200.32.64.230 | [11 empty] | Fernando Ramos | Fernando Ramos | Fernando Ramos
I023752UNL1 | I023752UNL1 |  |  | Top | Namet & Rub | SAUDI ARABIA | SAUDI_ARABIA_JEDDAH_BINZAGR_UNILEVER_FACTORY |  |  | un-amt-sabzl-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | Unilever | Uni |  |  | 2020-06-15 | 2020-06-15 | Complete | 2020-06-20 | 2020-06-22 | Complete | 2020-08-19 | 2020-07-02 | Complete | 2020-09-02 | 2020-08-26 | Complete | 26/08: Migration successful 21/08: Migration unsuccessful - issue with ISP link. Re-planned for 26th August 20/08: CRQ fully approved and change announcement sent. Ready for tomorrow. 06/08: Migration date confirmed for 21st August 17/07 - MA chased for an updated 16/07 - no field engineers required from Cisco for Migration - pending testing results from site - migration on seperate days 15/07 - email from MA confirmed Circuit test on 16th July 9:30 am 13/07 - Alwan, Mohammad <Mohammad.Alwan@unilever.com> confirmed two circuits physically installed and waiting for ISP confirming test date - he will update on migration date by end of the week 10/07 - email sent to Sanjay Gehani requesting status update 24/06 - Deepak shared details of 2x30Mbps circuits to be signed with BTAS by end of this week. Deepak confirmed following links are pretty much ready as soon as order is signed and we should target migration in July. IP details shared with Aga who confirms she will ask my team to initiate Zscaler/Algosec requests and start the prep work for the migration. | Complete | Circuit Migrated | [18 empty] | 30 | [18 empty] | IP address 185.133.85.106-110 Subnet 255.255.255.248 Gateway 185.133.85.105 DNS 8.8.4.4 DNS 185.51.205.205 | 185.133.85.105 | 185.133.85.106 | [14 empty] | Complex site type - requires redesign | Complete | [5 empty] | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 07:00 to 15:00 | 10:00 to 18:00 | 115261 |  |  |  | CRQ000000702423 | Completed | Completed |  |  |  | Circuit Migrated
I021213UNL1 | I021213UNL1 |  |  | Top | Namet & Rub | SAUDI ARABIA | SAUDI_ARABIA_JEDDAH_UNILEVER_HOUSE |  |  | un-amt-sajed-vpn002 | Eloise Shepheard | WAN Circuit Migration |  | Unilever | Uni |  |  | 2020-06-15 | 2020-06-15 | Complete | 2020-06-20 | 2020-06-22 | Complete | 2020-08-19 | 2020-07-02 | Complete | 2020-09-02 | 2020-08-28 | Complete | 28/08: Migration successful 21/08: Migration postponed - factory has to be migrated before - re-planned for 28th August 20/08: Migration on track - Eloise sent out email for end user communication.(20/08) Eloise also to check if approval from Andrew C is required because of red zone. 06/08: Migration date confirmed for 26th August 17/07 - MA chased for an updated 16/07 - no field engineers required from Cisco for Migration - pending testing results from site - migration on seperate days 15/07 - email from MA confirmed Circuit test on 16th July 9:30 am 13/07 - Alwan, Mohammad <Mohammad.Alwan@unilever.com> confirmed two circuits physically installed and waiting for ISP confirming test date - he will update on migration date by end of the week 10/07 - email sent to Sanjay Gehani requesting status update 24/06 - Deepak shared details of 2x30Mbps circuits to be signed with BTAS by end of this week. Deepak confirmed following links are pretty much ready as soon as order is signed and we should target migration in July. IP details shared with Aga who confirms she will ask my team to initiate Zscaler/Algosec requests and start the prep work for the migration. | Complete | Circuit Migrated | [18 empty] | 30 | [18 empty] | IP address Details: IP address 185.164.30.226-230 Subnet 255.255.255.248 Gateway 185.164.30.225 DNS 8.8.4.4 DNS 185.164.30.30 WAN IP address Details: PE 192.168.181.14 CE 192.168.181.13 | 185.164.30.225 | 185.164.30.226 | [14 empty] | Complex site type - requires redesign | Complete | [5 empty] | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms not sent |  | 07:00 to 15:00 | 10:00 to 17:00 | 117273 |  |  |  | CRQ000000702334 | Completed | Completed |  |  |  | Circuit Migrated - First Time right
I0120089CTL1 | I0120089CTL1 |  |  |  | North America | United States | UNITED STATES_BURLINGTON_ 60 LAKE STREET_SEVENTH GENERATION, 60 LAKE STREET, BURLINGTON |  |  |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-05-15 | 2020-05-20 | Amber | 2020-05-20 | 2020-05-22 | Amber | 2020-07-19 | 2020-08-14 | Red | 2020-07-31 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 25-May: Pending circuit delivery | Yellow | Circuit not ordered | Circuit Provider
I019436CTL1 | I019436CTL1 |  |  |  | North America | United States | UNITED STATES_CINCINNATI_UNILEVER_BEST_FOODS |  |  | un-una-usacin1-vpn001 | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-05-05 | 2020-05-05 | Complete | 2020-05-10 | 2020-05-12 | Complete | 2020-07-09 | 2020-06-05 | Complete | 2020-07-23 | 2020-09-14 | Red | 31-Aug: Circuit test successful. Migration approved for Sep 14th at 9AM EST. 24-Aug: Circuit test pending. Migration on Sep 4th to be confirmed. 6-Aug: Migration on Aug 25 to be confirmed. 26-Jun: Circuit delivered. Pending circuit testing. | Pink | Circuit Delivered | [17 empty] | 20 | 50 | [11 empty] | 9AM EST | [6 empty] | LAN: 4.58.69.240/29 WAN: 4.53.70.160/30 CTL: 4.53.70.161 UNI: 4.53.70.162 | 4.53.70.161 | 4.53.70.162 | 4.58.69.240/29 | [8 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  |  | In Progress |  | No |  |  | No | Assessment Complete |  |  | 13hrs UTC | 9AM EST |  |  |  |  | CRQ000000702278 | Completed | Completed
I0120234BT1 | I0120234BT1 |  |  |  | North America | United States | Amityville 11 - S Ranick Dr |  |  |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-04-29 | 2020-04-29 | Complete | 2020-05-04 | 2020-05-07 | Amber | 2020-07-03 | 2020-07-30 | Red | 2020-07-17 | 2020-10-30 | Red |  | Yellow | Circuit Ordered | [8 empty] | 11 Ranick Drive South | [8 empty] | 10M | 100 | [30 empty] | Rene Gonzalez Iniguez |  |  |  |  | Standard site type - Hybrid (MPLS + DMVPN) | [6 empty] | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved
I0120235BT1 | I0120235BT1 |  |  |  | North America | United States | Amityville 36 - W Ranick Dr |  |  | un-una-usaami1-vpn002 | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-04-29 | 2020-04-29 | Complete | 2020-05-04 | 2020-05-07 | Amber | 2020-07-03 | 2020-07-30 | Red | 2020-07-17 | 2020-10-30 | Red |  | Yellow | Circuit Ordered | [8 empty] | 36 Ranick Drive South | [8 empty] | 6M | 40 | [30 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku |  |  | Standard site type - Hybrid (MPLS + DMVPN) | [6 empty] | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved
I0120236BT1 | I0120236BT1 |  |  |  | North America | United States | USA_FRAMINGDALE_1 ADAMS BLVD |  |  |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-05 | 2020-05-05 | Complete | 2020-05-10 | 2020-05-12 | Amber | 2020-07-09 | 2020-08-05 | Red | 2020-07-23 | 2020-10-30 | Red |  | Yellow | Circuit Ordered | [18 empty] | 100 | [30 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku
I021050BT1 | I021050BT1 |  |  |  | North America | United States | USA_JEFFERSON_CITY_WEST_TRUMAN_BOULEVARD |  |  |  | Juan Simon | WAN Circuit Migration |  | BT | BT |  |  | 2020-05-15 | 2020-05-30 | Red | 2020-05-20 | 2020-05-22 | Amber | 2020-07-19 | 2020-08-14 | Red | 2020-07-31 | 2020-10-30 | Red |  | Yellow | Circuit not ordered | [18 empty] | 100
I0220109CTL1 | I0220109CTL1 |  |  |  | North America | United States | USA_NEWYORK_Sir Kensington |  |  |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-05-05 | 2020-05-05 | Complete | 2020-05-10 | 2020-05-12 | Amber | 2020-07-09 | 2020-08-05 | Red | 2020-07-23 | 2020-10-30 | Red | 1-Jun: Sales site closed until September. 27-May: Pending circuit delivery. | Yellow | Circuit Ordered | [18 empty] | 50 | [30 empty] | Fernando Ramos
I01168UNL1 | I01168UNL1 |  |  | Top | South Asia | Pakistan | PAKISTAN_KARACHI_FATIMA_JINNAH_ROAD |  |  | un-sea-pkkar-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Jazz | 2020438277 | 2020-05-15 | 2020-05-20 | Complete | 2020-05-20 | 2020-05-22 | Complete | 2020-07-19 | 2020-08-15 | Red | 2020-07-31 | 2020-09-12 | Red | Next Action: ISP to deliver circuit. 28-Aug: Rolled back. Multiple spoke sites were not working. Issue with cable length to connect between router and switch. | Green | Circuit Order Accepted | Circuit Provider | [17 empty] | 300 | [18 empty] | WAN: 210.2.131.32/30 LAN: 210.2.131.208/29 | [5 empty] | Jazz | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | [10 empty] | Window Date agreed - End user Comms not sent |  | 3:00 am to 3 pm UTC | 8 am to 8 pm local time | 117675, CHG000000000041982 |  |  |  | CRQ000000695234 | Completed | Completed
I02168UNL1 | I02168UNL1 |  |  | Top | South Asia | Pakistan | PAKISTAN_KARACHI_FATIMA_JINNAH_ROAD |  |  | un-sea-pkkar-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Transworld | CIR-206 | 2020-05-15 | 2020-05-20 | Complete | 2020-05-20 | 2020-05-22 | Complete | 2020-07-19 | 2020-08-12 | Red | 2020-07-31 | 2020-09-12 | Red | Next Action: ISP to deliver circuit. 28-Aug: Rolled back. Multiple spoke sites were not working. Issue with cable length to connect between router and switch. | Green | Circuit Order Accepted | Circuit Provider | [17 empty] | 300 | [18 empty] | Customer LAN IP Pool (routed statically or via BGP on P2P IPs): 110.93.217.24/29 [Useable IP: 110.93.217.25 to 110.93.217.30] P2P IP pool : 110.93.232.184/30 [GW IP @ TW end : 110.93.232.185/30] | 110.93.232.185 | 110.93.232.186 | 110.93.217.24/29 |  |  | Transworld | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | [10 empty] | Window Date agreed - End user Comms not sent |  | 3:00 am to 3 pm UTC | 8 am to 8 pm local time | 117675, CHG000000000041982 |  |  |  | CRQ000000694546 | Completed | Completed
I011216UNL1 | I011216UNL1 |  |  | Top | South Asia | Pakistan | PAKISTAN_LAHORE_SALES_DRP |  |  | un-sea-pklhrs-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | PTCL | UNILEVER/IPBW-FIBER/LHR/CCCS67-- LHR585-PE03 | 2020-05-15 | 2020-05-20 | Complete | 2020-05-20 | 2020-05-22 | Complete | 2020-07-19 | 2020-07-13 | Complete | 2020-07-31 | 2020-08-19 | Complete | Next Action: Finalise circuit ordering. | Complete | Circuit Migrated | Circuit Provider | [7 empty] | Lahore Sales Office, + 14 Km Multan Road, Shahpur Interchange, Lahore | [9 empty] | 300 | [18 empty] | WAN Pool: 119.156.26.52/30 PIE end: 119.156.26.53 Customer end: 119.156.26.54 LAN IP pool: 119.156.29.88/29 | [5 empty] | PTCL | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | [10 empty] | Window Date agreed - End user Comms sent |  | 2:00 pm to 8 pm UTC | 6 pm to 12 am local time | 112016 |  |  |  | CRQ000000692834 | Completed | Completed
I0110248CTL1 | I0110248CTL1 |  |  | Medium | North America | United States | USA_Cresskill |  |  |  | Juan Simon | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-05-30 | 2020-05-30 | Green | 2020-06-04 | 2020-06-07 | Amber | 2020-08-03 | 2020-08-30 | Red | 2020-08-17 | 2020-10-30 | Red | 31-Aug: Complicated site (warehouse). Will need to do detailed analysis. Internal cabling pending. | Yellow | Circuit not ordered | [18 empty] | 30 | [18 empty] | LAN: 4.16.88.200/29 WAN: 4.15.27.200/30 CTL: 4.15.27.201 UNI: 4.15.27.202 | [11 empty] | Hugo Trejo
I02WC016ORA1 | I02WC016ORA1 |  |  | Medium | Latin America | Mexico | MEXICO_MONTERREY_4001 FUNDADORES_OF_REG_MONTERREY |  |  |  | Juan Simon | WAN Circuit Migration |  | Orange | ORA |  |  | 2020-05-30 | 2020-05-30 | Green | 2020-06-04 | 2020-06-07 | Amber | 2020-08-03 | 2020-08-30 | Red | 2020-08-17 | 2020-10-15 | Red | 10-Sep: Site to be closed. Circuit order cancelled. | Out of Scope | Circuit not ordered | [18 empty] | 30
I0111023GTT1 | I0111023GTT1 |  |  |  | Europe | GERMANY | GERMANY_HAMBURG_WENDENSTRASSE |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | GTT | GTT |  | GTT/001968723 | 2020-05-30 | 2020-05-30 | Green | 2020-06-04 | 2020-06-08 | Amber | 2020-08-03 | 2020-09-30 | Red | 2020-08-17 | 2020-12-11 | Red | 15/07 - waiting for landlord approval required 10/07 - Indicative completion date - site survey needed 16/06 - Email sent by Swati.Samanta2@unilever.com to Gergana confirming local site details and demarc point | Yellow | Circuit not ordered | [18 empty] | 10 | [18 empty] | 154.14.96.28/30 Network - 154.14.96.28 First usable - 154.14.96.29 Last usable - 154.14.96.30 Broadcast - 154.14.96.31 Subnet Mask - 255.255.255.252 154.14.96.80/29 Network - 154.14.96.80 First usable - 154.14.96.81 Last usable - 154.14.96.86 Broadcast - 154.14.96.87 Subnet Mask - 255.255.255.248
I0211023CTL1 | I0211023CTL1 |  |  |  | Europe | GERMANY | GERMANY_HAMBURG_WENDENSTRASSE |  |  |  | Eloise Shepheard | WAN Circuit Migration |  | CenturyLink | CL |  |  | 2020-05-30 | 2020-05-30 | Green | 2020-06-04 | 2020-06-08 | Amber | 2020-08-03 | 2020-08-31 | Red | 2020-08-17 | 2020-11-14 | Red | 10/07 - Pending delivery 01/07 - Very early stages with provider and CTL waiting for update | Yellow | Circuit not ordered | [18 empty] | 10
I029436GTT1 | I029436GTT1 |  |  |  | North America | United States | UNITED STATES_CINCINNATI_UNILEVER_BEST_FOODS |  |  | un-una-usacin1-vpn002 | Juan Simon | WAN Circuit Migration |  | GTT | GTT |  | GTT/001968638 | 2020-05-15 | 2020-05-20 | Amber | 2020-05-20 | 2020-05-27 | Red | 2020-07-19 | 2020-09-30 | Red | 2020-07-31 | 2020-09-18 | Red | 9-Sep: Migration tentatively approved for September 18th. Could be pushed to Sep-21. Depending on issue with this router down right now. Will try to fix on migration. | Green | Circuit not ordered |  | Check dates | [35 empty] | 209.120.191.88/30 Network - 209.120.191.88 First usable - 209.120.191.89 Last usable - 209.120.191.90 Broadcast - 209.120.191.91 Subnet Mask - 255.255.255.252 209.120.191.80/29 Network - 209.120.191.80 First usable - 209.120.191.81 Last usable - 209.120.191.86 Broadcast - 209.120.191.87 Subnet Mask - 255.255.255.248 | 209.120.191.89 | 209.120.191.90/30 | 209.120.191.80/29 | [8 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku | [8 empty] | No
I0120352UNL1 | I0120352UNL1 |  |  |  | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_CARMONA |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | PLDT | UP1I01-092018-30821 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-07-13 | Complete | 2020-07-17 | 2020-07-13 | Complete |  | Complete | Circuit Migrated |  | Check dates | [16 empty] | 10 | [11 empty] | 10 am to 3 pm local time | [6 empty] | PID1-1ANV0T6_UNILEVER RFM ICE CREAM, INC._I-GATE PREMIUM_10M IGATE TYPE = PREMIUM LAN IPv4 = 27.110.137.112/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 122.55.191.98 | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | [10 empty] | Window Date agreed - End user Comms sent |  | 0200 hrs too 0700 hrs | 1000 hrs to1500 hrs | 92845 |  |  |  | CRQ000000686245 | Completed | Completed
I0111156UNL2 | I0111156UNL2 |  |  |  | SEAA | Philippines | PHILIPPINES_URIC_DEPOT_DAVAO |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | PLDT | UP1I01-022019-88563 | 2020-04-30 | 2020-04-30 | Complete | 2020-05-05 | 2020-05-08 | Complete | 2020-07-04 | 2020-07-14 | Complete | 2020-07-17 | 2020-07-14 | Complete |  | Complete | Circuit Migrated |  | Check dates | [16 empty] | 10 | [11 empty] | 10 am to 3 pm local time | [6 empty] | PID1-1ANV15R_UNILEVER PHILS. INC._IGATE PREMIUM_10M IGATE TYPE = PREMIUM LAN IPv4 = 210.1.83.232/29 SUBNETMASK = 255.255.255.248 WAN CUSTOMER IPv4/30 = 210.1.87.26 | [5 empty] | PLDT | [5 empty] | Sunil Manjunath | Sunil Manjunath | Sunil Manjunath | [10 empty] | Window Date agreed - End user Comms not sent |  | 0200 hrs too 0700 hrs | 1000 hrs to1500 hrs | 92883 |  |  |  | CRQ000000686412 | Completed | Completed
I019674UNL1 | I019674UNL1 |  |  |  | South Asia | India | AMLI PP FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-29 | Red | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd Silvassa Amli Personal Product Survey No 907 Near Gandhigram Bus Stop Kilwani Naka Amli Village 396230 | [34 empty] | BHARTI AIRTEL
I029674UNL1 | I029674UNL1 |  |  |  | South Asia | India | AMLI PP FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | VODAFONE |  | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 |  | Complete | 2020-09-02 | 2020-08-28 | Green | 2020-09-16 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd Silvassa Amli Personal Product Survey No 907 Near Gandhigram Bus Stop Kilwani Naka Amli Village 396230 | [34 empty] | VODAFONE
I012275UNL1 | I012275UNL1 |  |  |  | South Asia | India | BELAPUR (MUMBAI RO) |  |  | un-sea-ind-mumro-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | TATA | 091MUMB030035417097_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-07-15 | Complete | 2020-09-16 | 2020-08-31 | Complete | 17-Aug; While performing speed testing on 17th Aug, encountered issue related to DHCP. During troubleshooting lost access to dmvpn router and had to roll back to MPLS link. Migration replanned on 31st AUg. 12-Aug: Issue related to circuit Speed. Need to plan one more testing window and perform speed test on the link. | Complete | Circuit Migrated | [8 empty] | Hindustan Unilever Ltd, Branch Office, Uttara, Plot # 2, Sector No. 11, CBD,Belapur, Navi Mumbai -,Mumbai,Maharashtra India 400614 | [8 empty] | 100MB | [19 empty] | WAN IP POOL :- 115.114.89.136/30 WAN IP TCL GATEWAY :- 115.114.89.137 WAN IP HUL :- 115.114.89.138 LAN IP POOL :- 115.114.131.72/29 ROUTING PROTOCOL :- STATIC | 115.114.89.137 | 115.114.89.138 | 115.114.131.72/29 |  |  | TATA | [5 empty] | Jahnavi Gonuguntla | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual MPLS | Complete |  | Yes | Yes | Yes |  | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 4:30 am to 11:30 am UTC | 10 am to 4 pm | 111563 and 111462 -for speed test by ISP.117721 -latest migration |  |  |  | CRQ000000695988 | Completed | Completed
I022275UNL1 | I022275UNL1 |  |  |  | South Asia | India | BELAPUR (MUMBAI RO) |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | SIFY | 2020069065 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-11-07 | Red | 2020-09-16 | 2020-10-30 | Red |  | Pink | Circuit Order Accepted |  | Check dates | [6 empty] | HUL, Branch Office, Uttara, Plot # 2, Sector No. 11, CBD Belapur, Navi Mumbai |  |  |  |  | Rashmi.Sisodia@unilever.com | 7409400115 | [28 empty] | SIFY | [5 empty] | Jahnavi Gonuguntla
I012264UNL1 | I012264UNL1 |  |  |  | South Asia | India | CHENNAI RO |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-26 | Red | 2020-09-11 | 2020-09-29 | Red |  | Yellow | Circuit Order Accepted |  | Check dates | [6 empty] | HUL, 101, Santhome High Road, Entrance from South Canal Road, Chennai | [34 empty] | BHARTI AIRTEL | [5 empty] | Jahnavi Gonuguntla
I022264UNL1 | I022264UNL1 |  |  |  | South Asia | India | CHENNAI RO |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | TATA | 091CHEN030035417060_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-09-15 | Red | 2020-09-16 | 2020-09-29 | Red |  | Pink | Circuit Order Accepted | [8 empty] | HUL, 101, Santhome High Road, Entrance from South Canal Road, Chennai | [34 empty] | TATA | [5 empty] | Jahnavi Gonuguntla
I012742UNL1 | I012742UNL1 |  |  |  | South Asia | India | CHIPLUN FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-08-25 | Green | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever ltd, B-7, Lote Parshuram MIDC, Tal Khed , Dist Ratnagiri Maharashtra | [34 empty] | BHARTI AIRTEL
I022742UNL1 | I022742UNL1 |  |  |  | South Asia | India | CHIPLUN FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Jio |  | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 |  | Complete | 2020-09-02 | 2020-08-28 | Green | 2020-09-16 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever ltd, B-7, Lote Parshuram MIDC, Tal Khed , Dist Ratnagiri Maharashtra | [34 empty] | Jio
I013277UNL1 | I013277UNL1 |  |  |  | South Asia | India | DOOMDOOMA FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-24 | Red | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Dag No-21, Off 122 Fs Grant Mouza Tingrai, Doom Dooma Industrial Estate, Off NH-37, Dist. Tinsukia, Assam | [34 empty] | BHARTI AIRTEL | [5 empty] | Jahnavi Gonuguntla
I023277UNL1 | I023277UNL1 |  |  |  | South Asia | India | DOOMDOOMA FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Jio |  | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 |  | Complete | 2020-09-02 | 2020-08-28 | Green | 2020-09-16 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Dag No-21, Off 122 Fs Grant Mouza Tingrai, Doom Dooma Industrial Estate, Off NH-37, Dist. Tinsukia, Assam | [34 empty] | Jio | [5 empty] | Jahnavi Gonuguntla
I012724UNL1 | I012724UNL1 |  |  |  | South Asia | India | GRF FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-29 | Red | 2020-09-11 | 2020-10-05 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Limited, Garden Reach Factory, 63,Garden Reach, Kolkatta | [34 empty] | BHARTI AIRTEL | [5 empty] | Jahnavi Gonuguntla
I022724UNL1 | I022724UNL1 |  |  |  | South Asia | India | GRF FACTORY |  |  | un-sea-ind-grf-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | SIFY | 2020069062 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-09-10 | Complete | 2020-09-16 | 2020-10-12 | Red |  | Pink | Circuit Delivered | [8 empty] | Hindustan Unilever Limited, Garden Reach Factory, 63,Garden Reach, Kolkatta |  |  |  |  | Manas.Mukherjee@unilever.com | 9007098121 | [22 empty] | LAN IP - 1.6.134.248/29 WAN IP - 1.6.135.0/30 | 1.6.135.1/30 | 1.6.135.2/30 | 1.6.134.248/29 |  |  | SIFY | [5 empty] | Jahnavi Gonuguntla | [20 empty] | CRQ000000707174 | Completed | Completed
I012721UNL1 | I012721UNL1 |  |  |  | South Asia | India | HALDIA FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-08-25 | Green | 2020-09-11 | 2020-10-07 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | HINDUSTAN UNILEVER LIMITED Haldia Detergent Factory¦ P. O. - Durgachak Haldia¦ Purba Midnapore - West Bengal | [34 empty] | BHARTI AIRTEL
I022721UNL1 | I022721UNL1 |  |  |  | South Asia | India | HALDIA FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | TATA | 091HALD030035416986_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-09-15 | Red | 2020-09-16 | 2020-10-14 | Red |  | Pink | Circuit Order Accepted | [8 empty] | HINDUSTAN UNILEVER LIMITED Haldia Detergent Factory¦ P. O. - Durgachak Haldia¦ Purba Midnapore - West Bengal | [34 empty] | TATA
I012749UNL1 | I012749UNL1 |  |  |  | South Asia | India | HARIDWAR FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | TATA | 091HARI030035417245_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-08-31 | Green | 2020-09-16 | 2020-10-09 | Red |  | Pink | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd., Plot No. 1, Sector - 1A, Integrated Indl Estate, Ranipur, Haridwar | [34 empty] | TATA
I022749UNL1 | I022749UNL1 |  |  |  | South Asia | India | HARIDWAR FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Jio |  | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 |  | Complete | 2020-09-02 | 2020-08-28 | Green | 2020-09-16 | 2020-10-16 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd., Plot No. 1, Sector - 1A, Integrated Indl Estate, Ranipur, Haridwar | [34 empty] | Jio
I012267UNL1 | I012267UNL1 |  |  |  | South Asia | India | HURC WHITEFIELD |  |  | un-sea-ind-hurcblr-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL | 16038731 | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-08-29 | Complete | 2020-09-11 | 2020-09-30 | Red |  | Pink | Circuit Delivered | [8 empty] | Hindustan Unilever Limited HURC, No. 64, Main Road, Whitefields P.O., Bangalore,Karnataka India 560066 | [8 empty] | 200 | [19 empty] | WAN Pool -202.56.198.72/30 PE IP-202.56.198.73 CE IP -202.56.198.74 Subnet-255.255.255.252 LAN IP -192.168.6.0/29 Subnet-255.255.255.248 | 202.56.198.73/30 | 202.56.198.74/30 | 192.168.6.0/29 |  |  | BHARTI AIRTEL | [5 empty] | Jahnavi Gonuguntla |  |  |  |  | Standard site type - Dual MPLS | Complete |  |  |  | Yes |  | Assessment Complete Received tunnel IP or LAN IP (if required) | [8 empty] | CRQ000000710360 | Submitted | Submitted
I022267UNL1 | I022267UNL1 |  |  |  | South Asia | India | HURC WHITEFIELD |  |  | un-sea-ind-hurcblr-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | TATA | 091BANG030035417023_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-09-15 | Red | 2020-09-16 | 2020-09-30 | Red |  | Pink | Circuit Order Accepted | [8 empty] | Hindustan Unilever Limited HURC, No. 64, Main Road, Whitefields P.O., Bangalore,Karnataka India 560066 | [28 empty] | WAN IP POOL :- 121.244.199.140/30 WAN IP TCL GATEWAY :- 121.244.199.141 WAN IP HUL :- 121.244.199.142 LAN IP POOL :- 121.244.210.192/29 | 121.244.199.141/30 | 121.244.199.142/30 | 121.244.210.192/29 |  |  | TATA | [5 empty] | Jahnavi Gonuguntla | [5 empty] | Complete | [5 empty] | Assessment Complete Received tunnel IP or LAN IP (if required) | [8 empty] | CRQ000000710362 | Submitted | Submitted
I0110925UNL1 | I0110925UNL1 |  |  |  | South Asia | India | INDORE RO |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router + DMVPN conversion, Agile wifi consolidation | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-08-25 | Green | 2020-09-11 | 2020-09-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Limited – Indore Princess Business Skypark , 511 to 514 , Block No 22,23,24 , PU-3 , AB Road , opp Orbit Mall , Indore, Madhya Pradesh | [34 empty] | BHARTI AIRTEL | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I0210925UNL1 | I0210925UNL1 |  |  |  | South Asia | India | INDORE RO |  |  | un-sea-ind-indoro-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router + DMVPN conversion | Unilever | Uni | TATA | 091INDO030035416949_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-07-15 | Complete | 2020-09-16 | 2020-08-25 | Complete |  | Complete | Circuit Migrated | [8 empty] | Hindustan Unilever Limited – Indore Princess Business Skypark , 511 to 514 , Block No 22,23,24 , PU-3 , AB Road , opp Orbit Mall , Indore, Madhya Pradesh | [8 empty] | 12M | [19 empty] | WAN IP POOL :- 121.244.116.248/30 WAN IP TCL GATEWAY :- 121.244.116.249 WAN IP HUL :- 121.244.116.250 LAN IP POOL :- 121.244.113.112/29 ROUTING PROTOCOL :- STATIC | 121.244.116.249 | 121.244.116.250 | 121.244.113.112/29 |  |  | TATA | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual MPLS | Complete |  | Yes | Yes | Yes | Yes-Onboarding file created for CMS | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms not sent |  | 4:30 am to 11:30 am UTC | 10 am to 4 pm | 116282 |  |  |  | CRQ000000695991 | Completed | Completed | Tested -Pass-First Time
I012718UNL1 | I012718UNL1 |  |  |  | South Asia | India | KANDLA FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | TATA | 091KUTC030035417282_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-09-15 | Red | 2020-09-16 | 2020-10-23 | Red |  | Pink | Circuit Order Accepted | [8 empty] | Unilever India Export Limited, Plot No. 253 - 257, Sector No.IV, Kandla Special Economic Zone (KASEZ), Gandhidham - Kutch, State - Gujara | [34 empty] | TATA
I022718UNL1 | I022718UNL1 |  |  |  | South Asia | India | KANDLA FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Jio |  | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 |  | Complete | 2020-09-02 | 2020-08-28 | Green | 2020-09-16 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Unilever India Export Limited, Plot No. 253 - 257, Sector No.IV, Kandla Special Economic Zone (KASEZ), Gandhidham - Kutch, State - Gujara | [34 empty] | Jio
I012754UNL1 | I012754UNL1 |  |  |  | South Asia | India | KHAMGAON FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-22 | Red | 2020-09-11 | 2020-11-02 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd., C-9, MIDC Industrial Estate, Khamgaon, Dist: Dhuldhal, Maharasthra | [34 empty] | BHARTI AIRTEL | [5 empty] | Jahnavi Gonuguntla
I022754UNL1 | I022754UNL1 |  |  |  | South Asia | India | KHAMGAON FACTORY |  |  | un-sea-ind-khmgn-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | SIFY | 2020069063 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-09-25 | Red | 2020-09-16 | 2020-11-09 | Red |  | Pink | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd., C-9, MIDC Industrial Estate, Khamgaon, Dist: Dhuldhal, Maharasthra |  |  |  |  | Ashwanik.Bhatia@unilever.com | 8550999084 |  |  | 12MB | [19 empty] | LAN IP - 1.7.160.200/29 WAN IP - 1.7.160.240/30 | 1.7.160.241/30 | 1.7.160.242/30 | 1.7.160.200/29 |  |  | SIFY | [5 empty] | Jahnavi Gonuguntla |  |  |  |  | Standard site type - Dual MPLS |  |  |  | Yes | [11 empty] | CRQ000000707099 | Completed | Completed
I012273UNL1 | I012273UNL1 |  |  |  | South Asia | India | KOLKATTA RO |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-29 | Red | 2020-09-11 | 2020-09-20 | Red |  | Yellow | Circuit Order Accepted |  | Check dates | [6 empty] | HUL, Branch Office, Brooke House ,9, Shakespeare Sarani, P.O.Box:187, Kolkatta | [34 empty] | BHARTI AIRTEL | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla
I022273UNL1 | I022273UNL1 |  |  |  | South Asia | India | KOLKATTA RO |  |  | un-sea-ind-kolkro-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | TATA | 091KOLK030035417171_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-07-22 | Complete | 2020-09-16 | 2020-08-24 | Complete |  | Complete | Circuit Migrated | [8 empty] | HUL, Branch Office, Brooke House ,9, Shakespeare Sarani, P.O.Box:187, Kolkatta | [8 empty] | 30MB | [19 empty] | WAN IP POOL :- 115.110.125.148/30 WAN IP TCL GATEWAY :- 115.110.125.149 WAN IP HUL :- 115.110.125.150 LAN IP POOL :- 121.242.162.128/29 ROUTING PROTOCOL :- STATIC | 115.110.125.149 | 115.110.125.150 | 121.242.162.128/29 |  |  | TATA | [5 empty] | Jahnavi Gonuguntla | Jahnavi Gonuguntla | Jahnavi Gonuguntla |  |  | Standard site type - Dual MPLS | Complete |  | Yes | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 4:30 am to 11:30 am UTC | 10 am to 4 pm | 115436 |  |  |  | CRQ000000695993 | Completed | Completed
I01WC110UNL1 | I01WC110UNL1 |  |  |  | South Asia | India | KPF FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | TATA | 091KOLK030035417208_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-09-30 | Red | 2020-09-16 | 2020-11-04 | Red |  | Pink | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd., (Kidderpore Factory) Tea Excellence Center, 1, Transport Depot Road, Kolkatta Calcutta, West Bengal | [34 empty] | TATA
I02WC110UNL1 | I02WC110UNL1 |  |  |  | South Asia | India | KPF FACTORY |  |  | un-sea-ind-kpf-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | SIFY | 2020069067 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-10-08 | Red | 2020-09-16 | 2020-11-06 | Red |  | Pink | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd., (Kidderpore Factory) Tea Excellence Center, 1, Transport Depot Road, Kolkatta Calcutta, West Bengal |  |  |  |  | Manas.Mukherjee@unilever.com | 9007098121 | [22 empty] | LAN IP - 1.6.134.240/29 WAN IP - 1.6.134.236/30 | 1.6.134.237/30 | 1.6.134.238/30 | 1.6.134.240/29 |  |  | SIFY | [26 empty] | CRQ000000707275 | Completed | Completed
I0110924UNL1 | I0110924UNL1 |  |  |  | South Asia | India | LUCKNOW RO |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-27 | Red | 2020-09-11 | 2020-09-25 | Red |  | Yellow | Circuit Order Accepted |  | Check dates | [6 empty] | Hindustan Unilever Ltd, Shalimar Titanium Corporate Park, First Floor,Vibhuti Khand, Gomti Nagar, Lucknow,Uttar Pradesh | [34 empty] | BHARTI AIRTEL | [5 empty] | Jahnavi Gonuguntla
I0210924UNL1 | I0210924UNL1 |  |  |  | South Asia | India | LUCKNOW RO |  |  | un-sea-ind-lknwro-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | TATA | 091LUCK030035417134_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-07-25 | Complete | 2020-09-16 | 2020-08-13 | Complete |  | Complete | Circuit Migrated | [8 empty] | Hindustan Unilever Ltd, Shalimar Titanium Corporate Park, First Floor,Vibhuti Khand, Gomti Nagar, Lucknow,Uttar Pradesh | [8 empty] | 30M | [19 empty] | WAN IP POOL :- 115.114.69.100/30 WAN IP TCL GATEWAY :- 115.114.69.101 WAN IP HUL :- 115.114.69.102 LAN IP POOL :- 115.114.96.248/29 | 115.114.69.101 | 115.114.69.102 | 115.114.96.248/29 |  |  | TATA | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual MPLS | Complete |  | Yes | Yes | Yes |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms not sent |  | 4:30 am to 11:30 am UTC | 10 am to 4 pm | 111066 |  |  |  | CRQ000000696519 | Completed | Completed | Tested -Pass-First Time
I012762UNL1 | I012762UNL1 |  |  |  | South Asia | India | NASIK ICD FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-21 | Red | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd., A8 / A9, MIDC, Malegaon, Sinnar, Dist. Nashik | [34 empty] | BHARTI AIRTEL
I022762UNL1 | I022762UNL1 |  |  |  | South Asia | India | NASIK ICD FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | VODAFONE |  | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 |  | Complete | 2020-09-02 | 2020-07-29 | Green | 2020-09-16 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd., A8 / A9, MIDC, Malegaon, Sinnar, Dist. Nashik | [34 empty] | VODAFONE
I012751UNL1 | I012751UNL1 |  |  |  | South Asia | India | ORAI FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-07-26 | Green | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | A-1, UPSIDC Industrial Area, Orai Distt. Jalaun (UP) | [34 empty] | BHARTI AIRTEL
I022751UNL1 | I022751UNL1 |  |  |  | South Asia | India | ORAI FACTORY |  |  | un-sea-ind-orai-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | SIFY | 2020069066 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-08-29 | Complete | 2020-09-16 | 2020-10-30 | Red |  | Pink | Circuit Delivered | [8 empty] | A-1, UPSIDC Industrial Area, Orai Distt. Jalaun (UP) |  |  |  |  | Ashwanik.Bhatia@unilever.com | 8550999084 | [22 empty] | LAN IP - 1.6.129.88/29 WAN IP - 1.6.129.132/30 | 1.6.129.133/30 | 1.6.129.134/30 | 1.6.129.88/29 |  |  | SIFY | [26 empty] | CRQ000000707155 | Completed | Completed
I012731UNL1 | I012731UNL1 |  |  |  | South Asia | India | PONDY DETS FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-28 | Red | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Pondicherry Dets Factory, Hindustan Lever Ltd., Soap Division, Off NH 45 Vadamangallam | [34 empty] | BHARTI AIRTEL
I022731UNL1 | I022731UNL1 |  |  |  | South Asia | India | PONDY DETS FACTORY |  |  | un-sea-ind-pondydets-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | SIFY | 2020069061 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-08-26 | Complete | 2020-09-16 | 2020-10-30 | Red |  | Pink | Circuit Delivered | [8 empty] | Pondicherry Dets Factory, Hindustan Lever Ltd., Soap Division, Off NH 45 Vadamangallam |  |  |  |  | Sathish.Ramappa@unilever.com | 9791904713/8971672867 | [21 empty] | Switch port: Gi0/2 | WAN IP : 1.7.167.240/30 LAN IP :1.7.167.200/29 | 1.7.167.241/30 | 1.7.167.242/30 | 1.7.167.200/29 |  |  | SIFY | [26 empty] | CRQ000000707244 | Completed | Completed
I012738UNL1 | I012738UNL1 |  |  |  | South Asia | India | RAJPURA FACTORY(PATIALA) |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-30 | Red | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Lever Ltd. A-5, Phase 2B, Focal Point, Rajpura, Patiala, Punjab India 140401 | [34 empty] | BHARTI AIRTEL | [5 empty] | Jahnavi Gonuguntla
I022738UNL1 | I022738UNL1 |  |  |  | South Asia | India | RAJPURA FACTORY(PATIALA) |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | TATA | 091PATI030035416875_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-09-25 | Red | 2020-09-16 | 2020-10-30 | Red |  | Pink | Circuit Order Accepted | [8 empty] | Hindustan Lever Ltd. A-5, Phase 2B, Focal Point, Rajpura, Patiala, Punjab India 140401 | [34 empty] | TATA | [5 empty] | Jahnavi Gonuguntla
I012761UNL1 | I012761UNL1 |  |  |  | South Asia | India | SILVASSA DETS FACTORY(DAPADA) |  |  | un-sea-ind-silvdets-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit + Router + DMVPN conversion | Unilever | Uni | BHARTI AIRTEL | 13169439 | 2019-05-28 | 2019-05-28 | Complete | 2019-06-02 | 2020-05-28 | Complete | 2019-08-01 | 2019-09-14 | Complete | 2019-08-15 | 2020-09-30 | Red |  | Pink | Circuit Delivered | [8 empty] | HLL-Silvasa Dets, 151/1, Khanvel Road, Dapada Village, Silvassa - 396230 | [8 empty] | 12MB | [19 empty] | CE WAN IP -125.22.82.14 PE WAN IP -125.22.82.13 SUBNET MASK- 255.255.255.252 LAN Pool_125.18.100.136/29 | 125.22.82.13 | 125.22.82.14 | 125.18.100.136/29 |  |  | BHARTI AIRTEL | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual MPLS | Complete |  | Yes | Yes | Yes | Yes-Onboarding file created for CMS |  |  |  | 3:30am to 3:30 pm UTC | 9 am to 9 pm local time |  |  |  |  | CRQ000000695995 | Completed | Completed
I022761UNL1 | I022761UNL1 |  |  |  | South Asia | India | SILVASSA DETS FACTORY(DAPADA) |  |  | un-sea-ind-silvdets-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit + Router + DMVPN conversion | Unilever | Uni | Vodafone | ENT32AHMSLV057896 | 2019-05-28 | 2019-05-28 | Complete | 2019-06-02 | 2020-05-28 | Complete | 2019-08-01 | 2019-08-10 | Complete | 2019-08-15 | 2020-09-30 | Red |  | Pink | Circuit Delivered | [8 empty] | HLL-Silvasa Dets, 151/1, Khanvel Road, Dapada Village, Silvassa - 396230 | [8 empty] | 12MB | [19 empty] | WAN IP Pool:- 122.15.15.232/30 ,LAN IP Pool:- 122.15.250.224/29, | 122.15.15.234 | 122.15.15.233 | 122.15.250.224/29 |  |  | Vodafone | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual MPLS | Complete |  | Yes | Yes | Yes | Yes-Onboarding file created for CMS |  |  |  | 3:30am to 3:30 pm UTC | 9 am to 9 pm local time |  |  |  |  | CRQ000000696242/CRQ000000705437 | Completed | Completed
I019517UNL1 | I019517UNL1 |  |  |  | South Asia | India | SOLAN BAROTIWALA FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-30 | Red | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | HINDUSTAN UNILEVER LTD, KHASRA NO. 94-96,355-409 VILL Balyana, Barotiwala INDUSTRIAL AREA, TEHSIL BADDI, DISTT SOLAN HP | [34 empty] | BHARTI AIRTEL
I029517UNL1 | I029517UNL1 |  |  |  | South Asia | India | SOLAN BAROTIWALA FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Jio |  | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 |  | Complete | 2020-09-02 | 2020-07-29 | Green | 2020-09-16 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | HINDUSTAN UNILEVER LTD, KHASRA NO. 94-96,355-409 VILL Balyana, Barotiwala INDUSTRIAL AREA, TEHSIL BADDI, DISTT SOLAN HP | [34 empty] | Jio
I012265UNL1 | I012265UNL1 |  |  |  | South Asia | India | SOUTH CITY (DELHI RO) |  |  | un-sea-ind-delhro-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-29 | Red | 2020-09-11 | 2020-09-30 | Red |  | Yellow | Circuit Order Accepted |  | Check dates | [6 empty] | Hindustan Unilever Ltd, Plot B, Block A, South City, Delhi-Jaipur Highway, Gurgaon, Haryana India 122001 | [34 empty] | BHARTI AIRTEL | [5 empty] | Jahnavi Gonuguntla
I022265UNL1 | I022265UNL1 |  |  |  | South Asia | India | SOUTH CITY (DELHI RO) |  |  | un-sea-ind-delhro-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | TATA | 091GURG030035417319_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-07-15 | Complete | 2020-09-16 | 2020-08-10 | Complete |  | Complete | Circuit Migrated | [8 empty] | Hindustan Unilever Ltd, Plot B, Block A, South City, Delhi-Jaipur Highway, Gurgaon, Haryana India 122001 | [8 empty] | 30M | [19 empty] | WAN IP POOL :- 115.110.232.248/30 WAN IP TCL GATEWAY :- 115.110.232.249 WAN IP HUL :- 115.110.232.250 LAN IP POOL :- 121.244.146.152/29 ROUTING PROTOCOL :- STATIC | 115.110.232.249 | 115.110.232.250 | 121.244.146.152/29 |  |  | TATA | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Dual MPLS | Complete |  | Yes | Yes | Yes |  | Assessment Complete CMSP ticket raised MOP created & config created Partner MOP created Prep documents uploaded to central storage Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) SSR approved | Window Date agreed - End user Comms sent |  | 4:30 am to 11:30 am UTC | 10 am to 4 pm | 109097 |  |  |  | CRQ000000696176 | Completed | Completed | Tested -Pass-First Time
I013273UNL1 | I013273UNL1 |  |  |  | South Asia | India | TATAPURAM FACTORY COCHIN |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-30 | Red | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Tatapuram factory,Mathai Manjooran road - Ernakulam north PO - | [34 empty] | BHARTI AIRTEL | [5 empty] | Jahnavi Gonuguntla
I023273UNL1 | I023273UNL1 |  |  |  | South Asia | India | TATAPURAM FACTORY COCHIN |  |  | un-sea-ind-tatapurm-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | SIFY | 2020069060 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-07-29 | Complete | 2020-09-16 | 2020-10-30 | Red |  | Pink | Circuit Delivered | [8 empty] | Tatapuram factory,Mathai Manjooran road - Ernakulam north PO - |  |  |  |  | Sathish.Ramappa@unilever.com | 9791904713/8971672867 | [22 empty] | LAN IP - 1.7.166.8/29 WAN IP - "1.7.166.112/30 " | 1.7.166.113/30 | 1.7.166.114/30 | 1.7.166.8/29 |  |  | SIFY | [5 empty] | Jahnavi Gonuguntla | [20 empty] | CRQ000000707090 | Completed | Completed
I013293UNL1 | I013293UNL1 |  |  |  | South Asia | India | NALAGARH ICD FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-21 | Red | 2020-09-11 | 2020-09-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Limited ,Hud bust No 143,khasra No 182-183-187/1 Vill-,Kirpalpur, Teh- Nalagarh, Distt-Solan, Himachal Pradesh India 174101 | [34 empty] | BHARTI AIRTEL | [5 empty] | Jahnavi Gonuguntla
I023293UNL1 | I023293UNL1 |  |  |  | South Asia | India | NALAGARH ICD FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | TATA | 091SOLA030035416912_871471 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-09-15 | Red | 2020-09-16 | 2020-09-30 | Red |  | Pink | Circuit Order Accepted | [8 empty] | Hindustan Unilever Limited ,Hud bust No 143,khasra No 182-183-187/1 Vill-,Kirpalpur, Teh- Nalagarh, Distt-Solan, Himachal Pradesh India 174101 | [34 empty] | TATA | [5 empty] | Jahnavi Gonuguntla
I013869UNL1 | I013869UNL1 |  |  |  | South Asia | India | TEC KOLKATTA |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-08-25 | Green | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | TEC KOLKATTA,Hindustan Unilever Ltd, Tea Excellence Center 1, Transport Depot Road, Kolkatta | [34 empty] | BHARTI AIRTEL
I023869UNL1 | I023869UNL1 |  |  |  | South Asia | India | TEC KOLKATTA |  |  | un-sea-teckolk-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | SIFY | 2020069064 | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 | 2020-07-04 | Complete | 2020-09-02 | 2020-10-08 | Red | 2020-09-16 | 2020-10-30 | Red |  | Pink | Circuit Order Accepted | [8 empty] | TEC KOLKATTA,Hindustan Unilever Ltd, Tea Excellence Center 1, Transport Depot Road, Kolkatta |  |  |  |  | Manas.Mukherjee@unilever.com | 9007098121 | [22 empty] | LAN IP - 1.6.135.8/29 WAN IP - 1.6.135.4/30 | 1.6.135.5/30 | 1.6.135.6/30 | 1.6.135.8/29 |  |  | SIFY | [26 empty] | CRQ000000706990 | Completed | Completed
I012748UNL1 | I012748UNL1 |  |  |  | South Asia | India | SUMERPUR FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-08-25 | Green | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd, A1, UPSIDC, Industrial Area, Bharua-Sumerpur, Hamirpur, (UP) - 210502 | [34 empty] | BHARTI AIRTEL
I022748UNL1 | I022748UNL1 |  |  |  | South Asia | India | SUMERPUR FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Jio |  | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 |  | Complete | 2020-09-02 | 2020-08-28 | Green | 2020-09-16 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd, A1, UPSIDC, Industrial Area, Bharua-Sumerpur, Hamirpur, (UP) - 210502 | [34 empty] | Jio
I0111254UNL1 | I0111254UNL1 |  |  |  | South Asia | India | CHIKKABALLAPUR DEPOT |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-19 | Red | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | HUL, C/o Linfox Logistics India Pvt Ltd., Musaddilal's Logistics Parrk, Guvvalakkanahobli Village, National Highway No. 7, Chikkaballapur Taluk, Bangalore - 562101 | [34 empty] | BHARTI AIRTEL
I0211254UNL1 | I0211254UNL1 |  |  |  | South Asia | India | CHIKKABALLAPUR DEPOT |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Jio |  | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 |  | Complete | 2020-09-02 | 2020-08-28 | Green | 2020-09-16 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | HUL, C/o Linfox Logistics India Pvt Ltd., Musaddilal's Logistics Parrk, Guvvalakkanahobli Village, National Highway No. 7, Chikkaballapur Taluk, Bangalore - 562101 | [34 empty] | Jio
I0112014UNL1 | I0112014UNL1 |  |  |  | South Asia | India | CHENNAI MEGA DEPOT |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | BHARTI AIRTEL |  | 2020-06-26 | 2020-06-26 | Complete | 2020-07-01 |  | Complete | 2020-08-30 | 2020-09-30 | Red | 2020-09-11 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd, Linfox Logistics,C/O Vinplex Pvt Ltd,86, Maduravasal Village,Uthukottai Taluk,Thiruvallur Dist., Chennai - 601102 | [34 empty] | BHARTI AIRTEL
I0212014UNL1 | I0212014UNL1 |  |  |  | South Asia | India | CHENNAI MEGA DEPOT |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Jio |  | 2020-06-29 | 2020-06-29 | Complete | 2020-07-04 |  | Complete | 2020-09-02 | 2020-08-28 | Green | 2020-09-16 | 2020-10-30 | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hindustan Unilever Ltd, Linfox Logistics,C/O Vinplex Pvt Ltd,86, Maduravasal Village,Uthukottai Taluk,Thiruvallur Dist., Chennai - 601102 | [34 empty] | Jio
I012169BT1 | I012169BT1 |  |  |  | North America | Canada | REXDALE_BELFIELD_RD |  |  |  | Juan Simon | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-06-19 | 2020-06-19 | Green | 2020-06-24 |  | Red | 2020-08-23 |  | Red | 2020-09-04 | 2020-10-30 | Red |  | Yellow | Circuit not ordered | [18 empty] | 40
I0111010UNL1 | I0111010UNL1 |  |  |  | SEAA | Indonesia | Indonesia_FF1 |  |  | un-sea-idnffi-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Lintasarta | 2020229956 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-09-14 | Red | 2020-09-17 | 2020-09-14 | Green |  | Green | Circuit Order Accepted |  | Check dates | [6 empty] | Jl. Jababeka VI blok L1-2, Kawasan Industri Jababeka Cikarang, Bekasi, 17550 | [8 empty] | 10M | 50 | [18 empty] | WAN: 202.152.28.178/30 CE IP to be configured on the customer end to remain the same: 202.152.28.176/30 LAN IP pool: 123.231.129.120/29 | 202.152.28.177/30 | 202.152.28.178/30 | 123.231.129.120/29 |  |  | Lintasarta | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  | No | Yes | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression Received tunnel IP or LAN IP (if required) | Window Date agreed - End user Comms sent |  | 4 am to 1 pm UTC | 11 am to 8 pm local time |  |  |  |  | CRQ000000708406 | Completed | Completed
I0211010UNL1 | I0211010UNL1 |  |  |  | SEAA | Indonesia | Indonesia_FF1 |  |  | un-sea-idnffi-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Indosat | IDIA UNILV JBB 180063 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-09-16 | Red | 2020-09-17 | 2020-09-16 | Green |  | Green | Circuit Order Accepted |  | Check dates | [6 empty] | Jl. Jababeka VI blok L1-2, Kawasan Industri Jababeka Cikarang, Bekasi, 17550 | [8 empty] | 25M | 50 | [18 empty] | 114.4.209.14/30 114.4.196.48/28 | 114.4.209.13/30 | 114.4.209.14/30 | 114.4.196.48/28 |  |  | Indosat | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala |  |  | Standard site type - Hybrid (MPLS + DMVPN) | Complete |  | No | No | Yes | No | Assessment Complete CMSP ticket raised MOP created & config created Raised an SSR for alarm suppression | Window Date agreed - End user Comms sent |  | 4 am to 9 pm UTC | 11 am to 4 pm local time
I011498UNL1 | I011498UNL1 |  |  |  | SEAA | Indonesia | Indonesia_RKT |  |  | un-sea-idnrkt-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Lintasarta | 2020230014 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-09-19 | Red | 2020-09-17 | 2020-09-21 | Amber |  | Green | Circuit Order Accepted |  | Check dates | [6 empty] | Jl. Rungkut Industri IV/5-11 Surabaya 60291, Indonesia | [9 empty] | 80 | [18 empty] | PE IP: 123.231.175.57/30 CE IP: 123.231.175.58/30 LAN IP pool: 123.231.199.88/29 | 123.231.175.57/30 | 123.231.175.58/30 | 123.231.199.88/29 |  |  | Lintasarta | [5 empty] | Rajeshware Gopalakrishnan Sasikala | [14 empty] | 4 am to 1 pm UTC | 11 am to 8 pm local time |  |  |  |  | CRQ000000709662 | In Progress | Completed
I021498UNL1 | I021498UNL1 |  |  |  | SEAA | Indonesia | Indonesia_RKT |  |  | un-sea-idnrkt-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Indosat | IDIA UNILV RKT 180061 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-09-18 | Red | 2020-09-17 | 2020-09-18 | Amber |  | Green | Circuit Order Accepted |  | Check dates | [6 empty] | Jl. Rungkut Industri IV/5-11 Surabaya 60291, Indonesia | [9 empty] | 80 | [18 empty] | 114.5.97.74/30 114.5.85.32/28 | 114.5.97.73/30 | 114.5.97.74/30 | 114.5.85.32/28 |  |  | Indosat | [5 empty] | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | Rajeshware Gopalakrishnan Sasikala | [10 empty] | Window Date agreed - End user Comms sent |  | 4 am to 9 pm UTC | 11 am to 4 pm local time | [6 empty] | Completed
I012708UNL1 | I012708UNL1 |  |  |  | SEAA | Indonesia | Indonesia_NSC |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Lintasarta | 2020224620 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-11 | Red | 2020-09-17 |  | Red |  | Pink | Circuit Order Accepted | [8 empty] | Kawasan Industri Jababeka Jl. Jababeka Raya Blok O - KIJ Cikarang, Bekasi 17530, Indonesia | [9 empty] | 80 | [24 empty] | Lintasarta | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I022708UNL1 | I022708UNL1 |  |  |  | SEAA | Indonesia | Indonesia_NSC |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Indosat |  | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-11 | Red | 2020-09-17 | 2020-10-11 | Red |  | Pink | Circuit Order Accepted |  | Check dates | [6 empty] | Kawasan Industri Jababeka Jl. Jababeka Raya Blok O - KIJ Cikarang, Bekasi 17530, Indonesia | [9 empty] | 80 | [24 empty] | Indosat | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I013821UNL1 | I013821UNL1 |  |  |  | SEAA | Indonesia | Indonesia_CIK |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Lintasarta | 2020228149 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-05 | Red | 2020-09-17 |  | Red |  | Pink | Circuit Order Accepted | [8 empty] | Kawasan Industri Jababeka JL. Jababeka IX Blok D 1-29 Cikarang, Bekasi 17520, Indonesia | [9 empty] | 100 | [18 empty] | PE IP: 123.231.230.17/30 CE IP: 123.231.230.18/30 LAN IP pool: 182.23.88.200/29 | [5 empty] | Lintasarta | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I023821UNL1 | I023821UNL1 |  |  |  | SEAA | Indonesia | Indonesia_CIK |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Indosat |  | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-02 | Red | 2020-09-17 | 2020-10-02 | Red |  | Pink | Circuit Order Accepted |  | Check dates | [6 empty] | Kawasan Industri Jababeka JL. Jababeka IX Blok D 1-29 Cikarang, Bekasi 17520, Indonesia | [9 empty] | 100 | [24 empty] | Indosat | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I0110627UNL1 | I0110627UNL1 |  |  |  | SEAA | Indonesia | Indonesia_WDC |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Lintasarta | 2020228165 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-14 | Red | 2020-09-17 |  | Red |  | Pink | Circuit Order Accepted | [8 empty] | Kawasan Industri MM 2100 Jl. Irian Blok SS No.7, 17520 | [9 empty] | 70 | [24 empty] | Lintasarta | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I0210627UNL1 | I0210627UNL1 |  |  |  | SEAA | Indonesia | Indonesia_WDC |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Indosat |  | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-15 | Red | 2020-09-17 | 2020-10-15 | Red |  | Pink | Circuit Order Accepted |  | Check dates | [6 empty] | Kawasan Industri MM 2100 Jl. Irian Blok SS No.7, 17520 | [9 empty] | 70 | [24 empty] | Indosat | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I0110029UNL1 | I0110029UNL1 |  |  |  | SEAA | Indonesia | Indonesia_CRMS |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Lintasarta | 2020224650 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-03 | Red | 2020-09-17 |  | Red |  | Pink | Circuit Order Accepted | [8 empty] | Jl. Jababeka II blok C 9-10, Kawasan Industri Jababeka Cikarang, Bekasi 17550 | [9 empty] | 10 | [24 empty] | Lintasarta | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I0210029UNL1 | I0210029UNL1 |  |  |  | SEAA | Indonesia | Indonesia_CRMS |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Indosat |  | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-06 | Red | 2020-09-17 | 2020-10-06 | Red |  | Pink | Circuit Order Accepted |  | Check dates | [6 empty] | Jl. Jababeka II blok C 9-10, Kawasan Industri Jababeka Cikarang, Bekasi 17550 | [9 empty] | 10 | [24 empty] | Indosat | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I0110031UNL1 | I0110031UNL1 |  |  |  | SEAA | Indonesia | Indonesia_MMLC |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Lintasarta | 2020224623 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-06 | Red | 2020-09-17 |  | Red |  | Pink | Circuit Order Accepted | [8 empty] | Jl. Megamendung Pusdik, Megamendung, Kec. Megamendung, Bogor, Jawa Barat 16770 | [9 empty] | 20 | [24 empty] | Lintasarta | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I019507UNL1 | I019507UNL1 |  |  |  | SEAA | Indonesia | Indonesia_Subang Bango |  |  | un-sea-idnsub1-vpn002 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Lintasarta | 2020228161 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-09-23 | Red | 2020-09-17 | 2020-09-23 | Red |  | Green | Circuit Order Accepted |  | Check dates | [6 empty] | Jl. Megamendung Pusdik, Megamendung, Kec. Megamendung, Bogor, Jawa Barat 16770 | [9 empty] | 20 | [18 empty] | PE IP: 23.231.164.233/30 CE IP: 23.231.164.234/30 LAN IP pool: 123.231.189.64/29 | 123.231.164.233/30 | 123.231.164.234/30 | 123.231.189.64/29 |  |  | Lintasarta | [5 empty] | Rajeshware Gopalakrishnan Sasikala | [14 empty] | 4 am to 1 pm UTC | 11 am to 8 pm local time |  |  |  |  | CRQ000000710505 | Submitted | Submitted
I029507UNL1 | I029507UNL1 |  |  |  | SEAA | Indonesia | Indonesia_Subang Bango |  |  | un-sea-idnsub1-vpn001 | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Indosat | DIA_MTX077156 73_SUB_2236 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-09-25 | Red | 2020-09-17 | 2020-09-25 | Red |  | Green | Circuit Order Accepted |  | Check dates | [16 empty] | 20 | [18 empty] | 114.7.124.118/30 114.7.145.208/28 | 114.7.124.117/30 | 114.7.124.118/30 | 114.7.145.208/28 |  |  | Indosat | [5 empty] | Rajeshware Gopalakrishnan Sasikala | [14 empty] | 4 am to 9 pm UTC | 11 am to 4 pm local time | [6 empty] | Submitted
I013829UNL1 | I013829UNL1 |  |  |  | SEAA | Indonesia | Indonesia_Depo Yogyakarta |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Lintasarta | 2020228171 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-09-30 | Red | 2020-09-17 |  | Red |  | Pink | Circuit Order Accepted | [18 empty] | 20 | [18 empty] | PE IP: 123.231.183.25/30 CE IP: 123.231.183.26/30 LAN IP pool: 123.231.184.112/29 | [5 empty] | Lintasarta | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I023829UNL1 | I023829UNL1 |  |  |  | SEAA | Indonesia | Indonesia_Depo Yogyakarta |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Indosat |  | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-13 | Red | 2020-09-17 | 2020-10-13 | Red |  | Pink | Circuit Order Accepted |  | Check dates | [6 empty] | Jl. Nyi Condro Lukito No 103 C (Monjali) Sinduadi, Mlati, Sleman, Yogyakarta 55284 | [9 empty] | 20 | [24 empty] | Indosat | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I013822UNL1 | I013822UNL1 |  |  |  | SEAA | Indonesia | Indonesia_Zra |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Lintasarta | 2020229555 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-16 | Red | 2020-09-17 |  | Red |  | Pink | Circuit Order Accepted | [8 empty] | Jl. Nyi Condro Lukito No 103 C (Monjali) Sinduadi, Mlati, Sleman, Yogyakarta 55284 | [9 empty] | 40 | [18 empty] | PE IP: 61.8.69.217/30 CE IP: 61.8.69.218/30 LAN IP pool: 123.231.131.40/29 | [5 empty] | Lintasarta | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I023822UNL1 | I023822UNL1 |  |  |  | SEAA | Indonesia | Indonesia_Zra |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Indosat |  | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-17 | Red | 2020-09-17 | 2020-10-17 | Red |  | Pink | Circuit Order Accepted |  | Check dates | [6 empty] | Jl. Cempaka Besar No. 24, RT-002 RW-001, Kelurahan Kertak Baru Ulu, Kec. Banjarmasin Tengah, Banjarmasin, Kalimantan Selatan 70111 | [9 empty] | 40 | [24 empty] | Indosat | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I0110688UNL1 | I0110688UNL1 |  |  |  | SEAA | Indonesia | Indonesia_UOI Factory |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Lintasarta | 2020228164 | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-08 | Red | 2020-09-17 |  | Red |  | Pink | Circuit Order Accepted | [8 empty] | Green Office Park Kav. 3, Jl BSD Boulevard Barat, BSD City, Tangerang 15345, Indonesia | [9 empty] | 50 | [18 empty] | PE IP: 123.231.251.25/30 CE IP: 123.231.251.26/30 LAN IP pool: 123.231.191.32/29 | [5 empty] | Lintasarta | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I0210688UNL1 | I0210688UNL1 |  |  |  | SEAA | Indonesia | Indonesia_UOI Factory |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Indosat |  | 2020-06-30 | 2020-06-30 | Complete | 2020-07-05 | 2020-07-05 | Complete | 2020-09-03 | 2020-10-07 | Red | 2020-09-17 | 2020-10-07 | Red |  | Pink | Circuit Order Accepted |  | Check dates | [6 empty] | Green Office Park Kav. 3, Jl BSD Boulevard Barat, BSD City, Tangerang 15345, Indonesia | [9 empty] | 50 | [24 empty] | Indosat | [5 empty] | Rajeshware Gopalakrishnan Sasikala
I012319UNL1 | I012319UNL1 |  |  |  | North Asia | Japan | JAPAN_FUKUOKA_SALES_OFFICE |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-10-14 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Fukuoka eight Bldg 4F, 4-3-2 Sumiyoshi, Hakata-ku | [9 empty] | 100 BE | [24 empty] | Softbank
I012321UNL1 | I012321UNL1 |  |  |  | North Asia | Japan | JAPAN_HIROSHIMA_SALES_OFFICE |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-10-14 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Hiroshima Intes 4F, 10-10 Hashimoto cho, Naka-ku | [9 empty] | 100 BE | [24 empty] | Softbank
I019532UNL1 | I019532UNL1 |  |  |  | North Asia | Japan | JAPAN_KANAGAWA_KSP |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-09-29 | Green | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Kanagawa Science Park C-9F, 3-2-1, Sakado, Kawasaki-shi | [9 empty] | 100 BE | [24 empty] | Softbank
I029532GTT1 | I029532GTT1 |  |  |  | North Asia | Japan | JAPAN_KANAGAWA_KSP |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | GTT | GTT |  |  | 2020-07-31 | 2020-08-10 | Complete | 2020-08-05 | 2020-08-17 | Complete | 2020-10-04 | 2020-10-31 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Kanagawa Science Park C-9F, 3-2-1, Sakado, Kawasaki-shi | [9 empty] | 100 BE | [50 empty] | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH
I011503UNL1 | I011503UNL1 |  |  |  | North Asia | Japan | JAPAN_MIYAGI-KEN_4-6-1 CHUO AOBA-KU SENDAI-SHI_JAPAN_SENDAI_SALES_OFFICE |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-10-14 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | SS30 Sumitomoseimei Sendai Chuo Bldg 9F, 4-6-1 Chuo Aoba-ku | [9 empty] | 100 BE | [24 empty] | Softbank
I011500UNL1 | I011500UNL1 |  |  |  | North Asia | Japan | JAPAN_NAGOYA_SHI_SALES_OFFICE |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-10-14 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Grand Square Shin Sakae 4F, 2-19-6 Shin-sakae, Naka-ku | [9 empty] | 100 BE | [24 empty] | Softbank
I011501UNL1 | I011501UNL1 |  |  |  | North Asia | Japan | JAPAN_OSAKA |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-10-29 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Shin Osaka Kowa Bulding 2F, 4-6-18 Miyahara, Yodogawa-ku | [9 empty] | 100 BE | [24 empty] | Softbank
I021501UNL1 | I021501UNL1 |  |  |  | North Asia | Japan | JAPAN_OSAKA |  |  |  | Vishal Joshi | Soft Delete | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Green | 2020-08-05 | 2020-08-05 | Green | 2020-10-04 | 2020-10-29 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit not ordered | [8 empty] | Shin Osaka Kowa Bulding 2F, 4-6-18 Miyahara, Yodogawa-ku | [9 empty] | 100 BE | [24 empty] | Softbank
I011502UNL1 | I011502UNL1 |  |  |  | North Asia | Japan | JAPAN_SAGAMIHARA_SHI_FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-09-29 | Green | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | 2-14-1 Onodai Minami-ku | [9 empty] | 100 BE | [24 empty] | Softbank
I021502GTT1 | I021502GTT1 |  |  |  | North Asia | Japan | JAPAN_SAGAMIHARA_SHI_FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | GTT | GTT |  |  | 2020-07-31 | 2020-08-18 | Complete | 2020-08-05 | 2020-08-21 | Complete | 2020-10-04 | 2020-10-31 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | 2-14-1 Onodai Minami-ku | [9 empty] | 100 BE | [50 empty] | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH
I011504UNL1 | I011504UNL1 |  |  |  | North Asia | Japan | Japan_Sapporo |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-10-29 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Norte Plaza 6F, 3-19-1, Kita-Kyujou, Nishi-Kita-ku | [9 empty] | 100 BE | [24 empty] | Softbank
I011499UNL1 | I011499UNL1 |  |  |  | North Asia | Japan | JAPAN_SHIZUOKA_FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-09-29 | Green | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | 3989-1, Iida, Morimachi | [9 empty] | 100 BE | [24 empty] | Softbank
I021499GTT1 | I021499GTT1 |  |  |  | North Asia | Japan | JAPAN_SHIZUOKA_FACTORY |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | GTT | GTT |  |  | 2020-07-31 | 2020-08-18 | Complete | 2020-08-05 | 2020-08-21 | Complete | 2020-10-04 | 2020-10-31 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | 3989-1, Iida, Morimachi | [9 empty] | 100 BE | [50 empty] | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH
P012320UNL1 | P012320UNL1 |  |  |  | North Asia | Japan | JAPAN_TOKYO_HEAD_OFFICE_NAKAMEGURO |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-10-29 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | 2-1-1 Kamimeguro, Meguro-Ku, Nakameguro GT Tower | [9 empty] | 100 | [24 empty] | Softbank
I012774UNL1 | I012774UNL1 |  |  |  | North Asia | Japan | JAPAN_TOKYO_LIPTON_BROOKE_BOND_HOUSE |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-10-29 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Ginza Fujiya Bldg 2F, 1-3-1 Ginza | [9 empty] | 100 BE | [24 empty] | Softbank
I0111120UNL1 | I0111120UNL1 |  |  |  | North Asia | Japan | JAPAN_TOYOSU_DATA_CENTER |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-10-29 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Toyosu 6-2-15 | [9 empty] | 100 | [24 empty] | Softbank | [25 empty] | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH
P0211120UNL1 | P0211120UNL1 |  |  |  | North Asia | Japan | JAPAN_TOYOSU_DATA_CENTER |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Complete | 2020-08-05 | 2020-08-05 | Complete | 2020-10-04 | 2020-10-29 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit Order Accepted | [8 empty] | Toyosu 6-2-15 | [9 empty] | 100 | [24 empty] | Softbank | [25 empty] | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH
I029661BT2 | I029661BT2 |  |  |  | North Asia | TAIWAN | TAIWAN_TAIPEI_UFS_OFFICE |  |  |  | Vishal Joshi | WAN Circuit Migration | Soft Upgrade + Fail over | BT | BT |  | GID9685048 | 2020-06-19 | 2020-06-19 | Complete | 2020-06-24 | 2020-06-24 | Complete | 2020-08-23 | 2020-09-02 | Complete | 2020-09-04 | 2020-09-04 | Complete | 4-Sep: Soft upgrade completed. Need to schedule fail over testing on 15th Sep. | Complete | Circuit Migrated |  | Check dates | [16 empty] | 10 | [24 empty] | Telstra | [5 empty] | Fat Nela
I0111188BT2 | I0111188BT2 |  |  |  | North Asia | TAIWAN | TAIWAN_TAOYUAN_TWH |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-06-19 | 2020-06-19 | Complete | 2020-06-24 | 2020-06-24 | Complete | 2020-08-23 | 2020-07-31 | Green | 2020-09-04 |  | Red |  | Yellow | Circuit Order Accepted | [18 empty] | 6
I0211188BT2 | I0211188BT2 |  |  |  | North Asia | TAIWAN | TAIWAN_TAOYUAN_TWH |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-06-19 | 2020-06-19 | Complete | 2020-06-24 | 2020-06-24 | Complete | 2020-08-23 | 2020-07-31 | Green | 2020-09-04 |  | Red |  | Yellow | Circuit Order Accepted | [18 empty] | 6
I0120364UNL1 | I0120364UNL1 |  |  |  | South Asia | NEPAL | NEPAL_HETAUDA |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Subisu |  | 2020-07-10 | 2020-07-10 | Complete | 2020-07-15 | 2020-07-15 | Complete | 2020-09-13 | 2020-08-29 | Green | 2020-09-25 | 2020-10-31 | Red | Dependency on procuring SFP and NIM Modules. | Yellow | Circuit Order Accepted | [8 empty] | Unilever Nepal Basmadi, Hetauda |  |  |  | Deepak Gajurel |  | +977 9845705111 |  |  |  | 35 | [24 empty] | Subisu | [5 empty] | Sunil Manjunath
I0220364UNL1 | I0220364UNL1 |  |  |  | South Asia | NEPAL | NEPAL_HETAUDA |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Mercantile |  | 2020-07-10 | 2020-07-10 | Complete | 2020-07-15 | 2020-07-15 | Complete | 2020-09-13 | 2020-08-29 | Green | 2020-09-25 | 2020-10-31 | Red | Dependency on procuring SFP and NIM Modules. | Yellow | Circuit Order Accepted | [8 empty] | Unilever Nepal Basmadi, Hetauda |  |  |  | Deepak Gajurel |  | +977 9845705111 |  |  |  | 50 | [24 empty] | Ncell | [5 empty] | Sunil Manjunath
I0120365UNL1 | I0120365UNL1 |  |  |  | South Asia | NEPAL | NEPAL_KATHMANDU |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Subisu |  | 2020-07-10 | 2020-07-10 | Complete | 2020-07-15 | 2020-07-15 | Complete | 2020-09-13 | 2020-08-29 | Green | 2020-09-25 | 2020-10-31 | Red | Dependency on procuring SFP and NIM Modules. | Yellow | Circuit Order Accepted | [8 empty] | Unilever Nepal CITY SQUARE BUILDING, Baneshwor-10 Kathmandu Nepal¦ 44600 |  |  |  | Shailendra Kr Yadav |  | +977 9801134066 |  |  |  | 35 | [24 empty] | Subisu | [5 empty] | Sunil Manjunath
I0220365UNL1 | I0220365UNL1 |  |  |  | South Asia | NEPAL | NEPAL_KATHMANDU |  |  |  | Vishal Joshi | WAN Circuit Migration | Circuit + Router | Unilever | Uni | Mercantile |  | 2020-07-10 | 2020-07-10 | Complete | 2020-07-15 | 2020-07-15 | Complete | 2020-09-13 | 2020-08-29 | Green | 2020-09-25 | 2020-10-31 | Red | Dependency on procuring SFP and NIM Modules. | Yellow | Circuit Order Accepted | [8 empty] | Unilever Nepal CITY SQUARE BUILDING, Baneshwor-10 Kathmandu Nepal¦ 44600 |  |  |  | Shailendra Kr Yadav |  | +977 9801134066 |  |  |  | 50 | [24 empty] | Ncell | [5 empty] | Sunil Manjunath
I014764BT1 | I014764BT1 |  |  |  | Namet & Rub | Turkey | TURKEY_ISTANBUL_HEAD_OFFICE |  |  |  | Eloise Shepheard | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-06-19 | 2020-06-19 | Complete | 2020-06-24 | 2020-07-23 | Red | 2020-08-23 | 2020-11-06 | Red | 2020-09-04 | 2020-11-16 | Red | 20/08: Order placed on 23rd July. Circuit delivery planned for Late October to Early Nov | Yellow | Circuit Ordered | [8 empty] | Unilever Saray Mahallesi, Dr. Adnan Büyükdeniz Cad. No:13
I019895BT1 | I019895BT1 |  |  |  | Namet & Rub | Turkey | TURKEY_ISTANBUL_SARIGAZI_FSS_OFFICE |  |  |  | Eloise Shepheard | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-06-19 | 2020-06-19 | Complete | 2020-06-24 | 2020-06-24 | Green | 2020-08-23 | 2020-10-17 | Red | 2020-09-04 | 2020-11-16 | Red | 20/08: Order placed on 23rd July. Circuit delivery planned for Late October to Early Nov | Yellow | Circuit Ordered | [8 empty] | Unilever Karsan Plaza Meclis Mah. Bogazici Cad. Seheryeli Sok. No:1
I0110897BT1 | I0110897BT1 |  |  |  | Europe | ITALY | Lodi Depot |  |  |  | Eloise Shepheard | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-07-30 | 2020-07-30 | Green | 2020-08-04 | 2020-08-04 | Green | 2020-10-03 | 2020-10-30 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit not ordered | [18 empty] | 10 | [50 empty] | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH
I0210897UNL1 | I0210897UNL1 |  |  |  | Europe | ITALY | Lodi Depot |  |  |  | Eloise Shepheard | WAN Circuit Migration | Circuit | Unilever | Uni |  |  | 2020-07-30 | 2020-07-30 | Green | 2020-08-04 | 2020-08-04 | Green | 2020-10-03 | 2020-10-30 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit not ordered | [18 empty] | 10
I02WC011CTL1 | I02WC011CTL1 |  |  |  | Latin America | Dominican Republic | SANTO_DOMINGO_AUTOPISTA |  |  |  | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  |  | 2020-06-22 | 2020-06-22 | Complete | 2020-06-27 | 2020-04-29 | Complete | 2020-08-26 | 2020-09-20 | Red | 2020-09-09 | 2020-09-25 | Red | 14-Aug: New router and circuit installation confirmed and approved for September 8th at 10AM. 31-Jul: If circuit delivered and tested on time, this migration is approved for August 18th at 10AM, along with its peer new circuit. | Green | Circuit Order Accepted | [8 empty] | AUTOPISTA 30 DE MAYO, KM12.5, SANTO DOMINGO DOMINICAN REPUBLIC ZIP CODE 91000 | [9 empty] | 10 | [30 empty] | Dulce Basilio Gonzalez
I0220234CTL1 | I0220234CTL1 |  |  |  | North America | United States | Amityville 11 - S Ranick Dr |  |  | un-una-usaami2-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  |  | 2020-04-29 | 2020-04-29 | Complete | 2020-05-04 | 2020-04-29 | Complete | 2020-07-03 | 2020-07-30 | Complete | 2020-07-17 | 2020-08-24 | Complete | 24-Aug: Migration successful. | Complete | Circuit Migrated | [8 empty] | 11 Ranick Drive South | [8 empty] | 10M | 100 | [18 empty] | LAN: 4.16.133.72/29 WAN: 4.16.134.108/30 CTL: 4.16.134.109 UNI: 4.16.134.110 | 4.16.134.109 | 4.16.134.110 | 4.16.133.72/29 | [8 empty] | Rene Gonzalez Iniguez |  |  |  |  | Standard site type - Hybrid (MPLS + DMVPN) |  |  | No |  |  | No | Assessment Complete MOP created & config created Partner MOP created | [8 empty] | CRQ000000702164 | Completed | Completed
I0220235CTL1 | I0220235CTL1 |  |  |  | North America | United States | Amityville 36 - W Ranick Dr |  |  | un-una-usaami1-vpn002 | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  |  | 2020-04-29 | 2020-04-29 | Complete | 2020-05-04 | 2020-04-29 | Complete | 2020-07-03 | 2020-09-23 | Complete | 2020-07-17 | 2020-08-31 | Complete | Aug-31: Migration successful. Aug-24: Circuit test successful. Pending confirmation on Migration tentatively scheduled on August 31st. | Complete | Circuit Migrated |  | Check dates | [6 empty] | 36 Ranick Drive South | [9 empty] | 40 | [19 empty] | 4.71.188.33 | 4.71.188.34 | 4.59.128.104/29 | [8 empty] | Sedat Citaku | Sedat Citaku | Sedat Citaku | [18 empty] | CRQ000000702543 | Completed | Completed
I0220236CTL1 | I0220236CTL1 |  |  |  | North America | United States | FRAMINGDALE_1 ADAMS BLVD |  |  |  | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  |  | 2020-05-05 | 2020-05-05 | Complete | 2020-05-10 | 2020-04-29 | Green | 2020-07-09 | 2020-08-03 | Red | 2020-07-23 | 2020-10-30 | Red |  | Yellow | Circuit Ordered | [8 empty] | 1 Adams Blvd | [9 empty] | 100 | [30 empty] | Hugo Trejo
SVPN012320UNL1 | SVPN012320UNL1 |  |  |  | North Asia | Japan | JAPAN_TOKYO_HEAD_OFFICE_NAKAMEGURO |  |  |  | Vishal Joshi | Soft Delete | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Green | 2020-08-05 | 2020-08-04 | Green | 2020-10-04 | 2020-10-30 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit not ordered | [8 empty] | 2-1-1 Kamimeguro, Meguro-Ku, Nakameguro GT Tower | [9 empty] | 100 | [24 empty] | Softbank
SVPN02WC065UNL1 | SVPN02WC065UNL1 |  | #NO MATCH |  | North Asia | Japan | JAPAN_TOYOSU_DATA_CENTER |  |  | #NO MATCH | Vishal Joshi | Soft Delete | Circuit | Unilever | Uni | Softbank |  | 2020-07-31 | 2020-07-31 | Green | 2020-08-05 | 2020-08-04 | Green | 2020-10-04 | 2020-10-30 | Red | 2020-10-16 |  | Red |  | Yellow | Circuit not ordered | [8 empty] | Toyosu 6-2-15 | [8 empty] | #NO MATCH | 100 | [19 empty] | #NO MATCH | #NO MATCH | #NO MATCH |  |  | Softbank | [10 empty] | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH | #NO MATCH
I013200CTL1 | I013200CTL1 |  |  |  | North America | [5 empty] | Juan Simon | WAN Circuit Migration | Circuit | CenturyLink | CL |  |  | 2020-07-30 | 2020-07-23 | Complete | 2020-08-04 | 2020-08-04 | Green | 2020-10-03 | 2020-10-30 | Red | 2020-10-16 |  | Red |  |  | Circuit Ordered | [18 empty] | 10
I023200ORA1 | I023200ORA1 |  |  |  | North America | [5 empty] | Juan Simon | WAN Circuit Migration | Circuit | Orange | ORA |  |  | 2020-07-30 | 2020-08-07 | Complete | 2020-08-04 | 2020-08-04 | Green | 2020-10-03 | 2020-10-30 | Red | 2020-10-16 |  | Red |  |  | Circuit Ordered | [18 empty] | 10
I024727BT1 | I024727BT1 |  |  |  | North America | [5 empty] | Juan Simon | WAN Circuit Migration | Circuit | BT | BT |  |  | 2020-07-31 | 2020-08-14 | Red | 2020-08-05 | 2020-08-04 | Green | 2020-10-04 | 2020-09-30 | Green | 2020-10-16 |  | Red |  |  | Circuit not ordered
I019661BT2 | I019661BT2 |  |  |  | North Asia | TAIWAN | TAIWAN_TAIPEI_UFS_OFFICE |  |  |  | Vishal Joshi | WAN Circuit Migration | Soft Upgrade + Fail over | BT | BT |  | 02-A0263-12R-0 | 2020-08-01 | 2020-08-01 | Complete | 2020-08-06 | 2020-06-24 | Complete | 2020-10-05 | 2020-08-14 | Complete | 2020-10-19 | 2020-08-27 | Complete | 4-Sep: Soft upgrade completed. Need to schedule fail over testing on 15th Sep. | Complete | Circuit Migrated | [18 empty] | 10 | [24 empty] | Sparq | [5 empty] | Fat Nela
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
[23 empty] | Red |  |  | Red | #INVALID DATA TYPE |  | Red |  |  | Circuit not ordered
Last | [27 empty] | #NO MATCH |  | #NO MATCH